## Template Guide
MASTER ESTIMATE WORKBOOK - TEMPLATE | Blackline QSi Pro ¦ template Rev1 (14 Oct 2026)
Purpose | Clean master for one job. An external AI (or the estimator) fills it from the tender documents; the Blackline QSi Pro app imports it and recalculates every figure itself.
Instructions | Read instructions/Workbook_Builder_Instructions.md before filling anything. The sheet names, header rows and column positions below are a contract with the app.
CAPACITY
QS Takeoff | Rows 3-202 (one item per row; total on row 203). Formula columns F, G, L-O, R are pre-filled.
Resource Build-Up | Rows 7-306. All formula columns are pre-filled; type only the input columns (see instructions section 5.2).
Resource Rate Library | Rows 5-200. The existing company rates are kept; add rates only with source, date and verification status.
Programme Export | Rows 7-206 follow QS rows 3-202; rows 207-226 are for control tasks (cure, holds) that are not QS items.
Rate Verification | One row per Build-Up row (rows 8-307); fill the evidence columns K-P, T, U.
Tender Build-Up | Type the QS section names in A10:A19 (exactly as written on QS Takeoff). Row 21 must read OK.
Cover & Instructions | Assumptions A1-A15, exclusions EX-01 to EX-08, RFIs RFI-01 to RFI-30, 9 document categories. Copy a row inside a block to add more.
Consolidated Package | Rows 6-11 are subcontract package slots. Row 13 holds a confirmed overlap.
Weather Risk | B13 and B14 are set to =0 in the template. Point them at the Build-Up rows that carry daily time-related preliminaries and weekly hire, e.g. B13 ='Resource Build-Up'!Y22*8 and B14 ='Resource Build-Up'!Y48+'Resource Build-Up'!Y60.
COMPANY DEFAULTS KEPT | Overhead 10% (markup) and profit 15% (true margin) on Commercial Inputs CA17/CA18 are the company's current settings; confirm per job. All other allowances are OFF and zero.
FULL MASTER | All the supporting sheets are present (Summary, Stage Cashflow, Estimate Review Board, ERB Adjudication, Programme Adjudication, Programme Notes, Materials & Component Takeoff, MS Project Import). The app reads what it needs and ignores the rest; they stay for the old workflow and future import.
MS Project Import | Generated from Programme Export: compact rows, predecessors as task IDs (column F), predecessor codes (R) and a helper column (S). Save as CSV (or copy the filled rows) to load into MS Project; the platform reads the same table and builds its programme from it.
Estimate Review Board | Coverage rows follow QS Takeoff rows 3-72; findings register ERF-001 to ERF-100.
WEATHER TOOL | NZ_Weather_Risk_Estimating_Tool_Rev2.xlsx (kept beside this template) is the approved weather tool: run it, then record its outputs in Weather Risk B19:B31 and link B13/B14.
Scope Coverage | One row per requirement of the job (rows 2-301, IDs SC-001...). Group / Owner / Treatment are drop-down lists. The app reads this sheet and checks that every treatment is backed up (QS code carries a cost, exclusion or RFI recorded, quote linked). Fill it before pricing.
LOGS | Email Log, RFI Log, Quote Log, Document Register, Decision Log, Contacts, Change Log: headers are fixed (instructions section 8).
RECALCULATE | After editing, recalculate and save so formulas hold values (LibreOffice: soffice --headless --convert-to xlsx --outdir out file.xlsx).

## Cover & Instructions
TENDER SNAPSHOT / START HERE
THE FIRST QUESTION: WHAT WILL THIS COST? |  |  |  | CURRENT COMMERCIAL BUILD-UP
Own works pre-commercial
Subcontract packages (known)
Current known cost before OH/profit
Company overhead
WORKING ALL-IN TENDER, EXCL. GST |  |  |  | Profit
WORKING ALL-IN TENDER
Gross margin on sell
KEY CONTROLS
Own works standalone tender
Management Reserve, pre-margin
Weather allowance
Dry programme (working days)
Weather-adjusted planning (days)
Risk Truth release gate
HOW TO READ THIS WORKBOOK - SIMPLE WORKFLOW
1 | Cover & Instructions | Job details, document register, assumptions, exclusions, RFIs, release QA
2 | Consolidated Package | Own works + subcontract packages + overhead + profit = all-in tender
3 | QS Takeoff | One row per priced item with quantity, source, status
4 | Resource Build-Up | How each QS item is built: labour, plant, materials, subcontract, preliminaries
5 | Commercial Inputs | Allowances, management reserve, overhead, profit, GST
6 | Tender Build-Up | The commercial stack, calculated
7 | Risk Truth | Risk register, exposures, duplication controls, release gate
8 | Weather Risk / Programme Export | Project weather inputs and task durations / logic
9 | Supplier Quote Register + logs | Quotes, emails, RFIs, documents, decisions, changes
CURRENT RELEASE POSITION
(Write where the estimate stands and what blocks release. List every RED item.)
Project | NOT PROVIDED |  | Location | NOT PROVIDED
Current drawings | NOT PROVIDED |  | Issue date | NOT PROVIDED
Scope | NOT PROVIDED |  | GST | All values shown exclude GST
Programme | NOT PROVIDED |  | Weather | NOT PROVIDED
Price status | NOT PROVIDED |  | Commercial | NOT PROVIDED
Risk Truth | Risk-control and reconciliation module. Tracks baseline vs residual exposure, provision routing, duplication and release gate.
DRAWING / DOCUMENT REGISTER
Document / Drawing | Reference | Estimate use
Plans / drawings
Specifications
Geotechnical / ground information
Survey / CAD / models
Tender / contract / scope documents
Supplier / subcontract quotations
Other consultants / approvals
Correspondence / addenda / clarifications
Backend construction intelligence
ASSUMPTIONS / QUALIFICATIONS / RFIs
A1
A2
A3
A4
A5
A6
A7
A8
A9
A10
A11
A12
A13
A14
A15
EX-01
EX-02
EX-03
EX-04
EX-05
EX-06
EX-07
EX-08
PRICING QUALIFICATIONS / RFIs
RFI-01
RFI-02
RFI-03
RFI-04
RFI-05
RFI-06
RFI-07
RFI-08
RFI-09
RFI-10
RFI-11
RFI-12
RFI-13
RFI-14
RFI-15
RFI-16
RFI-17
RFI-18
RFI-19
RFI-20
RFI-21
RFI-22
RFI-23
RFI-24
RFI-25
RFI-26
RFI-27
RFI-28
RFI-29
RFI-30
KEY RISKS / WATCHOUTS
Risk ID | Risk | Likelihood | Impact
TENDER RELEASE QA
Section | Requirement | Status (colour + reason) | Owner | Required Before Tender?
References | Current Intake, Master Prompt, Triple Verification and applicable standards recorded
Documents | Current drawing/specification/tender register complete
Scope | Work-package inclusions, exclusions and interfaces defined
Takeoff | Major quantities measured/provided/calculated and referenced to current documents
Resource build-up | Every active QS code has linked labour/plant/material/subcontract rows or an explicit PC
Rate verification | Important rates classified and three-way verified or flagged
Quotes / PCs | PC sums and quote-required packages reconciled to the Quote Log
Assumptions | Assumptions and exclusions are explicit, current and defensible
Interfaces | By-others / client / authority / consultant responsibilities identified
Risk Truth | All material risks have baseline, residual exposure and cost treatment
Risk duplication | No residual risk is costed twice; overlap groups and cost-treatment owners checked
Weather | Weather Risk reviewed; approved tool run current or documented
Ground / geotech | Ground and groundwater risks aligned to current geotechnical information
Earthworks / haulage | Balance, bulking, haul, disposal and import assumptions defined
Temporary works | Temporary works requirements and responsibility identified
Programme | Working days, productive crew days and elapsed duration reconciled
Programme cost check | Programme Export resource/QS cost checks all read OK
Commercial | Overhead, profit, escalation, securities and commercial inputs confirmed
Pricing schedule | Client pricing schedule mapped without double counting
Independent review | Review completed or consciously waived by the estimator
Release | Risk Truth, Weather and commercial gates reviewed
Approval | Final tender/estimate approved by the authorised reviewer
TRIPLE VERIFICATION & RISK TRUTH - MANDATORY
1 | No rate, quantity, productivity, duration, allowance or risk treatment is GREEN without current primary evidence, an independent check and a first-principles check.
2 | Quantifiable physical risk consequences return to Resource Build-Up / QS; only distinct residual uncertainty goes to Risk Truth.
3 | CA01 and CA02 default to Risk Truth residual feeds; manual percentages are not used unless documented.
4 | Weather remains in the Weather Risk specialist path and is never also added inside rates.
5 | Any RED duplication, programme reconciliation or unresolved material RED exposure blocks final release.
REVISION RECORD (full history on the Change Log sheet)
Revision | Date | Description

## Scope Coverage
Scope ID | Group | Requirement | Detail | Source (document / sheet / page) | Owner | Treatment | Cost refs (QS codes / CA lines) | Register refs (A#, EX-#, RFI-#) | Quote refs | Basis (what was priced and why) | Action
SC-001
SC-002
SC-003
SC-004
SC-005
SC-006
SC-007
SC-008
SC-009
SC-010
SC-011
SC-012
SC-013
SC-014
SC-015
SC-016
SC-017
SC-018
SC-019
SC-020
SC-021
SC-022
SC-023
SC-024
SC-025
SC-026
SC-027
SC-028
SC-029
SC-030
SC-031
SC-032
SC-033
SC-034
SC-035
SC-036
SC-037
SC-038
SC-039
SC-040
SC-041
SC-042
SC-043
SC-044
SC-045
SC-046
SC-047
SC-048
SC-049
SC-050
SC-051
SC-052
SC-053
SC-054
SC-055
SC-056
SC-057
SC-058
SC-059
SC-060
SC-061
SC-062
SC-063
SC-064
SC-065
SC-066
SC-067
SC-068
SC-069
SC-070
SC-071
SC-072
SC-073
SC-074
SC-075
SC-076
SC-077
SC-078
SC-079
SC-080
SC-081
SC-082
SC-083
SC-084
SC-085
SC-086
SC-087
SC-088
SC-089
SC-090
SC-091
SC-092
SC-093
SC-094
SC-095
SC-096
SC-097
SC-098
SC-099
SC-100
SC-101
SC-102
SC-103
SC-104
SC-105
SC-106
SC-107
SC-108
SC-109
SC-110
SC-111
SC-112
SC-113
SC-114
SC-115
SC-116
SC-117
SC-118
SC-119
SC-120
SC-121
SC-122
SC-123
SC-124
SC-125
SC-126
SC-127
SC-128
SC-129
SC-130
SC-131
SC-132
SC-133
SC-134
SC-135
SC-136
SC-137
SC-138
SC-139
SC-140
SC-141
SC-142
SC-143
SC-144
SC-145
SC-146
SC-147
SC-148
SC-149
SC-150
SC-151
SC-152
SC-153
SC-154
SC-155
SC-156
SC-157
SC-158
SC-159
SC-160
SC-161
SC-162
SC-163
SC-164
SC-165
SC-166
SC-167
SC-168
SC-169
SC-170
SC-171
SC-172
SC-173
SC-174
SC-175
SC-176
SC-177
SC-178
SC-179
SC-180
SC-181
SC-182
SC-183
SC-184
SC-185
SC-186
SC-187
SC-188
SC-189
SC-190
SC-191
SC-192
SC-193
SC-194
SC-195
SC-196
SC-197
SC-198
SC-199
SC-200
SC-201
SC-202
SC-203
SC-204
SC-205
SC-206
SC-207
SC-208
SC-209
SC-210
SC-211
SC-212
SC-213
SC-214
SC-215
SC-216
SC-217
SC-218
SC-219
SC-220
SC-221
SC-222
SC-223
SC-224
SC-225
SC-226
SC-227
SC-228
SC-229
SC-230
SC-231
SC-232
SC-233
SC-234
SC-235
SC-236
SC-237
SC-238
SC-239
SC-240
SC-241
SC-242
SC-243
SC-244
SC-245
SC-246
SC-247
SC-248
SC-249
SC-250
SC-251
SC-252
SC-253
SC-254
SC-255
SC-256
SC-257
SC-258
SC-259
SC-260
SC-261
SC-262
SC-263
SC-264
SC-265
SC-266
SC-267
SC-268
SC-269
SC-270
SC-271
SC-272
SC-273
SC-274
SC-275
SC-276
SC-277
SC-278
SC-279
SC-280
SC-281
SC-282
SC-283
SC-284
SC-285
SC-286
SC-287
SC-288
SC-289
SC-290
SC-291
SC-292
SC-293
SC-294
SC-295
SC-296
SC-297
SC-298
SC-299
SC-300

## Summary
ESTIMATE SUMMARY - MASTER ESTIMATE WORKBOOK
WORKING ALL-IN TENDER
Current known cost before OH/profit |  |  | Project
Issue
Programme
Siteworks standalone tender |  |  | Weather allowance
Subcontract packages (known) |  |  | Management Reserve
GST
Release status |  |  | Ground basis
Supplier/material costs within the own-works estimate are already included in the Resource Build-Up; subcontract packages are added once in the Consolidated Package.
Key Quantities
Pricing Summary (direct-cost estimate)
Section | Amount
Total priced amount excl. GST
Pricing basis
GST
Scope
Accuracy
Programme basis
Tender Completion Build-Up (client-adjustable commercial provisions)
Purpose | This block reflects Tender Build-Up and current Commercial Inputs selections.
Input sheet | Use Commercial Inputs to adjust allowances, overhead and profit method, bonds, retention finance and GST.
Line
Base direct estimate excl. GST |  |  |  | QS direct-cost estimate
Pre-margin additions |  |  |  | Commercial Inputs CA01-CA16 incl. CA16 Management Reserve
Commercial adjustments |  |  |  | Commercial Inputs CA17-CA20 commercial adjustments
Tender total excl. GST |  |  |  | Working tender incl. Management Reserve; excl GST
GST if selected |  |  |  | Optional display
Tender total incl. GST if selected |  |  |  | Optional tax-inclusive check
Net pre-GST payment after retention |  |  |  | Tender total less retention withholding after CA25 deposit treatment.
Retention release after holding period |  |  |  | Released after CA23 retention period; amount follows CA25 deposit retention treatment.
Deposit / advance payment |  |  |  | Part of tender total; controlled by CA24
Stage cashflow tab |  |  |  | Editable stage profile and cumulative cashflow
COST CHAIN INTEGRITY
Check | Upstream | Downstream | Difference | Status
Resource Build-Up -> QS
QS -> Tender Build-Up
Tender Build-Up -> Summary
Commercial Inputs -> Tender Build-Up
Formula control | Formula/output cells are edit-blocked with Stop validation; yellow cells are intended inputs.
Release rule | All chain checks must read OK before issue.
Weather Engine output -> Commercial Inputs CA10 Engine Amount (audit only)
RATE & PROGRAMME QA RELEASE GATE
Check | Count / Amount | Status | Action
GREEN active resource rows |  |  | Three checks present
AMBER active resource rows |  |  | Disclose allowance and firm before award
RED active resource rows |  |  | Quote/design evidence required
Active QS items mapped to programme |  |  | Checked against populated Programme Export QS codes
Overall release
Weather model / task factors
Weather integration rerun gate
Risk Truth release gate |  |  | PASS required for final release
Risk Truth recalculated tender total |  | INFO | Should equal the live tender total when Risk Truth feeds and commercial logic reconcile.
INDEPENDENT ESTIMATE REVIEW BOARD RELEASE GATE
Review Board gate |  |  | PASS or PASS WITH AMBER required for release
Active QS items fully reviewed |  |  | Every active QS item must pass all mandatory review columns
Unresolved material findings |  |  | RED blocks release; AMBER must be disclosed and actioned
Reviewer independence / commitment |  |  | Required reviewers must be blind, independent and committed before comparison
PROGRAMME RECONCILIATION
Calculated controlling path working days
Tender baseline working days
Coordination float / buffer working days | 0
Controlling path
Programme release
PROGRAMME CALENDAR BASIS
Tender-season assumed start
Weekday-only base finish
Elapsed calendar span
Holiday / shutdown treatment
CONSOLIDATED PACKAGE REVIEW - NOT FINAL TENDER UNTIL RELEASED
Own works current pre-commercial |  | LINKED
Subcontract packages (known) |  | QUOTED
Gross current known package |  | CALCULATED
Confirmed overlap with own works |  | CLOSED
Current known package after reconciliation |  | CALCULATED
Company O/H |  | PROVIDED
Contractor profit |  | PROVIDED
Tender adjudication status

## Consolidated Package
CONSOLIDATED ALL-IN PACKAGE - OWN WORKS + SUBCONTRACT PACKAGES
WORKING ALL-IN TENDER EXCL GST
Package / Control | Amount excl GST | Classification | Included in Siteworks direct? | Status | Release
Own works current pre-commercial package |  | LINKED / CURRENT | Yes | Own works | AMBER / WORKING
|  | QUOTED | No |  | AMBER
|  | QUOTED | No |  | AMBER
|  | QUOTED | No |  | AMBER
|  | QUOTED | No |  | AMBER
|  | QUOTED | No |  | AMBER
|  | QUOTED | No |  | AMBER
GROSS CURRENT KNOWN PACKAGE |  | CALCULATED | Review total only | Not final tender | HOLD
Confirmed overlap between own works and a package | 0 | CLOSED | None | Interface closed | AMBER / CLOSED
Current known package after overlap |  | CALCULATED | Review only | Not final tender | HOLD
Unpriced packages (see Quote Log) |  | UNPRICED | No
WORKING ALL-IN TENDER EXCL GST |  | CALCULATED / WORKING | N/A
Rules: one row per subcontract package (rows 6-11; insert more by copying a row). Amount as a number, 'Included in Siteworks direct?' = No, classification QUOTED / QUOTED BASE / CONFIRMED ADDITIONAL / ALLOCATED (never CALCULATED). A package with no price yet stays as a row with no amount and is recorded on the Quote Log.
CURRENT WORKING COMMERCIAL SCENARIO - OVERHEAD AND PROFIT FROM COMMERCIAL INPUTS CA17 / CA18
Scenario | Precommercial cost | Overhead | Subtotal after OH | Profit | Tender excl GST | Commercial uplift
Current known package after overlap

## Tender Build-Up
MASTER ESTIMATE WORKBOOK - TENDER BUILD-UP
Project
Pricing status
GST | Optional GST display via Commercial Inputs CA21.
Retention | Cashflow only by default.
No direct-cost values are entered on this sheet. Base costs flow from QS Takeoff; commercial provisions flow from Commercial Inputs.
Base direct estimate (by QS section) | Amount excl. GST | Source | Treatment | Notes
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project scope, classification, source and firm-up action.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project ESC scope and requirements.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project quantities, ground basis, haul and disposal assumptions.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project stormwater / detention design and supplier requirements.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project wastewater / water scope and authority interfaces.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project pavement / concrete scope and specification.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project kerb / external sitework scope.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current project retaining-wall design, quantities and temporary works.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current testing, survey, as-built and compliance obligations.
|  | QS Takeoff (type the section name exactly as used on QS Takeoff) | Priced / provisional | Linked QS section total; confirm current reinstatement, defects and handover obligations.
Base direct estimate excl. GST |  |  | Subtotal | Direct cost sourced from Resource Build-Up through QS Takeoff; includes measured, provisional, allowance and PC items.
Check: QS sections not listed above (must be zero)
Pre-margin additions | Calculated amount excl. GST | Input source | Include? | Basis / Notes
CA01 - Design / scope residual risk - Risk Truth |  |  |  | CA01 defaults to Risk Truth. PC Sum or % may be selected as a stated adjudication override; Include? controls whether the selected treatment enters the tender.
CA02 - Construction / execution residual risk - Risk Truth |  |  |  | CA02 defaults to Risk Truth. PC Sum or % may be selected as a stated adjudication override; Include? controls whether the selected treatment enters the tender.
CA08 - Abnormal ground / contamination / rock allowance |  |  |  | No generic ground percentage. Use only an explicit evidence-based provision not more truthfully placed in QS or a specialist engine.
Project-specific construction water-control provision only; check overlap with Weather / Ground risk treatment.
CA10 defaults to Weather Engine. PC Sum or % may be selected explicitly; Include? can turn the weather allowance off while the engine output remains retained for audit.
Reasonable defects / closeout attendance is included under RH01.
Basic Siteworks traffic / pedestrian / access controls are included within the itemised PG01 preliminaries.
PROVIDED / AMBER management adjudication reserve
Pre-margin additions subtotal
Subtotal before commercial adjustments
Overhead, profit and other commercial adjustments | Calculated amount excl. GST | Input source | Include? | Basis / Notes
Commercial adjustments subtotal
Tender total excl. GST |  |  | Subtotal | Base direct estimate + selected pre-margin additions + commercial adjustments.
GST if selected |  | Commercial Inputs CA21 | Optional | GST applies only when CA21 Include? is Yes.
Tender total incl. GST if selected |  |  | Subtotal | For GST-inclusive check only.
Cashflow / contract security visibility only | Calculated value | Input source | Include? | Notes
Contract retention withholding |  | Commercial Inputs CA22 | Cashflow only | Retention withholding on retention-applicable contract value; deposit treatment controlled by CA25.
Net pre-GST payment after retention |  | Calculated | Cashflow only | Tender total excl. GST less current retention withholding.
Retention holding period |  | Commercial Inputs CA23 | Cashflow only | Months from practical completion unless contract states otherwise.
Retention released after holding period |  | Calculated | Cashflow only | Equals current retention withholding; released after the CA23 holding period.
Total pre-GST receipts including retention release |  | Calculated | Cashflow only | Equals tender total excl. GST.

## Commercial Inputs
COMMERCIAL INPUTS - BELOW-THE-LINE SOURCE OF TRUTH | [6 empty] | Profit method
[7 empty] | CA18 method (linked) |  | The calculation method is selected in column C. There is no second profit-method selector.
CA01/CA02: Risk Engine, PC Sum or %. CA10: Weather Engine, PC Sum or %. Other pre-margin allowances: PC Sum or %. Column F Include? is the on/off switch. Engine outputs remain live in column L even when another method is selected, preserving the audit trail.
Ref | Allowance / adjustment | Input method | Input % | PC Sum excl. GST | Include? | Pricing stage | Calculation / treatment | Notes / basis | Firm-up action | Pricing method / flag shown in QS | Engine Amount excl. GST | Engine Source / Status
CA01 | Design / scope residual risk - Risk Truth linked | Risk Engine |  |  | Yes | Pre-margin addition |  | Residual design/scope risk only where the consequence cannot be more truthfully placed in Resource Build-Up/QS or a specialist engine. | Close Risk Truth RED items and confirm residual is distinct / integration complete.
CA02 | Construction / execution residual risk - Risk Truth linked | Risk Engine |  |  | Yes | Pre-margin addition |  | Residual construction/execution risk only where the consequence cannot be more truthfully placed in Resource Build-Up/QS or a specialist engine. | Close Risk Truth RED items and confirm residual is distinct / integration complete.
CA03 | Escalation / tender validity allowance | % |  |  | No | Pre-margin addition |  | Enter only where escalation is evidence-based; do not default to a generic percentage. | Confirm construction start and validity.
CA04 | Final subcontractor quote gap / market adjustment | PC Sum |  |  | No | Pre-margin addition |  | Use only for a distinct reconciled live-quote gap not already included in QS/PC items or Risk Truth. | Use only after supplier quote returns are reconciled and a distinct uncovered market gap is evidenced.
CA05 | Council / authority consent and inspection fees | PC Sum |  |  | No | Pre-margin addition |  | Confirm contractual responsibility before inclusion. | Confirm fee responsibility.
CA06 | Utility authority fees / relocations | PC Sum |  |  | No | Pre-margin addition |  | Confirm contractual responsibility; physical construction scope should normally sit in QS. | Confirm utilities.
CA07 | Temporary works engineering / PS documentation | PC Sum |  |  | No | Pre-margin addition |  | Use only for temporary-works engineering / documentation not already in direct scope. | Avoid duplication.
CA08 | Abnormal ground / contamination / rock allowance | PC Sum |  |  | No | Pre-margin addition |  | Do not use as a generic ground-risk percentage. Quantifiable ground consequences belong in QS or an approved specialist risk treatment. | Review geotech/contamination data.
CA09 | Construction dewatering / groundwater control | PC Sum |  |  | No | Pre-margin addition |  | Construction water / dewatering PC pending final programme/groundwater conditions. Distinct from normal weather CA10. | Firm methodology after earthworks programme and site conditions are confirmed.
CA10 | Weather risk allowance - linked approved engine | Weather Engine |  |  | Yes | Pre-margin addition |  | Weather Risk engine feeds this line when the method is Weather Engine. | Rerun the weather tool when the start date, programme or weather-exposed scope changes. | Weather Engine - AMBER / CURRENT TENDER SCENARIO |  | Weather tool run recorded on Weather Risk (CA10 engine feed)
CA11 | Extended preliminaries beyond weather-adjusted tender baseline | PC Sum |  |  | No | Pre-margin addition |  | Do not use for weather delay already treated through CA10. | Add only for non-weather instructed extension or revised contract programme after checking CA10 overlap.
CA12 | Defects liability / maintenance beyond base | PC Sum |  |  | No | Pre-margin addition |  | Reasonable defects / closeout attendance is carried in RH01. | Confirm special maintenance obligations.
CA13 | Stakeholder liaison / access marshals beyond base | PC Sum |  |  | No | Pre-margin addition |  | Basic Siteworks traffic / pedestrian / access controls are carried within the itemised PG01 preliminaries. | Confirm restricted operations.
CA14 | Out-of-hours / restricted access premium | PC Sum |  |  | No | Pre-margin addition |  | Normal weekday access assumed. | Confirm work windows.
CA15 | Unforeseen post-tender client scope additions | PC Sum |  |  | No | Pre-margin addition |  | No allowance for later scope changes. | Include only if instructed.
CA16 | Management Reserve - residual tender-stage uncertainty (adjudication) | Fixed Amount |  |  | No | Pre-margin adjudication provision |  | PROVIDED management reserve selected at tender adjudication. Purpose: protect the tender against aggregate residual tender-stage uncertainty and unknown-unknowns that remain after known/measurable scope, PCs, quoted packages, Weather Risk and Risk Truth treatments have already been allowed. It is not a Risk Truth contingency and does not close or downgrade any RED item. | Reassess whenever a RED is resolved, a material scope/quantity/rate changes, or before contract award. If an exposure becomes measurable, price the actual consequence in the correct cost line and reassess the reserve rather than automatically consuming it. | Fixed Amount - PROVIDED / AMBER / 4.0% ADJUDICATION BASIS
CA17 | Company overhead recovery | Markup % | 10% |  | Yes | Commercial adjustment | 10% markup applied to subtotal before profit | Company overhead recovery, applied as markup to the subtotal before profit. Set per job. | Review against Siteworks actual overhead recovery when company financial basis is available; no tender hold created by this user-provided input. | Markup % - PROVIDED / WORKING BASIS
CA18 | Contractor profit | Margin % | 15% |  | Yes | Commercial adjustment | 15% TRUE MARGIN after overhead and other selected commercial costs | Contractor profit as true margin after overhead and other selected allowances. Set per job. | Change only if Siteworks instructs a different profit method/rate. | Margin % - PROVIDED / WORKING BASIS
CA19 | Bonds / contract securities allowance | % |  |  | No | Commercial adjustment | Applied if selected | Include only where contract securities create a genuine contractor cost. | Confirm security terms. | % user input provision
CA20 | Retention finance / cashflow cost allowance | % |  |  | No | Commercial adjustment | Applied if selected | Finance cost only; retention withholding itself is a cashflow item. | Confirm retention terms. | % user input provision
CA21 | GST | % | 15% |  | No | Tax | Applied to tender total if selected | Optional tax display. Set 15% for NZ GST or 10% for Australian GST when applicable; estimate control total remains ex tax. | Confirm submission format. | % user input provision
CA22 | Contract retention withholding | % | 0% |  | No | Cashflow only | Visibility only | Not added to tender price. | Confirm retention cap/terms. | User input
CA23 | Retention holding period | Months | 0 |  | No | Cashflow only | Times retention release | No retention holding period assumed; CA23 remains 0 until contract terms are supplied. | Confirm contract. | % user input provision
CA24 | Deposit / advance payment | [6 empty] | Used as first cashflow stage. | Confirm whether permitted. | User selection
CA25 | Retention applies to deposit | [6 empty] | Normally No. | Confirm contract.
Notes
1 | Leave Include? as No for any provision that is not to be included. Enter Input % or PC Sum depending on the intended basis; PC Sum overrides % where populated.
MANAGEMENT RESERVE - ADJUDICATION BASIS
Control | Value | Classification | Basis / meaning | Unresolved item 1 RED | Unresolved item 2 RED | Unresolved item 3 RED | Unresolved item 4 RED
Reserve base
Selected reserve rate
Pre-OH/profit Management Reserve
Tender effect of reserve
Probability note | N/A |  | Do not weight any item with a probability unless it is evidenced. Unknown probability = sensitivity only, never an expected value.
Consumption rule | N/A |  | Do not automatically consume the reserve when a risk resolves; Rick adjudicates any change under change control.

## QS Takeoff
QS TAKEOFF - MASTER ESTIMATE WORKBOOK - RESOURCE-LINKED | [10 empty] | Rate and Amount are linked from Resource Build-Up. One row per priced item; the section name goes on every row. Do not type over the grey formula columns.
Civil Scope / WBS | Code | Description | Unit | Quantity | Rate excl. GST | Amount excl. GST | Quantity Basis | Source drawing / scope | Status | Notes / Assumptions | Pricing Method | Pricing Basis / Build-up | Source Type | Source URL(s) | Pricing Flag | Confidence / Firm-up Action | Owner | Verification Status | Quote / Reference
TOTAL DIRECT COST

## Resource Build-Up
RESOURCE BUILD-UP - MASTER ESTIMATE WORKBOOK - LINKED COST / DURATION FORMULAS
Every active QS Code must have resource rows here. Extended Cost totals by QS Code are pulled into QS Takeoff; do not type a second QS rate or amount.
Ordinary civil plant stays Plant whether owned or hired. Specialist delivered capability such as mobile cranes is normally Subcontract. Wet hire must record operator/fuel inclusions to stop double counting.
Calculation modes: Time x Count; QS Qty x Factor; Direct Qty; Lump Sum / Quote. Duration is derived from quantity/productivity or explicitly overridden where sequencing requires it.
Weather controls: AK:AM are estimator inputs; AN is formula-controlled exposed Labour/Plant cost feeding Weather Risk. Materials, fixed subcontract and Other costs are excluded from direct weather productivity by default.
Build-Up Row ID | QS Code | WBS / Section | Task Description | QS Qty | QS Unit | Estimate Class | Methodology / Work Step | Productivity Rate | Productivity Unit | Calc Duration hrs | Duration Override hrs | Applied Duration hrs | Calculation Mode | Resource Type | Resource Code | Resource Description | Resource Count / Factor | Manual Resource Qty | Resource Unit | Utilisation % | Waste % | Library Rate | Job Rate Override | Applied Rate | Extended Cost | Library Source | Job Quote / Source Ref | Source Date | Operator Included? | Fuel Included? | Confidence | Assumption / RFI | Verified? | QA / Double-Count Check | Notes | Weather Exposed? | Weather Task Type | Weather Basis / Status | Weather-Exposed Labour + Plant Cost

## Resource Rate Library
COMPANY RESOURCE RATE LIBRARY - MASTER ESTIMATE WORKBOOK
Reusable company / benchmark resource library. Retain useful history; update verified rates with source, effective date, region, GST basis, inclusions/exclusions and supersession reason.
Enter verified actual company/supplier rates with source, date, region, GST basis, inclusions and exclusions. Mark replaced rates superseded/inactive rather than deleting useful history.
Resource Code | Resource Category | Resource Description | Default Cost Type | Unit | Procurement Mode | Operator Included? | Fuel Included? | Base Rate excl. GST | Region / Market | Effective Date | Source Type | Supplier / Source | Source URL / Quote Ref | Minimum / Mobilisation | Rate Inclusions | Rate Exclusions | Confidence | Verification Status | Notes
LAB-FOREMAN | Labour | Civil foreman / working foreman | Labour | hr | Internal / agency | N/A | N/A | 64 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | SEEK / statutory on-cost basis | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Margin, vehicle, overtime | Medium | AMBER - market/on-cost benchmark; company payroll required | Firm to company payroll before award
LAB-SUPERVISOR | Labour | Site supervisor / project manager | Labour | hr | Internal / agency | N/A | N/A | 73 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | SEEK / statutory on-cost basis | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Margin, vehicle, overtime | Medium | AMBER - market/on-cost benchmark; company payroll required | Firm to company payroll before award
LAB-OPERATOR | Labour | Plant operator | Labour | hr | Internal / agency | N/A | N/A | 45 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | Auckland civil market | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Plant and overtime | Medium | AMBER - market/on-cost benchmark; company payroll required
LAB-DRAINLAYER | Labour | Registered drainlayer / pipe layer | Labour | hr | Internal / agency | N/A | N/A | 51 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | Auckland civil market | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Vehicle and overtime | Medium | AMBER - market/on-cost benchmark; company payroll required
LAB-LABOURER | Labour | Civil labourer | Labour | hr | Internal / agency | N/A | N/A | 38 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | Auckland civil market | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Overtime | Medium | AMBER - market/on-cost benchmark; company payroll required
LAB-CONCRETE | Labour | Concrete placer / finisher | Labour | hr | Internal / agency | N/A | N/A | 44 | Auckland / NZ | 13-Aug-2026 | Template market benchmark | Auckland civil market | https://nz.seek.com/civil-drainage-jobs/in-All-Auckland ¦ https://nz.seek.com/drainage-foreman-jobs/in-All-Auckland/full-time |  | Direct employment allowance | Specialist pump | Medium | AMBER - market/on-cost benchmark; company payroll required
PL-EXC-1.7 | Plant | 1.7 t excavator wet hire | Plant | hr | Wet hire | Yes | Yes | 85 | Auckland | 13-Aug-2026 | Published supplier wet-hire rate | ASAP Machine Hire; NZ Machine Hire cross-check | https://www.asapmachinehire.co.nz/price-list ¦ https://www.nzmachinehire.co.nz/_files/ugd/d7f8c7_1379402df1a242f88fef70fc3ce1475c.pdf | Delivery by quote | Machine, operator, fuel and normal buckets | Delivery, overtime and specialist attachments | High | GREEN - 3-point checked | Wet rate. Do not add a separate operator or fuel line.
PL-EXC-5 | Plant | 5.5 t excavator wet hire | Plant | hr | Wet hire | Yes | Yes | 110 | Auckland | 13-Aug-2026 | Published supplier wet-hire rate | ASAP Machine Hire; NZ Machine Hire cross-check | https://www.asapmachinehire.co.nz/price-list ¦ https://www.nzmachinehire.co.nz/_files/ugd/d7f8c7_1379402df1a242f88fef70fc3ce1475c.pdf | Delivery by quote | Machine, operator, fuel and normal buckets | Delivery, overtime and specialist attachments | High | GREEN - 3-point checked | Wet rate. Separate excavator-operator lines set to zero.
PL-EXC-13 | Plant | 14 t excavator wet hire | Plant | hr | Wet hire | Yes | Yes | 150 | Auckland | 13-Aug-2026 | Published supplier wet-hire rate | ASAP Machine Hire; NZ Machine Hire cross-check | https://www.asapmachinehire.co.nz/price-list ¦ https://www.nzmachinehire.co.nz/_files/ugd/d7f8c7_1379402df1a242f88fef70fc3ce1475c.pdf | Delivery by quote | Machine, operator, fuel and normal buckets | Delivery, overtime and specialist attachments | High | GREEN - 3-point checked | Published current wet rate. Separate excavator-operator lines set to zero.
PL-ROLLER | Plant | 7-9 t roller wet-hire equivalent | Plant | hr | Wet-hire equivalent | Yes | Yes | 110 | Auckland | 13-Aug-2026 | Two-supplier dry-rate build-up | NZ Machine Hire; Hire Smart | https://www.nzmachinehire.co.nz/all-rollers ¦ https://www.hiresmart.co.nz/for-hire/rollers/ | Transport by quote | Dry hire, operator, normal fuel and insurance allowance | Transport, overtime and specialist attachments | Medium | AMBER - 3-point benchmark; quote required | Built from two published dry rates plus operator/fuel allowance; obtain a project quote.
PL-LOADER | Plant | Loader / skid-steer dry hire | Plant | hr | Dry hire | No | No | 120 | Auckland | 13-Aug-2026 | Estimator benchmark | Plant-hire market | Allowance - obtain hire quote |  | Machine only | Operator, fuel, mobilisation | Medium | AMBER - benchmark/allowance only
MAT-IMPFILL | Material | AP65-equivalent approved engineered fill delivered | Material | m3 | Merchant supply | N/A | N/A | 65 | Auckland | 13-Aug-2026 | Tender allowance | Aggregate supplier | https://www.urbanquarry.co.nz/pricelist-2-2 ¦ https://www.aggregate2u.co.nz/aggregates-delivery-south-auckland |  | Delivered clean approved fill | Testing and placement | Low | AMBER - two market checks; specification/delivery quote required | Product specification and delivered rate still require supplier confirmation.
MAT-AP65 | Material | AP65 subbase aggregate | Material | t | Merchant supply | N/A | N/A | 30.5 | Auckland | 13-Aug-2026 | Template market benchmark | Auckland quarry market | https://www.urbanquarry.co.nz/pricelist-2-2 ¦ https://www.aggregate2u.co.nz/aggregates-delivery-south-auckland |  | Ex-quarry / base material allowance | Haul and placement | High | AMBER - two market checks; specification/delivery quote required | Published GAP/AP benchmark; confirm specified grading and haul.
MAT-AP40 | Material | AP40 / GAP40 basecourse aggregate | Material | t | Merchant supply | N/A | N/A | 31 | Auckland | 13-Aug-2026 | Template market benchmark | Auckland quarry market | https://www.urbanquarry.co.nz/pricelist-2-2 ¦ https://www.aggregate2u.co.nz/aggregates-delivery-south-auckland |  | Ex-quarry / base material allowance | Haul and placement | High | AMBER - two market checks; specification/delivery quote required | Published GAP/AP benchmark; confirm specified grading and haul.
MAT-DRAINAGG | Material | Drainage aggregate | Material | t | Merchant supply | N/A | N/A | 48.5 | Auckland | 13-Aug-2026 | Template market benchmark | Auckland quarry market | https://www.aggregate2u.co.nz/aggregates-delivery-south-auckland ¦ https://www.urbanquarry.co.nz/pricelist-2-2 |  | Aggregate | Haul and placement | High | AMBER - two market checks; specification/delivery quote required | Drainage aggregate benchmark; confirm delivered project quote.
MAT-GEOTEXTILE | Material | Bidim A19 or approved geotextile | Material | m2 | Merchant supply | N/A | N/A | 3.25 | Auckland | 13-Aug-2026 | Template market benchmark | Civil merchant | Template baseline dated 13-Aug-2026 |  | Material only | Installation | Medium | AMBER - benchmark/allowance only
MAT-CONC25 | Material | 25 MPa ready-mix concrete | Material | m3 | Delivered supply | N/A | N/A | 325 | Auckland | 13-Aug-2026 | Template market benchmark | Ready-mix market | Template baseline dated 13-Aug-2026 |  | Delivered concrete allowance | Pump, testing, placing | Medium | AMBER - benchmark/allowance only
MAT-MESH | Material | SE62 / 662 mesh allowance | Material | m2 | Merchant supply | N/A | N/A | 20 | Auckland | 13-Aug-2026 | Template market benchmark | Steel merchant | Template baseline dated 13-Aug-2026 |  | Mesh material | Chairs, laps above waste factor | Medium | AMBER - benchmark/allowance only | Confirm project-specific mesh grade and specification before order.
MAT-PIPE150 | Material | 150 mm uPVC RRJ drainage pipe | Material | lm | Merchant supply | N/A | N/A | 45 | Auckland | 13-Aug-2026 | Tender allowance | Civil merchant | Quote required |  | Pipe and standard joints | Fittings, bedding, install | Low | AMBER - benchmark/allowance only
MAT-PIPE225 | Material | 225 mm uPVC RRJ stormwater pipe | Material | lm | Merchant supply | N/A | N/A | 95 | Auckland | 13-Aug-2026 | Tender allowance | Civil merchant | Quote required |  | Pipe and standard joints | Fittings, bedding, install | Low | AMBER - benchmark/allowance only
MAT-SUB110 | Material | 110 mm perforated subsoil pipe with sock | Material | lm | Merchant supply | N/A | N/A | 20 | Auckland | 13-Aug-2026 | Tender allowance | Civil merchant | Quote required |  | Pipe and sock | Aggregate and install | Low | AMBER - benchmark/allowance only
MAT-WATER50 | Material | 50 mm PE watermain and fittings allowance | Material | lm | Merchant supply | N/A | N/A | 22 | Auckland | 13-Aug-2026 | Tender allowance | Civil merchant | Quote required |  | PE pipe and normal fittings | Connection, meter, testing | Low | AMBER - benchmark/allowance only
MAT-SWMH | Material | Precast stormwater manhole set | Material | ea | Precast supplier | N/A | N/A | 5500 | Auckland | 13-Aug-2026 | Tender allowance | Precast supplier | Quote required |  | Chamber/riser/lid allowance | Excavation, concrete, install | Low | AMBER - benchmark/allowance only
MAT-SSMH | Material | Precast sewer manhole set | Material | ea | Precast supplier | N/A | N/A | 7000 | Auckland | 13-Aug-2026 | Tender allowance | Precast supplier | Quote required |  | Chamber/riser/lid allowance | Excavation, testing, install | Low | AMBER - benchmark/allowance only
MAT-IC600 | Material | 600 mm inspection chamber set | Material | ea | Merchant supply | N/A | N/A | 1800 | Auckland | 13-Aug-2026 | Tender allowance | Civil merchant | Quote required |  | Chamber and lid | Excavation and install | Low | AMBER - benchmark/allowance only
MAT-CP | Material | Standard catchpit set | Material | ea | Precast supplier | N/A | N/A | 1800 | Auckland | 13-Aug-2026 | Tender allowance | Precast supplier | Quote required |  | Chamber, lid and grate | Excavation and install | Low | AMBER - benchmark/allowance only
MAT-DCP | Material | Double side-entry cesspit set | Material | ea | Precast supplier | N/A | N/A | 4500 | Auckland | 13-Aug-2026 | Tender allowance | Precast supplier | Quote required |  | Chamber, lid and grates | Excavation and install | Low | AMBER - benchmark/allowance only
SUB-ASPHALT30 | Subcontract | 30 mm asphalt surfacing incl prime/seal | Subcontract | m2 | Specialist subcontract | Yes | Yes | 55 | Auckland | 13-Aug-2026 | Budget allowance | Asphalt subcontractor | Quote required |  | 30 mm asphalt surfacing allowance | Basecourse and testing | Low | RED - quote or job-specific evidence required
SUB-KERB-T3 | Subcontract | Type 3 kerb and channel installed | Subcontract | lm | Specialist subcontract | Yes | Yes | 145 | Auckland | 13-Aug-2026 | Budget allowance | Kerb contractor | Quote required |  | Form/place/finish concrete kerb/channel | Excavation and major base repair | Low | RED - quote or job-specific evidence required
SUB-KERB-T7 | Subcontract | Type 7 kerb installed | Subcontract | lm | Specialist subcontract | Yes | Yes | 115 | Auckland | 13-Aug-2026 | Budget allowance | Kerb contractor | Quote required |  | Form/place/finish kerb | Excavation and major base repair | Low | RED - quote or job-specific evidence required
SUB-ACO-K100 | Subcontract | ACO K100S channel drain installed | Subcontract | lm | Specialist subcontract | Yes | Yes | 275 | Auckland | 13-Aug-2026 | Budget allowance | ACO / drainage installer | Quote required |  | Channel, grates and concrete surround allowance | Outlet structures and design changes | Low | RED - quote or job-specific evidence required
SUB-SPECIALIST | Subcontract | Project-specific specialist package | Subcontract | LS | Specialist subcontract | N/A | N/A | 1 | Project-specific | 13-Aug-2026 | Job override required | Relevant specialist | Quote / PC allowance shown in Resource Build-Up |  | Only scope stated on build-up row | Unstated scope | Low | RED - quote or job-specific evidence required | Base $1 forces explicit job-rate override
OTH-GENERAL | Other | Project-specific transparent allowance | Other | LS | Job-specific | N/A | N/A | 1 | Project-specific | 13-Aug-2026 | Job override required | Estimator allowance | Basis shown in Resource Build-Up |  | Only scope stated on build-up row | Unstated scope | Medium | RED - quote or job-specific evidence required | Base $1 forces explicit job-rate override
OTH-DISPOSAL | Other | Clean spoil disposal / tipping fee | Other | t | Commercial tip | N/A | N/A | 22 | Auckland | 13-Aug-2026 | Template market benchmark | Auckland disposal market | Template baseline dated 13-Aug-2026 |  | Clean spoil tipping | Haul and contaminated material | High | AMBER - benchmark/allowance only
LAB-RIGGER | Labour | Certified crane rigger / dogman / lifting crew | Labour | hr | Specialist labour / subcontract | N/A | N/A | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Crane / rigging subcontractor | Quote required | Minimum call-out by quote | Certified rigger/dogman labour to stated lift methodology | Crane, rigging gear, travel and overtime unless specifically included | Low | RED - quote or job-specific evidence required | Base $1 forces explicit job-rate override; verify competency and crew composition.
PL-CRANE-70AT | Plant | 70 t all-terrain mobile crane wet hire | Plant | hr | Specialist crane hire | Yes | Yes | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Mobile crane supplier | Quote required | Minimum hire + mobilisation by quote | Crane, operator and normal fuel subject to supplier quote | Mobilisation, ballast transport, rigging, dogman, mats, travel/overtime unless included | Low | RED - quote or job-specific evidence required | Capacity class only. Verify certified load chart, lift radius, ballast, outrigger reactions, access and minimum hire.
PL-CRANE-90AT | Plant | 90 t all-terrain mobile crane wet hire | Plant | hr | Specialist crane hire | Yes | Yes | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Mobile crane supplier | Quote required | Minimum hire + mobilisation by quote | Crane, operator and normal fuel subject to supplier quote | Mobilisation, ballast transport, rigging, dogman, mats, travel/overtime unless included | Low | RED - quote or job-specific evidence required | Capacity class only. Verify certified load chart, lift radius, ballast, outrigger reactions, access and minimum hire.
PL-CRANE-120AT | Plant | 120 t all-terrain mobile crane wet hire | Plant | hr | Specialist crane hire | Yes | Yes | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Mobile crane supplier | Quote required | Minimum hire + mobilisation by quote | Crane, operator and normal fuel subject to supplier quote | Mobilisation, ballast transport, rigging, dogman, mats, travel/overtime unless included | Low | RED - quote or job-specific evidence required | Capacity class only. Verify certified load chart, lift radius, ballast, outrigger reactions, access and minimum hire.
PL-CRANE-MATS | Plant | Crane mats / outrigger spreader mats hire set | Plant | day | Specialist hire | N/A | N/A | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Crane / temporary works supplier | Quote required | Minimum hire / transport by quote | Mats/spreader set to supplier/temp-works requirement | Transport, placement, design/certification and abnormal ground treatment unless included | Low | RED - quote or job-specific evidence required | Base $1 forces explicit job override. Check whether crane supplier already includes mats to avoid duplication.
PL-RIGGING-SET | Plant | Certified crane rigging / lifting gear set | Plant | day | Specialist hire | N/A | N/A | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Crane / rigging supplier | Quote required | Minimum hire / mobilisation by quote | Certified slings, shackles and stated lifting gear set | Project-specific lifting beam, proprietary clutches, engineered lifting frame and rigger labour unless included | Low | RED - quote or job-specific evidence required | Base $1 forces explicit job override; reconcile with crane quote and precaster lifting requirements.
PL-TRUCK-6W | Plant | 6-wheel tip truck wet hire | Plant | hr | Wet hire / cartage | Yes | Yes | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Civil cartage supplier | Quote required | Minimum hours / travel by quote | Truck, driver and normal fuel subject to quote | Tipping fees, material supply, permits and abnormal waiting unless included | Low | RED - quote or job-specific evidence required | Use for internal/site cartage where hourly wet hire is the truthful basis; do not duplicate supplier-delivery charges.
PL-TRANSPORT-HEAVY | Plant | Heavy / oversize transporter or precast internal haul | Plant | trip | Specialist transport | Yes | Yes | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Heavy transport / precast carrier | Quote required | Mobilisation, permits and escort by quote | Transport vehicle and driver to stated route/load | Craneage, loading/unloading, permits/escorts and route strengthening unless included | Low | RED - quote or job-specific evidence required | Use only where contractor transport scope is confirmed. Verify route, axle/load limits, turning and delivery responsibility.
OTH-CARTAGE-LOAD | Other | Supplier delivery / cartage charge per load | Other | load | Job-specific supplier delivery | N/A | N/A | 1 | Project-specific | 15-Aug-2026 | Job override required | Material supplier / carrier | Quote required | Load size / zone / minimum by quote | Delivery/cartage charge only to stated site and load size | Material supply, waiting time, tipping, permits and rehandling unless included | Low | RED - quote or job-specific evidence required | Reusable cost code only; project location, load size and delivered rate must be overridden from current evidence.
SUB-PROOFROLL | Subcontract | Proof-roll / working-platform verification / field testing attendance | Subcontract | LS | Specialist subcontract | N/A | N/A | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Geotech / testing provider | Quote required | Attendance / testing scope by quote | Proof-roll or stated field-verification/testing attendance | Temporary works design, geotech design certification, remediation and repeat visits unless included | Low | RED - quote or job-specific evidence required | Keep testing/verification separate from temporary-works design and from physical platform construction.
MAT-GEOGRID | Material | Geogrid / ground-stabilisation reinforcement - project specified | Material | m2 | Merchant supply | N/A | N/A | 1 | NZ / AU project-specific | 15-Aug-2026 | Job override required | Civil merchant / geosynthetics supplier | Quote required | Product/specification by quote | Specified geogrid material only | Design, geotextile, aggregate, installation and laps/waste unless included | Low | RED - quote or job-specific evidence required | No generic rate. Select product from temporary works/geotech design and obtain project-specific quote.
HIST-LAB-FOREMAN-01 | Labour | Civil foreman / working foreman - historical contractor benchmark | Labour | hr | Internal / agency | N/A | N/A | 65 | Auckland / NZ | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark | HBR-001; comparison baseline LAB-FOREMAN = $64.00/hr |  | Direct employment allowance | Margin, vehicle, overtime | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-LAB-SUPERVISOR-01 | Labour | Site supervisor / project manager - historical contractor benchmark | Labour | hr | Internal / agency | N/A | N/A | 70 | Auckland / NZ | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark | HBR-002; comparison baseline LAB-SUPERVISOR = $73.00/hr |  | Direct employment allowance | Margin, vehicle, overtime | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-LAB-DRAINLAYER-01 | Labour | Registered drainlayer / pipe layer - historical contractor benchmark | Labour | hr | Internal / agency | N/A | N/A | 45 | Auckland / NZ | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark | HBR-003; comparison baseline LAB-DRAINLAYER = $51.00/hr |  | Direct employment allowance | Vehicle and overtime | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-PL-EXC-1.7-01 | Plant | 1.7 t excavator wet hire - historical contractor benchmark | Plant | hr | Wet hire | Yes | Yes | 75 | Auckland | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark | HBR-004; comparison baseline PL-EXC-1.7 = $85.00/hr | Delivery by quote | Machine, operator, fuel and normal buckets | Delivery, overtime and specialist attachments | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-MAT-AP65-01 | Material | AP65 subbase aggregate - historical contractor benchmark | Material | t | Merchant supply | N/A | N/A | 29 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Auckland quarry historical contractor basis | HBR-005; comparison baseline MAT-AP65 = $30.50/t |  | Ex-quarry / base material allowance | Haul and placement; confirm whether historical contractor $/t basis includes T&T direct delivery | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-MAT-AP40-01 | Material | AP40 / GAP40 basecourse aggregate - historical contractor benchmark | Material | t | Merchant supply | N/A | N/A | 29 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Auckland quarry historical contractor basis | HBR-006; comparison baseline MAT-AP40 = $31.00/t |  | Ex-quarry / base material allowance | Haul and placement; confirm whether historical contractor $/t basis includes T&T direct delivery | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-MAT-DRAINAGG-01 | Material | Drainage aggregate - historical contractor benchmark | Material | t | Merchant supply | N/A | N/A | 36 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Auckland quarry historical contractor basis | HBR-007; comparison baseline MAT-DRAINAGG = $48.50/t |  | Aggregate | Haul and placement; confirm whether historical contractor $/t basis includes T&T direct delivery | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-MAT-SWMH-01 | Material | Precast stormwater manhole set - historical contractor benchmark | Material | ea | Precast supplier | N/A | N/A | 7000 | Auckland | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark / authority requirement | HBR-008; comparison baseline MAT-SWMH = $5,500/ea |  | Chamber, riser, lid and safety grate allowance | Excavation, concrete and installation | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-OTH-FACILITIES-01 | Other | Temporary facilities, utilities and welfare weekly allowance - historical benchmark | Other | week | Job-specific / hire allowance | N/A | N/A | 410 | Auckland | 17-Aug-2026 | Historical contractor benchmark (AMBER) | Internal historical contractor benchmark | HBR-009; 20-week historical control = $8,200 | Confirm hire minimums and mobilisation | Weekly facilities, toilet, temporary power/water and consumables allowance | Mobilisation, site-specific setup and abnormal servicing unless confirmed | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-SUB-SURVEY-SET-01 | Subcontract | Drainage construction setout package - historical benchmark | Subcontract | LS | Specialist subcontract | N/A | N/A | 1500 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Historical survey supplier - identity withheld in client issue | HBR-010; historical rate recorded excl. GST | One drainage setout package | Drainage construction setout | Other survey, rework, as-builts and additional visits | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-SUB-SURVEY-ASB-01 | Subcontract | Drainage as-built survey package - historical benchmark | Subcontract | LS | Specialist subcontract | N/A | N/A | 2500 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Historical survey supplier - identity withheld in client issue | HBR-011; historical rate recorded excl. GST | One drainage as-built package | Drainage as-built survey | Setout, other survey, rework and additional visits | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-SUB-GPR-VISIT-01 | Subcontract | GPR utility-locating visit - historical benchmark | Subcontract | visit | Specialist subcontract | N/A | N/A | 250 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Historical utility-locating supplier - identity withheld in client issue | HBR-012; historical commercial basis requires verification | Per visit; minimums and mobilisation to confirm | GPR utility-locating visit | Potholing, traffic management, additional visits and formal report unless confirmed | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-SUB-TMP-DAY-01 | Subcontract | Traffic management delivery day - historical benchmark | Subcontract | day | Specialist subcontract | Yes | Yes | 1600 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Historical traffic-management supplier - identity withheld in client issue | HBR-013; TMP plan/design additional | Daily minimum; confirm working hours | On-site traffic management delivery day | TMP plan/design, approvals, after-hours, fees and extensions | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
HIST-SUB-LINEMARK-01 | Subcontract | Standard line marking - historical benchmark | Subcontract | lm | Specialist subcontract | Yes | Yes | 22 | Auckland | 17-Aug-2026 | Historical supplier benchmark (AMBER) | Historical line-marking supplier - identity withheld in client issue | HBR-014; historical line-marking benchmark | Minimum job charge to confirm | Standard line marking per lineal metre | Arrows, symbols, accessible markings, signs, preparation and traffic management unless quoted | Medium | AMBER - historical benchmark only | Verify against current project/company/supplier evidence before use.
MAT-AP20 | Material | AP20 / GAP20 basecourse aggregate | Material | t | Merchant supply | N/A | N/A | 39.5 | Auckland | 11-May-2026 | Published supplier price | The Urban Quarry - Onehunga | https://www.urbanquarry.co.nz/pricelist-2-2 |  | Ex-gate aggregate supply | GST, delivery/haul and placement | High | AMBER - current published price; delivered project quote required | Valid from 11-May-2026 until further notice; current web check 06-Sep-2026.
MAT-MESH665 | Material | 665 reinforcing mesh 4.51m x 1.96m | Material | sheet | Merchant supply | N/A | N/A | 62.5 | Auckland | 06-Sep-2026 | Current published supplier price | Quality Steel Supplies Auckland | https://qualitysteelsupplies.co.nz/shop/ |  | 665 mesh sheet supply | Delivery, laps/waste, chairs and installation | High | AMBER - current supplier price; project order/delivery quote required | Current published price excl. GST. Effective cover/waste to be calculated in job build-up.
MAT-KEYSTONE-COMPAC | Material | Firth Keystone Compac III straight-face block | Material | ea | Merchant / manufacturer supply | N/A | N/A | 19.35 | Auckland / NZ | 06-Sep-2026 | Current published market benchmark | Mighty Outdoor; Firth technical cross-check | https://www.mightyoutdoor.co.nz/retaining-wall-selection/firth-retaining-blocks/keycomiii.html ¦ https://www.firth.co.nz/paving-and-retaining/retaining-and-fences/compac-iii |  | Straight-face Compac III block supply | Freight, pins, caps, corners, no-fines concrete and installation | Medium | AMBER - published market benchmark; project supplier quote required | $22.25 incl. GST converted to $19.35 excl. GST; Bunnings current independent price is higher.
MAT-KEYSTONE-CAP | Material | Firth Keystone Compac III capping unit | Material | ea | Merchant / manufacturer supply | N/A | N/A | 12.57 | Auckland / NZ | 06-Sep-2026 | Current published market benchmark | Bunnings NZ; Firth technical cross-check | https://www.bunnings.co.nz/firth-100-x-457-x-270mm-compac-iii-rockface-keystone-retaining-cap_p0271202 ¦ https://www.firth.co.nz/paving-and-retaining/retaining-and-fences/compac-iii |  | Compac III cap supply | Freight, adhesive, blocks, corners and installation | Medium | AMBER - published market benchmark; project supplier quote required | $14.45 incl. GST converted to $12.57 excl. GST. Confirm actual trade/supplier rate and colour.
PL-EXC-3-INHOUSE | Plant | 3.0 t excavator in-house historical project rate - operator included | Plant | hr | In-house / historical company-project control | Yes | Unclear - historical rate treated all-in; no separate fuel added | 97.5 | Auckland | 19-Mar-2026 | Historical project estimate / company control | 48 Eastglen Road - Blackline estimate cost tracker | Blackline_Estimate_Cost_Tracker_48_Eastglen.xlsx / 48 Eastglen project |  | 3.0t excavator historical direct project rate incl. operator | Specialist auger attachment, mobilisation, overtime; fuel basis not separately evidenced | Medium | AMBER - company comparable; current-project productivity/plant availability to verify | Use only as an in-house self-perform control. Independent reasonableness check: current 5.5t wet hire = $110/hr; do not add a separate operator.
PL-AUGER-3T-INHOUSE | Plant | 3 t excavator auger / drill attachment in-house historical project rate | Plant | hr | In-house / historical company-project control | N/A | N/A | 22.5 | Auckland | 19-Mar-2026 | Historical project estimate / company control | 48 Eastglen Road - Blackline estimate cost tracker | Blackline_Estimate_Cost_Tracker_48_Eastglen.xlsx / 48 Eastglen project |  | Auger / drill attachment historical project rate | Excavator, operator, mobilisation, extraordinary wear, specialist casing/formtube | Medium | AMBER - company comparable; confirm 450/500mm tooling and condition | Eastglen comparable used 3t drill gear as a separate plant resource. Pair with PL-EXC-3-INHOUSE; do not duplicate machine/operator.
OTH-PORTABLE-TOILET | Other | Portable toilet hire and servicing - tender benchmark | Other | week | Hire allowance | N/A | N/A | 120 | Auckland / NZ | 08-Sep-2026 | Reviewed comparable estimate allowance | 3Bears / Orion Point Stage 5 | Orion_Point_Stage5_Client_Estimate_Report_Draft.pdf | Confirm delivery/pickup/servicing | Portable toilet weekly hire/service allowance | Abnormal servicing, damage, relocation and project-specific supplier minimums | Medium | AMBER - comparable estimate benchmark | Use as tender benchmark only; replace with Siteworks/supplier actual if provided.
OTH-SITE-LOCKUP | Other | 20ft lockable container / site lockup - tender benchmark | Other | week | Hire allowance | N/A | N/A | 175 | Auckland / NZ | 08-Sep-2026 | Reviewed comparable estimate allowance | 3Bears / Orion Point Stage 5 | Orion_Point_Stage5_Client_Estimate_Report_Draft.pdf | Confirm delivery/pickup/minimum hire | 20ft lockable container / site lockup weekly allowance | Separate office cabin, abnormal delivery/craneage, power and security | Medium | AMBER - comparable estimate benchmark | Use as tender benchmark only; replace with Siteworks/supplier actual if provided.
OTH-PLANT-TRANSPORT-PROXY | Other | Plant mobilisation / transporter wet-hire proxy | Other | hr | Transport allowance | Yes | Yes | 175 | Auckland / NZ | 08-Sep-2026 | Current published supplier benchmark | ASAP Machine Hire & Earthworks | https://www.asapmachinehire.co.nz/price-list | Actual 5.5t+ transporter rates by quote | Truck/trailer, driver and normal fuel benchmark | Heavy transporter premium, permits, escorts, waiting and abnormal access | Medium | AMBER - transport proxy / heavy transporter rate to verify | Published truck-and-trailer wet-hire benchmark only. ASAP states 5.5t+ transporter rates are by quote.
MAT-SILTFENCE-50 | Material | Cirtex premium silt fence 1.0 x 50m, code 76027 | Material | roll | Merchant supply | N/A | N/A | 87.07 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS / Cirtex 76027 | CARTERS Standard Price Book export 08-Sep-2026 | 50m roll | Fabric supply only | Posts, wire, clips/pins, caps, delivery and installation | High | GREEN - current account rate + independent current retail + quantity check | CARTERS $87.07/roll excl GST. Independent Mitre10 $72.98. https://www.mitre10.co.nz/shop/strol-cirtex-silt-fence-woven-silt-sediment-control-fabric-1m-x-50m-black/p/228126
MAT-YPOST-180 | Material | Fencing standard Y post 1.80m | Material | ea | Merchant supply | N/A | N/A | 12.8 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS | CARTERS Standard Price Book export 08-Sep-2026 | Each | 1.8m Y post supply | Safety cap, delivery and installation | High | GREEN - current account rate + independent retail + spacing check | CARTERS $12.80/ea excl GST. Bunnings current $11.93. https://www.bunnings.co.nz/summit-steel-wire-1-8m-black-y-post_p0814015
MAT-YPOST-CAP | Material | Safety cap for starter / Y post | Material | ea | Merchant supply | N/A | N/A | 0.98 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS | CARTERS Standard Price Book export 08-Sep-2026 | Each | Safety cap supply | Post and installation | Medium | AMBER - current primary price / independent direct price incomplete | One cap per Y post.
MAT-WIRE-HT650 | Material | Premium fencing wire 2.5mm HT, 25kg / 650m coil | Material | coil | Merchant supply | N/A | N/A | 114.91 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS | CARTERS Standard Price Book export 08-Sep-2026 | 650m coil | High-tensile support wire | Fixings and installation | Medium | AMBER - current primary price | One coil exceeds current working fence length and leaves repair reserve.
MAT-SILTFENCE-PINS100 | Material | Cirtex 75mm SiltFence pins - 100 pack | Material | bag | Retail / merchant | N/A | N/A | 27 | NZ / Auckland | 09-Sep-2026 | Current published retail | Bunnings NZ / Cirtex 76062 | https://www.bunnings.co.nz/search/products?q=siltfence+pack | 100 pins/bag | Pins for fixing fence fabric to support wire | Delivery and installation | Medium | AMBER - current retail / project merchant quote not held | Cirtex guidance permits pins/clips; high-tensile wire basis uses up to 500mm fixing spacing.
MAT-WIRE-STRAINER | Material | Wire strainer clip-lock type | Material | ea | Merchant supply | N/A | N/A | 4.88 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS / Strainrite | CARTERS Standard Price Book export 08-Sep-2026 | Each | Wire strainer supply | Installation | Medium | AMBER - current primary / functional equivalent | Cirtex calculator calls for one wire strainer per 25m; exact proprietary strainer not project-specified.
MAT-GEOTEX-AS280ROLL | Material | Duraforce AS280 geotextile 1.9 x 50m roll, code 76021 | Material | roll | Merchant supply | N/A | N/A | 176.64 | Auckland / NZ | 08-Sep-2026 | Current account pricebook | CARTERS / Cirtex | CARTERS Standard Price Book export 08-Sep-2026 | 95m2 roll | Geotextile material | Delivery and placement | Medium | AMBER - current primary / final approved geotextile grade to confirm | One roll covers 49m2 entrance including overlaps/cuts.
MAT-ESC-AGG15050 | Material | SGC 150/50 aggregate - stabilised entrance size control | Material | t | Quarry supply | N/A | N/A | 42 | Auckland / NZ | 09-Sep-2026 | Current published quarry price | The Landing Quarry - Mangere | https://www.thelandingquarry.co.nz/products | Ex-gate; published density 1.05t/m3 | 150/50 aggregate supply | Delivery, placement; washed status/project acceptance not explicitly confirmed | Medium | AMBER - exact size current / washed status and delivery to confirm | DWG241 requires 50-150mm washed aggregate. Published SGC150/50 matches size; source warns engineering gradings require project testing/confirmation.

## Rate Verification
RATE & ALLOWANCE VERIFICATION - MASTER ESTIMATE WORKBOOK
GREEN requires: (1) current primary evidence, (2) an independent market check, and (3) a first-principles quantity/scope/arithmetic check. Anything less is AMBER; missing or conflicting is RED.
Status | Active rows | Cost exposure excl. GST |  | Status | Active rows | Cost exposure excl. GST
GREEN |  |  |  | RED
AMBER |  |  |  | Release gate | Tender issue only | RED items must be disclosed and replaced before award
Audit ID | Build-Up Row | QS Code | WBS / Section | Task / Method | Resource Code | Resource | Unit | Applied Rate | Extended Cost | Evidence 1 - primary/current | Result 1 | Evidence 2 - independent check | Result 2 | Evidence 3 - build-up/scope | Result 3 | Score | Source Date | Confidence | Release Status | Required Action | Scope / Assumption
RV-001
RV-002
RV-003
RV-004
RV-005
RV-006
RV-007
RV-008
RV-009
RV-010
RV-011
RV-012
RV-013
RV-014
RV-015
RV-016
RV-017
RV-018
RV-019
RV-020
RV-021
RV-022
RV-023
RV-024
RV-025
RV-026
RV-027
RV-028
RV-029
RV-030
RV-031
RV-032
RV-033
RV-034
RV-035
RV-036
RV-037
RV-038
RV-039
RV-040
RV-041
RV-042
RV-043
RV-044
RV-045
RV-046
RV-047
RV-048
RV-049
RV-050
RV-051
RV-052
RV-053
RV-054
RV-055
RV-056
RV-057
RV-058
RV-059
RV-060
RV-061
RV-062
RV-063
RV-064
RV-065
RV-066
RV-067
RV-068
RV-069
RV-070
RV-071
RV-072
RV-073
RV-074
RV-075
RV-076
RV-077
RV-078
RV-079
RV-080
RV-081
RV-082
RV-083
RV-084
RV-085
RV-086
RV-087
RV-088
RV-089
RV-090
RV-091
RV-092
RV-093
RV-094
RV-095
RV-096
RV-097
RV-098
RV-099
RV-100
RV-101
RV-102
RV-103
RV-104
RV-105
RV-106
RV-107
RV-108
RV-109
RV-110
RV-111
RV-112
RV-113
RV-114
RV-115
RV-116
RV-117
RV-118
RV-119
RV-120
RV-121
RV-122
RV-123
RV-124
RV-125
RV-126
RV-127
RV-128
RV-129
RV-130
RV-131
RV-132
RV-133
RV-134
RV-135
RV-136
RV-137
RV-138
RV-139
RV-140
RV-141
RV-142
RV-143
RV-144
RV-145
RV-146
RV-147
RV-148
RV-149
RV-150
RV-151
RV-152
RV-153
RV-154
RV-155
RV-156
RV-157
RV-158
RV-159
RV-160
RV-161
RV-162
RV-163
RV-164
RV-165
RV-166
RV-167
RV-168
RV-169
RV-170
RV-171
RV-172
RV-173
RV-174
RV-175
RV-176
RV-177
RV-178
RV-179
RV-180
RV-181
RV-182
RV-183
RV-184
RV-185
RV-186
RV-187
RV-188
RV-189
RV-190
RV-191
RV-192
RV-193
RV-194
RV-195
RV-196
RV-197
RV-198
RV-199
RV-200
RV-201
RV-202
RV-203
RV-204
RV-205
RV-206
RV-207
RV-208
RV-209
RV-210
RV-211
RV-212
RV-213
RV-214
RV-215
RV-216
RV-217
RV-218
RV-219
RV-220
RV-221
RV-222
RV-223
RV-224
RV-225
RV-226
RV-227
RV-228
RV-229
RV-230
RV-231
RV-232
RV-233
RV-234
RV-235
RV-236
RV-237
RV-238
RV-239
RV-240
RV-241
RV-242
RV-243
RV-244
RV-245
RV-246
RV-247
RV-248
RV-249
RV-250
RV-251
RV-252
RV-253
RV-254
RV-255
RV-256
RV-257
RV-258
RV-259
RV-260
RV-261
RV-262
RV-263
RV-264
RV-265
RV-266
RV-267
RV-268
RV-269
RV-270
RV-271
RV-272
RV-273
RV-274
RV-275
RV-276
RV-277
RV-278
RV-279
RV-280
RV-281
RV-282
RV-283
RV-284
RV-285
RV-286
RV-287
RV-288
RV-289
RV-290
RV-291
RV-292
RV-293
RV-294
RV-295
RV-296
RV-297
RV-298
RV-299
RV-300

## Programme Export
PROGRAMME BUILD-UP & MICROSOFT PROJECT EXPORT - MASTER ESTIMATE WORKBOOK
Programme durations derive from Resource Build-Up quantity/productivity unless an explicit programme override is entered. Set the current project calendar, start date, holidays, shutdowns and work fronts before issue.
MS Project: import Tasks and map Name, Duration, Predecessors, Fixed Cost, Text fields, Notes, Task Mode and Fixed Cost Accrual. Do not also import the same resource costs when Fixed Cost is used, or costs will double.
Microsoft import guidance: https://support.microsoft.com/en-us/project/export-or-import-data-to-another-file-format
PROGRAMME RECONCILIATION: J takes the largest linked Resource Build-Up applied duration for each QS code; K converts hours to working days; M uses the override in L when one is entered. Rows 7-206 follow QS Takeoff rows 3-202. Control tasks that are not QS items (cure, inspection holds, proof rolls) go in rows 207-226: type the code in D, the name in E, the days in L and predecessor codes in P.
Import ID | QS Row | WBS / Section | QS Code | Task Name | Quantity | Unit | QS Fixed Cost | Resource Cost Check | Max Resource Duration hrs | Derived Duration days | Programme Override days | Export Duration days | Duration | Duration Basis | Predecessor QS Codes | Predecessors | Resource Summary | Rate QA Status | QS / Resource Difference | Cost Check | Task Mode | Cost Accrual | Notes | Task sequence (helper)
1 | 3 | [19 empty] | Auto Scheduled | Prorated
2 | 4 | [19 empty] | Auto Scheduled | Prorated
3 | 5 | [19 empty] | Auto Scheduled | Prorated
4 | 6 | [19 empty] | Auto Scheduled | Prorated
5 | 7 | [19 empty] | Auto Scheduled | Prorated
6 | 8 | [19 empty] | Auto Scheduled | Prorated
7 | 9 | [19 empty] | Auto Scheduled | Prorated
8 | 10 | [19 empty] | Auto Scheduled | Prorated
9 | 11 | [19 empty] | Auto Scheduled | Prorated
10 | 12 | [19 empty] | Auto Scheduled | Prorated
11 | 13 | [19 empty] | Auto Scheduled | Prorated
12 | 14 | [19 empty] | Auto Scheduled | Prorated
13 | 15 | [19 empty] | Auto Scheduled | Prorated
14 | 16 | [19 empty] | Auto Scheduled | Prorated
15 | 17 | [19 empty] | Auto Scheduled | Prorated
16 | 18 | [19 empty] | Auto Scheduled | Prorated
17 | 19 | [19 empty] | Auto Scheduled | Prorated
18 | 20 | [19 empty] | Auto Scheduled | Prorated
19 | 21 | [19 empty] | Auto Scheduled | Prorated
20 | 22 | [19 empty] | Auto Scheduled | Prorated
21 | 23 | [19 empty] | Auto Scheduled | Prorated
22 | 24 | [19 empty] | Auto Scheduled | Prorated
23 | 25 | [19 empty] | Auto Scheduled | Prorated
24 | 26 | [19 empty] | Auto Scheduled | Prorated
25 | 27 | [19 empty] | Auto Scheduled | Prorated
26 | 28 | [19 empty] | Auto Scheduled | Prorated
27 | 29 | [19 empty] | Auto Scheduled | Prorated
28 | 30 | [19 empty] | Auto Scheduled | Prorated
29 | 31 | [19 empty] | Auto Scheduled | Prorated
30 | 32 | [19 empty] | Auto Scheduled | Prorated
31 | 33 | [19 empty] | Auto Scheduled | Prorated
32 | 34 | [19 empty] | Auto Scheduled | Prorated
33 | 35 | [19 empty] | Auto Scheduled | Prorated
34 | 36 | [19 empty] | Auto Scheduled | Prorated
35 | 37 | [19 empty] | Auto Scheduled | Prorated
36 | 38 | [19 empty] | Auto Scheduled | Prorated
37 | 39 | [19 empty] | Auto Scheduled | Prorated
38 | 40 | [19 empty] | Auto Scheduled | Prorated
39 | 41 | [19 empty] | Auto Scheduled | Prorated
40 | 42 | [19 empty] | Auto Scheduled | Prorated
41 | 43 | [19 empty] | Auto Scheduled | Prorated
42 | 44 | [19 empty] | Auto Scheduled | Prorated
43 | 45 | [19 empty] | Auto Scheduled | Prorated
44 | 46 | [19 empty] | Auto Scheduled | Prorated
45 | 47 | [19 empty] | Auto Scheduled | Prorated
46 | 48 | [19 empty] | Auto Scheduled | Prorated
47 | 49 | [19 empty] | Auto Scheduled | Prorated
48 | 50 | [19 empty] | Auto Scheduled | Prorated
49 | 51 | [19 empty] | Auto Scheduled | Prorated
50 | 52 | [19 empty] | Auto Scheduled | Prorated
51 | 53 | [19 empty] | Auto Scheduled | Prorated
52 | 54 | [19 empty] | Auto Scheduled | Prorated
53 | 55 | [19 empty] | Auto Scheduled | Prorated
54 | 56 | [19 empty] | Auto Scheduled | Prorated
55 | 57 | [19 empty] | Auto Scheduled | Prorated
56 | 58 | [19 empty] | Auto Scheduled | Prorated
57 | 59 | [19 empty] | Auto Scheduled | Prorated
58 | 60 | [19 empty] | Auto Scheduled | Prorated
59 | 61 | [19 empty] | Auto Scheduled | Prorated
60 | 62 | [19 empty] | Auto Scheduled | Prorated
61 | 63 | [19 empty] | Auto Scheduled | Prorated
62 | 64 | [19 empty] | Auto Scheduled | Prorated
63 | 65 | [19 empty] | Auto Scheduled | Prorated
64 | 66 | [19 empty] | Auto Scheduled | Prorated
65 | 67 | [19 empty] | Auto Scheduled | Prorated
66 | 68 | [19 empty] | Auto Scheduled | Prorated
67 | 69 | [19 empty] | Auto Scheduled | Prorated
68 | 70 | [19 empty] | Auto Scheduled | Prorated
69 | 71 | [19 empty] | Auto Scheduled | Prorated
70 | 72 | [19 empty] | Auto Scheduled | Prorated
71 | 73 | [19 empty] | Auto Scheduled | Prorated
72 | 74 | [19 empty] | Auto Scheduled | Prorated
73 | 75 | [19 empty] | Auto Scheduled | Prorated
74 | 76 | [19 empty] | Auto Scheduled | Prorated
75 | 77 | [19 empty] | Auto Scheduled | Prorated
76 | 78 | [19 empty] | Auto Scheduled | Prorated
77 | 79 | [19 empty] | Auto Scheduled | Prorated
78 | 80 | [19 empty] | Auto Scheduled | Prorated
79 | 81 | [19 empty] | Auto Scheduled | Prorated
80 | 82 | [19 empty] | Auto Scheduled | Prorated
81 | 83 | [19 empty] | Auto Scheduled | Prorated
82 | 84 | [19 empty] | Auto Scheduled | Prorated
83 | 85 | [19 empty] | Auto Scheduled | Prorated
84 | 86 | [19 empty] | Auto Scheduled | Prorated
85 | 87 | [19 empty] | Auto Scheduled | Prorated
86 | 88 | [19 empty] | Auto Scheduled | Prorated
87 | 89 | [19 empty] | Auto Scheduled | Prorated
88 | 90 | [19 empty] | Auto Scheduled | Prorated
89 | 91 | [19 empty] | Auto Scheduled | Prorated
90 | 92 | [19 empty] | Auto Scheduled | Prorated
91 | 93 | [19 empty] | Auto Scheduled | Prorated
92 | 94 | [19 empty] | Auto Scheduled | Prorated
93 | 95 | [19 empty] | Auto Scheduled | Prorated
94 | 96 | [19 empty] | Auto Scheduled | Prorated
95 | 97 | [19 empty] | Auto Scheduled | Prorated
96 | 98 | [19 empty] | Auto Scheduled | Prorated
97 | 99 | [19 empty] | Auto Scheduled | Prorated
98 | 100 | [19 empty] | Auto Scheduled | Prorated
99 | 101 | [19 empty] | Auto Scheduled | Prorated
100 | 102 | [19 empty] | Auto Scheduled | Prorated
101 | 103 | [19 empty] | Auto Scheduled | Prorated
102 | 104 | [19 empty] | Auto Scheduled | Prorated
103 | 105 | [19 empty] | Auto Scheduled | Prorated
104 | 106 | [19 empty] | Auto Scheduled | Prorated
105 | 107 | [19 empty] | Auto Scheduled | Prorated
106 | 108 | [19 empty] | Auto Scheduled | Prorated
107 | 109 | [19 empty] | Auto Scheduled | Prorated
108 | 110 | [19 empty] | Auto Scheduled | Prorated
109 | 111 | [19 empty] | Auto Scheduled | Prorated
110 | 112 | [19 empty] | Auto Scheduled | Prorated
111 | 113 | [19 empty] | Auto Scheduled | Prorated
112 | 114 | [19 empty] | Auto Scheduled | Prorated
113 | 115 | [19 empty] | Auto Scheduled | Prorated
114 | 116 | [19 empty] | Auto Scheduled | Prorated
115 | 117 | [19 empty] | Auto Scheduled | Prorated
116 | 118 | [19 empty] | Auto Scheduled | Prorated
117 | 119 | [19 empty] | Auto Scheduled | Prorated
118 | 120 | [19 empty] | Auto Scheduled | Prorated
119 | 121 | [19 empty] | Auto Scheduled | Prorated
120 | 122 | [19 empty] | Auto Scheduled | Prorated
121 | 123 | [19 empty] | Auto Scheduled | Prorated
122 | 124 | [19 empty] | Auto Scheduled | Prorated
123 | 125 | [19 empty] | Auto Scheduled | Prorated
124 | 126 | [19 empty] | Auto Scheduled | Prorated
125 | 127 | [19 empty] | Auto Scheduled | Prorated
126 | 128 | [19 empty] | Auto Scheduled | Prorated
127 | 129 | [19 empty] | Auto Scheduled | Prorated
128 | 130 | [19 empty] | Auto Scheduled | Prorated
129 | 131 | [19 empty] | Auto Scheduled | Prorated
130 | 132 | [19 empty] | Auto Scheduled | Prorated
131 | 133 | [19 empty] | Auto Scheduled | Prorated
132 | 134 | [19 empty] | Auto Scheduled | Prorated
133 | 135 | [19 empty] | Auto Scheduled | Prorated
134 | 136 | [19 empty] | Auto Scheduled | Prorated
135 | 137 | [19 empty] | Auto Scheduled | Prorated
136 | 138 | [19 empty] | Auto Scheduled | Prorated
137 | 139 | [19 empty] | Auto Scheduled | Prorated
138 | 140 | [19 empty] | Auto Scheduled | Prorated
139 | 141 | [19 empty] | Auto Scheduled | Prorated
140 | 142 | [19 empty] | Auto Scheduled | Prorated
141 | 143 | [19 empty] | Auto Scheduled | Prorated
142 | 144 | [19 empty] | Auto Scheduled | Prorated
143 | 145 | [19 empty] | Auto Scheduled | Prorated
144 | 146 | [19 empty] | Auto Scheduled | Prorated
145 | 147 | [19 empty] | Auto Scheduled | Prorated
146 | 148 | [19 empty] | Auto Scheduled | Prorated
147 | 149 | [19 empty] | Auto Scheduled | Prorated
148 | 150 | [19 empty] | Auto Scheduled | Prorated
149 | 151 | [19 empty] | Auto Scheduled | Prorated
150 | 152 | [19 empty] | Auto Scheduled | Prorated
151 | 153 | [19 empty] | Auto Scheduled | Prorated
152 | 154 | [19 empty] | Auto Scheduled | Prorated
153 | 155 | [19 empty] | Auto Scheduled | Prorated
154 | 156 | [19 empty] | Auto Scheduled | Prorated
155 | 157 | [19 empty] | Auto Scheduled | Prorated
156 | 158 | [19 empty] | Auto Scheduled | Prorated
157 | 159 | [19 empty] | Auto Scheduled | Prorated
158 | 160 | [19 empty] | Auto Scheduled | Prorated
159 | 161 | [19 empty] | Auto Scheduled | Prorated
160 | 162 | [19 empty] | Auto Scheduled | Prorated
161 | 163 | [19 empty] | Auto Scheduled | Prorated
162 | 164 | [19 empty] | Auto Scheduled | Prorated
163 | 165 | [19 empty] | Auto Scheduled | Prorated
164 | 166 | [19 empty] | Auto Scheduled | Prorated
165 | 167 | [19 empty] | Auto Scheduled | Prorated
166 | 168 | [19 empty] | Auto Scheduled | Prorated
167 | 169 | [19 empty] | Auto Scheduled | Prorated
168 | 170 | [19 empty] | Auto Scheduled | Prorated
169 | 171 | [19 empty] | Auto Scheduled | Prorated
170 | 172 | [19 empty] | Auto Scheduled | Prorated
171 | 173 | [19 empty] | Auto Scheduled | Prorated
172 | 174 | [19 empty] | Auto Scheduled | Prorated
173 | 175 | [19 empty] | Auto Scheduled | Prorated
174 | 176 | [19 empty] | Auto Scheduled | Prorated
175 | 177 | [19 empty] | Auto Scheduled | Prorated
176 | 178 | [19 empty] | Auto Scheduled | Prorated
177 | 179 | [19 empty] | Auto Scheduled | Prorated
178 | 180 | [19 empty] | Auto Scheduled | Prorated
179 | 181 | [19 empty] | Auto Scheduled | Prorated
180 | 182 | [19 empty] | Auto Scheduled | Prorated
181 | 183 | [19 empty] | Auto Scheduled | Prorated
182 | 184 | [19 empty] | Auto Scheduled | Prorated
183 | 185 | [19 empty] | Auto Scheduled | Prorated
184 | 186 | [19 empty] | Auto Scheduled | Prorated
185 | 187 | [19 empty] | Auto Scheduled | Prorated
186 | 188 | [19 empty] | Auto Scheduled | Prorated
187 | 189 | [19 empty] | Auto Scheduled | Prorated
188 | 190 | [19 empty] | Auto Scheduled | Prorated
189 | 191 | [19 empty] | Auto Scheduled | Prorated
190 | 192 | [19 empty] | Auto Scheduled | Prorated
191 | 193 | [19 empty] | Auto Scheduled | Prorated
192 | 194 | [19 empty] | Auto Scheduled | Prorated
193 | 195 | [19 empty] | Auto Scheduled | Prorated
194 | 196 | [19 empty] | Auto Scheduled | Prorated
195 | 197 | [19 empty] | Auto Scheduled | Prorated
196 | 198 | [19 empty] | Auto Scheduled | Prorated
197 | 199 | [19 empty] | Auto Scheduled | Prorated
198 | 200 | [19 empty] | Auto Scheduled | Prorated
199 | 201 | [19 empty] | Auto Scheduled | Prorated
200 | 202 | [19 empty] | Auto Scheduled | Prorated
201 | [20 empty] | Auto Scheduled | Prorated
202 | [20 empty] | Auto Scheduled | Prorated
203 | [20 empty] | Auto Scheduled | Prorated
204 | [20 empty] | Auto Scheduled | Prorated
205 | [20 empty] | Auto Scheduled | Prorated
206 | [20 empty] | Auto Scheduled | Prorated
207 | [20 empty] | Auto Scheduled | Prorated
208 | [20 empty] | Auto Scheduled | Prorated
209 | [20 empty] | Auto Scheduled | Prorated
210 | [20 empty] | Auto Scheduled | Prorated
211 | [20 empty] | Auto Scheduled | Prorated
212 | [20 empty] | Auto Scheduled | Prorated
213 | [20 empty] | Auto Scheduled | Prorated
214 | [20 empty] | Auto Scheduled | Prorated
215 | [20 empty] | Auto Scheduled | Prorated
216 | [20 empty] | Auto Scheduled | Prorated
217 | [20 empty] | Auto Scheduled | Prorated
218 | [20 empty] | Auto Scheduled | Prorated
219 | [20 empty] | Auto Scheduled | Prorated
220 | [20 empty] | Auto Scheduled | Prorated

## MS Project Import
ID | Outline Level | WBS | Task Name | Duration | Predecessors | Fixed Cost | Start | Finish | Resource Names | Category | Source Estimate | Quantity | Unit | Rate | Amount Excl GST | Notes | Predecessor codes | Source row (helper)

## Programme Adjudication
BOARD-ADJUDICATED PROGRAMME LOGIC
Seq | Activity | Duration WD | Predecessor | Workfront | Productive cost? | Evidence / adjudication | Notes

## Programme Notes
MICROSOFT PROJECT HANDOFF / PROGRAMME NOTES
Dry tender baseline
Weather
Calendar / start date
Key interfaces
Procurement lead times
Holds

## Weather Risk
WEATHER RISK — CURRENT LIVE PROJECT BASIS
This is the only current weather sheet for the estimate. It links the approved NZ Weather Risk Estimating Tool basis to live resources, programme, CA10, tender and cashflow. Historical run tabs are archived below for audit only.
LIVE PROJECT / PROGRAMME INPUTS |  |  | INTEGRATION / RELEASE CONTROLS
Project location |  |  | 1 | Weather tool remains the approved climate/task calculation source; this workbook does not replace NIWA/tool logic.
Weather station / representative location |  |  | 2 | CA10 is formula-linked to Selected Weather Allowance. Do not re-enter a flat weather percentage in Commercial Inputs.
Assumed construction start |  |  | 3 | Direct productivity applies only to Resource Build-Up Labour/Plant rows tagged Weather Exposed = Yes. Current exposed pool is $50,807.75; PC packages with no labour/plant split affect delay only where they sit on the critical path.
Baseline working days |  |  | 4 | Critical-path delay is not summed across concurrent tasks. Update the external Weather Tool when sequence or critical path changes.
Working days per week |  |  | 5 | Daily time-related preliminaries come from the Build-Up row linked in B13; weekly billed hire from the rows linked in B14.
Weather-tool weekday-only base finish |  |  | 6 | CA09 dewatering remains separate. Recovery/remediation in this sheet defaults to zero to avoid double counting unless project-specific evidence justifies it.
Public holiday / entered shutdown adjusted base finish |  |  | 7 | Wind proxy is excluded by default and remains AMBER unless a project-specific wind basis is verified.
Weather-exposed labour + plant cost |  |  | 8 | Rerun the Weather Tool when start date, baseline duration, exposed cost mix, work calendar or critical path materially changes.
Daily time-related preliminaries |  |  | 9 | Entered statutory holidays/shutdowns affect calendar completion only; they are not weather delay.
Weekly billed hire / facilities
Baseline billed weeks |  |  | Source / evidence | NIWA 1991-2020 climate normals via NZ_Weather_Risk_Estimating_Tool_Rev2; public holiday dates via Employment New Zealand.
Project-specific recovery / remediation allowance | 0 |  | Holiday source URL | https://www.employment.govt.nz/leave-and-holidays/public-holidays/public-holidays-and-anniversary-dates
WEATHER RUN RECORD (from the approved weather tool, if a run has been made) |  |  | WEATHER / TENDER RECONCILIATION
Approved tool version | NZ_Weather_Risk_Estimating_Tool_Rev2.xlsx |  | Current exposed-cost difference vs tool run
Tool run station |  |  | Current start vs tool run
Tool run start date |  |  | Current baseline WD vs tool run
Tool run baseline working days |  |  | Retained manual CA10 PC reference minus live Weather Engine output
Tool run exposed labour + plant cost |  |  | Selected wind status
Rain / wet-ground direct productivity output
Direct productivity impact rate
Critical-path weather delay working days
Additional billed hire weeks
Wind proxy sensitivity - additional cost
Include AMBER wind proxy? | No
Tool output confidence
Tool rerun status
LIVE WEATHER COST INTEGRATION
Direct productivity allowance - resource linked
Critical-path time-related preliminaries
Additional billed hire / facilities
Project recovery / remediation
Rain + wet-ground allowance
AMBER wind proxy sensitivity
WEATHER ENGINE OUTPUT -> Commercial Inputs CA10 Engine Amount (audit only)
Weather Engine audit output as % of base direct cost
Independent time-related P&G benchmark - daily |  |  | Benchmark source
Weather delay cost at benchmark daily P&G |  |  | Benchmark status
Direct rain/wet productivity + independent benchmark |  |  | Tender decision
Live CA10 Weather Engine difference vs benchmark |  |  | Rerun trigger
Tender delta vs previous approved
Weather-adjusted completion incl. entered non-working dates
Elapsed calendar days from assumed start
TENDER WEATHER INPUT PACKAGE
Programme controlling path
Derived critical-path working days
Tender baseline working days |  |  |  |  | NON-WORKING DATE REGISTER - affects calendar span, not weather probability |  |  |  | Weather Task Type - approved tool library
Weather-sensitive critical-path scope |  |  |  |  | Non-working date | Type / reason | Evidence / note |  | Erosion & sediment controls
Tender-season assumed start / finish | [5 empty] | Project non-working date / shutdown - enter if applicable | Estimator / contract calendar evidence |  | Bulk earthworks
Elapsed calendar span | [8 empty] | Detailed earthworks / trim subgrade
Holiday treatment | [8 empty] | Cut to fill / cartage
Building platform / pad prep
Drainage trenching
Manholes / chambers
Service trenches / ducting
Retaining wall excavation
Retaining wall installation
External concrete placing
External concrete finishing
Kerb & channel
Subbase / pavement prep
Asphalt / sealing
Landscaping / topsoil / grassing
Site establishment / temp fencing
External painting / coatings
QS Code | Weather task type | Start | Finish | Critical path? | Workdays | Exposed labour $ | Exposed plant $ | Avg wet probability | Rain/wet impact | Rain direct $ | Rain CP delay WD | Wind direct $ | Wind CP delay WD
[8 empty] | 37.21% | 13.15% | 506.7155 | 0.39463 | 0 | 0.045161
[8 empty] | 37.21% | 28.47% | 1408.1995 | 1.1387 | 94.9457 | 0.076774
[8 empty] | 37.21% | 28.47% | 5842.1077 | 2.562 | 393.8951 | 0.17274
[8 empty] | 37.21% | 35.17% | 912.9504 | 1.055 | 60.2981 | 0.069677
[8 empty] | 34.77% | 16.69% | 0 | 0.83452 | 0 | 0.049032
[8 empty] | 31.11% | 18.91% | 3752.8914 | 1.8908 | 262.44 | 0.13222
[8 empty] | 31.11% | 18.91% | 0 | 0.94539 | 0 | 0.066111
[8 empty] | 37.21% | 26.89% | 0 | 0 | 0 | 0
[8 empty] | 37.21% | 26.89% | 297.3554 | 0 | 21.2281 | 0
[10 empty] | 12213.5043 | 8.821 | 832.8069 | 0.61172
Weather activity run conclusion
Rain / wet-ground direct productivity
Critical-path rain / wet-ground delay WD
Time-related prelims using current AMBER $1,625/day proxy
Additional billed hire / facilities
Modelled rain + wet-ground allowance (NOT YET PROMOTED)
AMBER wind proxy sensitivity (excluded)

## Risk Truth
RISK TRUTH ENGINE - MASTER ESTIMATE WORKBOOK
Permanent risk-control and reconciliation module. Record tender baseline before residual exposure. Quantifiable physical consequences return to Resource Build-Up / QS Takeoff; specialist engines remain separate. CA01/CA02 receive residual cross-cutting provisions only and are never default project-value percentages.
RISK TRUTH / RELEASE CONTROL | Value / Status |  | INTEGRATION RULES |  |  |  |  | RISK TRUTH COMMERCIAL RECALC | Value
Previous approved tender total (optional) | 0 |  | 1 | Likelihood / impact prioritise management; they never create dollars automatically. |  |  |  | Subtotal before commercial adjustments
Current live tender total |  |  | 2 | Every exposure identifies where the risk is already treated before any residual is considered. |  |  |  | CA17 overhead
Previous approved CA01 (optional) | 0 |  | 3 | Quantifiable physical work returns to Resource Build-Up / QS Takeoff. |  |  |  | CA19 bonds
Previous approved CA02 (optional) | 0 |  | 4 | CA01 / CA02 receive residual cross-cutting provisions only when a more direct cost location is not truthful. |  |  |  | CA20 retention finance
Risk Truth CA01 design/scope residual total |  |  | 5 | Weather remains Weather Risk -> CA10. Dewatering remains CA09 unless separately changed. |  |  |  | CA18 profit
Risk Truth CA02 construction/execution residual total |  |  | 6 | Any RED exposure, unproven duplicate or incomplete programme dependency blocks final release. |  |  |  | Recalculated tender total
Risk Truth recalculated tender total |  |  | 7 | One cost can have several contributing risks, but only one PRIMARY cost-treatment owner.
Live CA01 feed -> Commercial Inputs |  |  | 8 | Actual outcomes are retained later for estimate-v-actual calibration; historic tender assumptions are not overwritten.
Live CA02 feed -> Commercial Inputs |  |  | 9 | CA16 Management Reserve is a separate PROVIDED/AMBER tender-adjudication commercial provision. It does not feed CA01/CA02, is not a Risk Truth contingency, and does not close RED exposures.
Current Risk Truth residual total
Risk Truth release gate
RED risk count
RED exposure count
Duplicate-cost gate
Programme dependency gate
Tender delta vs previous approved
Current tender equals Risk Truth recalculation?
Risk Truth calculation difference
Risk ID | Risk Description | Primary Class | Likelihood | Impact | Rating | Current Response | Owner | RFI / Action | Tender Baseline | Overall Status
Exposure ID
PERMANENT MASTER RELEASE RULES
Rule 1 | Likelihood / impact prioritise management; they do not create dollars automatically.
Rule 2 | Every risk exposure identifies where the risk is already treated before residual cost is considered.
Rule 3 | Quantifiable physical consequences return to Resource Build-Up / QS Takeoff.
Rule 4 | CA01 / CA02 contain residual cross-cutting risk only; generic project-value percentages are prohibited.
Rule 5 | Specialist-engine risks remain in their specialist cost path and are referenced, not duplicated.
Rule 6 | A positive Risk Truth addition requires a distinct residual basis, integration target and evidence status.
Rule 7 | Any RED duplication, programme reconciliation or material risk item blocks final release.
Rule 8 | Actual outcomes are retained later for estimate-v-actual calibration; historic tender assumptions are not overwritten.
MASTER PROMOTION VALIDATION
Cost-chain propagation | PASS | Resource rate and quantity changes propagated through linked direct-cost and tender outputs during development testing.
Risk residual propagation | PASS | Approved residual CA01/CA02 feeds were proven to enter the tender exactly once.
Duplicate-cost blocker | PASS | Non-distinct duplicate risk provisions were proven to return RED and block release.
Programme propagation | PASS | Productivity/duration changes were proven to flow to Programme Export and trigger weather rerun logic.
Formula compatibility | PASS | Programme maximum-duration logic uses AGGREGATE rather than incompatible MAXIFS storage.

## Estimate Review Board
INDEPENDENT ESTIMATE VERIFICATION BOARD - MASTER ESTIMATE WORKBOOK
GOVERNING RULE: Every material component is presumed incorrect until independently demonstrated to be correct. Reviewers must be impartial, work blind to the primary estimate until their independent position is committed, and challenge the evidence rather than seek agreement. Agreement is not verification. No voting or averaging is permitted; the Chief Estimator adjudicates on the strongest evidence.
Workflow: Primary estimate frozen -> independent clean-room reviews -> specialist blind challenges -> primary revealed -> variance/findings recorded -> evidence-led adjudication -> accepted changes integrated once into the existing cost/programme chain -> release gate.
BOARD / RELEASE CONTROL |  |  | NON-NEGOTIABLE INDEPENDENCE RULES
Review mode | FULL BOARD - mandatory for priced estimates |  | 1 | Assume the estimate is wrong until evidence proves the component correct.
Required clean-room whole-estimate reviewers | 3 |  | 2 | Clean-room reviewers receive project evidence but not the primary quantities, rates, productivity, duration, assumptions or tender total before commitment.
Required specialist challenge reviewers | 6 |  | 3 | Specialist reviewers are also blind to the primary answer until they have committed their independent challenge position wherever practicable.
Completed clean-room reviewers | 0 |  | 4 | Reviewers may not optimise toward a target total, previous tender, client budget or expected answer.
Completed specialist reviewers | 0 |  | 5 | Agreement between reviewers is not evidence. Majority vote and averaging are prohibited.
Reviewer independence failures | 0 |  | 6 | Every disagreement is resolved by evidence quality, scope alignment and first-principles logic.
Unresolved material RED findings | 0 |  | 7 | Accepted changes are made at the original source in Resource Library / Resource Build-Up / QS / Programme / Risk / Commercial Inputs - never as a second cost in this sheet.
Unresolved material AMBER findings | 0 |  | 8 | If true process isolation cannot be achieved, record the limitation. Each mandatory reviewer must have an Isolation / Context ID or equivalent audit reference. Do not describe a review as fully independent when the primary answer was visible or the reviewer shared the primary reasoning context.
QS items on review HOLD | 0
Accepted changes not integrated | 0
Active QS items
QS items fully reviewed | 0
Chief adjudicator status | NOT STARTED
BOARD RELEASE GATE | HOLD - Review Board not started
Operating standard | Independent Estimate Verification Board Standard Rev1 - development candidate
REVIEWER INDEPENDENCE & COMMITMENT REGISTER
Reviewer ID | Role | Review Type | Required? | Independent? | Primary estimate withheld until commitment? | Independent position committed? | Independence / method note | Isolation / Context ID | Reviewer / Agent | Completion date | Reviewer Status
ERB-01 | Independent Estimator A - whole estimate | Clean-room | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-02 | Independent Estimator B - whole estimate | Clean-room | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-03 | Independent Estimator C - whole estimate | Clean-room | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-04 | Scope & document challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-05 | Quantity & takeoff challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-06 | Method / productivity / crew challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-07 | Rate & procurement challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-08 | Programme & time-cost challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-09 | Risk / commercial / double-count challenge reviewer | Specialist | Yes |  |  | No |  |  | Independent reviewer context |  | PASS - COMMITTED
ERB-10 | Chief Estimator - evidence adjudicator | Adjudication | Yes |  |  | No |  |  | Chief Estimator |  | PASS WITH AMBER / WORKING HOLD
INTERNAL PRE-RELEASE RED-TEAM NOTE
QS ITEM VERIFICATION COVERAGE - EVERY ACTIVE QS ITEM (rows follow QS Takeoff rows 3-72; for a longer job copy the last row down)
QS Code | WBS / Section | Description | Quantity | Unit | Amount excl. GST | Estimator A | Estimator B | Estimator C | Scope | Quantity | Method / Productivity | Rate / Procurement | Programme | Risk / Commercial | Item Verification Gate | Finding IDs / Notes
CHALLENGE FINDINGS & EVIDENCE-LED ADJUDICATION REGISTER
Only record disagreements / material challenges here. The primary estimate is revealed only after the reviewer has committed the independent position. Accepted changes are integrated at the original source cell/path and then the affected review is rerun.
Finding ID | Target Type | Target ID | WBS / Description | Reviewer ID | Challenge Area | Independent Position / Recalculation | Independent Numeric | Unit | Primary Position / Basis (post-commitment) | Primary Numeric | Variance % | Evidence / Source 1 | Independent Evidence / Source 2 | First-Principles Basis | Material? | Severity | Finding / Why Primary May Be Wrong | Adjudication Decision | Accepted Value / Basis | Integration Target | Integrated? | Final Status | RFI / Action ID
ERF-001
ERF-002
ERF-003
ERF-004
ERF-005
ERF-006
ERF-007
ERF-008
ERF-009
ERF-010
ERF-011
ERF-012
ERF-013
ERF-014
ERF-015
ERF-016
ERF-017
ERF-018
ERF-019
ERF-020
ERF-021
ERF-022
ERF-023
ERF-024
ERF-025
ERF-026
ERF-027
ERF-028
ERF-029
ERF-030
ERF-031
ERF-032
ERF-033
ERF-034
ERF-035
ERF-036
ERF-037
ERF-038
ERF-039
ERF-040
ERF-041
ERF-042
ERF-043
ERF-044
ERF-045
ERF-046
ERF-047
ERF-048
ERF-049
ERF-050
ERF-051
ERF-052
ERF-053
ERF-054
ERF-055
ERF-056
ERF-057
ERF-058
ERF-059
ERF-060
ERF-061
ERF-062
ERF-063
ERF-064
ERF-065
ERF-066
ERF-067
ERF-068
ERF-069
ERF-070
ERF-071
ERF-072
ERF-073
ERF-074
ERF-075
ERF-076
ERF-077
ERF-078
ERF-079
ERF-080
ERF-081
ERF-082
ERF-083
ERF-084
ERF-085
ERF-086
ERF-087
ERF-088
ERF-089
ERF-090
ERF-091
ERF-092
ERF-093
ERF-094
ERF-095
ERF-096
ERF-097
ERF-098
ERF-099
ERF-100

## ERB Adjudication
FORMAL ERB ADJUDICATION
Frozen pre-Board primary
Frozen primary tender excl GST
Clean-room whole estimates
Board rule | No averaging / no voting; strongest aligned evidence governs.
Dry tender programme
Weather status
Release status
Topic | Frozen primary | Board evidence | Adjudication | Cost treatment | Status
|  |  | ACCEPT 55WD dry sequence | PG01 base duration revised | AMBER
|  |  | ACCEPT | Supervisor 440h; facilities 11 weeks | AMBER
|  |  | UPHOLD | No cost change | GREEN/AMBER
|  |  | UPHOLD METHOD | Retain PC / RFI reuse-export | AMBER
|  |  | UPHOLD TOTAL / VERIFY SPLIT | No current total change | AMBER
|  |  | REOPEN QTY / INTERFACE | Retain PC until quote/final measure | AMBER
|  |  | UPHOLD LENGTH / RFI HEIGHT | PCs retained | RED
|  |  | UPHOLD | No change | AMBER
|  |  | UPHOLD QTY | PC retained pending grate/outlet | AMBER
|  |  | UPHOLD PC | No change | AMBER
|  |  | VERIFY SOURCE / OWNERSHIP | PCs retained | AMBER
|  |  | REMOVE / EXCLUDE CURRENT BASIS | $0 | AMBER / CLOSED CURRENT BASIS
|  |  | NO WHOLESALE RESET | Quote-normalize line by line | AMBER
|  |  | RERUN COMPLETE FOR TENDER SCENARIO | CA10 $17,883.54 | AMBER
|  |  | ADOPT | CA17/CA18 active | CLOSED - PROVIDED / AMBER
RED

## Stage Cashflow
STAGE PAYMENT & CASHFLOW - MASTER ESTIMATE WORKBOOK
Only stage timing, stage percentages and retention applicability are inputs. Revenue and direct-cost allocations remain formula linked.
Cash on hand = cumulative net pre-GST receipts less base direct stage costs and included pre-margin provisions. Rev34 CA16 Management Reserve is carried in the pre-margin provision row for tender/cashflow reconciliation only; it is an unallocated commercial management reserve, not forecast physical expenditure unless subsequently consumed under change control.
Stage | Timing / milestone | Stage % | Retention applies? | Opening cash | Gross stage revenue excl. GST | Retention withheld | Net stage revenue excl. GST | Stage cost / provision | Net cash movement | Closing cash on hand | Cumulative net revenue | Cumulative retention held | GST if selected | Net stage receipt incl. GST | Notes
Deposit / advance | On contract award | [13 empty] | No deposit assumed; CA24 remains OFF.
Stage 1 - summary sections 1-2 | [14 empty] | Revenue stage percentage intentionally 0 pending head-contract payment schedule; costs shown are estimate cost allocation only.
Stage 2 - summary section 3 | [14 empty] | Earthworks/import-fill cost timing control only; revenue percentage not assumed.
Stage 3 - summary sections 4-5
Stage 4 - summary sections 6-7 | [14 empty] | Pavement/external-sitework cost timing control; revenue percentage pending contract schedule.
Stage 5 - summary section 8 | [14 empty] | Retaining workfront timing control; actual sequence depends on fill, stormwater clearance and supplier methodology.
Stage 6 - summary sections 9-10 | [14 empty] | Testing/closeout costs occur across work and at completion; revenue percentage pending contract schedule.
Included pre-margin provisions / Management Reserve |  | 0% | No |  | 0 | 0 | 0
Retention release | Post-completion - contract terms not supplied |  | No | [11 empty] | Retention terms/holding period are not assumed; CA22/CA23 remain OFF/0.
Cashflow checks
Stage percentages total | [14 empty] | Stage revenue percentages remain 0 until head-contract payment schedule is supplied. The current tender includes the active Commercial Inputs CA17/CA18 settings, so revenue CHECK / FUNDING REQUIRED indicators remain setup warnings rather than estimate cost-chain errors.
Gross stage revenue equals tender excl. GST
Base direct costs + pre-margin provisions allocated
Net receipts plus retention release equal tender
Final cash equals commercial adjustments after cost provisions
Lowest closing cash before retention release

## Materials & Component Takeoff
MATERIALS & COMPONENT TAKEOFF / COVER
COVERAGE AUDIT ONLY - NOT A SECOND COST CHAIN. Permanent components are linked to the existing Siteworks QS/Resource Build-Up or visibly classified as subcontract / RFI hold. Temporary ESC and ordinary consumables remain in Resource Build-Up.
Component ID | Permanent component / package | Owner | Treatment | Qty | Unit | Source / drawing | Original source link | QS Code | Cost location | Rate / quote source | Verification | Markup ID | Outstanding action | Notes
MC-001
MC-002
MC-003
MC-004
MC-005
MC-006
MC-007
MC-008
MC-009
MC-010
MC-011
MC-012
MC-013
MC-014
MC-015
MC-016
MC-017
MC-018
MC-019
MC-020
MC-021
MC-022
MC-023
MC-024
MC-025
MC-026
MC-027
MC-028
MC-029
MC-030
MC-031
MC-032
MC-033
MC-034
MC-035
MC-036
MC-037
MC-038
MC-039
MC-040
MC-041
MC-042
MC-043
MC-044
MC-045
MC-046
MC-047
MC-048
MC-049
MC-050
MC-051
MC-052
MC-053
MC-054
MC-055
MC-056
MC-057
MC-058
MC-059
MC-060

## Supplier Quote Register
SUPPLIER QUOTE REGISTER
One row per quote or quote request (Q-01, Q-02 ...). Keep consistent with the Quote Log sheet. A quote is evidence, not automatically the controlling amount.
Quote ID | Package | Estimate Ref | Current Qty | Unit | Current PC / Control excl. GST | Required Quote Scope | Documents to Issue | Preferred Supplier / Recipient | Status | Due / Action | Quote Ref / Notes

## Source & Markup Register
SOURCE & MARKUP REGISTER - PROVENANCE OF QUANTITIES
Source ID | Scope / QS Code | Original Source | Drawing / Page | Revision / Date | Original Source Link | Markup ID | Markup File | Markup Link | Status | Use / Quantity | Notes

## Email Log
Email ID | Date / time | Direction (In/Out) | From | To | Cc | Subject | Source reference (thread/message ID or file) | Category | Linked refs (RFI / Quote / QS codes) | Summary (1-3 neutral sentences) | Key wording (exact words that matter) | Attachments (and Document Register IDs) | Action required (Yes/No + what) | Action owner | Due | Status (Open/Closed/Info only) | Estimate impact (None/Quantity/Rate/Scope/Programme/Commercial) | Applied in estimate (revision + line, or Not yet)

## RFI Log
RFI ID | Date raised | Raised by | Addressed to | Subject | Question - what is missing | Where expected (document / drawing) | Why it matters | Decision impact (cost / programme / scope) | QS codes / risk IDs affected | Assumption in force until answered | Status (OPEN/CLOSED/SUPERSEDED) | RAG | Date answered | Answer summary | Answer source (Email ID / document) | Resulting estimate change (revision + line) | Owner

## Quote Log
Quote ID | Package / scope | Supplier / subcontractor | Contact (name only) | Quote number | Quote date | Valid until | Source (Email ID or file) | Scope included | Exclusions and qualifications | Price excl. GST | GST basis | Unit rates (if given) | Payment / retention terms | Lead time | QS codes fed | Treatment (Overlay / Fed into library rate / Reference only) | Amount used in estimate | Why this amount | Comparison with other quotes | Evidence strength (GREEN/AMBER/RED) | Status | Next action / due | Notes

## Document Register
Doc ID | Title | Type (Plan/Specification/Schedule/Geotech/Consent/Addendum/Photo/Email/Other) | Reference / drawing number | Revision | Date | Status (CURRENT/SUPERSEDED/UNCLEAR) | Superseded by | Source (file name, link, Email ID) | Received date | Used for (QS codes) | Notes

## Decision Log
Decision ID | Date | Decision | Made by | Options considered | Basis / evidence | Estimate impact | Revision applied | Status (Proposed/Approved by estimator/Superseded)

## Contacts
Organisation | Person | Role | Package / trade | Source of contact (Email ID) | Notes (no phone numbers or home addresses)

## Change Log
Revision | Date | What changed (scope / quantity / rate / quote / commercial / risk / programme) | Reason (document, email, decision) | Lines affected | Cost movement excl. GST (from the workbook, not estimated) | Recorded by