## Estimator
Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance | Weather Risk Estimator - Evidence-Based Allowance
Project and Cost Inputs | Project and Cost Inputs |  | Task Factors | Task Factors |  | Weather and Cost Outputs | Weather and Cost Outputs
Nearest NIWA location | Christchurch |  | Default rain exposure | 1.00 |  | Date-engine coverage | 01/01/2025 to 31/12/2040
Start date | 2026-09-01 |  | Override rain exposure |  |  | Standard workdays | 153
End date | 2027-04-01 |  | Effective rain exposure | 1.00 |  | Effective workdays | 153
Working days per week | 5 |  |  |  |  | Average NIWA wet-day probability | 21.01%
Working days override (optional) |  |  | Default rain productivity loss | 0.70 |  | Local-adjusted wet-day probability | 21.01%
Representative task | Bulk earthworks |  | Override rain productivity loss |  |  | Mean rain per wet day (context only) | 7.0023
Weather-exposed labour cost $ |  |  | Effective rain productivity loss | 0.70 |  | Effective wind-event probability | 0%
Weather-exposed plant cost $ | [5 empty] | Wind evidence status | RED - no wind frequency loaded
Daily time-related preliminaries $ |  |  | Default wet-ground carryover eq. days | 0.2
Weekly hire / facilities $ |  |  | Override carryover eq. days |  |  | On-day rain impact % | 12.5%
Project-specific recovery allowance $ | 0 |  | Effective carryover eq. days | 0.2 |  | Wet-ground carryover impact % | 3.572%
Wind probability override (optional) | [5 empty] | Wind impact % | 0%
Local wet-day factor | 1 |  | Default wind sensitivity | 0.15 |  | Combined direct impact % | 16.07%
Local factor basis / reference |  |  | Override wind sensitivity |  |  | Expected equivalent lost working days | 24.5906
Task is on critical path? | Yes |  | Effective wind sensitivity | 0.15 |  | Suggested critical-path delay working days | 24.5906
|  |  | Default wind productivity loss | 0.70 |  | Direct productivity allowance $ | 0 |  | Month | Wet-Day Probability | Rain per Wet Day (mm)
|  |  | Override wind productivity loss |  |  | Time-related preliminaries allowance $ | 0 |  | Jan | 19.46% | 7.0276
|  |  | Effective wind productivity loss | 0.70 |  | Additional billed hire weeks | 5 |  | Feb | 18.87% | 7.4625
[6 empty] | Hire / facilities allowance $ | 0 |  | Mar | 18.49% | 7.8663
|  |  | Default nonrecoverable share | 0.85 |  | Project-specific recovery allowance $ | 0 |  | Apr | 25.56% | 7.5
|  |  | Override nonrecoverable share |  |  | Total weather allowance $ | 0 |  | May | 23.01% | 8.1449
|  |  | Effective nonrecoverable share | 0.85 |  | Total as % of exposed direct cost | 0% |  | Jun | 28.67% | 7.9419
[9 empty] | Jul | 24.73% | 8.3739
[6 empty] | Chance of at least one wet workday | 100% |  | Aug | 23.55% | 7.9589
[6 empty] | Output confidence | RED - wind input missing for wind-sensitive task |  | Sep | 20.67% | 6.8065
[6 empty] | Release action | Resolve RED input before issue |  | Oct | 23.23% | 6.8194
[9 empty] | Nov | 23.33% | 6.4429
[9 empty] | Dec | 22.69% | 6.7962
Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls | Estimator Statement and Controls
Using NIWA 1991-2020 climate normals for Christchurch, the selected working period has an average 21.0% chance of a 1 mm wet day. For Bulk earthworks, the model estimates 24.59 equivalent lost working days and a total weather allowance of $0. NIWA data is sourced evidence; task sensitivity and carryover remain AMBER company assumptions until calibrated.
Controls: - A 1 mm wet day is not automatically a lost day. Task factors convert climate exposure into estimated productivity loss. - Rain, wet-ground carryover and wind are calculated separately. Rainfall intensity is shown as context only. - Wind uses an AMBER Auckland proxy only; other locations require a sourced override when wind matters. - Suggested delay days apply only when the representative task is genuinely on the critical path. - Public holidays and shutdowns are not included in the date engine. - Do not add task lost days across concurrent activities; use the Activity Allowances critical-path flags and the live programme.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Standard work pattern only. Public holidays, shutdowns and unusual rosters must be handled through the working-days override or the contract programme.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use a sourced probability that matches the task wind threshold. The Auckland default is only a legacy >63 km/h gust-day proxy.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Keep at 1.00 unless local exposure differs materially from the selected station. Record the evidence or professional basis in the next cell.

## Activity Allowances
Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link | Activity Weather Allowances - Programme and Cost Link
Local wet-day factor | 1 | Wind probability override |  | Daily time-related preliminaries $ |  | Weekly hire / facilities $ |  | Project recovery / remediation allowance $ | 0 |  | Use Critical Path = Yes only for sequential activities on the actual critical path. Concurrent task losses must not be added as programme delay. Direct productivity costs may still be assessed by activity.
Task | Category | Start | Finish | Critical Path? | Exposed Labour $ | Exposed Plant $ | Rain Exposure Default | Rain Exposure Override | Effective Rain Exposure | Rain Loss Default | Rain Loss Override | Effective Rain Loss | Carryover Default | Carryover Override | Effective Carryover | Wind Sensitivity Default | Wind Sensitivity Override | Effective Wind Sensitivity | Wind Loss Default | Wind Loss Override | Effective Wind Loss | Nonrecoverable Default | Nonrecoverable Override | Effective Nonrecoverable | Workdays | Avg Wet Probability | Adjusted Wet Probability | Wind Probability | Rain Impact % | Carryover Impact % | Wind Impact % | Combined Impact % | Direct Allowance $ | Equivalent Lost WD | CP Delay WD | Status | Basis / Note
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
|  |  |  | No | [23 empty] | 0%
Project Weather Summary | Project Weather Summary | Project Weather Summary | Project Weather Summary | Project Weather Summary | Project Weather Summary | Project Weather Summary | Project Weather Summary
Exposed labour + plant $ | 0 |  | Use this summary in the estimate only after: 1. Activities and dates align with the live programme. 2. Critical Path = Yes reflects the real critical path, not every weather-sensitive task. 3. Labour and plant values include only weather-exposed cost pools. 4. RED inputs are resolved or expressly excluded. 5. AMBER task factors are disclosed and assigned a firm-up action.
Direct productivity allowance $ | 0
Suggested critical-path delay working days | 0
Time-related preliminaries allowance $ | 0
Additional billed hire weeks | 0
Hire / facilities allowance $ | 0
Project recovery / remediation allowance $ | 0
Total weather allowance $ | 0

## Task Library
Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults | Task Weather Sensitivity Library - Company Defaults
These defaults are transparent company judgement, not NIWA facts. They remain AMBER until calibrated against actual project records and independently reviewed. Override only with a recorded job-specific basis. Wet-ground carryover is an equivalent lost-day fraction following each wet day, not a guaranteed shutdown.
Task | Category | Rain Exposure | Rain Productivity Loss | Wet-Ground Carryover Eq. Days / Wet Day | Wind Sensitivity | Wind Productivity Loss | Nonrecoverable Share | Default Status | Actual Records | Calibration Status | Original Basis Note | Required Review Action | Approved By | Approved Date
Site establishment / temp fencing | Civil | 0.35 | 0.20 | 0.02 | 0.10 | 0.20 | 0.40 | AMBER - company judgement | 0 | UNCALIBRATED | General outdoor set-up, usually partly workable. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Erosion & sediment controls | Civil | 0.85 | 0.50 | 0.08 | 0.20 | 0.50 | 0.70 | AMBER - company judgement | 0 | UNCALIBRATED | Often still required in wet weather, but slower and messier. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Bulk earthworks | Civil | 1.00 | 0.70 | 0.2 | 0.15 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Highly exposed to wet ground and access deterioration. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Detailed earthworks / trim subgrade | Civil | 1.00 | 0.80 | 0.25 | 0.15 | 0.80 | 0.90 | AMBER - company judgement | 0 | UNCALIBRATED | Fine tolerances make wet conditions painful. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Cut to fill / cartage | Civil | 0.95 | 0.65 | 0.15 | 0.10 | 0.65 | 0.80 | AMBER - company judgement | 0 | UNCALIBRATED | Wet haul roads and loaded traffic slow the whole chain. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Building platform / pad prep | Civil | 0.95 | 0.75 | 0.2 | 0.10 | 0.75 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Moisture condition and compaction control matter. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Drainage trenching | Civil | 0.95 | 0.65 | 0.15 | 0.10 | 0.65 | 0.80 | AMBER - company judgement | 0 | UNCALIBRATED | Water ingress, slumping, and access issues. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Manholes / chambers | Civil | 0.90 | 0.60 | 0.08 | 0.05 | 0.60 | 0.75 | AMBER - company judgement | 0 | UNCALIBRATED | Less affected than open trench runs, but still exposed. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Service trenches / ducting | Civil | 0.90 | 0.60 | 0.1 | 0.10 | 0.60 | 0.75 | AMBER - company judgement | 0 | UNCALIBRATED | Small but still sensitive to rain and reinstatement. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Bored piles / drilled holes | Civil | 1.00 | 0.70 | 0.15 | 0.15 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Wet ground and hole stability are key risks. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Driven poles / posts | Civil | 0.95 | 0.60 | 0.05 | 0.20 | 0.60 | 0.80 | AMBER - company judgement | 0 | UNCALIBRATED | Weather affects access and standing time. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Retaining wall excavation | Civil | 0.95 | 0.70 | 0.15 | 0.10 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Slope and spoil handling usually worsen in the wet. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Retaining wall installation | Civil | 0.85 | 0.50 | 0.05 | 0.15 | 0.50 | 0.70 | AMBER - company judgement | 0 | UNCALIBRATED | Less exposed than excavation, but still affected. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
External concrete placing | Civil | 0.95 | 0.70 | 0.05 | 0.10 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Rain cover, surface quality, and finishing risk. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
External concrete finishing | Civil | 1.00 | 0.80 | 0.02 | 0.05 | 0.80 | 0.90 | AMBER - company judgement | 0 | UNCALIBRATED | Finishing window can vanish fast in poor weather. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Kerb & channel | Civil | 0.95 | 0.70 | 0.05 | 0.10 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Open-air concrete work and wet prep surfaces. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Subbase / pavement prep | Civil | 0.95 | 0.70 | 0.2 | 0.10 | 0.70 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Compaction and moisture sensitivity. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Asphalt / sealing | Civil | 1.00 | 0.85 | 0.05 | 0.05 | 0.85 | 0.90 | AMBER - company judgement | 0 | UNCALIBRATED | Very weather-sensitive process. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Landscaping / topsoil / grassing | Civil | 0.90 | 0.50 | 0.12 | 0.10 | 0.50 | 0.60 | AMBER - company judgement | 0 | UNCALIBRATED | Often still possible, but efficiency drops. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Roof framing | Building | 0.95 | 0.65 | 0.02 | 0.25 | 0.65 | 0.75 | AMBER - company judgement | 0 | UNCALIBRATED | Rain and wind both matter before dry-in. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Roofing | Building | 1.00 | 0.75 | 0.02 | 0.35 | 0.75 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Wind-sensitive and usually fully exposed. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Wall framing (open structure) | Building | 0.85 | 0.45 | 0.02 | 0.20 | 0.45 | 0.60 | AMBER - company judgement | 0 | UNCALIBRATED | Some work can continue, but pace drops. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Cladding | Building | 0.80 | 0.45 | 0.02 | 0.15 | 0.45 | 0.60 | AMBER - company judgement | 0 | UNCALIBRATED | Exposure remains but some sequencing is possible. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Exterior windows / joinery | Building | 0.70 | 0.40 | 0.01 | 0.10 | 0.40 | 0.55 | AMBER - company judgement | 0 | UNCALIBRATED | Protection set-up often needed. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Deck framing | Building | 0.90 | 0.60 | 0.05 | 0.15 | 0.60 | 0.75 | AMBER - company judgement | 0 | UNCALIBRATED | Exposed external carpentry. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Decking | Building | 0.85 | 0.55 | 0.04 | 0.10 | 0.55 | 0.70 | AMBER - company judgement | 0 | UNCALIBRATED | Still weather-sensitive, but slightly less than framing. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Scaffolding | Building | 0.75 | 0.35 | 0.02 | 0.25 | 0.35 | 0.50 | AMBER - company judgement | 0 | UNCALIBRATED | Wind can be the bigger issue here. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Steel erection / crane lifts | Building | 0.95 | 0.70 | 0.02 | 0.35 | 0.70 | 0.80 | AMBER - company judgement | 0 | UNCALIBRATED | High wind sensitivity plus exposure. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
External block / brick laying | Building | 0.85 | 0.55 | 0.05 | 0.10 | 0.55 | 0.70 | AMBER - company judgement | 0 | UNCALIBRATED | Rain protection and mortar issues. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
External painting / coatings | Building | 0.95 | 0.75 | 0.05 | 0.05 | 0.75 | 0.85 | AMBER - company judgement | 0 | UNCALIBRATED | Often weather-window driven. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal framing | Building | 0.15 | 0.10 | 0 | 0.05 | 0.10 | 0.30 | AMBER - company judgement | 0 | UNCALIBRATED | Still gets minor drag from access, shelter, and material handling. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal linings / plasterboard | Building | 0.10 | 0.08 | 0 | 0.02 | 0.08 | 0.25 | AMBER - company judgement | 0 | UNCALIBRATED | Low weather effect, not zero. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal plastering / stopping | Building | 0.10 | 0.10 | 0 | 0.02 | 0.10 | 0.30 | AMBER - company judgement | 0 | UNCALIBRATED | Mostly protected, but drying and access can still bite. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal painting | Building | 0.10 | 0.12 | 0 | 0.02 | 0.12 | 0.30 | AMBER - company judgement | 0 | UNCALIBRATED | Humidity and site conditions can slow productivity. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Fitout / cabinetry / joinery | Building | 0.10 | 0.08 | 0 | 0.02 | 0.08 | 0.25 | AMBER - company judgement | 0 | UNCALIBRATED | Low but real weather drag. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal tiling / wet areas | Building | 0.15 | 0.12 | 0 | 0.02 | 0.12 | 0.35 | AMBER - company judgement | 0 | UNCALIBRATED | Protected, but humidity and site wetness can still influence output. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal flooring | Building | 0.10 | 0.10 | 0 | 0.02 | 0.10 | 0.25 | AMBER - company judgement | 0 | UNCALIBRATED | Low but non-zero effect. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Internal MEP rough-in / fit-off | Building | 0.15 | 0.10 | 0 | 0.03 | 0.10 | 0.30 | AMBER - company judgement | 0 | UNCALIBRATED | Protected, but deliveries and wet access still matter. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.
Workshop fabrication / sheltered prep | Building | 0.10 | 0.08 | 0 | 0.02 | 0.08 | 0.20 | AMBER - company judgement | 0 | UNCALIBRATED | Low but not zero. | Calibrate from Weather Log and obtain estimator/PM approval before GREEN.

## Climate Data
NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals | NIWA Climate Data - 1991-2020 Normals
Official NIWA mean monthly wet days and rainfall. Daily wet-day probability is calculated as mean wet days divided by normal calendar days. A wet day is 1 mm or more of rain; it is not automatically a lost construction day.
Location | Month # | Month | Mean Wet Days >=1 mm | Mean Rainfall (mm) | Normal Calendar Days | Daily Wet-Day Probability | Mean Rain per Wet Day (mm) | Source Period | Evidence Status
Kaitaia | 1 | Jan | 6.1364 | 75 | 31 | 19.79% | 12.2222 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 2 | Feb | 6.5 | 86 | 28.2667 | 23% | 13.2308 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 3 | Mar | 7.5909 | 84.7 | 31 | 24.49% | 11.1581 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 4 | Apr | 10.0909 | 98.8 | 30 | 33.64% | 9.791 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 5 | May | 13.2273 | 130.5 | 31 | 42.67% | 9.866 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 6 | Jun | 14.6818 | 149.9 | 30 | 48.94% | 10.2099 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 7 | Jul | 15.8636 | 168.1 | 31 | 51.17% | 10.5966 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 8 | Aug | 15.5 | 137 | 31 | 50% | 8.8387 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 9 | Sep | 12.7727 | 121.7 | 30 | 42.58% | 9.5281 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 10 | Oct | 10.3636 | 90.4 | 31 | 33.43% | 8.7228 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 11 | Nov | 9.2273 | 76.3 | 30 | 30.76% | 8.269 | 1991-2020 | GREEN - official NIWA normal
Kaitaia | 12 | Dec | 9.8636 | 101.6 | 31 | 31.82% | 10.3005 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 1 | Jan | 6.931 | 78 | 31 | 22.36% | 11.2537 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 2 | Feb | 7.2759 | 83.2 | 28.2667 | 25.74% | 11.4351 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 3 | Mar | 9 | 119.2 | 31 | 29.03% | 13.2444 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 4 | Apr | 9.7037 | 94.1 | 30 | 32.35% | 9.6973 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 5 | May | 13.0714 | 112.9 | 31 | 42.17% | 8.6372 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 6 | Jun | 14.0357 | 142.2 | 30 | 46.79% | 10.1313 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 7 | Jul | 15.0345 | 173.5 | 31 | 48.5% | 11.5401 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 8 | Aug | 15.2333 | 130 | 31 | 49.14% | 8.5339 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 9 | Sep | 12.8667 | 112.3 | 30 | 42.89% | 8.728 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 10 | Oct | 10.3103 | 76.8 | 31 | 33.26% | 7.4488 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 11 | Nov | 9.2333 | 75.9 | 30 | 30.78% | 8.2202 | 1991-2020 | GREEN - official NIWA normal
Whangarei | 12 | Dec | 8.7931 | 90.9 | 31 | 28.36% | 10.3376 | 1991-2020 | GREEN - official NIWA normal
Auckland | 1 | Jan | 6.7586 | 58.1 | 31 | 21.8% | 8.5964 | 1991-2020 | GREEN - official NIWA normal
Auckland | 2 | Feb | 6.5172 | 63.1 | 28.2667 | 23.06% | 9.682 | 1991-2020 | GREEN - official NIWA normal
Auckland | 3 | Mar | 7.7241 | 75 | 31 | 24.92% | 9.7098 | 1991-2020 | GREEN - official NIWA normal
Auckland | 4 | Apr | 9.6071 | 87.1 | 30 | 32.02% | 9.0662 | 1991-2020 | GREEN - official NIWA normal
Auckland | 5 | May | 13 | 119.8 | 31 | 41.94% | 9.2154 | 1991-2020 | GREEN - official NIWA normal
Auckland | 6 | Jun | 14.25 | 119.4 | 30 | 47.5% | 8.3789 | 1991-2020 | GREEN - official NIWA normal
Auckland | 7 | Jul | 15.2143 | 136.9 | 31 | 49.08% | 8.9981 | 1991-2020 | GREEN - official NIWA normal
Auckland | 8 | Aug | 14.6552 | 117.2 | 31 | 47.27% | 7.9972 | 1991-2020 | GREEN - official NIWA normal
Auckland | 9 | Sep | 12.4828 | 100.1 | 30 | 41.61% | 8.0191 | 1991-2020 | GREEN - official NIWA normal
Auckland | 10 | Oct | 11.5357 | 91.6 | 31 | 37.21% | 7.9406 | 1991-2020 | GREEN - official NIWA normal
Auckland | 11 | Nov | 9.3333 | 68.9 | 30 | 31.11% | 7.3821 | 1991-2020 | GREEN - official NIWA normal
Auckland | 12 | Dec | 9.0345 | 81.7 | 31 | 29.14% | 9.0431 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 1 | Jan | 6.2759 | 76.2 | 31 | 20.24% | 12.1418 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 2 | Feb | 6.7 | 83.2 | 28.2667 | 23.7% | 12.4179 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 3 | Mar | 8.0667 | 94.9 | 31 | 26.02% | 11.7645 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 4 | Apr | 8.7143 | 132.1 | 30 | 29.05% | 15.159 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 5 | May | 9.5862 | 116.2 | 31 | 30.92% | 12.1216 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 6 | Jun | 10.6786 | 120.6 | 30 | 35.6% | 11.2936 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 7 | Jul | 11.6552 | 133.4 | 31 | 37.6% | 11.4456 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 8 | Aug | 11.7407 | 111.6 | 31 | 37.87% | 9.5054 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 9 | Sep | 10.7143 | 86.5 | 30 | 35.71% | 8.0733 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 10 | Oct | 9.5667 | 80.4 | 31 | 30.86% | 8.4042 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 11 | Nov | 8.5667 | 63.4 | 30 | 28.56% | 7.4008 | 1991-2020 | GREEN - official NIWA normal
Tauranga | 12 | Dec | 8.4667 | 103 | 31 | 27.31% | 12.1654 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 1 | Jan | 6.6 | 75.4 | 31 | 21.29% | 11.4242 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 2 | Feb | 5.7857 | 65 | 28.2667 | 20.47% | 11.2346 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 3 | Mar | 6.1429 | 75.4 | 31 | 19.82% | 12.2744 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 4 | Apr | 9.5333 | 92.3 | 30 | 31.78% | 9.6818 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 5 | May | 11.4 | 103.3 | 31 | 36.77% | 9.0614 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 6 | Jun | 12.1333 | 117.8 | 30 | 40.44% | 9.7088 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 7 | Jul | 12.7333 | 124.2 | 31 | 41.08% | 9.7539 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 8 | Aug | 13.8 | 106.5 | 31 | 44.52% | 7.7174 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 9 | Sep | 12.8 | 100.1 | 30 | 42.67% | 7.8203 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 10 | Oct | 10.6 | 86 | 31 | 34.19% | 8.1132 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 11 | Nov | 9 | 79 | 30 | 30% | 8.7778 | 1991-2020 | GREEN - official NIWA normal
Hamilton | 12 | Dec | 9.0625 | 99.2 | 31 | 29.23% | 10.9462 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 1 | Jan | 7.7143 | 93.8 | 31 | 24.88% | 12.1593 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 2 | Feb | 7.5556 | 100.4 | 28.2667 | 26.73% | 13.2882 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 3 | Mar | 8.1379 | 100.3 | 31 | 26.25% | 12.325 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 4 | Apr | 9.3 | 133 | 30 | 31% | 14.3011 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 5 | May | 9.8571 | 130.2 | 31 | 31.8% | 13.2087 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 6 | Jun | 10.8621 | 131.9 | 30 | 36.21% | 12.1432 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 7 | Jul | 11.4138 | 137.4 | 31 | 36.82% | 12.0381 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 8 | Aug | 12.1071 | 125.2 | 31 | 39.06% | 10.341 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 9 | Sep | 11.037 | 106.6 | 30 | 36.79% | 9.6584 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 10 | Oct | 10.3214 | 92.9 | 31 | 33.29% | 9.0007 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 11 | Nov | 9.4815 | 86.8 | 30 | 31.6% | 9.1547 | 1991-2020 | GREEN - official NIWA normal
Rotorua | 12 | Dec | 10.75 | 117.1 | 31 | 34.68% | 10.893 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 1 | Jan | 6.2333 | 71.4 | 31 | 20.11% | 11.4545 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 2 | Feb | 7.5667 | 65.9 | 28.2667 | 26.77% | 8.7093 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 3 | Mar | 9 | 94 | 31 | 29.03% | 10.4444 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 4 | Apr | 9.3793 | 107.1 | 30 | 31.26% | 11.4188 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 5 | May | 9.931 | 84 | 31 | 32.04% | 8.4583 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 6 | Jun | 10.2069 | 107.4 | 30 | 34.02% | 10.5223 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 7 | Jul | 12.3929 | 118.7 | 31 | 39.98% | 9.5781 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 8 | Aug | 11.1379 | 78.1 | 31 | 35.93% | 7.0121 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 9 | Sep | 8.7143 | 73.1 | 30 | 29.05% | 8.3885 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 10 | Oct | 7.3333 | 76.1 | 31 | 23.66% | 10.3773 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 11 | Nov | 7.8 | 65.2 | 30 | 26% | 8.359 | 1991-2020 | GREEN - official NIWA normal
Gisborne | 12 | Dec | 7.2414 | 59.9 | 31 | 23.36% | 8.2719 | 1991-2020 | GREEN - official NIWA normal
Taupo | 1 | Jan | 6.9333 | 73.4 | 31 | 22.37% | 10.5865 | 1991-2020 | GREEN - official NIWA normal
Taupo | 2 | Feb | 6.3 | 64.8 | 28.2667 | 22.29% | 10.2857 | 1991-2020 | GREEN - official NIWA normal
Taupo | 3 | Mar | 7.1 | 65.9 | 31 | 22.9% | 9.2817 | 1991-2020 | GREEN - official NIWA normal
Taupo | 4 | Apr | 8.2069 | 77.3 | 30 | 27.36% | 9.4189 | 1991-2020 | GREEN - official NIWA normal
Taupo | 5 | May | 8.8333 | 79.4 | 31 | 28.49% | 8.9887 | 1991-2020 | GREEN - official NIWA normal
Taupo | 6 | Jun | 10.5333 | 93 | 30 | 35.11% | 8.8291 | 1991-2020 | GREEN - official NIWA normal
Taupo | 7 | Jul | 11.2 | 99.8 | 31 | 36.13% | 8.9107 | 1991-2020 | GREEN - official NIWA normal
Taupo | 8 | Aug | 11.6667 | 88.6 | 31 | 37.63% | 7.5943 | 1991-2020 | GREEN - official NIWA normal
Taupo | 9 | Sep | 10.8 | 79 | 30 | 36% | 7.3148 | 1991-2020 | GREEN - official NIWA normal
Taupo | 10 | Oct | 10.1 | 74.2 | 31 | 32.58% | 7.3465 | 1991-2020 | GREEN - official NIWA normal
Taupo | 11 | Nov | 8.6667 | 64.7 | 30 | 28.89% | 7.4654 | 1991-2020 | GREEN - official NIWA normal
Taupo | 12 | Dec | 9.5 | 88 | 31 | 30.65% | 9.2632 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 1 | Jan | 8.1379 | 76.3 | 31 | 26.25% | 9.3758 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 2 | Feb | 7.8276 | 89.8 | 28.2667 | 27.69% | 11.4722 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 3 | Mar | 8.5517 | 91.1 | 31 | 27.59% | 10.6528 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 4 | Apr | 10.3448 | 117.1 | 30 | 34.48% | 11.3197 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 5 | May | 13.5926 | 149.4 | 31 | 43.85% | 10.9913 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 6 | Jun | 14.6296 | 143.6 | 30 | 48.77% | 9.8157 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 7 | Jul | 14.5 | 141.3 | 31 | 46.77% | 9.7448 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 8 | Aug | 14.7857 | 128.8 | 31 | 47.7% | 8.7111 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 9 | Sep | 14.2414 | 122.9 | 30 | 47.47% | 8.6298 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 10 | Oct | 12.8966 | 127 | 31 | 41.6% | 9.8476 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 11 | Nov | 10.9333 | 103.7 | 30 | 36.44% | 9.4848 | 1991-2020 | GREEN - official NIWA normal
New Plymouth | 12 | Dec | 11.4828 | 119.3 | 31 | 37.04% | 10.3895 | 1991-2020 | GREEN - official NIWA normal
Napier | 1 | Jan | 6.2 | 63.8 | 31 | 20% | 10.2903 | 1991-2020 | GREEN - official NIWA normal
Napier | 2 | Feb | 6.2 | 54.1 | 28.2667 | 21.93% | 8.7258 | 1991-2020 | GREEN - official NIWA normal
Napier | 3 | Mar | 7.3667 | 61.8 | 31 | 23.76% | 8.3891 | 1991-2020 | GREEN - official NIWA normal
Napier | 4 | Apr | 7.7586 | 81.2 | 30 | 25.86% | 10.4658 | 1991-2020 | GREEN - official NIWA normal
Napier | 5 | May | 6.8621 | 62.2 | 31 | 22.14% | 9.0643 | 1991-2020 | GREEN - official NIWA normal
Napier | 6 | Jun | 7.8667 | 78.5 | 30 | 26.22% | 9.9788 | 1991-2020 | GREEN - official NIWA normal
Napier | 7 | Jul | 8.8333 | 97 | 31 | 28.49% | 10.9811 | 1991-2020 | GREEN - official NIWA normal
Napier | 8 | Aug | 7.9333 | 57 | 31 | 25.59% | 7.1849 | 1991-2020 | GREEN - official NIWA normal
Napier | 9 | Sep | 7.4667 | 58.1 | 30 | 24.89% | 7.7812 | 1991-2020 | GREEN - official NIWA normal
Napier | 10 | Oct | 7.4333 | 60.9 | 31 | 23.98% | 8.1928 | 1991-2020 | GREEN - official NIWA normal
Napier | 11 | Nov | 6.5172 | 57.3 | 30 | 21.72% | 8.7921 | 1991-2020 | GREEN - official NIWA normal
Napier | 12 | Dec | 6.9333 | 57.8 | 31 | 22.37% | 8.3365 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 1 | Jan | 6.3333 | 58.1 | 31 | 20.43% | 9.1737 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 2 | Feb | 6.3571 | 69.6 | 28.2667 | 22.49% | 10.9483 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 3 | Mar | 7.5517 | 60.5 | 31 | 24.36% | 8.0114 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 4 | Apr | 8.931 | 84.5 | 30 | 29.77% | 9.4614 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 5 | May | 10 | 80.8 | 31 | 32.26% | 8.08 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 6 | Jun | 11.6 | 90.3 | 30 | 38.67% | 7.7845 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 7 | Jul | 11.3 | 87 | 31 | 36.45% | 7.6991 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 8 | Aug | 12.1 | 83.5 | 31 | 39.03% | 6.9008 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 9 | Sep | 10.5 | 75.9 | 30 | 35% | 7.2286 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 10 | Oct | 10.4667 | 89.1 | 31 | 33.76% | 8.5127 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 11 | Nov | 9.2 | 75.3 | 30 | 30.67% | 8.1848 | 1991-2020 | GREEN - official NIWA normal
Whanganui | 12 | Dec | 9.5667 | 89.5 | 31 | 30.86% | 9.3554 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 1 | Jan | 8.2105 | 58.7 | 31 | 26.49% | 7.1494 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 2 | Feb | 6.8421 | 68.6 | 28.2667 | 24.21% | 10.0262 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 3 | Mar | 7.2632 | 57.4 | 31 | 23.43% | 7.9029 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 4 | Apr | 9.1 | 83.6 | 30 | 30.33% | 9.1868 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 5 | May | 10.4 | 87.2 | 31 | 33.55% | 8.3846 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 6 | Jun | 11.95 | 95.5 | 30 | 39.83% | 7.9916 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 7 | Jul | 11.55 | 87.5 | 31 | 37.26% | 7.5758 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 8 | Aug | 12.65 | 83.5 | 31 | 40.81% | 6.6008 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 9 | Sep | 11.75 | 89 | 30 | 39.17% | 7.5745 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 10 | Oct | 12.4 | 96.3 | 31 | 40% | 7.7661 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 11 | Nov | 9.85 | 86.3 | 30 | 32.83% | 8.7614 | 1991-2020 | GREEN - official NIWA normal
Palmerston North | 12 | Dec | 10.2 | 89.9 | 31 | 32.9% | 8.8137 | 1991-2020 | GREEN - official NIWA normal
Masterton | 1 | Jan | 5.2 | 52.4 | 31 | 16.77% | 10.0769 | 1991-2020 | GREEN - official NIWA normal
Masterton | 2 | Feb | 4.7273 | 48.5 | 28.2667 | 16.72% | 10.2596 | 1991-2020 | GREEN - official NIWA normal
Masterton | 3 | Mar | 6.1818 | 69.9 | 31 | 19.94% | 11.3074 | 1991-2020 | GREEN - official NIWA normal
Masterton | 4 | Apr | 8.5455 | 71.5 | 30 | 28.48% | 8.367 | 1991-2020 | GREEN - official NIWA normal
Masterton | 5 | May | 10.3333 | 72.9 | 31 | 33.33% | 7.0548 | 1991-2020 | GREEN - official NIWA normal
Masterton | 6 | Jun | 9.875 | 91 | 30 | 32.92% | 9.2152 | 1991-2020 | GREEN - official NIWA normal
Masterton | 7 | Jul | 10.625 | 113.6 | 31 | 34.27% | 10.6918 | 1991-2020 | GREEN - official NIWA normal
Masterton | 8 | Aug | 11.8 | 81.7 | 31 | 38.06% | 6.9237 | 1991-2020 | GREEN - official NIWA normal
Masterton | 9 | Sep | 10.7273 | 73.2 | 30 | 35.76% | 6.8237 | 1991-2020 | GREEN - official NIWA normal
Masterton | 10 | Oct | 9.1667 | 82 | 31 | 29.57% | 8.9455 | 1991-2020 | GREEN - official NIWA normal
Masterton | 11 | Nov | 8.4545 | 71.9 | 30 | 28.18% | 8.5043 | 1991-2020 | GREEN - official NIWA normal
Masterton | 12 | Dec | 6.9091 | 60.6 | 31 | 22.29% | 8.7711 | 1991-2020 | GREEN - official NIWA normal
Wellington | 1 | Jan | 6.8667 | 79.2 | 31 | 22.15% | 11.534 | 1991-2020 | GREEN - official NIWA normal
Wellington | 2 | Feb | 6.9375 | 55.5 | 28.2667 | 24.54% | 8 | 1991-2020 | GREEN - official NIWA normal
Wellington | 3 | Mar | 9.2857 | 99.6 | 31 | 29.95% | 10.7262 | 1991-2020 | GREEN - official NIWA normal
Wellington | 4 | Apr | 10.2667 | 126.7 | 30 | 34.22% | 12.3409 | 1991-2020 | GREEN - official NIWA normal
Wellington | 5 | May | 13.2941 | 144.9 | 31 | 42.88% | 10.8996 | 1991-2020 | GREEN - official NIWA normal
Wellington | 6 | Jun | 13.4375 | 123.8 | 30 | 44.79% | 9.213 | 1991-2020 | GREEN - official NIWA normal
Wellington | 7 | Jul | 12.8 | 147.1 | 31 | 41.29% | 11.4922 | 1991-2020 | GREEN - official NIWA normal
Wellington | 8 | Aug | 12.4615 | 139.1 | 31 | 40.2% | 11.1623 | 1991-2020 | GREEN - official NIWA normal
Wellington | 9 | Sep | 10.8824 | 108 | 30 | 36.27% | 9.9243 | 1991-2020 | GREEN - official NIWA normal
Wellington | 10 | Oct | 12.4375 | 118.7 | 31 | 40.12% | 9.5437 | 1991-2020 | GREEN - official NIWA normal
Wellington | 11 | Nov | 9.5294 | 85.4 | 30 | 31.76% | 8.9617 | 1991-2020 | GREEN - official NIWA normal
Wellington | 12 | Dec | 10 | 91.1 | 31 | 32.26% | 9.11 | 1991-2020 | GREEN - official NIWA normal
Nelson | 1 | Jan | 6.8276 | 73.2 | 31 | 22.02% | 10.7212 | 1991-2020 | GREEN - official NIWA normal
Nelson | 2 | Feb | 5.3333 | 62.8 | 28.2667 | 18.87% | 11.775 | 1991-2020 | GREEN - official NIWA normal
Nelson | 3 | Mar | 6.0667 | 71.1 | 31 | 19.57% | 11.7198 | 1991-2020 | GREEN - official NIWA normal
Nelson | 4 | Apr | 7.3 | 84.9 | 30 | 24.33% | 11.6301 | 1991-2020 | GREEN - official NIWA normal
Nelson | 5 | May | 7.4333 | 87.7 | 31 | 23.98% | 11.7982 | 1991-2020 | GREEN - official NIWA normal
Nelson | 6 | Jun | 8.6552 | 99.5 | 30 | 28.85% | 11.496 | 1991-2020 | GREEN - official NIWA normal
Nelson | 7 | Jul | 7.7333 | 78.6 | 31 | 24.95% | 10.1638 | 1991-2020 | GREEN - official NIWA normal
Nelson | 8 | Aug | 9.2 | 83.8 | 31 | 29.68% | 9.1087 | 1991-2020 | GREEN - official NIWA normal
Nelson | 9 | Sep | 9.8333 | 84.6 | 30 | 32.78% | 8.6034 | 1991-2020 | GREEN - official NIWA normal
Nelson | 10 | Oct | 8.9 | 89 | 31 | 28.71% | 10 | 1991-2020 | GREEN - official NIWA normal
Nelson | 11 | Nov | 7.5 | 67.9 | 30 | 25% | 9.0533 | 1991-2020 | GREEN - official NIWA normal
Nelson | 12 | Dec | 8.6333 | 93 | 31 | 27.85% | 10.7722 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 1 | Jan | 4.7917 | 43 | 31 | 15.46% | 8.9739 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 2 | Feb | 4.1667 | 44.6 | 28.2667 | 14.74% | 10.704 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 3 | Mar | 4.6667 | 39.4 | 31 | 15.05% | 8.4429 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 4 | Apr | 5.75 | 53.8 | 30 | 19.17% | 9.3565 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 5 | May | 7 | 56.9 | 31 | 22.58% | 8.1286 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 6 | Jun | 7.6 | 68.6 | 30 | 25.33% | 9.0263 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 7 | Jul | 7.2 | 64.2 | 31 | 23.23% | 8.9167 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 8 | Aug | 7.6 | 57.9 | 31 | 24.52% | 7.6184 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 9 | Sep | 7.44 | 54.4 | 30 | 24.8% | 7.3118 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 10 | Oct | 7.24 | 57.2 | 31 | 23.35% | 7.9006 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 11 | Nov | 6.28 | 49.1 | 30 | 20.93% | 7.8185 | 1991-2020 | GREEN - official NIWA normal
Blenheim | 12 | Dec | 6.12 | 49.7 | 31 | 19.74% | 8.1209 | 1991-2020 | GREEN - official NIWA normal
Westport | 1 | Jan | 11.963 | 163.4 | 31 | 38.59% | 13.6588 | 1991-2020 | GREEN - official NIWA normal
Westport | 2 | Feb | 10.4138 | 121.4 | 28.2667 | 36.84% | 11.6576 | 1991-2020 | GREEN - official NIWA normal
Westport | 3 | Mar | 11.6429 | 143.1 | 31 | 37.56% | 12.2908 | 1991-2020 | GREEN - official NIWA normal
Westport | 4 | Apr | 12.3333 | 163.8 | 30 | 41.11% | 13.2811 | 1991-2020 | GREEN - official NIWA normal
Westport | 5 | May | 15.3214 | 186.5 | 31 | 49.42% | 12.1725 | 1991-2020 | GREEN - official NIWA normal
Westport | 6 | Jun | 16.3929 | 199.5 | 30 | 54.64% | 12.1699 | 1991-2020 | GREEN - official NIWA normal
Westport | 7 | Jul | 14.1154 | 170.1 | 31 | 45.53% | 12.0507 | 1991-2020 | GREEN - official NIWA normal
Westport | 8 | Aug | 15.7037 | 187 | 31 | 50.66% | 11.908 | 1991-2020 | GREEN - official NIWA normal
Westport | 9 | Sep | 16.9655 | 182.6 | 30 | 56.55% | 10.763 | 1991-2020 | GREEN - official NIWA normal
Westport | 10 | Oct | 17.8929 | 202.2 | 31 | 57.72% | 11.3006 | 1991-2020 | GREEN - official NIWA normal
Westport | 11 | Nov | 14.5862 | 157.3 | 30 | 48.62% | 10.7842 | 1991-2020 | GREEN - official NIWA normal
Westport | 12 | Dec | 14.8966 | 196.9 | 31 | 48.05% | 13.2178 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 1 | Jan | 6.5556 | 47.4 | 31 | 21.15% | 7.2305 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 2 | Feb | 5.7037 | 39.3 | 28.2667 | 20.18% | 6.8903 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 3 | Mar | 6.5862 | 66.1 | 31 | 21.25% | 10.0361 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 4 | Apr | 7.069 | 66.6 | 30 | 23.56% | 9.4215 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 5 | May | 6.3103 | 51 | 31 | 20.36% | 8.082 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 6 | Jun | 8.1429 | 73 | 30 | 27.14% | 8.9649 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 7 | Jul | 7.9333 | 86.5 | 31 | 25.59% | 10.9034 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 8 | Aug | 6.6897 | 59.1 | 31 | 21.58% | 8.8345 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 9 | Sep | 6.4138 | 53.6 | 30 | 21.38% | 8.357 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 10 | Oct | 8.0741 | 64.4 | 31 | 26.05% | 7.9761 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 11 | Nov | 6.963 | 58.8 | 30 | 23.21% | 8.4447 | 1991-2020 | GREEN - official NIWA normal
Kaikoura | 12 | Dec | 7.2593 | 49.3 | 31 | 23.42% | 6.7913 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 1 | Jan | 12.4483 | 257.4 | 31 | 40.16% | 20.6776 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 2 | Feb | 10.8 | 191.7 | 28.2667 | 38.21% | 17.75 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 3 | Mar | 12.1034 | 213.4 | 31 | 39.04% | 17.6313 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 4 | Apr | 13.1 | 244.9 | 30 | 43.67% | 18.6947 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 5 | May | 15 | 252.8 | 31 | 48.39% | 16.8533 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 6 | Jun | 14.7667 | 261.2 | 30 | 49.22% | 17.6885 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 7 | Jul | 14.069 | 228 | 31 | 45.38% | 16.2059 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 8 | Aug | 15.3333 | 246.9 | 31 | 49.46% | 16.1022 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 9 | Sep | 16.8667 | 244.7 | 30 | 56.22% | 14.5079 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 10 | Oct | 17.7333 | 284.8 | 31 | 57.2% | 16.0602 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 11 | Nov | 14.5333 | 222.9 | 30 | 48.44% | 15.3372 | 1991-2020 | GREEN - official NIWA normal
Hokitika | 12 | Dec | 15.6552 | 272.1 | 31 | 50.5% | 17.3808 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 1 | Jan | 6.0333 | 42.4 | 31 | 19.46% | 7.0276 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 2 | Feb | 5.3333 | 39.8 | 28.2667 | 18.87% | 7.4625 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 3 | Mar | 5.7333 | 45.1 | 31 | 18.49% | 7.8663 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 4 | Apr | 7.6667 | 57.5 | 30 | 25.56% | 7.5 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 5 | May | 7.1333 | 58.1 | 31 | 23.01% | 8.1449 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 6 | Jun | 8.6 | 68.3 | 30 | 28.67% | 7.9419 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 7 | Jul | 7.6667 | 64.2 | 31 | 24.73% | 8.3739 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 8 | Aug | 7.3 | 58.1 | 31 | 23.55% | 7.9589 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 9 | Sep | 6.2 | 42.2 | 30 | 20.67% | 6.8065 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 10 | Oct | 7.2 | 49.1 | 31 | 23.23% | 6.8194 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 11 | Nov | 7 | 45.1 | 30 | 23.33% | 6.4429 | 1991-2020 | GREEN - official NIWA normal
Christchurch | 12 | Dec | 7.0333 | 47.8 | 31 | 22.69% | 6.7962 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 1 | Jan | 11.25 | 418.7 | 31 | 36.29% | 37.2178 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 2 | Feb | 8.95 | 272 | 28.2667 | 31.66% | 30.3911 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 3 | Mar | 10 | 315 | 31 | 32.26% | 31.5 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 4 | Apr | 11.5238 | 336.5 | 30 | 38.41% | 29.2004 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 5 | May | 15.2381 | 377.8 | 31 | 49.16% | 24.7931 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 6 | Jun | 14.1905 | 291 | 30 | 47.3% | 20.5067 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 7 | Jul | 13.15 | 288.6 | 31 | 42.42% | 21.9468 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 8 | Aug | 13.55 | 283.8 | 31 | 43.71% | 20.9446 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 9 | Sep | 15 | 361 | 30 | 50% | 24.0667 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 10 | Oct | 15.8095 | 394.4 | 31 | 51% | 24.947 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 11 | Nov | 13.5238 | 367.6 | 30 | 45.08% | 27.1817 | 1991-2020 | GREEN - official NIWA normal
Mt Cook | 12 | Dec | 13.8095 | 425.9 | 31 | 44.55% | 30.841 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 1 | Jan | 4.9412 | 38.1 | 31 | 15.94% | 7.7107 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 2 | Feb | 4.4118 | 42.2 | 28.2667 | 15.61% | 9.5653 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 3 | Mar | 4.7647 | 29.2 | 31 | 15.37% | 6.1284 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 4 | Apr | 5.9412 | 51 | 30 | 19.8% | 8.5842 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 5 | May | 7.7647 | 71.6 | 31 | 25.05% | 9.2212 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 6 | Jun | 7.2353 | 52.1 | 30 | 24.12% | 7.2008 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 7 | Jul | 6.7778 | 50.3 | 31 | 21.86% | 7.4213 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 8 | Aug | 7.1765 | 38.2 | 31 | 23.15% | 5.323 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 9 | Sep | 6.4118 | 33.8 | 30 | 21.37% | 5.2716 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 10 | Oct | 7.3333 | 44.9 | 31 | 23.66% | 6.1227 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 11 | Nov | 5.8889 | 42.3 | 30 | 19.63% | 7.183 | 1991-2020 | GREEN - official NIWA normal
Lake Tekapo | 12 | Dec | 6.1667 | 41.1 | 31 | 19.89% | 6.6649 | 1991-2020 | GREEN - official NIWA normal
Timaru | 1 | Jan | 7.6364 | 50.3 | 31 | 24.63% | 6.5869 | 1991-2020 | GREEN - official NIWA normal
Timaru | 2 | Feb | 6 | 52.3 | 28.2667 | 21.23% | 8.7167 | 1991-2020 | GREEN - official NIWA normal
Timaru | 3 | Mar | 5.75 | 38.6 | 31 | 18.55% | 6.713 | 1991-2020 | GREEN - official NIWA normal
Timaru | 4 | Apr | 7.3333 | 49.3 | 30 | 24.44% | 6.7227 | 1991-2020 | GREEN - official NIWA normal
Timaru | 5 | May | 6.4167 | 39.7 | 31 | 20.7% | 6.187 | 1991-2020 | GREEN - official NIWA normal
Timaru | 6 | Jun | 5.25 | 39.4 | 30 | 17.5% | 7.5048 | 1991-2020 | GREEN - official NIWA normal
Timaru | 7 | Jul | 5 | 42 | 31 | 16.13% | 8.4 | 1991-2020 | GREEN - official NIWA normal
Timaru | 8 | Aug | 5.6154 | 44.6 | 31 | 18.11% | 7.9425 | 1991-2020 | GREEN - official NIWA normal
Timaru | 9 | Sep | 5.3846 | 33.5 | 30 | 17.95% | 6.2214 | 1991-2020 | GREEN - official NIWA normal
Timaru | 10 | Oct | 8.0769 | 47.8 | 31 | 26.05% | 5.9181 | 1991-2020 | GREEN - official NIWA normal
Timaru | 11 | Nov | 7.2308 | 51.5 | 30 | 24.1% | 7.1223 | 1991-2020 | GREEN - official NIWA normal
Timaru | 12 | Dec | 7 | 54 | 31 | 22.58% | 7.7143 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 1 | Jan | 16.2941 | 667.2 | 31 | 52.56% | 40.9473 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 2 | Feb | 12.8421 | 466.6 | 28.2667 | 45.43% | 36.3336 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 3 | Mar | 14.3889 | 571.3 | 31 | 46.42% | 39.7042 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 4 | Apr | 13.3333 | 528.2 | 30 | 44.44% | 39.615 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 5 | May | 15.6429 | 645.1 | 31 | 50.46% | 41.2393 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 6 | Jun | 14.5556 | 440.4 | 30 | 48.52% | 30.2565 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 7 | Jul | 14.3529 | 468 | 31 | 46.3% | 32.6066 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 8 | Aug | 16 | 457 | 31 | 51.61% | 28.5625 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 9 | Sep | 17.5714 | 541.3 | 30 | 58.57% | 30.8057 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 10 | Oct | 17.6111 | 617.2 | 31 | 56.81% | 35.0461 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 11 | Nov | 15.3333 | 557.7 | 30 | 51.11% | 36.3717 | 1991-2020 | GREEN - official NIWA normal
Milford Sound | 12 | Dec | 16.9 | 585.1 | 31 | 54.52% | 34.6213 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 1 | Jan | 7.5714 | 71.6 | 31 | 24.42% | 9.4566 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 2 | Feb | 6.5357 | 51 | 28.2667 | 23.12% | 7.8033 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 3 | Mar | 7.3 | 49.3 | 31 | 23.55% | 6.7534 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 4 | Apr | 7.2667 | 57.5 | 30 | 24.22% | 7.9128 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 5 | May | 9.6552 | 75.1 | 31 | 31.15% | 7.7782 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 6 | Jun | 8.5714 | 62.2 | 30 | 28.57% | 7.2567 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 7 | Jul | 7.7931 | 55.8 | 31 | 25.14% | 7.1602 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 8 | Aug | 8.069 | 52.8 | 31 | 26.03% | 6.5436 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 9 | Sep | 8.3448 | 62.3 | 30 | 27.82% | 7.4657 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 10 | Oct | 8.4286 | 62.4 | 31 | 27.19% | 7.4034 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 11 | Nov | 7.7 | 60.7 | 30 | 25.67% | 7.8831 | 1991-2020 | GREEN - official NIWA normal
Queenstown | 12 | Dec | 8.6897 | 60.3 | 31 | 28.03% | 6.9393 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 1 | Jan | 5.9048 | 46.9 | 31 | 19.05% | 7.9427 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 2 | Feb | 5.2273 | 41.1 | 28.2667 | 18.49% | 7.8626 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 3 | Mar | 5.2 | 31.2 | 31 | 16.77% | 6 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 4 | Apr | 4.85 | 22 | 30 | 16.17% | 4.5361 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 5 | May | 6.75 | 34.3 | 31 | 21.77% | 5.0815 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 6 | Jun | 5.4 | 30.9 | 30 | 18% | 5.7222 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 7 | Jul | 4.8636 | 25.2 | 31 | 15.69% | 5.1813 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 8 | Aug | 4.24 | 15.4 | 31 | 13.68% | 3.6321 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 9 | Sep | 5.0476 | 21.3 | 30 | 16.83% | 4.2198 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 10 | Oct | 6.2381 | 29.6 | 31 | 20.12% | 4.745 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 11 | Nov | 5.5238 | 32.7 | 30 | 18.41% | 5.9198 | 1991-2020 | GREEN - official NIWA normal
Alexandra | 12 | Dec | 7 | 34.5 | 31 | 22.58% | 4.9286 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 1 | Jan | 9.5 | 88.6 | 31 | 30.65% | 9.3263 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 2 | Feb | 8.0357 | 85.3 | 28.2667 | 28.43% | 10.6151 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 3 | Mar | 9.6429 | 82.7 | 31 | 31.11% | 8.5763 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 4 | Apr | 10.2143 | 85 | 30 | 34.05% | 8.3217 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 5 | May | 12.2593 | 104.4 | 31 | 39.55% | 8.516 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 6 | Jun | 11.9286 | 91.4 | 30 | 39.76% | 7.6623 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 7 | Jul | 11.7143 | 94.2 | 31 | 37.79% | 8.0415 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 8 | Aug | 10.8929 | 82 | 31 | 35.14% | 7.5279 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 9 | Sep | 12.0357 | 106.2 | 30 | 40.12% | 8.8237 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 10 | Oct | 12.7241 | 113 | 31 | 41.05% | 8.8808 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 11 | Nov | 10.5357 | 95.7 | 30 | 35.12% | 9.0834 | 1991-2020 | GREEN - official NIWA normal
Manapouri | 12 | Dec | 11.0345 | 97.4 | 31 | 35.6% | 8.8269 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 1 | Jan | 9.1304 | 70.5 | 31 | 29.45% | 7.7214 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 2 | Feb | 7.4783 | 69.9 | 28.2667 | 26.46% | 9.3471 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 3 | Mar | 7.6087 | 53.9 | 31 | 24.54% | 7.084 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 4 | Apr | 8.0435 | 60.8 | 30 | 26.81% | 7.5589 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 5 | May | 9.6818 | 63.6 | 31 | 31.23% | 6.569 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 6 | Jun | 8.5217 | 58.5 | 30 | 28.41% | 6.8648 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 7 | Jul | 7.7826 | 51.7 | 31 | 25.11% | 6.643 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 8 | Aug | 8.6522 | 54.7 | 31 | 27.91% | 6.3221 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 9 | Sep | 8.1667 | 47.1 | 30 | 27.22% | 5.7673 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 10 | Oct | 10.5417 | 60.1 | 31 | 34.01% | 5.7012 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 11 | Nov | 9.625 | 62.5 | 30 | 32.08% | 6.4935 | 1991-2020 | GREEN - official NIWA normal
Dunedin | 12 | Dec | 10.375 | 70.8 | 31 | 33.47% | 6.8241 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 1 | Jan | 12.56 | 88.7 | 31 | 40.52% | 7.0621 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 2 | Feb | 10.56 | 74.2 | 28.2667 | 37.36% | 7.0265 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 3 | Mar | 11.92 | 91.8 | 31 | 38.45% | 7.7013 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 4 | Apr | 12.1154 | 89.5 | 30 | 40.38% | 7.3873 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 5 | May | 14.68 | 108.4 | 31 | 47.35% | 7.3842 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 6 | Jun | 15.4231 | 95.1 | 30 | 51.41% | 6.1661 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 7 | Jul | 14.4231 | 88 | 31 | 46.53% | 6.1013 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 8 | Aug | 12.2692 | 70.4 | 31 | 39.58% | 5.7379 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 9 | Sep | 13.48 | 90.4 | 30 | 44.93% | 6.7062 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 10 | Oct | 15.4231 | 106.2 | 31 | 49.75% | 6.8858 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 11 | Nov | 14.4231 | 101.7 | 30 | 48.08% | 7.0512 | 1991-2020 | GREEN - official NIWA normal
Invercargill | 12 | Dec | 13.3462 | 92.9 | 31 | 43.05% | 6.9608 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 1 | Jan | 6.8333 | 49.2 | 31 | 22.04% | 7.2 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 2 | Feb | 7 | 64 | 28.2667 | 24.76% | 9.1429 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 3 | Mar | 8.5714 | 75.7 | 31 | 27.65% | 8.8317 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 4 | Apr | 11.7143 | 79 | 30 | 39.05% | 6.7439 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 5 | May | 14.4 | 88.3 | 31 | 46.45% | 6.1319 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 6 | Jun | 15.4 | 93.7 | 30 | 51.33% | 6.0844 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 7 | Jul | 15.3333 | 72.3 | 31 | 49.46% | 4.7152 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 8 | Aug | 12.8333 | 71 | 31 | 41.4% | 5.5325 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 9 | Sep | 12 | 71.3 | 30 | 40% | 5.9417 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 10 | Oct | 10.6667 | 56.2 | 31 | 34.41% | 5.2688 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 11 | Nov | 8.4 | 53.5 | 30 | 28% | 6.369 | 1991-2020 | GREEN - official NIWA normal
Chatham Islands | 12 | Dec | 10.125 | 62.9 | 31 | 32.66% | 6.2123 | 1991-2020 | GREEN - official NIWA normal

## Station Register
NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals | NIWA Station Register - 1991-2020 Climate Normals
Use the nearest representative station, then record any local site factor and its basis. Rainfall and wet-day station records are shown separately where NIWA used different stations.
Location Selector | Rain Station | Rain Network | Wet-Day Station | Wet-Day Network | Latitude | Longitude | Height (m)
Kaitaia | Kaitaia Ews | A53127 | Kaitaia Ews | A53127 | -35.1335 | 173.2629 | 85
Whangarei | Whangarei Aero Aws | A54737 | Whangarei Aero Aws | A54737 | -35.7706 | 174.3629 | 37
Auckland | Auckland Aero | C74082 | Auckland Aero | C74082 | -37.0081 | 174.7887 | 7
Tauranga | Tauranga Aero Aws | B76624 | Tauranga Aero Aws | B76624 | -37.675 | 176.192 | 2
Hamilton | Hamilton, Ruakura 2 Ews | C75734 | Hamilton, Ruakura 2 Ews | C75734 | -37.7739 | 175.3052 | 45
Rotorua | Rotorua Aero Aws | B86133 | Rotorua Aero Aws | B86133 | -38.1059 | 176.3148 | 286
Gisborne | Gisborne Ews | D87697 | Gisborne Aero Aws | D87695 | -38.6586 | 177.9851 | 5
Taupo | Taupo Aero Aws | B86704 | Taupo Aero Aws | B86704 | -38.7425 | 176.0811 | 402
New Plymouth | New Plymouth Aero Aws | C94012 | New Plymouth Aero Aws | C94012 | -39.0079 | 174.1838 | 28
Napier | Napier Aero Aws | D96484 | Napier Aero Aws | D96484 | -39.4703 | 176.8646 | 3
Whanganui | Whanganui, Spriggens Park Ews | E95902 | Whanganui, Spriggens Park Ews | E95902 | -39.937 | 175.0451 | 15
Palmerston North | Palmerston North Ews | E0536D | Palmerston North Ews | E0536D | -40.382 | 175.6091 | 21
Masterton | Masterton, Te Ore Ore Cws | D05974 | Masterton, Te Ore Ore Cws | D05974 | -40.957 | 175.707 | 110
Wellington | Wellington, Kelburn Aws | E1427P | Wellington, Kelburn Aws | E1427P | -41.2844 | 174.7679 | 125
Nelson | Nelson Aero | G13222 | Nelson Aero | G13222 | -41.299 | 173.226 | 2
Blenheim | Blenheim Research Ews | G13495 | Blenheim Research Ews | G13495 | -41.4989 | 173.9629 | 4
Westport | Westport Aero Aws | F11754 | Westport Aero Aws | F11754 | -41.7407 | 171.5798 | 5
Kaikoura | Kaikoura Aws | G23464 | Kaikoura Aws | G23464 | -42.4204 | 173.6963 | 108
Hokitika | Hokitika Aero | F20793 | Hokitika Aero | F20793 | -42.712 | 170.984 | 39
Christchurch | Christchurch Aero | H32451 | Christchurch Aero | H32451 | -43.493 | 172.537 | 37
Mt Cook | Mt Cook Ews | H30706 | Mt Cook Ews | H30706 | -43.7363 | 170.0977 | 730
Lake Tekapo | Lake Tekapo Ews | H40042 | Lake Tekapo Ews | H40042 | -44.0017 | 170.4432 | 762
Timaru | Timaru Ews | H41425 | Timaru Ews | H41425 | -44.4088 | 171.2543 | 17
Milford Sound | Milford Sound Aws | F47693 | Milford Sound Aws | F47693 | -44.6733 | 167.9243 | 3
Queenstown | Queenstown Aero Aws | I58075 | Queenstown Aero Aws | I58075 | -45.0176 | 168.7402 | 357
Alexandra | Alexandra | I59236 | Alexandra | I59236 | -45.246 | 169.3896 | 150
Manapouri | Manapouri Aero Aws | I57563 | Manapouri Aero Aws | I57563 | -45.5329 | 167.6416 | 209
Dunedin | Dunedin, Musselburgh Ews | I50954 | Dunedin, Musselburgh Ews | I50954 | -45.9013 | 170.5147 | 4
Invercargill | Invercargill Aero Aws | I68435 | Invercargill Aero Aws | I68435 | -46.411 | 168.3178 | 3
Chatham Islands | Chatham Island Aero Aws | K98617 | Chatham Island Aero Aws | K98617 | -43.8168 | -176.475 | 12

## Wind Proxy
Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER | Auckland Wind-Day Proxy - Optional and AMBER
This is not a current 1991-2020 monthly wind-day normal. It is an explicit proxy for Auckland only: NIWA reports 55 days/year with gusts above 63 km/h at Auckland Airport. Those days are distributed by NIWA's seasonal share of strong winds and normalised to 100%. Use only where the task threshold is comparable, or enter a project-specific wind probability override.
Location | Month # | Month | Season | Season Share | Annual Gust Days >63 km/h | Proxy Days in Month | Daily Wind Event Probability | Status | Basis
Auckland | 1 | Jan | Summer | 21% | 55 | 3.8889 | 12.54% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 2 | Feb | Summer | 21% | 55 | 3.8889 | 13.76% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 3 | Mar | Autumn | 19% | 55 | 3.5185 | 11.35% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 4 | Apr | Autumn | 19% | 55 | 3.5185 | 11.73% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 5 | May | Autumn | 19% | 55 | 3.5185 | 11.35% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 6 | Jun | Winter | 23% | 55 | 4.2593 | 14.2% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 7 | Jul | Winter | 23% | 55 | 4.2593 | 13.74% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 8 | Aug | Winter | 23% | 55 | 4.2593 | 13.74% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 9 | Sep | Spring | 36% | 55 | 6.6667 | 22.22% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 10 | Oct | Spring | 36% | 55 | 6.6667 | 21.51% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 11 | Nov | Spring | 36% | 55 | 6.6667 | 22.22% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.
Auckland | 12 | Dec | Summer | 21% | 55 | 3.8889 | 12.54% | AMBER - legacy proxy | Inference: 55 annual gust days allocated using seasonal strong-wind shares; not direct monthly observations.

## Weather Log
Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence | Actual Project Weather Log - Calibration Evidence
Record actual planned and lost crew hours by cause. Do not rewrite Task Library defaults automatically; review the evidence, normalise the job context, then approve any update under change control.
Project ID | Date | Location | Task | Planned Crew Hours | Lost Hours - Rain | Lost Hours - Wet Ground | Lost Hours - Wind | Recovered / Resequenced Hours | Net Lost Hours | Programme Delay Hours | Direct Cost Impact $ | Evidence / Daily Record | Notes | Reviewed By

## Calibration Summary
Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task | Weather Calibration Summary by Task
Observed records improve the company defaults, but record count alone does not make a factor GREEN. Review project comparability, causes, recovery, crew composition and independent evidence before approving a library change.
Task | Category | Records | Planned Hours | Rain Lost Hours | Wet-Ground Lost Hours | Wind Lost Hours | Recovered Hours | Net Lost Hours | Observed Net Loss % | Programme Delay Hours | Calibration Status | Action
Site establishment / temp fencing | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Erosion & sediment controls | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Bulk earthworks | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Detailed earthworks / trim subgrade | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Cut to fill / cartage | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Building platform / pad prep | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Drainage trenching | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Manholes / chambers | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Service trenches / ducting | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Bored piles / drilled holes | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Driven poles / posts | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Retaining wall excavation | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Retaining wall installation | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
External concrete placing | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
External concrete finishing | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Kerb & channel | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Subbase / pavement prep | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Asphalt / sealing | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Landscaping / topsoil / grassing | Civil | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Roof framing | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Roofing | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Wall framing (open structure) | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Cladding | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Exterior windows / joinery | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Deck framing | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Decking | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Scaffolding | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Steel erection / crane lifts | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
External block / brick laying | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
External painting / coatings | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal framing | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal linings / plasterboard | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal plastering / stopping | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal painting | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Fitout / cabinetry / joinery | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal tiling / wet areas | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal flooring | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Internal MEP rough-in / fit-off | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records
Workshop fabrication / sheltered prep | Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | UNCALIBRATED | Collect actual project records

## Calculation Audit
Weather Model Calculation Audit and Release Gate | Weather Model Calculation Audit and Release Gate | Weather Model Calculation Audit and Release Gate | Weather Model Calculation Audit and Release Gate | Weather Model Calculation Audit and Release Gate | Weather Model Calculation Audit and Release Gate
Check | Expected | Actual | Status | Why It Matters | Action if Not OK
NIWA location count | 30 | 30 | GREEN - OK | Location selector completeness | Reload official source data
Climate data rows | 360 | 360 | GREEN - OK | 12 months per location | Repair missing station/month rows
Missing wet-day values | 0 | 0 | GREEN - OK | Prevents unsupported probabilities | Stop use and reload source
Missing rainfall values | 0 | 0 | GREEN - OK | Source completeness | Stop use and reload source
Wet-day probability outside 0-100% | 0 | 0 | GREEN - OK | Probability validity | Repair source/formula
Task library rows | 39 | 39 | GREEN - OK | Original task coverage retained | Review task import
Date engine start | 2025-01-01 | 2025-01-01 | GREEN - OK | Input coverage | Extend engine
Date engine finish | 2040-12-31 | 2040-12-31 | GREEN - OK | Input coverage | Extend engine
Active Estimator RED controls | 0 | 1 | RED - CHECK | Blocks unsupported issue | Resolve inputs or qualify/exclude
Activity Allowances RED rows | 0 | 0 | GREEN - OK | Blocks unsupported issue | Resolve task dates/wind data
Source and Assumption Release Status | Source and Assumption Release Status | Source and Assumption Release Status | Source and Assumption Release Status | Source and Assumption Release Status | Source and Assumption Release Status
Component | Status | Reason
NIWA 1991-2020 wet-day and rainfall data | GREEN | Current official published climate normals
Task sensitivity defaults | AMBER | Company judgement pending actual-project calibration
Auckland wind proxy | AMBER | Legacy proxy and inferred monthly allocation
Non-Auckland wind inputs | RED if material | No public threshold-aligned frequency loaded
Tool release gate | RED - DO NOT ISSUE ACTIVE OUTPUT

## Source Register
Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations | Source Register and Model Limitations
Source ID | Variable / Use | Source | Period / Version | Accessed | Status | Source URL | Limitations / Required Action
SRC-WX-001 | Mean monthly wet days >=1 mm | NIWA / Earth Sciences New Zealand | 1991-2020 normals | 2026-08-14 | GREEN | https://niwa.co.nz/sites/default/files/inline-images/wet_days_1991-2020_1.xlsx | Official climate normal. A wet day is not automatically a construction lost day.
SRC-WX-002 | Mean monthly rainfall and rain per wet day context | NIWA / Earth Sciences New Zealand | 1991-2020 normals | 2026-08-14 | GREEN | https://niwa.co.nz/sites/default/files/inline-images/mean_monthly_rainfall_1991-2020_1.xlsx | Rainfall intensity is shown as context and does not directly set lost days.
SRC-WX-003 | Climate data landing page and reuse licence | NIWA / Earth Sciences New Zealand | Current page | 2026-08-14 | GREEN | https://niwa.co.nz/climate-and-weather/climate-data-and-activities | Downloads are published under Creative Commons Attribution 4.0.
SRC-WX-004 | Auckland gust-day proxy | NIWA Auckland climate report | Legacy regional climatology | 2026-08-14 | AMBER | https://webstatic.niwa.co.nz/static/web/Auckland_Climate_NIWA.pdf | 55 days/year with gusts >63 km/h. Monthly allocation is inferred from seasonal strong-wind shares; replace with threshold-aligned data where wind is material.
SRC-WX-005 | Task exposure, productivity, carryover and recovery factors | Company estimating judgement | Rev2 initial defaults | 2026-08-14 | AMBER | Internal Task Library | Uncalibrated starting points. Improve from Weather Log and independent review.
SRC-WX-006 | Local wet-day factor | Project-specific evidence | User input |  | RED until sourced when not 1.00 | Estimator input | Record topography, station comparison, site history or other defensible basis.
Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules | Model Interpretation Rules
1 | The output is a planning allowance based on long-run climate normals, not a weather forecast or guaranteed loss.
2 | Dates determine the monthly climate weighting and workday count. They do not predict weather on a particular day.
3 | Rain, wet-ground carryover, wind, direct productivity, critical-path delay, time-related preliminaries, hire and recovery are separate cost drivers.
4 | Do not sum programme delay across concurrent tasks. Use only the verified critical path from the programme.
5 | Task factors are AMBER until actual company data and an independent review support change control.
6 | If the site is outside 2025-2040 date-engine coverage, update the engine before use.
7 | If the selected location is not Auckland and wind is material, supply threshold-aligned wind data or exclude / qualify the wind risk.

## Date Engine
Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040 | Date Engine - 2025 to 2040
Calculation support sheet. Workday flags follow the Estimator working-days-per-week input. Public holidays and shutdowns are not included; use the working-days override once the contract calendar is known.
Date | Year | Month # | Month | Day | Weekday # | Standard Workday | Daily Wet-Day Probability | Mean Rain per Wet Day (mm) | Daily Wind Proxy Probability
2025-01-01 | 2025 | 1 | Jan | 1 | 3 | 1 | 19.46% | 7.0276 | 0%
2025-01-02 | 2025 | 1 | Jan | 2 | 4 | 1 | 19.46% | 7.0276 | 0%
2025-01-03 | 2025 | 1 | Jan | 3 | 5 | 1 | 19.46% | 7.0276 | 0%
2025-01-04 | 2025 | 1 | Jan | 4 | 6 | 0 | 19.46% | 7.0276 | 0%
2025-01-05 | 2025 | 1 | Jan | 5 | 7 | 0 | 19.46% | 7.0276 | 0%
2025-01-06 | 2025 | 1 | Jan | 6 | 1 | 1 | 19.46% | 7.0276 | 0%
2025-01-07 | 2025 | 1 | Jan | 7 | 2 | 1 | 19.46% | 7.0276 | 0%
2025-01-08 | 2025 | 1 | Jan | 8 | 3 | 1 | 19.46% | 7.0276 | 0%
2025-01-09 | 2025 | 1 | Jan | 9 | 4 | 1 | 19.46% | 7.0276 | 0%
2025-01-10 | 2025 | 1 | Jan | 10 | 5 | 1 | 19.46% | 7.0276 | 0%
2025-01-11 | 2025 | 1 | Jan | 11 | 6 | 0 | 19.46% | 7.0276 | 0%
2025-01-12 | 2025 | 1 | Jan | 12 | 7 | 0 | 19.46% | 7.0276 | 0%
2025-01-13 | 2025 | 1 | Jan | 13 | 1 | 1 | 19.46% | 7.0276 | 0%
2025-01-14 | 2025 | 1 | Jan | 14 | 2 | 1 | 19.46% | 7.0276 | 0%
2025-01-15 | 2025 | 1 | Jan | 15 | 3 | 1 | 19.46% | 7.0276 | 0%
2025-01-16 | 2025 | 1 | Jan | 16 | 4 | 1 | 19.46% | 7.0276 | 0%
2025-01-17 | 2025 | 1 | Jan | 17 | 5 | 1 | 19.46% | 7.0276 | 0%
2025-01-18 | 2025 | 1 | Jan | 18 | 6 | 0 | 19.46% | 7.0276 | 0%
2025-01-19 | 2025 | 1 | Jan | 19 | 7 | 0 | 19.46% | 7.0276 | 0%
2025-01-20 | 2025 | 1 | Jan | 20 | 1 | 1 | 19.46% | 7.0276 | 0%
2025-01-21 | 2025 | 1 | Jan | 21 | 2 | 1 | 19.46% | 7.0276 | 0%
2025-01-22 | 2025 | 1 | Jan | 22 | 3 | 1 | 19.46% | 7.0276 | 0%
2025-01-23 | 2025 | 1 | Jan | 23 | 4 | 1 | 19.46% | 7.0276 | 0%
2025-01-24 | 2025 | 1 | Jan | 24 | 5 | 1 | 19.46% | 7.0276 | 0%
2025-01-25 | 2025 | 1 | Jan | 25 | 6 | 0 | 19.46% | 7.0276 | 0%
2025-01-26 | 2025 | 1 | Jan | 26 | 7 | 0 | 19.46% | 7.0276 | 0%
2025-01-27 | 2025 | 1 | Jan | 27 | 1 | 1 | 19.46% | 7.0276 | 0%
2025-01-28 | 2025 | 1 | Jan | 28 | 2 | 1 | 19.46% | 7.0276 | 0%
2025-01-29 | 2025 | 1 | Jan | 29 | 3 | 1 | 19.46% | 7.0276 | 0%
2025-01-30 | 2025 | 1 | Jan | 30 | 4 | 1 | 19.46% | 7.0276 | 0%
2025-01-31 | 2025 | 1 | Jan | 31 | 5 | 1 | 19.46% | 7.0276 | 0%
2025-02-01 | 2025 | 2 | Feb | 1 | 6 | 0 | 18.87% | 7.4625 | 0%
2025-02-02 | 2025 | 2 | Feb | 2 | 7 | 0 | 18.87% | 7.4625 | 0%
2025-02-03 | 2025 | 2 | Feb | 3 | 1 | 1 | 18.87% | 7.4625 | 0%
2025-02-04 | 2025 | 2 | Feb | 4 | 2 | 1 | 18.87% | 7.4625 | 0%
2025-02-05 | 2025 | 2 | Feb | 5 | 3 | 1 | 18.87% | 7.4625 | 0%
2025-02-06 | 2025 | 2 | Feb | 6 | 4 | 1 | 18.87% | 7.4625 | 0%
2025-02-07 | 2025 | 2 | Feb | 7 | 5 | 1 | 18.87% | 7.4625 | 0%
2025-02-08 | 2025 | 2 | Feb | 8 | 6 | 0 | 18.87% | 7.4625 | 0%
2025-02-09 | 2025 | 2 | Feb | 9 | 7 | 0 | 18.87% | 7.4625 | 0%
2025-02-10 | 2025 | 2 | Feb | 10 | 1 | 1 | 18.87% | 7.4625 | 0%
2025-02-11 | 2025 | 2 | Feb | 11 | 2 | 1 | 18.87% | 7.4625 | 0%
2025-02-12 | 2025 | 2 | Feb | 12 | 3 | 1 | 18.87% | 7.4625 | 0%
2025-02-13 | 2025 | 2 | Feb | 13 | 4 | 1 | 18.87% | 7.4625 | 0%
2025-02-14 | 2025 | 2 | Feb | 14 | 5 | 1 | 18.87% | 7.4625 | 0%
2025-02-15 | 2025 | 2 | Feb | 15 | 6 | 0 | 18.87% | 7.4625 | 0%
2025-02-16 | 2025 | 2 | Feb | 16 | 7 | 0 | 18.87% | 7.4625 | 0%
2025-02-17 | 2025 | 2 | Feb | 17 | 1 | 1 | 18.87% | 7.4625 | 0%
2025-02-18 | 2025 | 2 | Feb | 18 | 2 | 1 | 18.87% | 7.4625 | 0%
2025-02-19 | 2025 | 2 | Feb | 19 | 3 | 1 | 18.87% | 7.4625 | 0%
2025-02-20 | 2025 | 2 | Feb | 20 | 4 | 1 | 18.87% | 7.4625 | 0%
2025-02-21 | 2025 | 2 | Feb | 21 | 5 | 1 | 18.87% | 7.4625 | 0%
2025-02-22 | 2025 | 2 | Feb | 22 | 6 | 0 | 18.87% | 7.4625 | 0%
2025-02-23 | 2025 | 2 | Feb | 23 | 7 | 0 | 18.87% | 7.4625 | 0%
2025-02-24 | 2025 | 2 | Feb | 24 | 1 | 1 | 18.87% | 7.4625 | 0%
2025-02-25 | 2025 | 2 | Feb | 25 | 2 | 1 | 18.87% | 7.4625 | 0%
2025-02-26 | 2025 | 2 | Feb | 26 | 3 | 1 | 18.87% | 7.4625 | 0%
2025-02-27 | 2025 | 2 | Feb | 27 | 4 | 1 | 18.87% | 7.4625 | 0%
2025-02-28 | 2025 | 2 | Feb | 28 | 5 | 1 | 18.87% | 7.4625 | 0%
2025-03-01 | 2025 | 3 | Mar | 1 | 6 | 0 | 18.49% | 7.8663 | 0%
2025-03-02 | 2025 | 3 | Mar | 2 | 7 | 0 | 18.49% | 7.8663 | 0%
2025-03-03 | 2025 | 3 | Mar | 3 | 1 | 1 | 18.49% | 7.8663 | 0%
2025-03-04 | 2025 | 3 | Mar | 4 | 2 | 1 | 18.49% | 7.8663 | 0%
2025-03-05 | 2025 | 3 | Mar | 5 | 3 | 1 | 18.49% | 7.8663 | 0%
2025-03-06 | 2025 | 3 | Mar | 6 | 4 | 1 | 18.49% | 7.8663 | 0%
2025-03-07 | 2025 | 3 | Mar | 7 | 5 | 1 | 18.49% | 7.8663 | 0%
2025-03-08 | 2025 | 3 | Mar | 8 | 6 | 0 | 18.49% | 7.8663 | 0%
2025-03-09 | 2025 | 3 | Mar | 9 | 7 | 0 | 18.49% | 7.8663 | 0%
2025-03-10 | 2025 | 3 | Mar | 10 | 1 | 1 | 18.49% | 7.8663 | 0%
2025-03-11 | 2025 | 3 | Mar | 11 | 2 | 1 | 18.49% | 7.8663 | 0%
2025-03-12 | 2025 | 3 | Mar | 12 | 3 | 1 | 18.49% | 7.8663 | 0%
2025-03-13 | 2025 | 3 | Mar | 13 | 4 | 1 | 18.49% | 7.8663 | 0%
2025-03-14 | 2025 | 3 | Mar | 14 | 5 | 1 | 18.49% | 7.8663 | 0%
2025-03-15 | 2025 | 3 | Mar | 15 | 6 | 0 | 18.49% | 7.8663 | 0%
2025-03-16 | 2025 | 3 | Mar | 16 | 7 | 0 | 18.49% | 7.8663 | 0%
2025-03-17 | 2025 | 3 | Mar | 17 | 1 | 1 | 18.49% | 7.8663 | 0%
2025-03-18 | 2025 | 3 | Mar | 18 | 2 | 1 | 18.49% | 7.8663 | 0%
2025-03-19 | 2025 | 3 | Mar | 19 | 3 | 1 | 18.49% | 7.8663 | 0%
2025-03-20 | 2025 | 3 | Mar | 20 | 4 | 1 | 18.49% | 7.8663 | 0%
2025-03-21 | 2025 | 3 | Mar | 21 | 5 | 1 | 18.49% | 7.8663 | 0%
2025-03-22 | 2025 | 3 | Mar | 22 | 6 | 0 | 18.49% | 7.8663 | 0%
2025-03-23 | 2025 | 3 | Mar | 23 | 7 | 0 | 18.49% | 7.8663 | 0%
2025-03-24 | 2025 | 3 | Mar | 24 | 1 | 1 | 18.49% | 7.8663 | 0%
2025-03-25 | 2025 | 3 | Mar | 25 | 2 | 1 | 18.49% | 7.8663 | 0%
2025-03-26 | 2025 | 3 | Mar | 26 | 3 | 1 | 18.49% | 7.8663 | 0%
2025-03-27 | 2025 | 3 | Mar | 27 | 4 | 1 | 18.49% | 7.8663 | 0%
2025-03-28 | 2025 | 3 | Mar | 28 | 5 | 1 | 18.49% | 7.8663 | 0%
2025-03-29 | 2025 | 3 | Mar | 29 | 6 | 0 | 18.49% | 7.8663 | 0%
2025-03-30 | 2025 | 3 | Mar | 30 | 7 | 0 | 18.49% | 7.8663 | 0%
2025-03-31 | 2025 | 3 | Mar | 31 | 1 | 1 | 18.49% | 7.8663 | 0%
2025-04-01 | 2025 | 4 | Apr | 1 | 2 | 1 | 25.56% | 7.5 | 0%
2025-04-02 | 2025 | 4 | Apr | 2 | 3 | 1 | 25.56% | 7.5 | 0%
2025-04-03 | 2025 | 4 | Apr | 3 | 4 | 1 | 25.56% | 7.5 | 0%
2025-04-04 | 2025 | 4 | Apr | 4 | 5 | 1 | 25.56% | 7.5 | 0%
2025-04-05 | 2025 | 4 | Apr | 5 | 6 | 0 | 25.56% | 7.5 | 0%
2025-04-06 | 2025 | 4 | Apr | 6 | 7 | 0 | 25.56% | 7.5 | 0%
2025-04-07 | 2025 | 4 | Apr | 7 | 1 | 1 | 25.56% | 7.5 | 0%
2025-04-08 | 2025 | 4 | Apr | 8 | 2 | 1 | 25.56% | 7.5 | 0%
2025-04-09 | 2025 | 4 | Apr | 9 | 3 | 1 | 25.56% | 7.5 | 0%
2025-04-10 | 2025 | 4 | Apr | 10 | 4 | 1 | 25.56% | 7.5 | 0%
2025-04-11 | 2025 | 4 | Apr | 11 | 5 | 1 | 25.56% | 7.5 | 0%
2025-04-12 | 2025 | 4 | Apr | 12 | 6 | 0 | 25.56% | 7.5 | 0%
2025-04-13 | 2025 | 4 | Apr | 13 | 7 | 0 | 25.56% | 7.5 | 0%
2025-04-14 | 2025 | 4 | Apr | 14 | 1 | 1 | 25.56% | 7.5 | 0%
2025-04-15 | 2025 | 4 | Apr | 15 | 2 | 1 | 25.56% | 7.5 | 0%
2025-04-16 | 2025 | 4 | Apr | 16 | 3 | 1 | 25.56% | 7.5 | 0%
2025-04-17 | 2025 | 4 | Apr | 17 | 4 | 1 | 25.56% | 7.5 | 0%
2025-04-18 | 2025 | 4 | Apr | 18 | 5 | 1 | 25.56% | 7.5 | 0%
2025-04-19 | 2025 | 4 | Apr | 19 | 6 | 0 | 25.56% | 7.5 | 0%
2025-04-20 | 2025 | 4 | Apr | 20 | 7 | 0 | 25.56% | 7.5 | 0%
2025-04-21 | 2025 | 4 | Apr | 21 | 1 | 1 | 25.56% | 7.5 | 0%
2025-04-22 | 2025 | 4 | Apr | 22 | 2 | 1 | 25.56% | 7.5 | 0%
2025-04-23 | 2025 | 4 | Apr | 23 | 3 | 1 | 25.56% | 7.5 | 0%
2025-04-24 | 2025 | 4 | Apr | 24 | 4 | 1 | 25.56% | 7.5 | 0%
2025-04-25 | 2025 | 4 | Apr | 25 | 5 | 1 | 25.56% | 7.5 | 0%
2025-04-26 | 2025 | 4 | Apr | 26 | 6 | 0 | 25.56% | 7.5 | 0%
2025-04-27 | 2025 | 4 | Apr | 27 | 7 | 0 | 25.56% | 7.5 | 0%
2025-04-28 | 2025 | 4 | Apr | 28 | 1 | 1 | 25.56% | 7.5 | 0%
2025-04-29 | 2025 | 4 | Apr | 29 | 2 | 1 | 25.56% | 7.5 | 0%
2025-04-30 | 2025 | 4 | Apr | 30 | 3 | 1 | 25.56% | 7.5 | 0%
2025-05-01 | 2025 | 5 | May | 1 | 4 | 1 | 23.01% | 8.1449 | 0%
2025-05-02 | 2025 | 5 | May | 2 | 5 | 1 | 23.01% | 8.1449 | 0%
2025-05-03 | 2025 | 5 | May | 3 | 6 | 0 | 23.01% | 8.1449 | 0%
2025-05-04 | 2025 | 5 | May | 4 | 7 | 0 | 23.01% | 8.1449 | 0%
2025-05-05 | 2025 | 5 | May | 5 | 1 | 1 | 23.01% | 8.1449 | 0%
2025-05-06 | 2025 | 5 | May | 6 | 2 | 1 | 23.01% | 8.1449 | 0%
2025-05-07 | 2025 | 5 | May | 7 | 3 | 1 | 23.01% | 8.1449 | 0%
2025-05-08 | 2025 | 5 | May | 8 | 4 | 1 | 23.01% | 8.1449 | 0%
2025-05-09 | 2025 | 5 | May | 9 | 5 | 1 | 23.01% | 8.1449 | 0%
2025-05-10 | 2025 | 5 | May | 10 | 6 | 0 | 23.01% | 8.1449 | 0%
2025-05-11 | 2025 | 5 | May | 11 | 7 | 0 | 23.01% | 8.1449 | 0%
2025-05-12 | 2025 | 5 | May | 12 | 1 | 1 | 23.01% | 8.1449 | 0%
2025-05-13 | 2025 | 5 | May | 13 | 2 | 1 | 23.01% | 8.1449 | 0%
2025-05-14 | 2025 | 5 | May | 14 | 3 | 1 | 23.01% | 8.1449 | 0%
2025-05-15 | 2025 | 5 | May | 15 | 4 | 1 | 23.01% | 8.1449 | 0%
2025-05-16 | 2025 | 5 | May | 16 | 5 | 1 | 23.01% | 8.1449 | 0%
2025-05-17 | 2025 | 5 | May | 17 | 6 | 0 | 23.01% | 8.1449 | 0%
2025-05-18 | 2025 | 5 | May | 18 | 7 | 0 | 23.01% | 8.1449 | 0%
2025-05-19 | 2025 | 5 | May | 19 | 1 | 1 | 23.01% | 8.1449 | 0%
2025-05-20 | 2025 | 5 | May | 20 | 2 | 1 | 23.01% | 8.1449 | 0%
2025-05-21 | 2025 | 5 | May | 21 | 3 | 1 | 23.01% | 8.1449 | 0%
2025-05-22 | 2025 | 5 | May | 22 | 4 | 1 | 23.01% | 8.1449 | 0%
2025-05-23 | 2025 | 5 | May | 23 | 5 | 1 | 23.01% | 8.1449 | 0%
2025-05-24 | 2025 | 5 | May | 24 | 6 | 0 | 23.01% | 8.1449 | 0%
2025-05-25 | 2025 | 5 | May | 25 | 7 | 0 | 23.01% | 8.1449 | 0%
2025-05-26 | 2025 | 5 | May | 26 | 1 | 1 | 23.01% | 8.1449 | 0%
2025-05-27 | 2025 | 5 | May | 27 | 2 | 1 | 23.01% | 8.1449 | 0%
2025-05-28 | 2025 | 5 | May | 28 | 3 | 1 | 23.01% | 8.1449 | 0%
2025-05-29 | 2025 | 5 | May | 29 | 4 | 1 | 23.01% | 8.1449 | 0%
2025-05-30 | 2025 | 5 | May | 30 | 5 | 1 | 23.01% | 8.1449 | 0%
2025-05-31 | 2025 | 5 | May | 31 | 6 | 0 | 23.01% | 8.1449 | 0%
2025-06-01 | 2025 | 6 | Jun | 1 | 7 | 0 | 28.67% | 7.9419 | 0%
2025-06-02 | 2025 | 6 | Jun | 2 | 1 | 1 | 28.67% | 7.9419 | 0%
2025-06-03 | 2025 | 6 | Jun | 3 | 2 | 1 | 28.67% | 7.9419 | 0%
2025-06-04 | 2025 | 6 | Jun | 4 | 3 | 1 | 28.67% | 7.9419 | 0%
2025-06-05 | 2025 | 6 | Jun | 5 | 4 | 1 | 28.67% | 7.9419 | 0%
2025-06-06 | 2025 | 6 | Jun | 6 | 5 | 1 | 28.67% | 7.9419 | 0%
2025-06-07 | 2025 | 6 | Jun | 7 | 6 | 0 | 28.67% | 7.9419 | 0%
2025-06-08 | 2025 | 6 | Jun | 8 | 7 | 0 | 28.67% | 7.9419 | 0%
2025-06-09 | 2025 | 6 | Jun | 9 | 1 | 1 | 28.67% | 7.9419 | 0%
2025-06-10 | 2025 | 6 | Jun | 10 | 2 | 1 | 28.67% | 7.9419 | 0%
2025-06-11 | 2025 | 6 | Jun | 11 | 3 | 1 | 28.67% | 7.9419 | 0%
2025-06-12 | 2025 | 6 | Jun | 12 | 4 | 1 | 28.67% | 7.9419 | 0%
2025-06-13 | 2025 | 6 | Jun | 13 | 5 | 1 | 28.67% | 7.9419 | 0%
2025-06-14 | 2025 | 6 | Jun | 14 | 6 | 0 | 28.67% | 7.9419 | 0%
2025-06-15 | 2025 | 6 | Jun | 15 | 7 | 0 | 28.67% | 7.9419 | 0%
2025-06-16 | 2025 | 6 | Jun | 16 | 1 | 1 | 28.67% | 7.9419 | 0%
2025-06-17 | 2025 | 6 | Jun | 17 | 2 | 1 | 28.67% | 7.9419 | 0%
2025-06-18 | 2025 | 6 | Jun | 18 | 3 | 1 | 28.67% | 7.9419 | 0%
2025-06-19 | 2025 | 6 | Jun | 19 | 4 | 1 | 28.67% | 7.9419 | 0%
2025-06-20 | 2025 | 6 | Jun | 20 | 5 | 1 | 28.67% | 7.9419 | 0%
2025-06-21 | 2025 | 6 | Jun | 21 | 6 | 0 | 28.67% | 7.9419 | 0%
2025-06-22 | 2025 | 6 | Jun | 22 | 7 | 0 | 28.67% | 7.9419 | 0%
2025-06-23 | 2025 | 6 | Jun | 23 | 1 | 1 | 28.67% | 7.9419 | 0%
2025-06-24 | 2025 | 6 | Jun | 24 | 2 | 1 | 28.67% | 7.9419 | 0%
2025-06-25 | 2025 | 6 | Jun | 25 | 3 | 1 | 28.67% | 7.9419 | 0%
2025-06-26 | 2025 | 6 | Jun | 26 | 4 | 1 | 28.67% | 7.9419 | 0%
2025-06-27 | 2025 | 6 | Jun | 27 | 5 | 1 | 28.67% | 7.9419 | 0%
2025-06-28 | 2025 | 6 | Jun | 28 | 6 | 0 | 28.67% | 7.9419 | 0%
2025-06-29 | 2025 | 6 | Jun | 29 | 7 | 0 | 28.67% | 7.9419 | 0%
2025-06-30 | 2025 | 6 | Jun | 30 | 1 | 1 | 28.67% | 7.9419 | 0%
2025-07-01 | 2025 | 7 | Jul | 1 | 2 | 1 | 24.73% | 8.3739 | 0%
2025-07-02 | 2025 | 7 | Jul | 2 | 3 | 1 | 24.73% | 8.3739 | 0%
2025-07-03 | 2025 | 7 | Jul | 3 | 4 | 1 | 24.73% | 8.3739 | 0%
2025-07-04 | 2025 | 7 | Jul | 4 | 5 | 1 | 24.73% | 8.3739 | 0%
2025-07-05 | 2025 | 7 | Jul | 5 | 6 | 0 | 24.73% | 8.3739 | 0%
2025-07-06 | 2025 | 7 | Jul | 6 | 7 | 0 | 24.73% | 8.3739 | 0%
2025-07-07 | 2025 | 7 | Jul | 7 | 1 | 1 | 24.73% | 8.3739 | 0%
2025-07-08 | 2025 | 7 | Jul | 8 | 2 | 1 | 24.73% | 8.3739 | 0%
2025-07-09 | 2025 | 7 | Jul | 9 | 3 | 1 | 24.73% | 8.3739 | 0%
2025-07-10 | 2025 | 7 | Jul | 10 | 4 | 1 | 24.73% | 8.3739 | 0%
2025-07-11 | 2025 | 7 | Jul | 11 | 5 | 1 | 24.73% | 8.3739 | 0%
2025-07-12 | 2025 | 7 | Jul | 12 | 6 | 0 | 24.73% | 8.3739 | 0%
2025-07-13 | 2025 | 7 | Jul | 13 | 7 | 0 | 24.73% | 8.3739 | 0%
2025-07-14 | 2025 | 7 | Jul | 14 | 1 | 1 | 24.73% | 8.3739 | 0%
2025-07-15 | 2025 | 7 | Jul | 15 | 2 | 1 | 24.73% | 8.3739 | 0%
2025-07-16 | 2025 | 7 | Jul | 16 | 3 | 1 | 24.73% | 8.3739 | 0%
2025-07-17 | 2025 | 7 | Jul | 17 | 4 | 1 | 24.73% | 8.3739 | 0%
2025-07-18 | 2025 | 7 | Jul | 18 | 5 | 1 | 24.73% | 8.3739 | 0%
2025-07-19 | 2025 | 7 | Jul | 19 | 6 | 0 | 24.73% | 8.3739 | 0%
2025-07-20 | 2025 | 7 | Jul | 20 | 7 | 0 | 24.73% | 8.3739 | 0%
2025-07-21 | 2025 | 7 | Jul | 21 | 1 | 1 | 24.73% | 8.3739 | 0%
2025-07-22 | 2025 | 7 | Jul | 22 | 2 | 1 | 24.73% | 8.3739 | 0%
2025-07-23 | 2025 | 7 | Jul | 23 | 3 | 1 | 24.73% | 8.3739 | 0%
2025-07-24 | 2025 | 7 | Jul | 24 | 4 | 1 | 24.73% | 8.3739 | 0%
2025-07-25 | 2025 | 7 | Jul | 25 | 5 | 1 | 24.73% | 8.3739 | 0%
2025-07-26 | 2025 | 7 | Jul | 26 | 6 | 0 | 24.73% | 8.3739 | 0%
2025-07-27 | 2025 | 7 | Jul | 27 | 7 | 0 | 24.73% | 8.3739 | 0%
2025-07-28 | 2025 | 7 | Jul | 28 | 1 | 1 | 24.73% | 8.3739 | 0%
2025-07-29 | 2025 | 7 | Jul | 29 | 2 | 1 | 24.73% | 8.3739 | 0%
2025-07-30 | 2025 | 7 | Jul | 30 | 3 | 1 | 24.73% | 8.3739 | 0%
2025-07-31 | 2025 | 7 | Jul | 31 | 4 | 1 | 24.73% | 8.3739 | 0%
2025-08-01 | 2025 | 8 | Aug | 1 | 5 | 1 | 23.55% | 7.9589 | 0%
2025-08-02 | 2025 | 8 | Aug | 2 | 6 | 0 | 23.55% | 7.9589 | 0%
2025-08-03 | 2025 | 8 | Aug | 3 | 7 | 0 | 23.55% | 7.9589 | 0%
2025-08-04 | 2025 | 8 | Aug | 4 | 1 | 1 | 23.55% | 7.9589 | 0%
2025-08-05 | 2025 | 8 | Aug | 5 | 2 | 1 | 23.55% | 7.9589 | 0%
2025-08-06 | 2025 | 8 | Aug | 6 | 3 | 1 | 23.55% | 7.9589 | 0%
2025-08-07 | 2025 | 8 | Aug | 7 | 4 | 1 | 23.55% | 7.9589 | 0%
2025-08-08 | 2025 | 8 | Aug | 8 | 5 | 1 | 23.55% | 7.9589 | 0%
2025-08-09 | 2025 | 8 | Aug | 9 | 6 | 0 | 23.55% | 7.9589 | 0%
2025-08-10 | 2025 | 8 | Aug | 10 | 7 | 0 | 23.55% | 7.9589 | 0%
2025-08-11 | 2025 | 8 | Aug | 11 | 1 | 1 | 23.55% | 7.9589 | 0%
2025-08-12 | 2025 | 8 | Aug | 12 | 2 | 1 | 23.55% | 7.9589 | 0%
2025-08-13 | 2025 | 8 | Aug | 13 | 3 | 1 | 23.55% | 7.9589 | 0%
2025-08-14 | 2025 | 8 | Aug | 14 | 4 | 1 | 23.55% | 7.9589 | 0%
2025-08-15 | 2025 | 8 | Aug | 15 | 5 | 1 | 23.55% | 7.9589 | 0%
2025-08-16 | 2025 | 8 | Aug | 16 | 6 | 0 | 23.55% | 7.9589 | 0%
2025-08-17 | 2025 | 8 | Aug | 17 | 7 | 0 | 23.55% | 7.9589 | 0%
2025-08-18 | 2025 | 8 | Aug | 18 | 1 | 1 | 23.55% | 7.9589 | 0%
2025-08-19 | 2025 | 8 | Aug | 19 | 2 | 1 | 23.55% | 7.9589 | 0%
2025-08-20 | 2025 | 8 | Aug | 20 | 3 | 1 | 23.55% | 7.9589 | 0%
2025-08-21 | 2025 | 8 | Aug | 21 | 4 | 1 | 23.55% | 7.9589 | 0%
2025-08-22 | 2025 | 8 | Aug | 22 | 5 | 1 | 23.55% | 7.9589 | 0%
2025-08-23 | 2025 | 8 | Aug | 23 | 6 | 0 | 23.55% | 7.9589 | 0%
2025-08-24 | 2025 | 8 | Aug | 24 | 7 | 0 | 23.55% | 7.9589 | 0%
2025-08-25 | 2025 | 8 | Aug | 25 | 1 | 1 | 23.55% | 7.9589 | 0%
2025-08-26 | 2025 | 8 | Aug | 26 | 2 | 1 | 23.55% | 7.9589 | 0%
2025-08-27 | 2025 | 8 | Aug | 27 | 3 | 1 | 23.55% | 7.9589 | 0%
2025-08-28 | 2025 | 8 | Aug | 28 | 4 | 1 | 23.55% | 7.9589 | 0%
2025-08-29 | 2025 | 8 | Aug | 29 | 5 | 1 | 23.55% | 7.9589 | 0%
2025-08-30 | 2025 | 8 | Aug | 30 | 6 | 0 | 23.55% | 7.9589 | 0%
2025-08-31 | 2025 | 8 | Aug | 31 | 7 | 0 | 23.55% | 7.9589 | 0%
2025-09-01 | 2025 | 9 | Sep | 1 | 1 | 1 | 20.67% | 6.8065 | 0%
2025-09-02 | 2025 | 9 | Sep | 2 | 2 | 1 | 20.67% | 6.8065 | 0%
2025-09-03 | 2025 | 9 | Sep | 3 | 3 | 1 | 20.67% | 6.8065 | 0%
2025-09-04 | 2025 | 9 | Sep | 4 | 4 | 1 | 20.67% | 6.8065 | 0%
2025-09-05 | 2025 | 9 | Sep | 5 | 5 | 1 | 20.67% | 6.8065 | 0%
2025-09-06 | 2025 | 9 | Sep | 6 | 6 | 0 | 20.67% | 6.8065 | 0%
2025-09-07 | 2025 | 9 | Sep | 7 | 7 | 0 | 20.67% | 6.8065 | 0%
2025-09-08 | 2025 | 9 | Sep | 8 | 1 | 1 | 20.67% | 6.8065 | 0%
2025-09-09 | 2025 | 9 | Sep | 9 | 2 | 1 | 20.67% | 6.8065 | 0%
2025-09-10 | 2025 | 9 | Sep | 10 | 3 | 1 | 20.67% | 6.8065 | 0%
2025-09-11 | 2025 | 9 | Sep | 11 | 4 | 1 | 20.67% | 6.8065 | 0%
2025-09-12 | 2025 | 9 | Sep | 12 | 5 | 1 | 20.67% | 6.8065 | 0%
2025-09-13 | 2025 | 9 | Sep | 13 | 6 | 0 | 20.67% | 6.8065 | 0%
2025-09-14 | 2025 | 9 | Sep | 14 | 7 | 0 | 20.67% | 6.8065 | 0%
2025-09-15 | 2025 | 9 | Sep | 15 | 1 | 1 | 20.67% | 6.8065 | 0%
2025-09-16 | 2025 | 9 | Sep | 16 | 2 | 1 | 20.67% | 6.8065 | 0%
2025-09-17 | 2025 | 9 | Sep | 17 | 3 | 1 | 20.67% | 6.8065 | 0%
2025-09-18 | 2025 | 9 | Sep | 18 | 4 | 1 | 20.67% | 6.8065 | 0%
2025-09-19 | 2025 | 9 | Sep | 19 | 5 | 1 | 20.67% | 6.8065 | 0%
2025-09-20 | 2025 | 9 | Sep | 20 | 6 | 0 | 20.67% | 6.8065 | 0%
2025-09-21 | 2025 | 9 | Sep | 21 | 7 | 0 | 20.67% | 6.8065 | 0%
2025-09-22 | 2025 | 9 | Sep | 22 | 1 | 1 | 20.67% | 6.8065 | 0%
2025-09-23 | 2025 | 9 | Sep | 23 | 2 | 1 | 20.67% | 6.8065 | 0%
2025-09-24 | 2025 | 9 | Sep | 24 | 3 | 1 | 20.67% | 6.8065 | 0%
2025-09-25 | 2025 | 9 | Sep | 25 | 4 | 1 | 20.67% | 6.8065 | 0%
2025-09-26 | 2025 | 9 | Sep | 26 | 5 | 1 | 20.67% | 6.8065 | 0%
2025-09-27 | 2025 | 9 | Sep | 27 | 6 | 0 | 20.67% | 6.8065 | 0%
2025-09-28 | 2025 | 9 | Sep | 28 | 7 | 0 | 20.67% | 6.8065 | 0%
2025-09-29 | 2025 | 9 | Sep | 29 | 1 | 1 | 20.67% | 6.8065 | 0%
2025-09-30 | 2025 | 9 | Sep | 30 | 2 | 1 | 20.67% | 6.8065 | 0%
2025-10-01 | 2025 | 10 | Oct | 1 | 3 | 1 | 23.23% | 6.8194 | 0%
2025-10-02 | 2025 | 10 | Oct | 2 | 4 | 1 | 23.23% | 6.8194 | 0%
2025-10-03 | 2025 | 10 | Oct | 3 | 5 | 1 | 23.23% | 6.8194 | 0%
2025-10-04 | 2025 | 10 | Oct | 4 | 6 | 0 | 23.23% | 6.8194 | 0%
2025-10-05 | 2025 | 10 | Oct | 5 | 7 | 0 | 23.23% | 6.8194 | 0%
2025-10-06 | 2025 | 10 | Oct | 6 | 1 | 1 | 23.23% | 6.8194 | 0%
2025-10-07 | 2025 | 10 | Oct | 7 | 2 | 1 | 23.23% | 6.8194 | 0%
2025-10-08 | 2025 | 10 | Oct | 8 | 3 | 1 | 23.23% | 6.8194 | 0%
2025-10-09 | 2025 | 10 | Oct | 9 | 4 | 1 | 23.23% | 6.8194 | 0%
2025-10-10 | 2025 | 10 | Oct | 10 | 5 | 1 | 23.23% | 6.8194 | 0%
2025-10-11 | 2025 | 10 | Oct | 11 | 6 | 0 | 23.23% | 6.8194 | 0%
2025-10-12 | 2025 | 10 | Oct | 12 | 7 | 0 | 23.23% | 6.8194 | 0%
2025-10-13 | 2025 | 10 | Oct | 13 | 1 | 1 | 23.23% | 6.8194 | 0%
2025-10-14 | 2025 | 10 | Oct | 14 | 2 | 1 | 23.23% | 6.8194 | 0%
2025-10-15 | 2025 | 10 | Oct | 15 | 3 | 1 | 23.23% | 6.8194 | 0%
2025-10-16 | 2025 | 10 | Oct | 16 | 4 | 1 | 23.23% | 6.8194 | 0%
2025-10-17 | 2025 | 10 | Oct | 17 | 5 | 1 | 23.23% | 6.8194 | 0%
2025-10-18 | 2025 | 10 | Oct | 18 | 6 | 0 | 23.23% | 6.8194 | 0%
2025-10-19 | 2025 | 10 | Oct | 19 | 7 | 0 | 23.23% | 6.8194 | 0%
2025-10-20 | 2025 | 10 | Oct | 20 | 1 | 1 | 23.23% | 6.8194 | 0%
2025-10-21 | 2025 | 10 | Oct | 21 | 2 | 1 | 23.23% | 6.8194 | 0%
2025-10-22 | 2025 | 10 | Oct | 22 | 3 | 1 | 23.23% | 6.8194 | 0%
2025-10-23 | 2025 | 10 | Oct | 23 | 4 | 1 | 23.23% | 6.8194 | 0%
2025-10-24 | 2025 | 10 | Oct | 24 | 5 | 1 | 23.23% | 6.8194 | 0%
2025-10-25 | 2025 | 10 | Oct | 25 | 6 | 0 | 23.23% | 6.8194 | 0%
2025-10-26 | 2025 | 10 | Oct | 26 | 7 | 0 | 23.23% | 6.8194 | 0%
2025-10-27 | 2025 | 10 | Oct | 27 | 1 | 1 | 23.23% | 6.8194 | 0%
2025-10-28 | 2025 | 10 | Oct | 28 | 2 | 1 | 23.23% | 6.8194 | 0%
2025-10-29 | 2025 | 10 | Oct | 29 | 3 | 1 | 23.23% | 6.8194 | 0%
2025-10-30 | 2025 | 10 | Oct | 30 | 4 | 1 | 23.23% | 6.8194 | 0%
2025-10-31 | 2025 | 10 | Oct | 31 | 5 | 1 | 23.23% | 6.8194 | 0%
2025-11-01 | 2025 | 11 | Nov | 1 | 6 | 0 | 23.33% | 6.4429 | 0%
2025-11-02 | 2025 | 11 | Nov | 2 | 7 | 0 | 23.33% | 6.4429 | 0%
2025-11-03 | 2025 | 11 | Nov | 3 | 1 | 1 | 23.33% | 6.4429 | 0%
2025-11-04 | 2025 | 11 | Nov | 4 | 2 | 1 | 23.33% | 6.4429 | 0%
2025-11-05 | 2025 | 11 | Nov | 5 | 3 | 1 | 23.33% | 6.4429 | 0%
2025-11-06 | 2025 | 11 | Nov | 6 | 4 | 1 | 23.33% | 6.4429 | 0%
2025-11-07 | 2025 | 11 | Nov | 7 | 5 | 1 | 23.33% | 6.4429 | 0%
2025-11-08 | 2025 | 11 | Nov | 8 | 6 | 0 | 23.33% | 6.4429 | 0%
2025-11-09 | 2025 | 11 | Nov | 9 | 7 | 0 | 23.33% | 6.4429 | 0%
2025-11-10 | 2025 | 11 | Nov | 10 | 1 | 1 | 23.33% | 6.4429 | 0%
2025-11-11 | 2025 | 11 | Nov | 11 | 2 | 1 | 23.33% | 6.4429 | 0%
2025-11-12 | 2025 | 11 | Nov | 12 | 3 | 1 | 23.33% | 6.4429 | 0%
2025-11-13 | 2025 | 11 | Nov | 13 | 4 | 1 | 23.33% | 6.4429 | 0%
2025-11-14 | 2025 | 11 | Nov | 14 | 5 | 1 | 23.33% | 6.4429 | 0%
2025-11-15 | 2025 | 11 | Nov | 15 | 6 | 0 | 23.33% | 6.4429 | 0%
2025-11-16 | 2025 | 11 | Nov | 16 | 7 | 0 | 23.33% | 6.4429 | 0%
2025-11-17 | 2025 | 11 | Nov | 17 | 1 | 1 | 23.33% | 6.4429 | 0%
2025-11-18 | 2025 | 11 | Nov | 18 | 2 | 1 | 23.33% | 6.4429 | 0%
2025-11-19 | 2025 | 11 | Nov | 19 | 3 | 1 | 23.33% | 6.4429 | 0%
2025-11-20 | 2025 | 11 | Nov | 20 | 4 | 1 | 23.33% | 6.4429 | 0%
2025-11-21 | 2025 | 11 | Nov | 21 | 5 | 1 | 23.33% | 6.4429 | 0%
2025-11-22 | 2025 | 11 | Nov | 22 | 6 | 0 | 23.33% | 6.4429 | 0%
2025-11-23 | 2025 | 11 | Nov | 23 | 7 | 0 | 23.33% | 6.4429 | 0%
2025-11-24 | 2025 | 11 | Nov | 24 | 1 | 1 | 23.33% | 6.4429 | 0%
2025-11-25 | 2025 | 11 | Nov | 25 | 2 | 1 | 23.33% | 6.4429 | 0%
2025-11-26 | 2025 | 11 | Nov | 26 | 3 | 1 | 23.33% | 6.4429 | 0%
2025-11-27 | 2025 | 11 | Nov | 27 | 4 | 1 | 23.33% | 6.4429 | 0%
2025-11-28 | 2025 | 11 | Nov | 28 | 5 | 1 | 23.33% | 6.4429 | 0%
2025-11-29 | 2025 | 11 | Nov | 29 | 6 | 0 | 23.33% | 6.4429 | 0%
2025-11-30 | 2025 | 11 | Nov | 30 | 7 | 0 | 23.33% | 6.4429 | 0%
2025-12-01 | 2025 | 12 | Dec | 1 | 1 | 1 | 22.69% | 6.7962 | 0%
2025-12-02 | 2025 | 12 | Dec | 2 | 2 | 1 | 22.69% | 6.7962 | 0%
2025-12-03 | 2025 | 12 | Dec | 3 | 3 | 1 | 22.69% | 6.7962 | 0%
2025-12-04 | 2025 | 12 | Dec | 4 | 4 | 1 | 22.69% | 6.7962 | 0%
2025-12-05 | 2025 | 12 | Dec | 5 | 5 | 1 | 22.69% | 6.7962 | 0%
2025-12-06 | 2025 | 12 | Dec | 6 | 6 | 0 | 22.69% | 6.7962 | 0%
2025-12-07 | 2025 | 12 | Dec | 7 | 7 | 0 | 22.69% | 6.7962 | 0%
2025-12-08 | 2025 | 12 | Dec | 8 | 1 | 1 | 22.69% | 6.7962 | 0%
2025-12-09 | 2025 | 12 | Dec | 9 | 2 | 1 | 22.69% | 6.7962 | 0%
2025-12-10 | 2025 | 12 | Dec | 10 | 3 | 1 | 22.69% | 6.7962 | 0%
2025-12-11 | 2025 | 12 | Dec | 11 | 4 | 1 | 22.69% | 6.7962 | 0%
2025-12-12 | 2025 | 12 | Dec | 12 | 5 | 1 | 22.69% | 6.7962 | 0%
2025-12-13 | 2025 | 12 | Dec | 13 | 6 | 0 | 22.69% | 6.7962 | 0%
2025-12-14 | 2025 | 12 | Dec | 14 | 7 | 0 | 22.69% | 6.7962 | 0%
2025-12-15 | 2025 | 12 | Dec | 15 | 1 | 1 | 22.69% | 6.7962 | 0%
2025-12-16 | 2025 | 12 | Dec | 16 | 2 | 1 | 22.69% | 6.7962 | 0%
2025-12-17 | 2025 | 12 | Dec | 17 | 3 | 1 | 22.69% | 6.7962 | 0%
2025-12-18 | 2025 | 12 | Dec | 18 | 4 | 1 | 22.69% | 6.7962 | 0%
2025-12-19 | 2025 | 12 | Dec | 19 | 5 | 1 | 22.69% | 6.7962 | 0%
2025-12-20 | 2025 | 12 | Dec | 20 | 6 | 0 | 22.69% | 6.7962 | 0%
2025-12-21 | 2025 | 12 | Dec | 21 | 7 | 0 | 22.69% | 6.7962 | 0%
2025-12-22 | 2025 | 12 | Dec | 22 | 1 | 1 | 22.69% | 6.7962 | 0%
2025-12-23 | 2025 | 12 | Dec | 23 | 2 | 1 | 22.69% | 6.7962 | 0%
2025-12-24 | 2025 | 12 | Dec | 24 | 3 | 1 | 22.69% | 6.7962 | 0%
2025-12-25 | 2025 | 12 | Dec | 25 | 4 | 1 | 22.69% | 6.7962 | 0%
2025-12-26 | 2025 | 12 | Dec | 26 | 5 | 1 | 22.69% | 6.7962 | 0%
2025-12-27 | 2025 | 12 | Dec | 27 | 6 | 0 | 22.69% | 6.7962 | 0%
2025-12-28 | 2025 | 12 | Dec | 28 | 7 | 0 | 22.69% | 6.7962 | 0%
2025-12-29 | 2025 | 12 | Dec | 29 | 1 | 1 | 22.69% | 6.7962 | 0%
2025-12-30 | 2025 | 12 | Dec | 30 | 2 | 1 | 22.69% | 6.7962 | 0%
2025-12-31 | 2025 | 12 | Dec | 31 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-01-01 | 2026 | 1 | Jan | 1 | 4 | 1 | 19.46% | 7.0276 | 0%
2026-01-02 | 2026 | 1 | Jan | 2 | 5 | 1 | 19.46% | 7.0276 | 0%
2026-01-03 | 2026 | 1 | Jan | 3 | 6 | 0 | 19.46% | 7.0276 | 0%
2026-01-04 | 2026 | 1 | Jan | 4 | 7 | 0 | 19.46% | 7.0276 | 0%
2026-01-05 | 2026 | 1 | Jan | 5 | 1 | 1 | 19.46% | 7.0276 | 0%
2026-01-06 | 2026 | 1 | Jan | 6 | 2 | 1 | 19.46% | 7.0276 | 0%
2026-01-07 | 2026 | 1 | Jan | 7 | 3 | 1 | 19.46% | 7.0276 | 0%
2026-01-08 | 2026 | 1 | Jan | 8 | 4 | 1 | 19.46% | 7.0276 | 0%
2026-01-09 | 2026 | 1 | Jan | 9 | 5 | 1 | 19.46% | 7.0276 | 0%
2026-01-10 | 2026 | 1 | Jan | 10 | 6 | 0 | 19.46% | 7.0276 | 0%
2026-01-11 | 2026 | 1 | Jan | 11 | 7 | 0 | 19.46% | 7.0276 | 0%
2026-01-12 | 2026 | 1 | Jan | 12 | 1 | 1 | 19.46% | 7.0276 | 0%
2026-01-13 | 2026 | 1 | Jan | 13 | 2 | 1 | 19.46% | 7.0276 | 0%
2026-01-14 | 2026 | 1 | Jan | 14 | 3 | 1 | 19.46% | 7.0276 | 0%
2026-01-15 | 2026 | 1 | Jan | 15 | 4 | 1 | 19.46% | 7.0276 | 0%
2026-01-16 | 2026 | 1 | Jan | 16 | 5 | 1 | 19.46% | 7.0276 | 0%
2026-01-17 | 2026 | 1 | Jan | 17 | 6 | 0 | 19.46% | 7.0276 | 0%
2026-01-18 | 2026 | 1 | Jan | 18 | 7 | 0 | 19.46% | 7.0276 | 0%
2026-01-19 | 2026 | 1 | Jan | 19 | 1 | 1 | 19.46% | 7.0276 | 0%
2026-01-20 | 2026 | 1 | Jan | 20 | 2 | 1 | 19.46% | 7.0276 | 0%
2026-01-21 | 2026 | 1 | Jan | 21 | 3 | 1 | 19.46% | 7.0276 | 0%
2026-01-22 | 2026 | 1 | Jan | 22 | 4 | 1 | 19.46% | 7.0276 | 0%
2026-01-23 | 2026 | 1 | Jan | 23 | 5 | 1 | 19.46% | 7.0276 | 0%
2026-01-24 | 2026 | 1 | Jan | 24 | 6 | 0 | 19.46% | 7.0276 | 0%
2026-01-25 | 2026 | 1 | Jan | 25 | 7 | 0 | 19.46% | 7.0276 | 0%
2026-01-26 | 2026 | 1 | Jan | 26 | 1 | 1 | 19.46% | 7.0276 | 0%
2026-01-27 | 2026 | 1 | Jan | 27 | 2 | 1 | 19.46% | 7.0276 | 0%
2026-01-28 | 2026 | 1 | Jan | 28 | 3 | 1 | 19.46% | 7.0276 | 0%
2026-01-29 | 2026 | 1 | Jan | 29 | 4 | 1 | 19.46% | 7.0276 | 0%
2026-01-30 | 2026 | 1 | Jan | 30 | 5 | 1 | 19.46% | 7.0276 | 0%
2026-01-31 | 2026 | 1 | Jan | 31 | 6 | 0 | 19.46% | 7.0276 | 0%
2026-02-01 | 2026 | 2 | Feb | 1 | 7 | 0 | 18.87% | 7.4625 | 0%
2026-02-02 | 2026 | 2 | Feb | 2 | 1 | 1 | 18.87% | 7.4625 | 0%
2026-02-03 | 2026 | 2 | Feb | 3 | 2 | 1 | 18.87% | 7.4625 | 0%
2026-02-04 | 2026 | 2 | Feb | 4 | 3 | 1 | 18.87% | 7.4625 | 0%
2026-02-05 | 2026 | 2 | Feb | 5 | 4 | 1 | 18.87% | 7.4625 | 0%
2026-02-06 | 2026 | 2 | Feb | 6 | 5 | 1 | 18.87% | 7.4625 | 0%
2026-02-07 | 2026 | 2 | Feb | 7 | 6 | 0 | 18.87% | 7.4625 | 0%
2026-02-08 | 2026 | 2 | Feb | 8 | 7 | 0 | 18.87% | 7.4625 | 0%
2026-02-09 | 2026 | 2 | Feb | 9 | 1 | 1 | 18.87% | 7.4625 | 0%
2026-02-10 | 2026 | 2 | Feb | 10 | 2 | 1 | 18.87% | 7.4625 | 0%
2026-02-11 | 2026 | 2 | Feb | 11 | 3 | 1 | 18.87% | 7.4625 | 0%
2026-02-12 | 2026 | 2 | Feb | 12 | 4 | 1 | 18.87% | 7.4625 | 0%
2026-02-13 | 2026 | 2 | Feb | 13 | 5 | 1 | 18.87% | 7.4625 | 0%
2026-02-14 | 2026 | 2 | Feb | 14 | 6 | 0 | 18.87% | 7.4625 | 0%
2026-02-15 | 2026 | 2 | Feb | 15 | 7 | 0 | 18.87% | 7.4625 | 0%
2026-02-16 | 2026 | 2 | Feb | 16 | 1 | 1 | 18.87% | 7.4625 | 0%
2026-02-17 | 2026 | 2 | Feb | 17 | 2 | 1 | 18.87% | 7.4625 | 0%
2026-02-18 | 2026 | 2 | Feb | 18 | 3 | 1 | 18.87% | 7.4625 | 0%
2026-02-19 | 2026 | 2 | Feb | 19 | 4 | 1 | 18.87% | 7.4625 | 0%
2026-02-20 | 2026 | 2 | Feb | 20 | 5 | 1 | 18.87% | 7.4625 | 0%
2026-02-21 | 2026 | 2 | Feb | 21 | 6 | 0 | 18.87% | 7.4625 | 0%
2026-02-22 | 2026 | 2 | Feb | 22 | 7 | 0 | 18.87% | 7.4625 | 0%
2026-02-23 | 2026 | 2 | Feb | 23 | 1 | 1 | 18.87% | 7.4625 | 0%
2026-02-24 | 2026 | 2 | Feb | 24 | 2 | 1 | 18.87% | 7.4625 | 0%
2026-02-25 | 2026 | 2 | Feb | 25 | 3 | 1 | 18.87% | 7.4625 | 0%
2026-02-26 | 2026 | 2 | Feb | 26 | 4 | 1 | 18.87% | 7.4625 | 0%
2026-02-27 | 2026 | 2 | Feb | 27 | 5 | 1 | 18.87% | 7.4625 | 0%
2026-02-28 | 2026 | 2 | Feb | 28 | 6 | 0 | 18.87% | 7.4625 | 0%
2026-03-01 | 2026 | 3 | Mar | 1 | 7 | 0 | 18.49% | 7.8663 | 0%
2026-03-02 | 2026 | 3 | Mar | 2 | 1 | 1 | 18.49% | 7.8663 | 0%
2026-03-03 | 2026 | 3 | Mar | 3 | 2 | 1 | 18.49% | 7.8663 | 0%
2026-03-04 | 2026 | 3 | Mar | 4 | 3 | 1 | 18.49% | 7.8663 | 0%
2026-03-05 | 2026 | 3 | Mar | 5 | 4 | 1 | 18.49% | 7.8663 | 0%
2026-03-06 | 2026 | 3 | Mar | 6 | 5 | 1 | 18.49% | 7.8663 | 0%
2026-03-07 | 2026 | 3 | Mar | 7 | 6 | 0 | 18.49% | 7.8663 | 0%
2026-03-08 | 2026 | 3 | Mar | 8 | 7 | 0 | 18.49% | 7.8663 | 0%
2026-03-09 | 2026 | 3 | Mar | 9 | 1 | 1 | 18.49% | 7.8663 | 0%
2026-03-10 | 2026 | 3 | Mar | 10 | 2 | 1 | 18.49% | 7.8663 | 0%
2026-03-11 | 2026 | 3 | Mar | 11 | 3 | 1 | 18.49% | 7.8663 | 0%
2026-03-12 | 2026 | 3 | Mar | 12 | 4 | 1 | 18.49% | 7.8663 | 0%
2026-03-13 | 2026 | 3 | Mar | 13 | 5 | 1 | 18.49% | 7.8663 | 0%
2026-03-14 | 2026 | 3 | Mar | 14 | 6 | 0 | 18.49% | 7.8663 | 0%
2026-03-15 | 2026 | 3 | Mar | 15 | 7 | 0 | 18.49% | 7.8663 | 0%
2026-03-16 | 2026 | 3 | Mar | 16 | 1 | 1 | 18.49% | 7.8663 | 0%
2026-03-17 | 2026 | 3 | Mar | 17 | 2 | 1 | 18.49% | 7.8663 | 0%
2026-03-18 | 2026 | 3 | Mar | 18 | 3 | 1 | 18.49% | 7.8663 | 0%
2026-03-19 | 2026 | 3 | Mar | 19 | 4 | 1 | 18.49% | 7.8663 | 0%
2026-03-20 | 2026 | 3 | Mar | 20 | 5 | 1 | 18.49% | 7.8663 | 0%
2026-03-21 | 2026 | 3 | Mar | 21 | 6 | 0 | 18.49% | 7.8663 | 0%
2026-03-22 | 2026 | 3 | Mar | 22 | 7 | 0 | 18.49% | 7.8663 | 0%
2026-03-23 | 2026 | 3 | Mar | 23 | 1 | 1 | 18.49% | 7.8663 | 0%
2026-03-24 | 2026 | 3 | Mar | 24 | 2 | 1 | 18.49% | 7.8663 | 0%
2026-03-25 | 2026 | 3 | Mar | 25 | 3 | 1 | 18.49% | 7.8663 | 0%
2026-03-26 | 2026 | 3 | Mar | 26 | 4 | 1 | 18.49% | 7.8663 | 0%
2026-03-27 | 2026 | 3 | Mar | 27 | 5 | 1 | 18.49% | 7.8663 | 0%
2026-03-28 | 2026 | 3 | Mar | 28 | 6 | 0 | 18.49% | 7.8663 | 0%
2026-03-29 | 2026 | 3 | Mar | 29 | 7 | 0 | 18.49% | 7.8663 | 0%
2026-03-30 | 2026 | 3 | Mar | 30 | 1 | 1 | 18.49% | 7.8663 | 0%
2026-03-31 | 2026 | 3 | Mar | 31 | 2 | 1 | 18.49% | 7.8663 | 0%
2026-04-01 | 2026 | 4 | Apr | 1 | 3 | 1 | 25.56% | 7.5 | 0%
2026-04-02 | 2026 | 4 | Apr | 2 | 4 | 1 | 25.56% | 7.5 | 0%
2026-04-03 | 2026 | 4 | Apr | 3 | 5 | 1 | 25.56% | 7.5 | 0%
2026-04-04 | 2026 | 4 | Apr | 4 | 6 | 0 | 25.56% | 7.5 | 0%
2026-04-05 | 2026 | 4 | Apr | 5 | 7 | 0 | 25.56% | 7.5 | 0%
2026-04-06 | 2026 | 4 | Apr | 6 | 1 | 1 | 25.56% | 7.5 | 0%
2026-04-07 | 2026 | 4 | Apr | 7 | 2 | 1 | 25.56% | 7.5 | 0%
2026-04-08 | 2026 | 4 | Apr | 8 | 3 | 1 | 25.56% | 7.5 | 0%
2026-04-09 | 2026 | 4 | Apr | 9 | 4 | 1 | 25.56% | 7.5 | 0%
2026-04-10 | 2026 | 4 | Apr | 10 | 5 | 1 | 25.56% | 7.5 | 0%
2026-04-11 | 2026 | 4 | Apr | 11 | 6 | 0 | 25.56% | 7.5 | 0%
2026-04-12 | 2026 | 4 | Apr | 12 | 7 | 0 | 25.56% | 7.5 | 0%
2026-04-13 | 2026 | 4 | Apr | 13 | 1 | 1 | 25.56% | 7.5 | 0%
2026-04-14 | 2026 | 4 | Apr | 14 | 2 | 1 | 25.56% | 7.5 | 0%
2026-04-15 | 2026 | 4 | Apr | 15 | 3 | 1 | 25.56% | 7.5 | 0%
2026-04-16 | 2026 | 4 | Apr | 16 | 4 | 1 | 25.56% | 7.5 | 0%
2026-04-17 | 2026 | 4 | Apr | 17 | 5 | 1 | 25.56% | 7.5 | 0%
2026-04-18 | 2026 | 4 | Apr | 18 | 6 | 0 | 25.56% | 7.5 | 0%
2026-04-19 | 2026 | 4 | Apr | 19 | 7 | 0 | 25.56% | 7.5 | 0%
2026-04-20 | 2026 | 4 | Apr | 20 | 1 | 1 | 25.56% | 7.5 | 0%
2026-04-21 | 2026 | 4 | Apr | 21 | 2 | 1 | 25.56% | 7.5 | 0%
2026-04-22 | 2026 | 4 | Apr | 22 | 3 | 1 | 25.56% | 7.5 | 0%
2026-04-23 | 2026 | 4 | Apr | 23 | 4 | 1 | 25.56% | 7.5 | 0%
2026-04-24 | 2026 | 4 | Apr | 24 | 5 | 1 | 25.56% | 7.5 | 0%
2026-04-25 | 2026 | 4 | Apr | 25 | 6 | 0 | 25.56% | 7.5 | 0%
2026-04-26 | 2026 | 4 | Apr | 26 | 7 | 0 | 25.56% | 7.5 | 0%
2026-04-27 | 2026 | 4 | Apr | 27 | 1 | 1 | 25.56% | 7.5 | 0%
2026-04-28 | 2026 | 4 | Apr | 28 | 2 | 1 | 25.56% | 7.5 | 0%
2026-04-29 | 2026 | 4 | Apr | 29 | 3 | 1 | 25.56% | 7.5 | 0%
2026-04-30 | 2026 | 4 | Apr | 30 | 4 | 1 | 25.56% | 7.5 | 0%
2026-05-01 | 2026 | 5 | May | 1 | 5 | 1 | 23.01% | 8.1449 | 0%
2026-05-02 | 2026 | 5 | May | 2 | 6 | 0 | 23.01% | 8.1449 | 0%
2026-05-03 | 2026 | 5 | May | 3 | 7 | 0 | 23.01% | 8.1449 | 0%
2026-05-04 | 2026 | 5 | May | 4 | 1 | 1 | 23.01% | 8.1449 | 0%
2026-05-05 | 2026 | 5 | May | 5 | 2 | 1 | 23.01% | 8.1449 | 0%
2026-05-06 | 2026 | 5 | May | 6 | 3 | 1 | 23.01% | 8.1449 | 0%
2026-05-07 | 2026 | 5 | May | 7 | 4 | 1 | 23.01% | 8.1449 | 0%
2026-05-08 | 2026 | 5 | May | 8 | 5 | 1 | 23.01% | 8.1449 | 0%
2026-05-09 | 2026 | 5 | May | 9 | 6 | 0 | 23.01% | 8.1449 | 0%
2026-05-10 | 2026 | 5 | May | 10 | 7 | 0 | 23.01% | 8.1449 | 0%
2026-05-11 | 2026 | 5 | May | 11 | 1 | 1 | 23.01% | 8.1449 | 0%
2026-05-12 | 2026 | 5 | May | 12 | 2 | 1 | 23.01% | 8.1449 | 0%
2026-05-13 | 2026 | 5 | May | 13 | 3 | 1 | 23.01% | 8.1449 | 0%
2026-05-14 | 2026 | 5 | May | 14 | 4 | 1 | 23.01% | 8.1449 | 0%
2026-05-15 | 2026 | 5 | May | 15 | 5 | 1 | 23.01% | 8.1449 | 0%
2026-05-16 | 2026 | 5 | May | 16 | 6 | 0 | 23.01% | 8.1449 | 0%
2026-05-17 | 2026 | 5 | May | 17 | 7 | 0 | 23.01% | 8.1449 | 0%
2026-05-18 | 2026 | 5 | May | 18 | 1 | 1 | 23.01% | 8.1449 | 0%
2026-05-19 | 2026 | 5 | May | 19 | 2 | 1 | 23.01% | 8.1449 | 0%
2026-05-20 | 2026 | 5 | May | 20 | 3 | 1 | 23.01% | 8.1449 | 0%
2026-05-21 | 2026 | 5 | May | 21 | 4 | 1 | 23.01% | 8.1449 | 0%
2026-05-22 | 2026 | 5 | May | 22 | 5 | 1 | 23.01% | 8.1449 | 0%
2026-05-23 | 2026 | 5 | May | 23 | 6 | 0 | 23.01% | 8.1449 | 0%
2026-05-24 | 2026 | 5 | May | 24 | 7 | 0 | 23.01% | 8.1449 | 0%
2026-05-25 | 2026 | 5 | May | 25 | 1 | 1 | 23.01% | 8.1449 | 0%
2026-05-26 | 2026 | 5 | May | 26 | 2 | 1 | 23.01% | 8.1449 | 0%
2026-05-27 | 2026 | 5 | May | 27 | 3 | 1 | 23.01% | 8.1449 | 0%
2026-05-28 | 2026 | 5 | May | 28 | 4 | 1 | 23.01% | 8.1449 | 0%
2026-05-29 | 2026 | 5 | May | 29 | 5 | 1 | 23.01% | 8.1449 | 0%
2026-05-30 | 2026 | 5 | May | 30 | 6 | 0 | 23.01% | 8.1449 | 0%
2026-05-31 | 2026 | 5 | May | 31 | 7 | 0 | 23.01% | 8.1449 | 0%
2026-06-01 | 2026 | 6 | Jun | 1 | 1 | 1 | 28.67% | 7.9419 | 0%
2026-06-02 | 2026 | 6 | Jun | 2 | 2 | 1 | 28.67% | 7.9419 | 0%
2026-06-03 | 2026 | 6 | Jun | 3 | 3 | 1 | 28.67% | 7.9419 | 0%
2026-06-04 | 2026 | 6 | Jun | 4 | 4 | 1 | 28.67% | 7.9419 | 0%
2026-06-05 | 2026 | 6 | Jun | 5 | 5 | 1 | 28.67% | 7.9419 | 0%
2026-06-06 | 2026 | 6 | Jun | 6 | 6 | 0 | 28.67% | 7.9419 | 0%
2026-06-07 | 2026 | 6 | Jun | 7 | 7 | 0 | 28.67% | 7.9419 | 0%
2026-06-08 | 2026 | 6 | Jun | 8 | 1 | 1 | 28.67% | 7.9419 | 0%
2026-06-09 | 2026 | 6 | Jun | 9 | 2 | 1 | 28.67% | 7.9419 | 0%
2026-06-10 | 2026 | 6 | Jun | 10 | 3 | 1 | 28.67% | 7.9419 | 0%
2026-06-11 | 2026 | 6 | Jun | 11 | 4 | 1 | 28.67% | 7.9419 | 0%
2026-06-12 | 2026 | 6 | Jun | 12 | 5 | 1 | 28.67% | 7.9419 | 0%
2026-06-13 | 2026 | 6 | Jun | 13 | 6 | 0 | 28.67% | 7.9419 | 0%
2026-06-14 | 2026 | 6 | Jun | 14 | 7 | 0 | 28.67% | 7.9419 | 0%
2026-06-15 | 2026 | 6 | Jun | 15 | 1 | 1 | 28.67% | 7.9419 | 0%
2026-06-16 | 2026 | 6 | Jun | 16 | 2 | 1 | 28.67% | 7.9419 | 0%
2026-06-17 | 2026 | 6 | Jun | 17 | 3 | 1 | 28.67% | 7.9419 | 0%
2026-06-18 | 2026 | 6 | Jun | 18 | 4 | 1 | 28.67% | 7.9419 | 0%
2026-06-19 | 2026 | 6 | Jun | 19 | 5 | 1 | 28.67% | 7.9419 | 0%
2026-06-20 | 2026 | 6 | Jun | 20 | 6 | 0 | 28.67% | 7.9419 | 0%
2026-06-21 | 2026 | 6 | Jun | 21 | 7 | 0 | 28.67% | 7.9419 | 0%
2026-06-22 | 2026 | 6 | Jun | 22 | 1 | 1 | 28.67% | 7.9419 | 0%
2026-06-23 | 2026 | 6 | Jun | 23 | 2 | 1 | 28.67% | 7.9419 | 0%
2026-06-24 | 2026 | 6 | Jun | 24 | 3 | 1 | 28.67% | 7.9419 | 0%
2026-06-25 | 2026 | 6 | Jun | 25 | 4 | 1 | 28.67% | 7.9419 | 0%
2026-06-26 | 2026 | 6 | Jun | 26 | 5 | 1 | 28.67% | 7.9419 | 0%
2026-06-27 | 2026 | 6 | Jun | 27 | 6 | 0 | 28.67% | 7.9419 | 0%
2026-06-28 | 2026 | 6 | Jun | 28 | 7 | 0 | 28.67% | 7.9419 | 0%
2026-06-29 | 2026 | 6 | Jun | 29 | 1 | 1 | 28.67% | 7.9419 | 0%
2026-06-30 | 2026 | 6 | Jun | 30 | 2 | 1 | 28.67% | 7.9419 | 0%
2026-07-01 | 2026 | 7 | Jul | 1 | 3 | 1 | 24.73% | 8.3739 | 0%
2026-07-02 | 2026 | 7 | Jul | 2 | 4 | 1 | 24.73% | 8.3739 | 0%
2026-07-03 | 2026 | 7 | Jul | 3 | 5 | 1 | 24.73% | 8.3739 | 0%
2026-07-04 | 2026 | 7 | Jul | 4 | 6 | 0 | 24.73% | 8.3739 | 0%
2026-07-05 | 2026 | 7 | Jul | 5 | 7 | 0 | 24.73% | 8.3739 | 0%
2026-07-06 | 2026 | 7 | Jul | 6 | 1 | 1 | 24.73% | 8.3739 | 0%
2026-07-07 | 2026 | 7 | Jul | 7 | 2 | 1 | 24.73% | 8.3739 | 0%
2026-07-08 | 2026 | 7 | Jul | 8 | 3 | 1 | 24.73% | 8.3739 | 0%
2026-07-09 | 2026 | 7 | Jul | 9 | 4 | 1 | 24.73% | 8.3739 | 0%
2026-07-10 | 2026 | 7 | Jul | 10 | 5 | 1 | 24.73% | 8.3739 | 0%
2026-07-11 | 2026 | 7 | Jul | 11 | 6 | 0 | 24.73% | 8.3739 | 0%
2026-07-12 | 2026 | 7 | Jul | 12 | 7 | 0 | 24.73% | 8.3739 | 0%
2026-07-13 | 2026 | 7 | Jul | 13 | 1 | 1 | 24.73% | 8.3739 | 0%
2026-07-14 | 2026 | 7 | Jul | 14 | 2 | 1 | 24.73% | 8.3739 | 0%
2026-07-15 | 2026 | 7 | Jul | 15 | 3 | 1 | 24.73% | 8.3739 | 0%
2026-07-16 | 2026 | 7 | Jul | 16 | 4 | 1 | 24.73% | 8.3739 | 0%
2026-07-17 | 2026 | 7 | Jul | 17 | 5 | 1 | 24.73% | 8.3739 | 0%
2026-07-18 | 2026 | 7 | Jul | 18 | 6 | 0 | 24.73% | 8.3739 | 0%
2026-07-19 | 2026 | 7 | Jul | 19 | 7 | 0 | 24.73% | 8.3739 | 0%
2026-07-20 | 2026 | 7 | Jul | 20 | 1 | 1 | 24.73% | 8.3739 | 0%
2026-07-21 | 2026 | 7 | Jul | 21 | 2 | 1 | 24.73% | 8.3739 | 0%
2026-07-22 | 2026 | 7 | Jul | 22 | 3 | 1 | 24.73% | 8.3739 | 0%
2026-07-23 | 2026 | 7 | Jul | 23 | 4 | 1 | 24.73% | 8.3739 | 0%
2026-07-24 | 2026 | 7 | Jul | 24 | 5 | 1 | 24.73% | 8.3739 | 0%
2026-07-25 | 2026 | 7 | Jul | 25 | 6 | 0 | 24.73% | 8.3739 | 0%
2026-07-26 | 2026 | 7 | Jul | 26 | 7 | 0 | 24.73% | 8.3739 | 0%
2026-07-27 | 2026 | 7 | Jul | 27 | 1 | 1 | 24.73% | 8.3739 | 0%
2026-07-28 | 2026 | 7 | Jul | 28 | 2 | 1 | 24.73% | 8.3739 | 0%
2026-07-29 | 2026 | 7 | Jul | 29 | 3 | 1 | 24.73% | 8.3739 | 0%
2026-07-30 | 2026 | 7 | Jul | 30 | 4 | 1 | 24.73% | 8.3739 | 0%
2026-07-31 | 2026 | 7 | Jul | 31 | 5 | 1 | 24.73% | 8.3739 | 0%
2026-08-01 | 2026 | 8 | Aug | 1 | 6 | 0 | 23.55% | 7.9589 | 0%
2026-08-02 | 2026 | 8 | Aug | 2 | 7 | 0 | 23.55% | 7.9589 | 0%
2026-08-03 | 2026 | 8 | Aug | 3 | 1 | 1 | 23.55% | 7.9589 | 0%
2026-08-04 | 2026 | 8 | Aug | 4 | 2 | 1 | 23.55% | 7.9589 | 0%
2026-08-05 | 2026 | 8 | Aug | 5 | 3 | 1 | 23.55% | 7.9589 | 0%
2026-08-06 | 2026 | 8 | Aug | 6 | 4 | 1 | 23.55% | 7.9589 | 0%
2026-08-07 | 2026 | 8 | Aug | 7 | 5 | 1 | 23.55% | 7.9589 | 0%
2026-08-08 | 2026 | 8 | Aug | 8 | 6 | 0 | 23.55% | 7.9589 | 0%
2026-08-09 | 2026 | 8 | Aug | 9 | 7 | 0 | 23.55% | 7.9589 | 0%
2026-08-10 | 2026 | 8 | Aug | 10 | 1 | 1 | 23.55% | 7.9589 | 0%
2026-08-11 | 2026 | 8 | Aug | 11 | 2 | 1 | 23.55% | 7.9589 | 0%
2026-08-12 | 2026 | 8 | Aug | 12 | 3 | 1 | 23.55% | 7.9589 | 0%
2026-08-13 | 2026 | 8 | Aug | 13 | 4 | 1 | 23.55% | 7.9589 | 0%
2026-08-14 | 2026 | 8 | Aug | 14 | 5 | 1 | 23.55% | 7.9589 | 0%
2026-08-15 | 2026 | 8 | Aug | 15 | 6 | 0 | 23.55% | 7.9589 | 0%
2026-08-16 | 2026 | 8 | Aug | 16 | 7 | 0 | 23.55% | 7.9589 | 0%
2026-08-17 | 2026 | 8 | Aug | 17 | 1 | 1 | 23.55% | 7.9589 | 0%
2026-08-18 | 2026 | 8 | Aug | 18 | 2 | 1 | 23.55% | 7.9589 | 0%
2026-08-19 | 2026 | 8 | Aug | 19 | 3 | 1 | 23.55% | 7.9589 | 0%
2026-08-20 | 2026 | 8 | Aug | 20 | 4 | 1 | 23.55% | 7.9589 | 0%
2026-08-21 | 2026 | 8 | Aug | 21 | 5 | 1 | 23.55% | 7.9589 | 0%
2026-08-22 | 2026 | 8 | Aug | 22 | 6 | 0 | 23.55% | 7.9589 | 0%
2026-08-23 | 2026 | 8 | Aug | 23 | 7 | 0 | 23.55% | 7.9589 | 0%
2026-08-24 | 2026 | 8 | Aug | 24 | 1 | 1 | 23.55% | 7.9589 | 0%
2026-08-25 | 2026 | 8 | Aug | 25 | 2 | 1 | 23.55% | 7.9589 | 0%
2026-08-26 | 2026 | 8 | Aug | 26 | 3 | 1 | 23.55% | 7.9589 | 0%
2026-08-27 | 2026 | 8 | Aug | 27 | 4 | 1 | 23.55% | 7.9589 | 0%
2026-08-28 | 2026 | 8 | Aug | 28 | 5 | 1 | 23.55% | 7.9589 | 0%
2026-08-29 | 2026 | 8 | Aug | 29 | 6 | 0 | 23.55% | 7.9589 | 0%
2026-08-30 | 2026 | 8 | Aug | 30 | 7 | 0 | 23.55% | 7.9589 | 0%
2026-08-31 | 2026 | 8 | Aug | 31 | 1 | 1 | 23.55% | 7.9589 | 0%
2026-09-01 | 2026 | 9 | Sep | 1 | 2 | 1 | 20.67% | 6.8065 | 0%
2026-09-02 | 2026 | 9 | Sep | 2 | 3 | 1 | 20.67% | 6.8065 | 0%
2026-09-03 | 2026 | 9 | Sep | 3 | 4 | 1 | 20.67% | 6.8065 | 0%
2026-09-04 | 2026 | 9 | Sep | 4 | 5 | 1 | 20.67% | 6.8065 | 0%
2026-09-05 | 2026 | 9 | Sep | 5 | 6 | 0 | 20.67% | 6.8065 | 0%
2026-09-06 | 2026 | 9 | Sep | 6 | 7 | 0 | 20.67% | 6.8065 | 0%
2026-09-07 | 2026 | 9 | Sep | 7 | 1 | 1 | 20.67% | 6.8065 | 0%
2026-09-08 | 2026 | 9 | Sep | 8 | 2 | 1 | 20.67% | 6.8065 | 0%
2026-09-09 | 2026 | 9 | Sep | 9 | 3 | 1 | 20.67% | 6.8065 | 0%
2026-09-10 | 2026 | 9 | Sep | 10 | 4 | 1 | 20.67% | 6.8065 | 0%
2026-09-11 | 2026 | 9 | Sep | 11 | 5 | 1 | 20.67% | 6.8065 | 0%
2026-09-12 | 2026 | 9 | Sep | 12 | 6 | 0 | 20.67% | 6.8065 | 0%
2026-09-13 | 2026 | 9 | Sep | 13 | 7 | 0 | 20.67% | 6.8065 | 0%
2026-09-14 | 2026 | 9 | Sep | 14 | 1 | 1 | 20.67% | 6.8065 | 0%
2026-09-15 | 2026 | 9 | Sep | 15 | 2 | 1 | 20.67% | 6.8065 | 0%
2026-09-16 | 2026 | 9 | Sep | 16 | 3 | 1 | 20.67% | 6.8065 | 0%
2026-09-17 | 2026 | 9 | Sep | 17 | 4 | 1 | 20.67% | 6.8065 | 0%
2026-09-18 | 2026 | 9 | Sep | 18 | 5 | 1 | 20.67% | 6.8065 | 0%
2026-09-19 | 2026 | 9 | Sep | 19 | 6 | 0 | 20.67% | 6.8065 | 0%
2026-09-20 | 2026 | 9 | Sep | 20 | 7 | 0 | 20.67% | 6.8065 | 0%
2026-09-21 | 2026 | 9 | Sep | 21 | 1 | 1 | 20.67% | 6.8065 | 0%
2026-09-22 | 2026 | 9 | Sep | 22 | 2 | 1 | 20.67% | 6.8065 | 0%
2026-09-23 | 2026 | 9 | Sep | 23 | 3 | 1 | 20.67% | 6.8065 | 0%
2026-09-24 | 2026 | 9 | Sep | 24 | 4 | 1 | 20.67% | 6.8065 | 0%
2026-09-25 | 2026 | 9 | Sep | 25 | 5 | 1 | 20.67% | 6.8065 | 0%
2026-09-26 | 2026 | 9 | Sep | 26 | 6 | 0 | 20.67% | 6.8065 | 0%
2026-09-27 | 2026 | 9 | Sep | 27 | 7 | 0 | 20.67% | 6.8065 | 0%
2026-09-28 | 2026 | 9 | Sep | 28 | 1 | 1 | 20.67% | 6.8065 | 0%
2026-09-29 | 2026 | 9 | Sep | 29 | 2 | 1 | 20.67% | 6.8065 | 0%
2026-09-30 | 2026 | 9 | Sep | 30 | 3 | 1 | 20.67% | 6.8065 | 0%
2026-10-01 | 2026 | 10 | Oct | 1 | 4 | 1 | 23.23% | 6.8194 | 0%
2026-10-02 | 2026 | 10 | Oct | 2 | 5 | 1 | 23.23% | 6.8194 | 0%
2026-10-03 | 2026 | 10 | Oct | 3 | 6 | 0 | 23.23% | 6.8194 | 0%
2026-10-04 | 2026 | 10 | Oct | 4 | 7 | 0 | 23.23% | 6.8194 | 0%
2026-10-05 | 2026 | 10 | Oct | 5 | 1 | 1 | 23.23% | 6.8194 | 0%
2026-10-06 | 2026 | 10 | Oct | 6 | 2 | 1 | 23.23% | 6.8194 | 0%
2026-10-07 | 2026 | 10 | Oct | 7 | 3 | 1 | 23.23% | 6.8194 | 0%
2026-10-08 | 2026 | 10 | Oct | 8 | 4 | 1 | 23.23% | 6.8194 | 0%
2026-10-09 | 2026 | 10 | Oct | 9 | 5 | 1 | 23.23% | 6.8194 | 0%
2026-10-10 | 2026 | 10 | Oct | 10 | 6 | 0 | 23.23% | 6.8194 | 0%
2026-10-11 | 2026 | 10 | Oct | 11 | 7 | 0 | 23.23% | 6.8194 | 0%
2026-10-12 | 2026 | 10 | Oct | 12 | 1 | 1 | 23.23% | 6.8194 | 0%
2026-10-13 | 2026 | 10 | Oct | 13 | 2 | 1 | 23.23% | 6.8194 | 0%
2026-10-14 | 2026 | 10 | Oct | 14 | 3 | 1 | 23.23% | 6.8194 | 0%
2026-10-15 | 2026 | 10 | Oct | 15 | 4 | 1 | 23.23% | 6.8194 | 0%
2026-10-16 | 2026 | 10 | Oct | 16 | 5 | 1 | 23.23% | 6.8194 | 0%
2026-10-17 | 2026 | 10 | Oct | 17 | 6 | 0 | 23.23% | 6.8194 | 0%
2026-10-18 | 2026 | 10 | Oct | 18 | 7 | 0 | 23.23% | 6.8194 | 0%
2026-10-19 | 2026 | 10 | Oct | 19 | 1 | 1 | 23.23% | 6.8194 | 0%
2026-10-20 | 2026 | 10 | Oct | 20 | 2 | 1 | 23.23% | 6.8194 | 0%
2026-10-21 | 2026 | 10 | Oct | 21 | 3 | 1 | 23.23% | 6.8194 | 0%
2026-10-22 | 2026 | 10 | Oct | 22 | 4 | 1 | 23.23% | 6.8194 | 0%
2026-10-23 | 2026 | 10 | Oct | 23 | 5 | 1 | 23.23% | 6.8194 | 0%
2026-10-24 | 2026 | 10 | Oct | 24 | 6 | 0 | 23.23% | 6.8194 | 0%
2026-10-25 | 2026 | 10 | Oct | 25 | 7 | 0 | 23.23% | 6.8194 | 0%
2026-10-26 | 2026 | 10 | Oct | 26 | 1 | 1 | 23.23% | 6.8194 | 0%
2026-10-27 | 2026 | 10 | Oct | 27 | 2 | 1 | 23.23% | 6.8194 | 0%
2026-10-28 | 2026 | 10 | Oct | 28 | 3 | 1 | 23.23% | 6.8194 | 0%
2026-10-29 | 2026 | 10 | Oct | 29 | 4 | 1 | 23.23% | 6.8194 | 0%
2026-10-30 | 2026 | 10 | Oct | 30 | 5 | 1 | 23.23% | 6.8194 | 0%
2026-10-31 | 2026 | 10 | Oct | 31 | 6 | 0 | 23.23% | 6.8194 | 0%
2026-11-01 | 2026 | 11 | Nov | 1 | 7 | 0 | 23.33% | 6.4429 | 0%
2026-11-02 | 2026 | 11 | Nov | 2 | 1 | 1 | 23.33% | 6.4429 | 0%
2026-11-03 | 2026 | 11 | Nov | 3 | 2 | 1 | 23.33% | 6.4429 | 0%
2026-11-04 | 2026 | 11 | Nov | 4 | 3 | 1 | 23.33% | 6.4429 | 0%
2026-11-05 | 2026 | 11 | Nov | 5 | 4 | 1 | 23.33% | 6.4429 | 0%
2026-11-06 | 2026 | 11 | Nov | 6 | 5 | 1 | 23.33% | 6.4429 | 0%
2026-11-07 | 2026 | 11 | Nov | 7 | 6 | 0 | 23.33% | 6.4429 | 0%
2026-11-08 | 2026 | 11 | Nov | 8 | 7 | 0 | 23.33% | 6.4429 | 0%
2026-11-09 | 2026 | 11 | Nov | 9 | 1 | 1 | 23.33% | 6.4429 | 0%
2026-11-10 | 2026 | 11 | Nov | 10 | 2 | 1 | 23.33% | 6.4429 | 0%
2026-11-11 | 2026 | 11 | Nov | 11 | 3 | 1 | 23.33% | 6.4429 | 0%
2026-11-12 | 2026 | 11 | Nov | 12 | 4 | 1 | 23.33% | 6.4429 | 0%
2026-11-13 | 2026 | 11 | Nov | 13 | 5 | 1 | 23.33% | 6.4429 | 0%
2026-11-14 | 2026 | 11 | Nov | 14 | 6 | 0 | 23.33% | 6.4429 | 0%
2026-11-15 | 2026 | 11 | Nov | 15 | 7 | 0 | 23.33% | 6.4429 | 0%
2026-11-16 | 2026 | 11 | Nov | 16 | 1 | 1 | 23.33% | 6.4429 | 0%
2026-11-17 | 2026 | 11 | Nov | 17 | 2 | 1 | 23.33% | 6.4429 | 0%
2026-11-18 | 2026 | 11 | Nov | 18 | 3 | 1 | 23.33% | 6.4429 | 0%
2026-11-19 | 2026 | 11 | Nov | 19 | 4 | 1 | 23.33% | 6.4429 | 0%
2026-11-20 | 2026 | 11 | Nov | 20 | 5 | 1 | 23.33% | 6.4429 | 0%
2026-11-21 | 2026 | 11 | Nov | 21 | 6 | 0 | 23.33% | 6.4429 | 0%
2026-11-22 | 2026 | 11 | Nov | 22 | 7 | 0 | 23.33% | 6.4429 | 0%
2026-11-23 | 2026 | 11 | Nov | 23 | 1 | 1 | 23.33% | 6.4429 | 0%
2026-11-24 | 2026 | 11 | Nov | 24 | 2 | 1 | 23.33% | 6.4429 | 0%
2026-11-25 | 2026 | 11 | Nov | 25 | 3 | 1 | 23.33% | 6.4429 | 0%
2026-11-26 | 2026 | 11 | Nov | 26 | 4 | 1 | 23.33% | 6.4429 | 0%
2026-11-27 | 2026 | 11 | Nov | 27 | 5 | 1 | 23.33% | 6.4429 | 0%
2026-11-28 | 2026 | 11 | Nov | 28 | 6 | 0 | 23.33% | 6.4429 | 0%
2026-11-29 | 2026 | 11 | Nov | 29 | 7 | 0 | 23.33% | 6.4429 | 0%
2026-11-30 | 2026 | 11 | Nov | 30 | 1 | 1 | 23.33% | 6.4429 | 0%
2026-12-01 | 2026 | 12 | Dec | 1 | 2 | 1 | 22.69% | 6.7962 | 0%
2026-12-02 | 2026 | 12 | Dec | 2 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-12-03 | 2026 | 12 | Dec | 3 | 4 | 1 | 22.69% | 6.7962 | 0%
2026-12-04 | 2026 | 12 | Dec | 4 | 5 | 1 | 22.69% | 6.7962 | 0%
2026-12-05 | 2026 | 12 | Dec | 5 | 6 | 0 | 22.69% | 6.7962 | 0%
2026-12-06 | 2026 | 12 | Dec | 6 | 7 | 0 | 22.69% | 6.7962 | 0%
2026-12-07 | 2026 | 12 | Dec | 7 | 1 | 1 | 22.69% | 6.7962 | 0%
2026-12-08 | 2026 | 12 | Dec | 8 | 2 | 1 | 22.69% | 6.7962 | 0%
2026-12-09 | 2026 | 12 | Dec | 9 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-12-10 | 2026 | 12 | Dec | 10 | 4 | 1 | 22.69% | 6.7962 | 0%
2026-12-11 | 2026 | 12 | Dec | 11 | 5 | 1 | 22.69% | 6.7962 | 0%
2026-12-12 | 2026 | 12 | Dec | 12 | 6 | 0 | 22.69% | 6.7962 | 0%
2026-12-13 | 2026 | 12 | Dec | 13 | 7 | 0 | 22.69% | 6.7962 | 0%
2026-12-14 | 2026 | 12 | Dec | 14 | 1 | 1 | 22.69% | 6.7962 | 0%
2026-12-15 | 2026 | 12 | Dec | 15 | 2 | 1 | 22.69% | 6.7962 | 0%
2026-12-16 | 2026 | 12 | Dec | 16 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-12-17 | 2026 | 12 | Dec | 17 | 4 | 1 | 22.69% | 6.7962 | 0%
2026-12-18 | 2026 | 12 | Dec | 18 | 5 | 1 | 22.69% | 6.7962 | 0%
2026-12-19 | 2026 | 12 | Dec | 19 | 6 | 0 | 22.69% | 6.7962 | 0%
2026-12-20 | 2026 | 12 | Dec | 20 | 7 | 0 | 22.69% | 6.7962 | 0%
2026-12-21 | 2026 | 12 | Dec | 21 | 1 | 1 | 22.69% | 6.7962 | 0%
2026-12-22 | 2026 | 12 | Dec | 22 | 2 | 1 | 22.69% | 6.7962 | 0%
2026-12-23 | 2026 | 12 | Dec | 23 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-12-24 | 2026 | 12 | Dec | 24 | 4 | 1 | 22.69% | 6.7962 | 0%
2026-12-25 | 2026 | 12 | Dec | 25 | 5 | 1 | 22.69% | 6.7962 | 0%
2026-12-26 | 2026 | 12 | Dec | 26 | 6 | 0 | 22.69% | 6.7962 | 0%
2026-12-27 | 2026 | 12 | Dec | 27 | 7 | 0 | 22.69% | 6.7962 | 0%
2026-12-28 | 2026 | 12 | Dec | 28 | 1 | 1 | 22.69% | 6.7962 | 0%
2026-12-29 | 2026 | 12 | Dec | 29 | 2 | 1 | 22.69% | 6.7962 | 0%
2026-12-30 | 2026 | 12 | Dec | 30 | 3 | 1 | 22.69% | 6.7962 | 0%
2026-12-31 | 2026 | 12 | Dec | 31 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-01-01 | 2027 | 1 | Jan | 1 | 5 | 1 | 19.46% | 7.0276 | 0%
2027-01-02 | 2027 | 1 | Jan | 2 | 6 | 0 | 19.46% | 7.0276 | 0%
2027-01-03 | 2027 | 1 | Jan | 3 | 7 | 0 | 19.46% | 7.0276 | 0%
2027-01-04 | 2027 | 1 | Jan | 4 | 1 | 1 | 19.46% | 7.0276 | 0%
2027-01-05 | 2027 | 1 | Jan | 5 | 2 | 1 | 19.46% | 7.0276 | 0%
2027-01-06 | 2027 | 1 | Jan | 6 | 3 | 1 | 19.46% | 7.0276 | 0%
2027-01-07 | 2027 | 1 | Jan | 7 | 4 | 1 | 19.46% | 7.0276 | 0%
2027-01-08 | 2027 | 1 | Jan | 8 | 5 | 1 | 19.46% | 7.0276 | 0%
2027-01-09 | 2027 | 1 | Jan | 9 | 6 | 0 | 19.46% | 7.0276 | 0%
2027-01-10 | 2027 | 1 | Jan | 10 | 7 | 0 | 19.46% | 7.0276 | 0%
2027-01-11 | 2027 | 1 | Jan | 11 | 1 | 1 | 19.46% | 7.0276 | 0%
2027-01-12 | 2027 | 1 | Jan | 12 | 2 | 1 | 19.46% | 7.0276 | 0%
2027-01-13 | 2027 | 1 | Jan | 13 | 3 | 1 | 19.46% | 7.0276 | 0%
2027-01-14 | 2027 | 1 | Jan | 14 | 4 | 1 | 19.46% | 7.0276 | 0%
2027-01-15 | 2027 | 1 | Jan | 15 | 5 | 1 | 19.46% | 7.0276 | 0%
2027-01-16 | 2027 | 1 | Jan | 16 | 6 | 0 | 19.46% | 7.0276 | 0%
2027-01-17 | 2027 | 1 | Jan | 17 | 7 | 0 | 19.46% | 7.0276 | 0%
2027-01-18 | 2027 | 1 | Jan | 18 | 1 | 1 | 19.46% | 7.0276 | 0%
2027-01-19 | 2027 | 1 | Jan | 19 | 2 | 1 | 19.46% | 7.0276 | 0%
2027-01-20 | 2027 | 1 | Jan | 20 | 3 | 1 | 19.46% | 7.0276 | 0%
2027-01-21 | 2027 | 1 | Jan | 21 | 4 | 1 | 19.46% | 7.0276 | 0%
2027-01-22 | 2027 | 1 | Jan | 22 | 5 | 1 | 19.46% | 7.0276 | 0%
2027-01-23 | 2027 | 1 | Jan | 23 | 6 | 0 | 19.46% | 7.0276 | 0%
2027-01-24 | 2027 | 1 | Jan | 24 | 7 | 0 | 19.46% | 7.0276 | 0%
2027-01-25 | 2027 | 1 | Jan | 25 | 1 | 1 | 19.46% | 7.0276 | 0%
2027-01-26 | 2027 | 1 | Jan | 26 | 2 | 1 | 19.46% | 7.0276 | 0%
2027-01-27 | 2027 | 1 | Jan | 27 | 3 | 1 | 19.46% | 7.0276 | 0%
2027-01-28 | 2027 | 1 | Jan | 28 | 4 | 1 | 19.46% | 7.0276 | 0%
2027-01-29 | 2027 | 1 | Jan | 29 | 5 | 1 | 19.46% | 7.0276 | 0%
2027-01-30 | 2027 | 1 | Jan | 30 | 6 | 0 | 19.46% | 7.0276 | 0%
2027-01-31 | 2027 | 1 | Jan | 31 | 7 | 0 | 19.46% | 7.0276 | 0%
2027-02-01 | 2027 | 2 | Feb | 1 | 1 | 1 | 18.87% | 7.4625 | 0%
2027-02-02 | 2027 | 2 | Feb | 2 | 2 | 1 | 18.87% | 7.4625 | 0%
2027-02-03 | 2027 | 2 | Feb | 3 | 3 | 1 | 18.87% | 7.4625 | 0%
2027-02-04 | 2027 | 2 | Feb | 4 | 4 | 1 | 18.87% | 7.4625 | 0%
2027-02-05 | 2027 | 2 | Feb | 5 | 5 | 1 | 18.87% | 7.4625 | 0%
2027-02-06 | 2027 | 2 | Feb | 6 | 6 | 0 | 18.87% | 7.4625 | 0%
2027-02-07 | 2027 | 2 | Feb | 7 | 7 | 0 | 18.87% | 7.4625 | 0%
2027-02-08 | 2027 | 2 | Feb | 8 | 1 | 1 | 18.87% | 7.4625 | 0%
2027-02-09 | 2027 | 2 | Feb | 9 | 2 | 1 | 18.87% | 7.4625 | 0%
2027-02-10 | 2027 | 2 | Feb | 10 | 3 | 1 | 18.87% | 7.4625 | 0%
2027-02-11 | 2027 | 2 | Feb | 11 | 4 | 1 | 18.87% | 7.4625 | 0%
2027-02-12 | 2027 | 2 | Feb | 12 | 5 | 1 | 18.87% | 7.4625 | 0%
2027-02-13 | 2027 | 2 | Feb | 13 | 6 | 0 | 18.87% | 7.4625 | 0%
2027-02-14 | 2027 | 2 | Feb | 14 | 7 | 0 | 18.87% | 7.4625 | 0%
2027-02-15 | 2027 | 2 | Feb | 15 | 1 | 1 | 18.87% | 7.4625 | 0%
2027-02-16 | 2027 | 2 | Feb | 16 | 2 | 1 | 18.87% | 7.4625 | 0%
2027-02-17 | 2027 | 2 | Feb | 17 | 3 | 1 | 18.87% | 7.4625 | 0%
2027-02-18 | 2027 | 2 | Feb | 18 | 4 | 1 | 18.87% | 7.4625 | 0%
2027-02-19 | 2027 | 2 | Feb | 19 | 5 | 1 | 18.87% | 7.4625 | 0%
2027-02-20 | 2027 | 2 | Feb | 20 | 6 | 0 | 18.87% | 7.4625 | 0%
2027-02-21 | 2027 | 2 | Feb | 21 | 7 | 0 | 18.87% | 7.4625 | 0%
2027-02-22 | 2027 | 2 | Feb | 22 | 1 | 1 | 18.87% | 7.4625 | 0%
2027-02-23 | 2027 | 2 | Feb | 23 | 2 | 1 | 18.87% | 7.4625 | 0%
2027-02-24 | 2027 | 2 | Feb | 24 | 3 | 1 | 18.87% | 7.4625 | 0%
2027-02-25 | 2027 | 2 | Feb | 25 | 4 | 1 | 18.87% | 7.4625 | 0%
2027-02-26 | 2027 | 2 | Feb | 26 | 5 | 1 | 18.87% | 7.4625 | 0%
2027-02-27 | 2027 | 2 | Feb | 27 | 6 | 0 | 18.87% | 7.4625 | 0%
2027-02-28 | 2027 | 2 | Feb | 28 | 7 | 0 | 18.87% | 7.4625 | 0%
2027-03-01 | 2027 | 3 | Mar | 1 | 1 | 1 | 18.49% | 7.8663 | 0%
2027-03-02 | 2027 | 3 | Mar | 2 | 2 | 1 | 18.49% | 7.8663 | 0%
2027-03-03 | 2027 | 3 | Mar | 3 | 3 | 1 | 18.49% | 7.8663 | 0%
2027-03-04 | 2027 | 3 | Mar | 4 | 4 | 1 | 18.49% | 7.8663 | 0%
2027-03-05 | 2027 | 3 | Mar | 5 | 5 | 1 | 18.49% | 7.8663 | 0%
2027-03-06 | 2027 | 3 | Mar | 6 | 6 | 0 | 18.49% | 7.8663 | 0%
2027-03-07 | 2027 | 3 | Mar | 7 | 7 | 0 | 18.49% | 7.8663 | 0%
2027-03-08 | 2027 | 3 | Mar | 8 | 1 | 1 | 18.49% | 7.8663 | 0%
2027-03-09 | 2027 | 3 | Mar | 9 | 2 | 1 | 18.49% | 7.8663 | 0%
2027-03-10 | 2027 | 3 | Mar | 10 | 3 | 1 | 18.49% | 7.8663 | 0%
2027-03-11 | 2027 | 3 | Mar | 11 | 4 | 1 | 18.49% | 7.8663 | 0%
2027-03-12 | 2027 | 3 | Mar | 12 | 5 | 1 | 18.49% | 7.8663 | 0%
2027-03-13 | 2027 | 3 | Mar | 13 | 6 | 0 | 18.49% | 7.8663 | 0%
2027-03-14 | 2027 | 3 | Mar | 14 | 7 | 0 | 18.49% | 7.8663 | 0%
2027-03-15 | 2027 | 3 | Mar | 15 | 1 | 1 | 18.49% | 7.8663 | 0%
2027-03-16 | 2027 | 3 | Mar | 16 | 2 | 1 | 18.49% | 7.8663 | 0%
2027-03-17 | 2027 | 3 | Mar | 17 | 3 | 1 | 18.49% | 7.8663 | 0%
2027-03-18 | 2027 | 3 | Mar | 18 | 4 | 1 | 18.49% | 7.8663 | 0%
2027-03-19 | 2027 | 3 | Mar | 19 | 5 | 1 | 18.49% | 7.8663 | 0%
2027-03-20 | 2027 | 3 | Mar | 20 | 6 | 0 | 18.49% | 7.8663 | 0%
2027-03-21 | 2027 | 3 | Mar | 21 | 7 | 0 | 18.49% | 7.8663 | 0%
2027-03-22 | 2027 | 3 | Mar | 22 | 1 | 1 | 18.49% | 7.8663 | 0%
2027-03-23 | 2027 | 3 | Mar | 23 | 2 | 1 | 18.49% | 7.8663 | 0%
2027-03-24 | 2027 | 3 | Mar | 24 | 3 | 1 | 18.49% | 7.8663 | 0%
2027-03-25 | 2027 | 3 | Mar | 25 | 4 | 1 | 18.49% | 7.8663 | 0%
2027-03-26 | 2027 | 3 | Mar | 26 | 5 | 1 | 18.49% | 7.8663 | 0%
2027-03-27 | 2027 | 3 | Mar | 27 | 6 | 0 | 18.49% | 7.8663 | 0%
2027-03-28 | 2027 | 3 | Mar | 28 | 7 | 0 | 18.49% | 7.8663 | 0%
2027-03-29 | 2027 | 3 | Mar | 29 | 1 | 1 | 18.49% | 7.8663 | 0%
2027-03-30 | 2027 | 3 | Mar | 30 | 2 | 1 | 18.49% | 7.8663 | 0%
2027-03-31 | 2027 | 3 | Mar | 31 | 3 | 1 | 18.49% | 7.8663 | 0%
2027-04-01 | 2027 | 4 | Apr | 1 | 4 | 1 | 25.56% | 7.5 | 0%
2027-04-02 | 2027 | 4 | Apr | 2 | 5 | 1 | 25.56% | 7.5 | 0%
2027-04-03 | 2027 | 4 | Apr | 3 | 6 | 0 | 25.56% | 7.5 | 0%
2027-04-04 | 2027 | 4 | Apr | 4 | 7 | 0 | 25.56% | 7.5 | 0%
2027-04-05 | 2027 | 4 | Apr | 5 | 1 | 1 | 25.56% | 7.5 | 0%
2027-04-06 | 2027 | 4 | Apr | 6 | 2 | 1 | 25.56% | 7.5 | 0%
2027-04-07 | 2027 | 4 | Apr | 7 | 3 | 1 | 25.56% | 7.5 | 0%
2027-04-08 | 2027 | 4 | Apr | 8 | 4 | 1 | 25.56% | 7.5 | 0%
2027-04-09 | 2027 | 4 | Apr | 9 | 5 | 1 | 25.56% | 7.5 | 0%
2027-04-10 | 2027 | 4 | Apr | 10 | 6 | 0 | 25.56% | 7.5 | 0%
2027-04-11 | 2027 | 4 | Apr | 11 | 7 | 0 | 25.56% | 7.5 | 0%
2027-04-12 | 2027 | 4 | Apr | 12 | 1 | 1 | 25.56% | 7.5 | 0%
2027-04-13 | 2027 | 4 | Apr | 13 | 2 | 1 | 25.56% | 7.5 | 0%
2027-04-14 | 2027 | 4 | Apr | 14 | 3 | 1 | 25.56% | 7.5 | 0%
2027-04-15 | 2027 | 4 | Apr | 15 | 4 | 1 | 25.56% | 7.5 | 0%
2027-04-16 | 2027 | 4 | Apr | 16 | 5 | 1 | 25.56% | 7.5 | 0%
2027-04-17 | 2027 | 4 | Apr | 17 | 6 | 0 | 25.56% | 7.5 | 0%
2027-04-18 | 2027 | 4 | Apr | 18 | 7 | 0 | 25.56% | 7.5 | 0%
2027-04-19 | 2027 | 4 | Apr | 19 | 1 | 1 | 25.56% | 7.5 | 0%
2027-04-20 | 2027 | 4 | Apr | 20 | 2 | 1 | 25.56% | 7.5 | 0%
2027-04-21 | 2027 | 4 | Apr | 21 | 3 | 1 | 25.56% | 7.5 | 0%
2027-04-22 | 2027 | 4 | Apr | 22 | 4 | 1 | 25.56% | 7.5 | 0%
2027-04-23 | 2027 | 4 | Apr | 23 | 5 | 1 | 25.56% | 7.5 | 0%
2027-04-24 | 2027 | 4 | Apr | 24 | 6 | 0 | 25.56% | 7.5 | 0%
2027-04-25 | 2027 | 4 | Apr | 25 | 7 | 0 | 25.56% | 7.5 | 0%
2027-04-26 | 2027 | 4 | Apr | 26 | 1 | 1 | 25.56% | 7.5 | 0%
2027-04-27 | 2027 | 4 | Apr | 27 | 2 | 1 | 25.56% | 7.5 | 0%
2027-04-28 | 2027 | 4 | Apr | 28 | 3 | 1 | 25.56% | 7.5 | 0%
2027-04-29 | 2027 | 4 | Apr | 29 | 4 | 1 | 25.56% | 7.5 | 0%
2027-04-30 | 2027 | 4 | Apr | 30 | 5 | 1 | 25.56% | 7.5 | 0%
2027-05-01 | 2027 | 5 | May | 1 | 6 | 0 | 23.01% | 8.1449 | 0%
2027-05-02 | 2027 | 5 | May | 2 | 7 | 0 | 23.01% | 8.1449 | 0%
2027-05-03 | 2027 | 5 | May | 3 | 1 | 1 | 23.01% | 8.1449 | 0%
2027-05-04 | 2027 | 5 | May | 4 | 2 | 1 | 23.01% | 8.1449 | 0%
2027-05-05 | 2027 | 5 | May | 5 | 3 | 1 | 23.01% | 8.1449 | 0%
2027-05-06 | 2027 | 5 | May | 6 | 4 | 1 | 23.01% | 8.1449 | 0%
2027-05-07 | 2027 | 5 | May | 7 | 5 | 1 | 23.01% | 8.1449 | 0%
2027-05-08 | 2027 | 5 | May | 8 | 6 | 0 | 23.01% | 8.1449 | 0%
2027-05-09 | 2027 | 5 | May | 9 | 7 | 0 | 23.01% | 8.1449 | 0%
2027-05-10 | 2027 | 5 | May | 10 | 1 | 1 | 23.01% | 8.1449 | 0%
2027-05-11 | 2027 | 5 | May | 11 | 2 | 1 | 23.01% | 8.1449 | 0%
2027-05-12 | 2027 | 5 | May | 12 | 3 | 1 | 23.01% | 8.1449 | 0%
2027-05-13 | 2027 | 5 | May | 13 | 4 | 1 | 23.01% | 8.1449 | 0%
2027-05-14 | 2027 | 5 | May | 14 | 5 | 1 | 23.01% | 8.1449 | 0%
2027-05-15 | 2027 | 5 | May | 15 | 6 | 0 | 23.01% | 8.1449 | 0%
2027-05-16 | 2027 | 5 | May | 16 | 7 | 0 | 23.01% | 8.1449 | 0%
2027-05-17 | 2027 | 5 | May | 17 | 1 | 1 | 23.01% | 8.1449 | 0%
2027-05-18 | 2027 | 5 | May | 18 | 2 | 1 | 23.01% | 8.1449 | 0%
2027-05-19 | 2027 | 5 | May | 19 | 3 | 1 | 23.01% | 8.1449 | 0%
2027-05-20 | 2027 | 5 | May | 20 | 4 | 1 | 23.01% | 8.1449 | 0%
2027-05-21 | 2027 | 5 | May | 21 | 5 | 1 | 23.01% | 8.1449 | 0%
2027-05-22 | 2027 | 5 | May | 22 | 6 | 0 | 23.01% | 8.1449 | 0%
2027-05-23 | 2027 | 5 | May | 23 | 7 | 0 | 23.01% | 8.1449 | 0%
2027-05-24 | 2027 | 5 | May | 24 | 1 | 1 | 23.01% | 8.1449 | 0%
2027-05-25 | 2027 | 5 | May | 25 | 2 | 1 | 23.01% | 8.1449 | 0%
2027-05-26 | 2027 | 5 | May | 26 | 3 | 1 | 23.01% | 8.1449 | 0%
2027-05-27 | 2027 | 5 | May | 27 | 4 | 1 | 23.01% | 8.1449 | 0%
2027-05-28 | 2027 | 5 | May | 28 | 5 | 1 | 23.01% | 8.1449 | 0%
2027-05-29 | 2027 | 5 | May | 29 | 6 | 0 | 23.01% | 8.1449 | 0%
2027-05-30 | 2027 | 5 | May | 30 | 7 | 0 | 23.01% | 8.1449 | 0%
2027-05-31 | 2027 | 5 | May | 31 | 1 | 1 | 23.01% | 8.1449 | 0%
2027-06-01 | 2027 | 6 | Jun | 1 | 2 | 1 | 28.67% | 7.9419 | 0%
2027-06-02 | 2027 | 6 | Jun | 2 | 3 | 1 | 28.67% | 7.9419 | 0%
2027-06-03 | 2027 | 6 | Jun | 3 | 4 | 1 | 28.67% | 7.9419 | 0%
2027-06-04 | 2027 | 6 | Jun | 4 | 5 | 1 | 28.67% | 7.9419 | 0%
2027-06-05 | 2027 | 6 | Jun | 5 | 6 | 0 | 28.67% | 7.9419 | 0%
2027-06-06 | 2027 | 6 | Jun | 6 | 7 | 0 | 28.67% | 7.9419 | 0%
2027-06-07 | 2027 | 6 | Jun | 7 | 1 | 1 | 28.67% | 7.9419 | 0%
2027-06-08 | 2027 | 6 | Jun | 8 | 2 | 1 | 28.67% | 7.9419 | 0%
2027-06-09 | 2027 | 6 | Jun | 9 | 3 | 1 | 28.67% | 7.9419 | 0%
2027-06-10 | 2027 | 6 | Jun | 10 | 4 | 1 | 28.67% | 7.9419 | 0%
2027-06-11 | 2027 | 6 | Jun | 11 | 5 | 1 | 28.67% | 7.9419 | 0%
2027-06-12 | 2027 | 6 | Jun | 12 | 6 | 0 | 28.67% | 7.9419 | 0%
2027-06-13 | 2027 | 6 | Jun | 13 | 7 | 0 | 28.67% | 7.9419 | 0%
2027-06-14 | 2027 | 6 | Jun | 14 | 1 | 1 | 28.67% | 7.9419 | 0%
2027-06-15 | 2027 | 6 | Jun | 15 | 2 | 1 | 28.67% | 7.9419 | 0%
2027-06-16 | 2027 | 6 | Jun | 16 | 3 | 1 | 28.67% | 7.9419 | 0%
2027-06-17 | 2027 | 6 | Jun | 17 | 4 | 1 | 28.67% | 7.9419 | 0%
2027-06-18 | 2027 | 6 | Jun | 18 | 5 | 1 | 28.67% | 7.9419 | 0%
2027-06-19 | 2027 | 6 | Jun | 19 | 6 | 0 | 28.67% | 7.9419 | 0%
2027-06-20 | 2027 | 6 | Jun | 20 | 7 | 0 | 28.67% | 7.9419 | 0%
2027-06-21 | 2027 | 6 | Jun | 21 | 1 | 1 | 28.67% | 7.9419 | 0%
2027-06-22 | 2027 | 6 | Jun | 22 | 2 | 1 | 28.67% | 7.9419 | 0%
2027-06-23 | 2027 | 6 | Jun | 23 | 3 | 1 | 28.67% | 7.9419 | 0%
2027-06-24 | 2027 | 6 | Jun | 24 | 4 | 1 | 28.67% | 7.9419 | 0%
2027-06-25 | 2027 | 6 | Jun | 25 | 5 | 1 | 28.67% | 7.9419 | 0%
2027-06-26 | 2027 | 6 | Jun | 26 | 6 | 0 | 28.67% | 7.9419 | 0%
2027-06-27 | 2027 | 6 | Jun | 27 | 7 | 0 | 28.67% | 7.9419 | 0%
2027-06-28 | 2027 | 6 | Jun | 28 | 1 | 1 | 28.67% | 7.9419 | 0%
2027-06-29 | 2027 | 6 | Jun | 29 | 2 | 1 | 28.67% | 7.9419 | 0%
2027-06-30 | 2027 | 6 | Jun | 30 | 3 | 1 | 28.67% | 7.9419 | 0%
2027-07-01 | 2027 | 7 | Jul | 1 | 4 | 1 | 24.73% | 8.3739 | 0%
2027-07-02 | 2027 | 7 | Jul | 2 | 5 | 1 | 24.73% | 8.3739 | 0%
2027-07-03 | 2027 | 7 | Jul | 3 | 6 | 0 | 24.73% | 8.3739 | 0%
2027-07-04 | 2027 | 7 | Jul | 4 | 7 | 0 | 24.73% | 8.3739 | 0%
2027-07-05 | 2027 | 7 | Jul | 5 | 1 | 1 | 24.73% | 8.3739 | 0%
2027-07-06 | 2027 | 7 | Jul | 6 | 2 | 1 | 24.73% | 8.3739 | 0%
2027-07-07 | 2027 | 7 | Jul | 7 | 3 | 1 | 24.73% | 8.3739 | 0%
2027-07-08 | 2027 | 7 | Jul | 8 | 4 | 1 | 24.73% | 8.3739 | 0%
2027-07-09 | 2027 | 7 | Jul | 9 | 5 | 1 | 24.73% | 8.3739 | 0%
2027-07-10 | 2027 | 7 | Jul | 10 | 6 | 0 | 24.73% | 8.3739 | 0%
2027-07-11 | 2027 | 7 | Jul | 11 | 7 | 0 | 24.73% | 8.3739 | 0%
2027-07-12 | 2027 | 7 | Jul | 12 | 1 | 1 | 24.73% | 8.3739 | 0%
2027-07-13 | 2027 | 7 | Jul | 13 | 2 | 1 | 24.73% | 8.3739 | 0%
2027-07-14 | 2027 | 7 | Jul | 14 | 3 | 1 | 24.73% | 8.3739 | 0%
2027-07-15 | 2027 | 7 | Jul | 15 | 4 | 1 | 24.73% | 8.3739 | 0%
2027-07-16 | 2027 | 7 | Jul | 16 | 5 | 1 | 24.73% | 8.3739 | 0%
2027-07-17 | 2027 | 7 | Jul | 17 | 6 | 0 | 24.73% | 8.3739 | 0%
2027-07-18 | 2027 | 7 | Jul | 18 | 7 | 0 | 24.73% | 8.3739 | 0%
2027-07-19 | 2027 | 7 | Jul | 19 | 1 | 1 | 24.73% | 8.3739 | 0%
2027-07-20 | 2027 | 7 | Jul | 20 | 2 | 1 | 24.73% | 8.3739 | 0%
2027-07-21 | 2027 | 7 | Jul | 21 | 3 | 1 | 24.73% | 8.3739 | 0%
2027-07-22 | 2027 | 7 | Jul | 22 | 4 | 1 | 24.73% | 8.3739 | 0%
2027-07-23 | 2027 | 7 | Jul | 23 | 5 | 1 | 24.73% | 8.3739 | 0%
2027-07-24 | 2027 | 7 | Jul | 24 | 6 | 0 | 24.73% | 8.3739 | 0%
2027-07-25 | 2027 | 7 | Jul | 25 | 7 | 0 | 24.73% | 8.3739 | 0%
2027-07-26 | 2027 | 7 | Jul | 26 | 1 | 1 | 24.73% | 8.3739 | 0%
2027-07-27 | 2027 | 7 | Jul | 27 | 2 | 1 | 24.73% | 8.3739 | 0%
2027-07-28 | 2027 | 7 | Jul | 28 | 3 | 1 | 24.73% | 8.3739 | 0%
2027-07-29 | 2027 | 7 | Jul | 29 | 4 | 1 | 24.73% | 8.3739 | 0%
2027-07-30 | 2027 | 7 | Jul | 30 | 5 | 1 | 24.73% | 8.3739 | 0%
2027-07-31 | 2027 | 7 | Jul | 31 | 6 | 0 | 24.73% | 8.3739 | 0%
2027-08-01 | 2027 | 8 | Aug | 1 | 7 | 0 | 23.55% | 7.9589 | 0%
2027-08-02 | 2027 | 8 | Aug | 2 | 1 | 1 | 23.55% | 7.9589 | 0%
2027-08-03 | 2027 | 8 | Aug | 3 | 2 | 1 | 23.55% | 7.9589 | 0%
2027-08-04 | 2027 | 8 | Aug | 4 | 3 | 1 | 23.55% | 7.9589 | 0%
2027-08-05 | 2027 | 8 | Aug | 5 | 4 | 1 | 23.55% | 7.9589 | 0%
2027-08-06 | 2027 | 8 | Aug | 6 | 5 | 1 | 23.55% | 7.9589 | 0%
2027-08-07 | 2027 | 8 | Aug | 7 | 6 | 0 | 23.55% | 7.9589 | 0%
2027-08-08 | 2027 | 8 | Aug | 8 | 7 | 0 | 23.55% | 7.9589 | 0%
2027-08-09 | 2027 | 8 | Aug | 9 | 1 | 1 | 23.55% | 7.9589 | 0%
2027-08-10 | 2027 | 8 | Aug | 10 | 2 | 1 | 23.55% | 7.9589 | 0%
2027-08-11 | 2027 | 8 | Aug | 11 | 3 | 1 | 23.55% | 7.9589 | 0%
2027-08-12 | 2027 | 8 | Aug | 12 | 4 | 1 | 23.55% | 7.9589 | 0%
2027-08-13 | 2027 | 8 | Aug | 13 | 5 | 1 | 23.55% | 7.9589 | 0%
2027-08-14 | 2027 | 8 | Aug | 14 | 6 | 0 | 23.55% | 7.9589 | 0%
2027-08-15 | 2027 | 8 | Aug | 15 | 7 | 0 | 23.55% | 7.9589 | 0%
2027-08-16 | 2027 | 8 | Aug | 16 | 1 | 1 | 23.55% | 7.9589 | 0%
2027-08-17 | 2027 | 8 | Aug | 17 | 2 | 1 | 23.55% | 7.9589 | 0%
2027-08-18 | 2027 | 8 | Aug | 18 | 3 | 1 | 23.55% | 7.9589 | 0%
2027-08-19 | 2027 | 8 | Aug | 19 | 4 | 1 | 23.55% | 7.9589 | 0%
2027-08-20 | 2027 | 8 | Aug | 20 | 5 | 1 | 23.55% | 7.9589 | 0%
2027-08-21 | 2027 | 8 | Aug | 21 | 6 | 0 | 23.55% | 7.9589 | 0%
2027-08-22 | 2027 | 8 | Aug | 22 | 7 | 0 | 23.55% | 7.9589 | 0%
2027-08-23 | 2027 | 8 | Aug | 23 | 1 | 1 | 23.55% | 7.9589 | 0%
2027-08-24 | 2027 | 8 | Aug | 24 | 2 | 1 | 23.55% | 7.9589 | 0%
2027-08-25 | 2027 | 8 | Aug | 25 | 3 | 1 | 23.55% | 7.9589 | 0%
2027-08-26 | 2027 | 8 | Aug | 26 | 4 | 1 | 23.55% | 7.9589 | 0%
2027-08-27 | 2027 | 8 | Aug | 27 | 5 | 1 | 23.55% | 7.9589 | 0%
2027-08-28 | 2027 | 8 | Aug | 28 | 6 | 0 | 23.55% | 7.9589 | 0%
2027-08-29 | 2027 | 8 | Aug | 29 | 7 | 0 | 23.55% | 7.9589 | 0%
2027-08-30 | 2027 | 8 | Aug | 30 | 1 | 1 | 23.55% | 7.9589 | 0%
2027-08-31 | 2027 | 8 | Aug | 31 | 2 | 1 | 23.55% | 7.9589 | 0%
2027-09-01 | 2027 | 9 | Sep | 1 | 3 | 1 | 20.67% | 6.8065 | 0%
2027-09-02 | 2027 | 9 | Sep | 2 | 4 | 1 | 20.67% | 6.8065 | 0%
2027-09-03 | 2027 | 9 | Sep | 3 | 5 | 1 | 20.67% | 6.8065 | 0%
2027-09-04 | 2027 | 9 | Sep | 4 | 6 | 0 | 20.67% | 6.8065 | 0%
2027-09-05 | 2027 | 9 | Sep | 5 | 7 | 0 | 20.67% | 6.8065 | 0%
2027-09-06 | 2027 | 9 | Sep | 6 | 1 | 1 | 20.67% | 6.8065 | 0%
2027-09-07 | 2027 | 9 | Sep | 7 | 2 | 1 | 20.67% | 6.8065 | 0%
2027-09-08 | 2027 | 9 | Sep | 8 | 3 | 1 | 20.67% | 6.8065 | 0%
2027-09-09 | 2027 | 9 | Sep | 9 | 4 | 1 | 20.67% | 6.8065 | 0%
2027-09-10 | 2027 | 9 | Sep | 10 | 5 | 1 | 20.67% | 6.8065 | 0%
2027-09-11 | 2027 | 9 | Sep | 11 | 6 | 0 | 20.67% | 6.8065 | 0%
2027-09-12 | 2027 | 9 | Sep | 12 | 7 | 0 | 20.67% | 6.8065 | 0%
2027-09-13 | 2027 | 9 | Sep | 13 | 1 | 1 | 20.67% | 6.8065 | 0%
2027-09-14 | 2027 | 9 | Sep | 14 | 2 | 1 | 20.67% | 6.8065 | 0%
2027-09-15 | 2027 | 9 | Sep | 15 | 3 | 1 | 20.67% | 6.8065 | 0%
2027-09-16 | 2027 | 9 | Sep | 16 | 4 | 1 | 20.67% | 6.8065 | 0%
2027-09-17 | 2027 | 9 | Sep | 17 | 5 | 1 | 20.67% | 6.8065 | 0%
2027-09-18 | 2027 | 9 | Sep | 18 | 6 | 0 | 20.67% | 6.8065 | 0%
2027-09-19 | 2027 | 9 | Sep | 19 | 7 | 0 | 20.67% | 6.8065 | 0%
2027-09-20 | 2027 | 9 | Sep | 20 | 1 | 1 | 20.67% | 6.8065 | 0%
2027-09-21 | 2027 | 9 | Sep | 21 | 2 | 1 | 20.67% | 6.8065 | 0%
2027-09-22 | 2027 | 9 | Sep | 22 | 3 | 1 | 20.67% | 6.8065 | 0%
2027-09-23 | 2027 | 9 | Sep | 23 | 4 | 1 | 20.67% | 6.8065 | 0%
2027-09-24 | 2027 | 9 | Sep | 24 | 5 | 1 | 20.67% | 6.8065 | 0%
2027-09-25 | 2027 | 9 | Sep | 25 | 6 | 0 | 20.67% | 6.8065 | 0%
2027-09-26 | 2027 | 9 | Sep | 26 | 7 | 0 | 20.67% | 6.8065 | 0%
2027-09-27 | 2027 | 9 | Sep | 27 | 1 | 1 | 20.67% | 6.8065 | 0%
2027-09-28 | 2027 | 9 | Sep | 28 | 2 | 1 | 20.67% | 6.8065 | 0%
2027-09-29 | 2027 | 9 | Sep | 29 | 3 | 1 | 20.67% | 6.8065 | 0%
2027-09-30 | 2027 | 9 | Sep | 30 | 4 | 1 | 20.67% | 6.8065 | 0%
2027-10-01 | 2027 | 10 | Oct | 1 | 5 | 1 | 23.23% | 6.8194 | 0%
2027-10-02 | 2027 | 10 | Oct | 2 | 6 | 0 | 23.23% | 6.8194 | 0%
2027-10-03 | 2027 | 10 | Oct | 3 | 7 | 0 | 23.23% | 6.8194 | 0%
2027-10-04 | 2027 | 10 | Oct | 4 | 1 | 1 | 23.23% | 6.8194 | 0%
2027-10-05 | 2027 | 10 | Oct | 5 | 2 | 1 | 23.23% | 6.8194 | 0%
2027-10-06 | 2027 | 10 | Oct | 6 | 3 | 1 | 23.23% | 6.8194 | 0%
2027-10-07 | 2027 | 10 | Oct | 7 | 4 | 1 | 23.23% | 6.8194 | 0%
2027-10-08 | 2027 | 10 | Oct | 8 | 5 | 1 | 23.23% | 6.8194 | 0%
2027-10-09 | 2027 | 10 | Oct | 9 | 6 | 0 | 23.23% | 6.8194 | 0%
2027-10-10 | 2027 | 10 | Oct | 10 | 7 | 0 | 23.23% | 6.8194 | 0%
2027-10-11 | 2027 | 10 | Oct | 11 | 1 | 1 | 23.23% | 6.8194 | 0%
2027-10-12 | 2027 | 10 | Oct | 12 | 2 | 1 | 23.23% | 6.8194 | 0%
2027-10-13 | 2027 | 10 | Oct | 13 | 3 | 1 | 23.23% | 6.8194 | 0%
2027-10-14 | 2027 | 10 | Oct | 14 | 4 | 1 | 23.23% | 6.8194 | 0%
2027-10-15 | 2027 | 10 | Oct | 15 | 5 | 1 | 23.23% | 6.8194 | 0%
2027-10-16 | 2027 | 10 | Oct | 16 | 6 | 0 | 23.23% | 6.8194 | 0%
2027-10-17 | 2027 | 10 | Oct | 17 | 7 | 0 | 23.23% | 6.8194 | 0%
2027-10-18 | 2027 | 10 | Oct | 18 | 1 | 1 | 23.23% | 6.8194 | 0%
2027-10-19 | 2027 | 10 | Oct | 19 | 2 | 1 | 23.23% | 6.8194 | 0%
2027-10-20 | 2027 | 10 | Oct | 20 | 3 | 1 | 23.23% | 6.8194 | 0%
2027-10-21 | 2027 | 10 | Oct | 21 | 4 | 1 | 23.23% | 6.8194 | 0%
2027-10-22 | 2027 | 10 | Oct | 22 | 5 | 1 | 23.23% | 6.8194 | 0%
2027-10-23 | 2027 | 10 | Oct | 23 | 6 | 0 | 23.23% | 6.8194 | 0%
2027-10-24 | 2027 | 10 | Oct | 24 | 7 | 0 | 23.23% | 6.8194 | 0%
2027-10-25 | 2027 | 10 | Oct | 25 | 1 | 1 | 23.23% | 6.8194 | 0%
2027-10-26 | 2027 | 10 | Oct | 26 | 2 | 1 | 23.23% | 6.8194 | 0%
2027-10-27 | 2027 | 10 | Oct | 27 | 3 | 1 | 23.23% | 6.8194 | 0%
2027-10-28 | 2027 | 10 | Oct | 28 | 4 | 1 | 23.23% | 6.8194 | 0%
2027-10-29 | 2027 | 10 | Oct | 29 | 5 | 1 | 23.23% | 6.8194 | 0%
2027-10-30 | 2027 | 10 | Oct | 30 | 6 | 0 | 23.23% | 6.8194 | 0%
2027-10-31 | 2027 | 10 | Oct | 31 | 7 | 0 | 23.23% | 6.8194 | 0%
2027-11-01 | 2027 | 11 | Nov | 1 | 1 | 1 | 23.33% | 6.4429 | 0%
2027-11-02 | 2027 | 11 | Nov | 2 | 2 | 1 | 23.33% | 6.4429 | 0%
2027-11-03 | 2027 | 11 | Nov | 3 | 3 | 1 | 23.33% | 6.4429 | 0%
2027-11-04 | 2027 | 11 | Nov | 4 | 4 | 1 | 23.33% | 6.4429 | 0%
2027-11-05 | 2027 | 11 | Nov | 5 | 5 | 1 | 23.33% | 6.4429 | 0%
2027-11-06 | 2027 | 11 | Nov | 6 | 6 | 0 | 23.33% | 6.4429 | 0%
2027-11-07 | 2027 | 11 | Nov | 7 | 7 | 0 | 23.33% | 6.4429 | 0%
2027-11-08 | 2027 | 11 | Nov | 8 | 1 | 1 | 23.33% | 6.4429 | 0%
2027-11-09 | 2027 | 11 | Nov | 9 | 2 | 1 | 23.33% | 6.4429 | 0%
2027-11-10 | 2027 | 11 | Nov | 10 | 3 | 1 | 23.33% | 6.4429 | 0%
2027-11-11 | 2027 | 11 | Nov | 11 | 4 | 1 | 23.33% | 6.4429 | 0%
2027-11-12 | 2027 | 11 | Nov | 12 | 5 | 1 | 23.33% | 6.4429 | 0%
2027-11-13 | 2027 | 11 | Nov | 13 | 6 | 0 | 23.33% | 6.4429 | 0%
2027-11-14 | 2027 | 11 | Nov | 14 | 7 | 0 | 23.33% | 6.4429 | 0%
2027-11-15 | 2027 | 11 | Nov | 15 | 1 | 1 | 23.33% | 6.4429 | 0%
2027-11-16 | 2027 | 11 | Nov | 16 | 2 | 1 | 23.33% | 6.4429 | 0%
2027-11-17 | 2027 | 11 | Nov | 17 | 3 | 1 | 23.33% | 6.4429 | 0%
2027-11-18 | 2027 | 11 | Nov | 18 | 4 | 1 | 23.33% | 6.4429 | 0%
2027-11-19 | 2027 | 11 | Nov | 19 | 5 | 1 | 23.33% | 6.4429 | 0%
2027-11-20 | 2027 | 11 | Nov | 20 | 6 | 0 | 23.33% | 6.4429 | 0%
2027-11-21 | 2027 | 11 | Nov | 21 | 7 | 0 | 23.33% | 6.4429 | 0%
2027-11-22 | 2027 | 11 | Nov | 22 | 1 | 1 | 23.33% | 6.4429 | 0%
2027-11-23 | 2027 | 11 | Nov | 23 | 2 | 1 | 23.33% | 6.4429 | 0%
2027-11-24 | 2027 | 11 | Nov | 24 | 3 | 1 | 23.33% | 6.4429 | 0%
2027-11-25 | 2027 | 11 | Nov | 25 | 4 | 1 | 23.33% | 6.4429 | 0%
2027-11-26 | 2027 | 11 | Nov | 26 | 5 | 1 | 23.33% | 6.4429 | 0%
2027-11-27 | 2027 | 11 | Nov | 27 | 6 | 0 | 23.33% | 6.4429 | 0%
2027-11-28 | 2027 | 11 | Nov | 28 | 7 | 0 | 23.33% | 6.4429 | 0%
2027-11-29 | 2027 | 11 | Nov | 29 | 1 | 1 | 23.33% | 6.4429 | 0%
2027-11-30 | 2027 | 11 | Nov | 30 | 2 | 1 | 23.33% | 6.4429 | 0%
2027-12-01 | 2027 | 12 | Dec | 1 | 3 | 1 | 22.69% | 6.7962 | 0%
2027-12-02 | 2027 | 12 | Dec | 2 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-12-03 | 2027 | 12 | Dec | 3 | 5 | 1 | 22.69% | 6.7962 | 0%
2027-12-04 | 2027 | 12 | Dec | 4 | 6 | 0 | 22.69% | 6.7962 | 0%
2027-12-05 | 2027 | 12 | Dec | 5 | 7 | 0 | 22.69% | 6.7962 | 0%
2027-12-06 | 2027 | 12 | Dec | 6 | 1 | 1 | 22.69% | 6.7962 | 0%
2027-12-07 | 2027 | 12 | Dec | 7 | 2 | 1 | 22.69% | 6.7962 | 0%
2027-12-08 | 2027 | 12 | Dec | 8 | 3 | 1 | 22.69% | 6.7962 | 0%
2027-12-09 | 2027 | 12 | Dec | 9 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-12-10 | 2027 | 12 | Dec | 10 | 5 | 1 | 22.69% | 6.7962 | 0%
2027-12-11 | 2027 | 12 | Dec | 11 | 6 | 0 | 22.69% | 6.7962 | 0%
2027-12-12 | 2027 | 12 | Dec | 12 | 7 | 0 | 22.69% | 6.7962 | 0%
2027-12-13 | 2027 | 12 | Dec | 13 | 1 | 1 | 22.69% | 6.7962 | 0%
2027-12-14 | 2027 | 12 | Dec | 14 | 2 | 1 | 22.69% | 6.7962 | 0%
2027-12-15 | 2027 | 12 | Dec | 15 | 3 | 1 | 22.69% | 6.7962 | 0%
2027-12-16 | 2027 | 12 | Dec | 16 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-12-17 | 2027 | 12 | Dec | 17 | 5 | 1 | 22.69% | 6.7962 | 0%
2027-12-18 | 2027 | 12 | Dec | 18 | 6 | 0 | 22.69% | 6.7962 | 0%
2027-12-19 | 2027 | 12 | Dec | 19 | 7 | 0 | 22.69% | 6.7962 | 0%
2027-12-20 | 2027 | 12 | Dec | 20 | 1 | 1 | 22.69% | 6.7962 | 0%
2027-12-21 | 2027 | 12 | Dec | 21 | 2 | 1 | 22.69% | 6.7962 | 0%
2027-12-22 | 2027 | 12 | Dec | 22 | 3 | 1 | 22.69% | 6.7962 | 0%
2027-12-23 | 2027 | 12 | Dec | 23 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-12-24 | 2027 | 12 | Dec | 24 | 5 | 1 | 22.69% | 6.7962 | 0%
2027-12-25 | 2027 | 12 | Dec | 25 | 6 | 0 | 22.69% | 6.7962 | 0%
2027-12-26 | 2027 | 12 | Dec | 26 | 7 | 0 | 22.69% | 6.7962 | 0%
2027-12-27 | 2027 | 12 | Dec | 27 | 1 | 1 | 22.69% | 6.7962 | 0%
2027-12-28 | 2027 | 12 | Dec | 28 | 2 | 1 | 22.69% | 6.7962 | 0%
2027-12-29 | 2027 | 12 | Dec | 29 | 3 | 1 | 22.69% | 6.7962 | 0%
2027-12-30 | 2027 | 12 | Dec | 30 | 4 | 1 | 22.69% | 6.7962 | 0%
2027-12-31 | 2027 | 12 | Dec | 31 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-01-01 | 2028 | 1 | Jan | 1 | 6 | 0 | 19.46% | 7.0276 | 0%
2028-01-02 | 2028 | 1 | Jan | 2 | 7 | 0 | 19.46% | 7.0276 | 0%
2028-01-03 | 2028 | 1 | Jan | 3 | 1 | 1 | 19.46% | 7.0276 | 0%
2028-01-04 | 2028 | 1 | Jan | 4 | 2 | 1 | 19.46% | 7.0276 | 0%
2028-01-05 | 2028 | 1 | Jan | 5 | 3 | 1 | 19.46% | 7.0276 | 0%
2028-01-06 | 2028 | 1 | Jan | 6 | 4 | 1 | 19.46% | 7.0276 | 0%
2028-01-07 | 2028 | 1 | Jan | 7 | 5 | 1 | 19.46% | 7.0276 | 0%
2028-01-08 | 2028 | 1 | Jan | 8 | 6 | 0 | 19.46% | 7.0276 | 0%
2028-01-09 | 2028 | 1 | Jan | 9 | 7 | 0 | 19.46% | 7.0276 | 0%
2028-01-10 | 2028 | 1 | Jan | 10 | 1 | 1 | 19.46% | 7.0276 | 0%
2028-01-11 | 2028 | 1 | Jan | 11 | 2 | 1 | 19.46% | 7.0276 | 0%
2028-01-12 | 2028 | 1 | Jan | 12 | 3 | 1 | 19.46% | 7.0276 | 0%
2028-01-13 | 2028 | 1 | Jan | 13 | 4 | 1 | 19.46% | 7.0276 | 0%
2028-01-14 | 2028 | 1 | Jan | 14 | 5 | 1 | 19.46% | 7.0276 | 0%
2028-01-15 | 2028 | 1 | Jan | 15 | 6 | 0 | 19.46% | 7.0276 | 0%
2028-01-16 | 2028 | 1 | Jan | 16 | 7 | 0 | 19.46% | 7.0276 | 0%
2028-01-17 | 2028 | 1 | Jan | 17 | 1 | 1 | 19.46% | 7.0276 | 0%
2028-01-18 | 2028 | 1 | Jan | 18 | 2 | 1 | 19.46% | 7.0276 | 0%
2028-01-19 | 2028 | 1 | Jan | 19 | 3 | 1 | 19.46% | 7.0276 | 0%
2028-01-20 | 2028 | 1 | Jan | 20 | 4 | 1 | 19.46% | 7.0276 | 0%
2028-01-21 | 2028 | 1 | Jan | 21 | 5 | 1 | 19.46% | 7.0276 | 0%
2028-01-22 | 2028 | 1 | Jan | 22 | 6 | 0 | 19.46% | 7.0276 | 0%
2028-01-23 | 2028 | 1 | Jan | 23 | 7 | 0 | 19.46% | 7.0276 | 0%
2028-01-24 | 2028 | 1 | Jan | 24 | 1 | 1 | 19.46% | 7.0276 | 0%
2028-01-25 | 2028 | 1 | Jan | 25 | 2 | 1 | 19.46% | 7.0276 | 0%
2028-01-26 | 2028 | 1 | Jan | 26 | 3 | 1 | 19.46% | 7.0276 | 0%
2028-01-27 | 2028 | 1 | Jan | 27 | 4 | 1 | 19.46% | 7.0276 | 0%
2028-01-28 | 2028 | 1 | Jan | 28 | 5 | 1 | 19.46% | 7.0276 | 0%
2028-01-29 | 2028 | 1 | Jan | 29 | 6 | 0 | 19.46% | 7.0276 | 0%
2028-01-30 | 2028 | 1 | Jan | 30 | 7 | 0 | 19.46% | 7.0276 | 0%
2028-01-31 | 2028 | 1 | Jan | 31 | 1 | 1 | 19.46% | 7.0276 | 0%
2028-02-01 | 2028 | 2 | Feb | 1 | 2 | 1 | 18.87% | 7.4625 | 0%
2028-02-02 | 2028 | 2 | Feb | 2 | 3 | 1 | 18.87% | 7.4625 | 0%
2028-02-03 | 2028 | 2 | Feb | 3 | 4 | 1 | 18.87% | 7.4625 | 0%
2028-02-04 | 2028 | 2 | Feb | 4 | 5 | 1 | 18.87% | 7.4625 | 0%
2028-02-05 | 2028 | 2 | Feb | 5 | 6 | 0 | 18.87% | 7.4625 | 0%
2028-02-06 | 2028 | 2 | Feb | 6 | 7 | 0 | 18.87% | 7.4625 | 0%
2028-02-07 | 2028 | 2 | Feb | 7 | 1 | 1 | 18.87% | 7.4625 | 0%
2028-02-08 | 2028 | 2 | Feb | 8 | 2 | 1 | 18.87% | 7.4625 | 0%
2028-02-09 | 2028 | 2 | Feb | 9 | 3 | 1 | 18.87% | 7.4625 | 0%
2028-02-10 | 2028 | 2 | Feb | 10 | 4 | 1 | 18.87% | 7.4625 | 0%
2028-02-11 | 2028 | 2 | Feb | 11 | 5 | 1 | 18.87% | 7.4625 | 0%
2028-02-12 | 2028 | 2 | Feb | 12 | 6 | 0 | 18.87% | 7.4625 | 0%
2028-02-13 | 2028 | 2 | Feb | 13 | 7 | 0 | 18.87% | 7.4625 | 0%
2028-02-14 | 2028 | 2 | Feb | 14 | 1 | 1 | 18.87% | 7.4625 | 0%
2028-02-15 | 2028 | 2 | Feb | 15 | 2 | 1 | 18.87% | 7.4625 | 0%
2028-02-16 | 2028 | 2 | Feb | 16 | 3 | 1 | 18.87% | 7.4625 | 0%
2028-02-17 | 2028 | 2 | Feb | 17 | 4 | 1 | 18.87% | 7.4625 | 0%
2028-02-18 | 2028 | 2 | Feb | 18 | 5 | 1 | 18.87% | 7.4625 | 0%
2028-02-19 | 2028 | 2 | Feb | 19 | 6 | 0 | 18.87% | 7.4625 | 0%
2028-02-20 | 2028 | 2 | Feb | 20 | 7 | 0 | 18.87% | 7.4625 | 0%
2028-02-21 | 2028 | 2 | Feb | 21 | 1 | 1 | 18.87% | 7.4625 | 0%
2028-02-22 | 2028 | 2 | Feb | 22 | 2 | 1 | 18.87% | 7.4625 | 0%
2028-02-23 | 2028 | 2 | Feb | 23 | 3 | 1 | 18.87% | 7.4625 | 0%
2028-02-24 | 2028 | 2 | Feb | 24 | 4 | 1 | 18.87% | 7.4625 | 0%
2028-02-25 | 2028 | 2 | Feb | 25 | 5 | 1 | 18.87% | 7.4625 | 0%
2028-02-26 | 2028 | 2 | Feb | 26 | 6 | 0 | 18.87% | 7.4625 | 0%
2028-02-27 | 2028 | 2 | Feb | 27 | 7 | 0 | 18.87% | 7.4625 | 0%
2028-02-28 | 2028 | 2 | Feb | 28 | 1 | 1 | 18.87% | 7.4625 | 0%
2028-02-29 | 2028 | 2 | Feb | 29 | 2 | 1 | 18.87% | 7.4625 | 0%
2028-03-01 | 2028 | 3 | Mar | 1 | 3 | 1 | 18.49% | 7.8663 | 0%
2028-03-02 | 2028 | 3 | Mar | 2 | 4 | 1 | 18.49% | 7.8663 | 0%
2028-03-03 | 2028 | 3 | Mar | 3 | 5 | 1 | 18.49% | 7.8663 | 0%
2028-03-04 | 2028 | 3 | Mar | 4 | 6 | 0 | 18.49% | 7.8663 | 0%
2028-03-05 | 2028 | 3 | Mar | 5 | 7 | 0 | 18.49% | 7.8663 | 0%
2028-03-06 | 2028 | 3 | Mar | 6 | 1 | 1 | 18.49% | 7.8663 | 0%
2028-03-07 | 2028 | 3 | Mar | 7 | 2 | 1 | 18.49% | 7.8663 | 0%
2028-03-08 | 2028 | 3 | Mar | 8 | 3 | 1 | 18.49% | 7.8663 | 0%
2028-03-09 | 2028 | 3 | Mar | 9 | 4 | 1 | 18.49% | 7.8663 | 0%
2028-03-10 | 2028 | 3 | Mar | 10 | 5 | 1 | 18.49% | 7.8663 | 0%
2028-03-11 | 2028 | 3 | Mar | 11 | 6 | 0 | 18.49% | 7.8663 | 0%
2028-03-12 | 2028 | 3 | Mar | 12 | 7 | 0 | 18.49% | 7.8663 | 0%
2028-03-13 | 2028 | 3 | Mar | 13 | 1 | 1 | 18.49% | 7.8663 | 0%
2028-03-14 | 2028 | 3 | Mar | 14 | 2 | 1 | 18.49% | 7.8663 | 0%
2028-03-15 | 2028 | 3 | Mar | 15 | 3 | 1 | 18.49% | 7.8663 | 0%
2028-03-16 | 2028 | 3 | Mar | 16 | 4 | 1 | 18.49% | 7.8663 | 0%
2028-03-17 | 2028 | 3 | Mar | 17 | 5 | 1 | 18.49% | 7.8663 | 0%
2028-03-18 | 2028 | 3 | Mar | 18 | 6 | 0 | 18.49% | 7.8663 | 0%
2028-03-19 | 2028 | 3 | Mar | 19 | 7 | 0 | 18.49% | 7.8663 | 0%
2028-03-20 | 2028 | 3 | Mar | 20 | 1 | 1 | 18.49% | 7.8663 | 0%
2028-03-21 | 2028 | 3 | Mar | 21 | 2 | 1 | 18.49% | 7.8663 | 0%
2028-03-22 | 2028 | 3 | Mar | 22 | 3 | 1 | 18.49% | 7.8663 | 0%
2028-03-23 | 2028 | 3 | Mar | 23 | 4 | 1 | 18.49% | 7.8663 | 0%
2028-03-24 | 2028 | 3 | Mar | 24 | 5 | 1 | 18.49% | 7.8663 | 0%
2028-03-25 | 2028 | 3 | Mar | 25 | 6 | 0 | 18.49% | 7.8663 | 0%
2028-03-26 | 2028 | 3 | Mar | 26 | 7 | 0 | 18.49% | 7.8663 | 0%
2028-03-27 | 2028 | 3 | Mar | 27 | 1 | 1 | 18.49% | 7.8663 | 0%
2028-03-28 | 2028 | 3 | Mar | 28 | 2 | 1 | 18.49% | 7.8663 | 0%
2028-03-29 | 2028 | 3 | Mar | 29 | 3 | 1 | 18.49% | 7.8663 | 0%
2028-03-30 | 2028 | 3 | Mar | 30 | 4 | 1 | 18.49% | 7.8663 | 0%
2028-03-31 | 2028 | 3 | Mar | 31 | 5 | 1 | 18.49% | 7.8663 | 0%
2028-04-01 | 2028 | 4 | Apr | 1 | 6 | 0 | 25.56% | 7.5 | 0%
2028-04-02 | 2028 | 4 | Apr | 2 | 7 | 0 | 25.56% | 7.5 | 0%
2028-04-03 | 2028 | 4 | Apr | 3 | 1 | 1 | 25.56% | 7.5 | 0%
2028-04-04 | 2028 | 4 | Apr | 4 | 2 | 1 | 25.56% | 7.5 | 0%
2028-04-05 | 2028 | 4 | Apr | 5 | 3 | 1 | 25.56% | 7.5 | 0%
2028-04-06 | 2028 | 4 | Apr | 6 | 4 | 1 | 25.56% | 7.5 | 0%
2028-04-07 | 2028 | 4 | Apr | 7 | 5 | 1 | 25.56% | 7.5 | 0%
2028-04-08 | 2028 | 4 | Apr | 8 | 6 | 0 | 25.56% | 7.5 | 0%
2028-04-09 | 2028 | 4 | Apr | 9 | 7 | 0 | 25.56% | 7.5 | 0%
2028-04-10 | 2028 | 4 | Apr | 10 | 1 | 1 | 25.56% | 7.5 | 0%
2028-04-11 | 2028 | 4 | Apr | 11 | 2 | 1 | 25.56% | 7.5 | 0%
2028-04-12 | 2028 | 4 | Apr | 12 | 3 | 1 | 25.56% | 7.5 | 0%
2028-04-13 | 2028 | 4 | Apr | 13 | 4 | 1 | 25.56% | 7.5 | 0%
2028-04-14 | 2028 | 4 | Apr | 14 | 5 | 1 | 25.56% | 7.5 | 0%
2028-04-15 | 2028 | 4 | Apr | 15 | 6 | 0 | 25.56% | 7.5 | 0%
2028-04-16 | 2028 | 4 | Apr | 16 | 7 | 0 | 25.56% | 7.5 | 0%
2028-04-17 | 2028 | 4 | Apr | 17 | 1 | 1 | 25.56% | 7.5 | 0%
2028-04-18 | 2028 | 4 | Apr | 18 | 2 | 1 | 25.56% | 7.5 | 0%
2028-04-19 | 2028 | 4 | Apr | 19 | 3 | 1 | 25.56% | 7.5 | 0%
2028-04-20 | 2028 | 4 | Apr | 20 | 4 | 1 | 25.56% | 7.5 | 0%
2028-04-21 | 2028 | 4 | Apr | 21 | 5 | 1 | 25.56% | 7.5 | 0%
2028-04-22 | 2028 | 4 | Apr | 22 | 6 | 0 | 25.56% | 7.5 | 0%
2028-04-23 | 2028 | 4 | Apr | 23 | 7 | 0 | 25.56% | 7.5 | 0%
2028-04-24 | 2028 | 4 | Apr | 24 | 1 | 1 | 25.56% | 7.5 | 0%
2028-04-25 | 2028 | 4 | Apr | 25 | 2 | 1 | 25.56% | 7.5 | 0%
2028-04-26 | 2028 | 4 | Apr | 26 | 3 | 1 | 25.56% | 7.5 | 0%
2028-04-27 | 2028 | 4 | Apr | 27 | 4 | 1 | 25.56% | 7.5 | 0%
2028-04-28 | 2028 | 4 | Apr | 28 | 5 | 1 | 25.56% | 7.5 | 0%
2028-04-29 | 2028 | 4 | Apr | 29 | 6 | 0 | 25.56% | 7.5 | 0%
2028-04-30 | 2028 | 4 | Apr | 30 | 7 | 0 | 25.56% | 7.5 | 0%
2028-05-01 | 2028 | 5 | May | 1 | 1 | 1 | 23.01% | 8.1449 | 0%
2028-05-02 | 2028 | 5 | May | 2 | 2 | 1 | 23.01% | 8.1449 | 0%
2028-05-03 | 2028 | 5 | May | 3 | 3 | 1 | 23.01% | 8.1449 | 0%
2028-05-04 | 2028 | 5 | May | 4 | 4 | 1 | 23.01% | 8.1449 | 0%
2028-05-05 | 2028 | 5 | May | 5 | 5 | 1 | 23.01% | 8.1449 | 0%
2028-05-06 | 2028 | 5 | May | 6 | 6 | 0 | 23.01% | 8.1449 | 0%
2028-05-07 | 2028 | 5 | May | 7 | 7 | 0 | 23.01% | 8.1449 | 0%
2028-05-08 | 2028 | 5 | May | 8 | 1 | 1 | 23.01% | 8.1449 | 0%
2028-05-09 | 2028 | 5 | May | 9 | 2 | 1 | 23.01% | 8.1449 | 0%
2028-05-10 | 2028 | 5 | May | 10 | 3 | 1 | 23.01% | 8.1449 | 0%
2028-05-11 | 2028 | 5 | May | 11 | 4 | 1 | 23.01% | 8.1449 | 0%
2028-05-12 | 2028 | 5 | May | 12 | 5 | 1 | 23.01% | 8.1449 | 0%
2028-05-13 | 2028 | 5 | May | 13 | 6 | 0 | 23.01% | 8.1449 | 0%
2028-05-14 | 2028 | 5 | May | 14 | 7 | 0 | 23.01% | 8.1449 | 0%
2028-05-15 | 2028 | 5 | May | 15 | 1 | 1 | 23.01% | 8.1449 | 0%
2028-05-16 | 2028 | 5 | May | 16 | 2 | 1 | 23.01% | 8.1449 | 0%
2028-05-17 | 2028 | 5 | May | 17 | 3 | 1 | 23.01% | 8.1449 | 0%
2028-05-18 | 2028 | 5 | May | 18 | 4 | 1 | 23.01% | 8.1449 | 0%
2028-05-19 | 2028 | 5 | May | 19 | 5 | 1 | 23.01% | 8.1449 | 0%
2028-05-20 | 2028 | 5 | May | 20 | 6 | 0 | 23.01% | 8.1449 | 0%
2028-05-21 | 2028 | 5 | May | 21 | 7 | 0 | 23.01% | 8.1449 | 0%
2028-05-22 | 2028 | 5 | May | 22 | 1 | 1 | 23.01% | 8.1449 | 0%
2028-05-23 | 2028 | 5 | May | 23 | 2 | 1 | 23.01% | 8.1449 | 0%
2028-05-24 | 2028 | 5 | May | 24 | 3 | 1 | 23.01% | 8.1449 | 0%
2028-05-25 | 2028 | 5 | May | 25 | 4 | 1 | 23.01% | 8.1449 | 0%
2028-05-26 | 2028 | 5 | May | 26 | 5 | 1 | 23.01% | 8.1449 | 0%
2028-05-27 | 2028 | 5 | May | 27 | 6 | 0 | 23.01% | 8.1449 | 0%
2028-05-28 | 2028 | 5 | May | 28 | 7 | 0 | 23.01% | 8.1449 | 0%
2028-05-29 | 2028 | 5 | May | 29 | 1 | 1 | 23.01% | 8.1449 | 0%
2028-05-30 | 2028 | 5 | May | 30 | 2 | 1 | 23.01% | 8.1449 | 0%
2028-05-31 | 2028 | 5 | May | 31 | 3 | 1 | 23.01% | 8.1449 | 0%
2028-06-01 | 2028 | 6 | Jun | 1 | 4 | 1 | 28.67% | 7.9419 | 0%
2028-06-02 | 2028 | 6 | Jun | 2 | 5 | 1 | 28.67% | 7.9419 | 0%
2028-06-03 | 2028 | 6 | Jun | 3 | 6 | 0 | 28.67% | 7.9419 | 0%
2028-06-04 | 2028 | 6 | Jun | 4 | 7 | 0 | 28.67% | 7.9419 | 0%
2028-06-05 | 2028 | 6 | Jun | 5 | 1 | 1 | 28.67% | 7.9419 | 0%
2028-06-06 | 2028 | 6 | Jun | 6 | 2 | 1 | 28.67% | 7.9419 | 0%
2028-06-07 | 2028 | 6 | Jun | 7 | 3 | 1 | 28.67% | 7.9419 | 0%
2028-06-08 | 2028 | 6 | Jun | 8 | 4 | 1 | 28.67% | 7.9419 | 0%
2028-06-09 | 2028 | 6 | Jun | 9 | 5 | 1 | 28.67% | 7.9419 | 0%
2028-06-10 | 2028 | 6 | Jun | 10 | 6 | 0 | 28.67% | 7.9419 | 0%
2028-06-11 | 2028 | 6 | Jun | 11 | 7 | 0 | 28.67% | 7.9419 | 0%
2028-06-12 | 2028 | 6 | Jun | 12 | 1 | 1 | 28.67% | 7.9419 | 0%
2028-06-13 | 2028 | 6 | Jun | 13 | 2 | 1 | 28.67% | 7.9419 | 0%
2028-06-14 | 2028 | 6 | Jun | 14 | 3 | 1 | 28.67% | 7.9419 | 0%
2028-06-15 | 2028 | 6 | Jun | 15 | 4 | 1 | 28.67% | 7.9419 | 0%
2028-06-16 | 2028 | 6 | Jun | 16 | 5 | 1 | 28.67% | 7.9419 | 0%
2028-06-17 | 2028 | 6 | Jun | 17 | 6 | 0 | 28.67% | 7.9419 | 0%
2028-06-18 | 2028 | 6 | Jun | 18 | 7 | 0 | 28.67% | 7.9419 | 0%
2028-06-19 | 2028 | 6 | Jun | 19 | 1 | 1 | 28.67% | 7.9419 | 0%
2028-06-20 | 2028 | 6 | Jun | 20 | 2 | 1 | 28.67% | 7.9419 | 0%
2028-06-21 | 2028 | 6 | Jun | 21 | 3 | 1 | 28.67% | 7.9419 | 0%
2028-06-22 | 2028 | 6 | Jun | 22 | 4 | 1 | 28.67% | 7.9419 | 0%
2028-06-23 | 2028 | 6 | Jun | 23 | 5 | 1 | 28.67% | 7.9419 | 0%
2028-06-24 | 2028 | 6 | Jun | 24 | 6 | 0 | 28.67% | 7.9419 | 0%
2028-06-25 | 2028 | 6 | Jun | 25 | 7 | 0 | 28.67% | 7.9419 | 0%
2028-06-26 | 2028 | 6 | Jun | 26 | 1 | 1 | 28.67% | 7.9419 | 0%
2028-06-27 | 2028 | 6 | Jun | 27 | 2 | 1 | 28.67% | 7.9419 | 0%
2028-06-28 | 2028 | 6 | Jun | 28 | 3 | 1 | 28.67% | 7.9419 | 0%
2028-06-29 | 2028 | 6 | Jun | 29 | 4 | 1 | 28.67% | 7.9419 | 0%
2028-06-30 | 2028 | 6 | Jun | 30 | 5 | 1 | 28.67% | 7.9419 | 0%
2028-07-01 | 2028 | 7 | Jul | 1 | 6 | 0 | 24.73% | 8.3739 | 0%
2028-07-02 | 2028 | 7 | Jul | 2 | 7 | 0 | 24.73% | 8.3739 | 0%
2028-07-03 | 2028 | 7 | Jul | 3 | 1 | 1 | 24.73% | 8.3739 | 0%
2028-07-04 | 2028 | 7 | Jul | 4 | 2 | 1 | 24.73% | 8.3739 | 0%
2028-07-05 | 2028 | 7 | Jul | 5 | 3 | 1 | 24.73% | 8.3739 | 0%
2028-07-06 | 2028 | 7 | Jul | 6 | 4 | 1 | 24.73% | 8.3739 | 0%
2028-07-07 | 2028 | 7 | Jul | 7 | 5 | 1 | 24.73% | 8.3739 | 0%
2028-07-08 | 2028 | 7 | Jul | 8 | 6 | 0 | 24.73% | 8.3739 | 0%
2028-07-09 | 2028 | 7 | Jul | 9 | 7 | 0 | 24.73% | 8.3739 | 0%
2028-07-10 | 2028 | 7 | Jul | 10 | 1 | 1 | 24.73% | 8.3739 | 0%
2028-07-11 | 2028 | 7 | Jul | 11 | 2 | 1 | 24.73% | 8.3739 | 0%
2028-07-12 | 2028 | 7 | Jul | 12 | 3 | 1 | 24.73% | 8.3739 | 0%
2028-07-13 | 2028 | 7 | Jul | 13 | 4 | 1 | 24.73% | 8.3739 | 0%
2028-07-14 | 2028 | 7 | Jul | 14 | 5 | 1 | 24.73% | 8.3739 | 0%
2028-07-15 | 2028 | 7 | Jul | 15 | 6 | 0 | 24.73% | 8.3739 | 0%
2028-07-16 | 2028 | 7 | Jul | 16 | 7 | 0 | 24.73% | 8.3739 | 0%
2028-07-17 | 2028 | 7 | Jul | 17 | 1 | 1 | 24.73% | 8.3739 | 0%
2028-07-18 | 2028 | 7 | Jul | 18 | 2 | 1 | 24.73% | 8.3739 | 0%
2028-07-19 | 2028 | 7 | Jul | 19 | 3 | 1 | 24.73% | 8.3739 | 0%
2028-07-20 | 2028 | 7 | Jul | 20 | 4 | 1 | 24.73% | 8.3739 | 0%
2028-07-21 | 2028 | 7 | Jul | 21 | 5 | 1 | 24.73% | 8.3739 | 0%
2028-07-22 | 2028 | 7 | Jul | 22 | 6 | 0 | 24.73% | 8.3739 | 0%
2028-07-23 | 2028 | 7 | Jul | 23 | 7 | 0 | 24.73% | 8.3739 | 0%
2028-07-24 | 2028 | 7 | Jul | 24 | 1 | 1 | 24.73% | 8.3739 | 0%
2028-07-25 | 2028 | 7 | Jul | 25 | 2 | 1 | 24.73% | 8.3739 | 0%
2028-07-26 | 2028 | 7 | Jul | 26 | 3 | 1 | 24.73% | 8.3739 | 0%
2028-07-27 | 2028 | 7 | Jul | 27 | 4 | 1 | 24.73% | 8.3739 | 0%
2028-07-28 | 2028 | 7 | Jul | 28 | 5 | 1 | 24.73% | 8.3739 | 0%
2028-07-29 | 2028 | 7 | Jul | 29 | 6 | 0 | 24.73% | 8.3739 | 0%
2028-07-30 | 2028 | 7 | Jul | 30 | 7 | 0 | 24.73% | 8.3739 | 0%
2028-07-31 | 2028 | 7 | Jul | 31 | 1 | 1 | 24.73% | 8.3739 | 0%
2028-08-01 | 2028 | 8 | Aug | 1 | 2 | 1 | 23.55% | 7.9589 | 0%
2028-08-02 | 2028 | 8 | Aug | 2 | 3 | 1 | 23.55% | 7.9589 | 0%
2028-08-03 | 2028 | 8 | Aug | 3 | 4 | 1 | 23.55% | 7.9589 | 0%
2028-08-04 | 2028 | 8 | Aug | 4 | 5 | 1 | 23.55% | 7.9589 | 0%
2028-08-05 | 2028 | 8 | Aug | 5 | 6 | 0 | 23.55% | 7.9589 | 0%
2028-08-06 | 2028 | 8 | Aug | 6 | 7 | 0 | 23.55% | 7.9589 | 0%
2028-08-07 | 2028 | 8 | Aug | 7 | 1 | 1 | 23.55% | 7.9589 | 0%
2028-08-08 | 2028 | 8 | Aug | 8 | 2 | 1 | 23.55% | 7.9589 | 0%
2028-08-09 | 2028 | 8 | Aug | 9 | 3 | 1 | 23.55% | 7.9589 | 0%
2028-08-10 | 2028 | 8 | Aug | 10 | 4 | 1 | 23.55% | 7.9589 | 0%
2028-08-11 | 2028 | 8 | Aug | 11 | 5 | 1 | 23.55% | 7.9589 | 0%
2028-08-12 | 2028 | 8 | Aug | 12 | 6 | 0 | 23.55% | 7.9589 | 0%
2028-08-13 | 2028 | 8 | Aug | 13 | 7 | 0 | 23.55% | 7.9589 | 0%
2028-08-14 | 2028 | 8 | Aug | 14 | 1 | 1 | 23.55% | 7.9589 | 0%
2028-08-15 | 2028 | 8 | Aug | 15 | 2 | 1 | 23.55% | 7.9589 | 0%
2028-08-16 | 2028 | 8 | Aug | 16 | 3 | 1 | 23.55% | 7.9589 | 0%
2028-08-17 | 2028 | 8 | Aug | 17 | 4 | 1 | 23.55% | 7.9589 | 0%
2028-08-18 | 2028 | 8 | Aug | 18 | 5 | 1 | 23.55% | 7.9589 | 0%
2028-08-19 | 2028 | 8 | Aug | 19 | 6 | 0 | 23.55% | 7.9589 | 0%
2028-08-20 | 2028 | 8 | Aug | 20 | 7 | 0 | 23.55% | 7.9589 | 0%
2028-08-21 | 2028 | 8 | Aug | 21 | 1 | 1 | 23.55% | 7.9589 | 0%
2028-08-22 | 2028 | 8 | Aug | 22 | 2 | 1 | 23.55% | 7.9589 | 0%
2028-08-23 | 2028 | 8 | Aug | 23 | 3 | 1 | 23.55% | 7.9589 | 0%
2028-08-24 | 2028 | 8 | Aug | 24 | 4 | 1 | 23.55% | 7.9589 | 0%
2028-08-25 | 2028 | 8 | Aug | 25 | 5 | 1 | 23.55% | 7.9589 | 0%
2028-08-26 | 2028 | 8 | Aug | 26 | 6 | 0 | 23.55% | 7.9589 | 0%
2028-08-27 | 2028 | 8 | Aug | 27 | 7 | 0 | 23.55% | 7.9589 | 0%
2028-08-28 | 2028 | 8 | Aug | 28 | 1 | 1 | 23.55% | 7.9589 | 0%
2028-08-29 | 2028 | 8 | Aug | 29 | 2 | 1 | 23.55% | 7.9589 | 0%
2028-08-30 | 2028 | 8 | Aug | 30 | 3 | 1 | 23.55% | 7.9589 | 0%
2028-08-31 | 2028 | 8 | Aug | 31 | 4 | 1 | 23.55% | 7.9589 | 0%
2028-09-01 | 2028 | 9 | Sep | 1 | 5 | 1 | 20.67% | 6.8065 | 0%
2028-09-02 | 2028 | 9 | Sep | 2 | 6 | 0 | 20.67% | 6.8065 | 0%
2028-09-03 | 2028 | 9 | Sep | 3 | 7 | 0 | 20.67% | 6.8065 | 0%
2028-09-04 | 2028 | 9 | Sep | 4 | 1 | 1 | 20.67% | 6.8065 | 0%
2028-09-05 | 2028 | 9 | Sep | 5 | 2 | 1 | 20.67% | 6.8065 | 0%
2028-09-06 | 2028 | 9 | Sep | 6 | 3 | 1 | 20.67% | 6.8065 | 0%
2028-09-07 | 2028 | 9 | Sep | 7 | 4 | 1 | 20.67% | 6.8065 | 0%
2028-09-08 | 2028 | 9 | Sep | 8 | 5 | 1 | 20.67% | 6.8065 | 0%
2028-09-09 | 2028 | 9 | Sep | 9 | 6 | 0 | 20.67% | 6.8065 | 0%
2028-09-10 | 2028 | 9 | Sep | 10 | 7 | 0 | 20.67% | 6.8065 | 0%
2028-09-11 | 2028 | 9 | Sep | 11 | 1 | 1 | 20.67% | 6.8065 | 0%
2028-09-12 | 2028 | 9 | Sep | 12 | 2 | 1 | 20.67% | 6.8065 | 0%
2028-09-13 | 2028 | 9 | Sep | 13 | 3 | 1 | 20.67% | 6.8065 | 0%
2028-09-14 | 2028 | 9 | Sep | 14 | 4 | 1 | 20.67% | 6.8065 | 0%
2028-09-15 | 2028 | 9 | Sep | 15 | 5 | 1 | 20.67% | 6.8065 | 0%
2028-09-16 | 2028 | 9 | Sep | 16 | 6 | 0 | 20.67% | 6.8065 | 0%
2028-09-17 | 2028 | 9 | Sep | 17 | 7 | 0 | 20.67% | 6.8065 | 0%
2028-09-18 | 2028 | 9 | Sep | 18 | 1 | 1 | 20.67% | 6.8065 | 0%
2028-09-19 | 2028 | 9 | Sep | 19 | 2 | 1 | 20.67% | 6.8065 | 0%
2028-09-20 | 2028 | 9 | Sep | 20 | 3 | 1 | 20.67% | 6.8065 | 0%
2028-09-21 | 2028 | 9 | Sep | 21 | 4 | 1 | 20.67% | 6.8065 | 0%
2028-09-22 | 2028 | 9 | Sep | 22 | 5 | 1 | 20.67% | 6.8065 | 0%
2028-09-23 | 2028 | 9 | Sep | 23 | 6 | 0 | 20.67% | 6.8065 | 0%
2028-09-24 | 2028 | 9 | Sep | 24 | 7 | 0 | 20.67% | 6.8065 | 0%
2028-09-25 | 2028 | 9 | Sep | 25 | 1 | 1 | 20.67% | 6.8065 | 0%
2028-09-26 | 2028 | 9 | Sep | 26 | 2 | 1 | 20.67% | 6.8065 | 0%
2028-09-27 | 2028 | 9 | Sep | 27 | 3 | 1 | 20.67% | 6.8065 | 0%
2028-09-28 | 2028 | 9 | Sep | 28 | 4 | 1 | 20.67% | 6.8065 | 0%
2028-09-29 | 2028 | 9 | Sep | 29 | 5 | 1 | 20.67% | 6.8065 | 0%
2028-09-30 | 2028 | 9 | Sep | 30 | 6 | 0 | 20.67% | 6.8065 | 0%
2028-10-01 | 2028 | 10 | Oct | 1 | 7 | 0 | 23.23% | 6.8194 | 0%
2028-10-02 | 2028 | 10 | Oct | 2 | 1 | 1 | 23.23% | 6.8194 | 0%
2028-10-03 | 2028 | 10 | Oct | 3 | 2 | 1 | 23.23% | 6.8194 | 0%
2028-10-04 | 2028 | 10 | Oct | 4 | 3 | 1 | 23.23% | 6.8194 | 0%
2028-10-05 | 2028 | 10 | Oct | 5 | 4 | 1 | 23.23% | 6.8194 | 0%
2028-10-06 | 2028 | 10 | Oct | 6 | 5 | 1 | 23.23% | 6.8194 | 0%
2028-10-07 | 2028 | 10 | Oct | 7 | 6 | 0 | 23.23% | 6.8194 | 0%
2028-10-08 | 2028 | 10 | Oct | 8 | 7 | 0 | 23.23% | 6.8194 | 0%
2028-10-09 | 2028 | 10 | Oct | 9 | 1 | 1 | 23.23% | 6.8194 | 0%
2028-10-10 | 2028 | 10 | Oct | 10 | 2 | 1 | 23.23% | 6.8194 | 0%
2028-10-11 | 2028 | 10 | Oct | 11 | 3 | 1 | 23.23% | 6.8194 | 0%
2028-10-12 | 2028 | 10 | Oct | 12 | 4 | 1 | 23.23% | 6.8194 | 0%
2028-10-13 | 2028 | 10 | Oct | 13 | 5 | 1 | 23.23% | 6.8194 | 0%
2028-10-14 | 2028 | 10 | Oct | 14 | 6 | 0 | 23.23% | 6.8194 | 0%
2028-10-15 | 2028 | 10 | Oct | 15 | 7 | 0 | 23.23% | 6.8194 | 0%
2028-10-16 | 2028 | 10 | Oct | 16 | 1 | 1 | 23.23% | 6.8194 | 0%
2028-10-17 | 2028 | 10 | Oct | 17 | 2 | 1 | 23.23% | 6.8194 | 0%
2028-10-18 | 2028 | 10 | Oct | 18 | 3 | 1 | 23.23% | 6.8194 | 0%
2028-10-19 | 2028 | 10 | Oct | 19 | 4 | 1 | 23.23% | 6.8194 | 0%
2028-10-20 | 2028 | 10 | Oct | 20 | 5 | 1 | 23.23% | 6.8194 | 0%
2028-10-21 | 2028 | 10 | Oct | 21 | 6 | 0 | 23.23% | 6.8194 | 0%
2028-10-22 | 2028 | 10 | Oct | 22 | 7 | 0 | 23.23% | 6.8194 | 0%
2028-10-23 | 2028 | 10 | Oct | 23 | 1 | 1 | 23.23% | 6.8194 | 0%
2028-10-24 | 2028 | 10 | Oct | 24 | 2 | 1 | 23.23% | 6.8194 | 0%
2028-10-25 | 2028 | 10 | Oct | 25 | 3 | 1 | 23.23% | 6.8194 | 0%
2028-10-26 | 2028 | 10 | Oct | 26 | 4 | 1 | 23.23% | 6.8194 | 0%
2028-10-27 | 2028 | 10 | Oct | 27 | 5 | 1 | 23.23% | 6.8194 | 0%
2028-10-28 | 2028 | 10 | Oct | 28 | 6 | 0 | 23.23% | 6.8194 | 0%
2028-10-29 | 2028 | 10 | Oct | 29 | 7 | 0 | 23.23% | 6.8194 | 0%
2028-10-30 | 2028 | 10 | Oct | 30 | 1 | 1 | 23.23% | 6.8194 | 0%
2028-10-31 | 2028 | 10 | Oct | 31 | 2 | 1 | 23.23% | 6.8194 | 0%
2028-11-01 | 2028 | 11 | Nov | 1 | 3 | 1 | 23.33% | 6.4429 | 0%
2028-11-02 | 2028 | 11 | Nov | 2 | 4 | 1 | 23.33% | 6.4429 | 0%
2028-11-03 | 2028 | 11 | Nov | 3 | 5 | 1 | 23.33% | 6.4429 | 0%
2028-11-04 | 2028 | 11 | Nov | 4 | 6 | 0 | 23.33% | 6.4429 | 0%
2028-11-05 | 2028 | 11 | Nov | 5 | 7 | 0 | 23.33% | 6.4429 | 0%
2028-11-06 | 2028 | 11 | Nov | 6 | 1 | 1 | 23.33% | 6.4429 | 0%
2028-11-07 | 2028 | 11 | Nov | 7 | 2 | 1 | 23.33% | 6.4429 | 0%
2028-11-08 | 2028 | 11 | Nov | 8 | 3 | 1 | 23.33% | 6.4429 | 0%
2028-11-09 | 2028 | 11 | Nov | 9 | 4 | 1 | 23.33% | 6.4429 | 0%
2028-11-10 | 2028 | 11 | Nov | 10 | 5 | 1 | 23.33% | 6.4429 | 0%
2028-11-11 | 2028 | 11 | Nov | 11 | 6 | 0 | 23.33% | 6.4429 | 0%
2028-11-12 | 2028 | 11 | Nov | 12 | 7 | 0 | 23.33% | 6.4429 | 0%
2028-11-13 | 2028 | 11 | Nov | 13 | 1 | 1 | 23.33% | 6.4429 | 0%
2028-11-14 | 2028 | 11 | Nov | 14 | 2 | 1 | 23.33% | 6.4429 | 0%
2028-11-15 | 2028 | 11 | Nov | 15 | 3 | 1 | 23.33% | 6.4429 | 0%
2028-11-16 | 2028 | 11 | Nov | 16 | 4 | 1 | 23.33% | 6.4429 | 0%
2028-11-17 | 2028 | 11 | Nov | 17 | 5 | 1 | 23.33% | 6.4429 | 0%
2028-11-18 | 2028 | 11 | Nov | 18 | 6 | 0 | 23.33% | 6.4429 | 0%
2028-11-19 | 2028 | 11 | Nov | 19 | 7 | 0 | 23.33% | 6.4429 | 0%
2028-11-20 | 2028 | 11 | Nov | 20 | 1 | 1 | 23.33% | 6.4429 | 0%
2028-11-21 | 2028 | 11 | Nov | 21 | 2 | 1 | 23.33% | 6.4429 | 0%
2028-11-22 | 2028 | 11 | Nov | 22 | 3 | 1 | 23.33% | 6.4429 | 0%
2028-11-23 | 2028 | 11 | Nov | 23 | 4 | 1 | 23.33% | 6.4429 | 0%
2028-11-24 | 2028 | 11 | Nov | 24 | 5 | 1 | 23.33% | 6.4429 | 0%
2028-11-25 | 2028 | 11 | Nov | 25 | 6 | 0 | 23.33% | 6.4429 | 0%
2028-11-26 | 2028 | 11 | Nov | 26 | 7 | 0 | 23.33% | 6.4429 | 0%
2028-11-27 | 2028 | 11 | Nov | 27 | 1 | 1 | 23.33% | 6.4429 | 0%
2028-11-28 | 2028 | 11 | Nov | 28 | 2 | 1 | 23.33% | 6.4429 | 0%
2028-11-29 | 2028 | 11 | Nov | 29 | 3 | 1 | 23.33% | 6.4429 | 0%
2028-11-30 | 2028 | 11 | Nov | 30 | 4 | 1 | 23.33% | 6.4429 | 0%
2028-12-01 | 2028 | 12 | Dec | 1 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-12-02 | 2028 | 12 | Dec | 2 | 6 | 0 | 22.69% | 6.7962 | 0%
2028-12-03 | 2028 | 12 | Dec | 3 | 7 | 0 | 22.69% | 6.7962 | 0%
2028-12-04 | 2028 | 12 | Dec | 4 | 1 | 1 | 22.69% | 6.7962 | 0%
2028-12-05 | 2028 | 12 | Dec | 5 | 2 | 1 | 22.69% | 6.7962 | 0%
2028-12-06 | 2028 | 12 | Dec | 6 | 3 | 1 | 22.69% | 6.7962 | 0%
2028-12-07 | 2028 | 12 | Dec | 7 | 4 | 1 | 22.69% | 6.7962 | 0%
2028-12-08 | 2028 | 12 | Dec | 8 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-12-09 | 2028 | 12 | Dec | 9 | 6 | 0 | 22.69% | 6.7962 | 0%
2028-12-10 | 2028 | 12 | Dec | 10 | 7 | 0 | 22.69% | 6.7962 | 0%
2028-12-11 | 2028 | 12 | Dec | 11 | 1 | 1 | 22.69% | 6.7962 | 0%
2028-12-12 | 2028 | 12 | Dec | 12 | 2 | 1 | 22.69% | 6.7962 | 0%
2028-12-13 | 2028 | 12 | Dec | 13 | 3 | 1 | 22.69% | 6.7962 | 0%
2028-12-14 | 2028 | 12 | Dec | 14 | 4 | 1 | 22.69% | 6.7962 | 0%
2028-12-15 | 2028 | 12 | Dec | 15 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-12-16 | 2028 | 12 | Dec | 16 | 6 | 0 | 22.69% | 6.7962 | 0%
2028-12-17 | 2028 | 12 | Dec | 17 | 7 | 0 | 22.69% | 6.7962 | 0%
2028-12-18 | 2028 | 12 | Dec | 18 | 1 | 1 | 22.69% | 6.7962 | 0%
2028-12-19 | 2028 | 12 | Dec | 19 | 2 | 1 | 22.69% | 6.7962 | 0%
2028-12-20 | 2028 | 12 | Dec | 20 | 3 | 1 | 22.69% | 6.7962 | 0%
2028-12-21 | 2028 | 12 | Dec | 21 | 4 | 1 | 22.69% | 6.7962 | 0%
2028-12-22 | 2028 | 12 | Dec | 22 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-12-23 | 2028 | 12 | Dec | 23 | 6 | 0 | 22.69% | 6.7962 | 0%
2028-12-24 | 2028 | 12 | Dec | 24 | 7 | 0 | 22.69% | 6.7962 | 0%
2028-12-25 | 2028 | 12 | Dec | 25 | 1 | 1 | 22.69% | 6.7962 | 0%
2028-12-26 | 2028 | 12 | Dec | 26 | 2 | 1 | 22.69% | 6.7962 | 0%
2028-12-27 | 2028 | 12 | Dec | 27 | 3 | 1 | 22.69% | 6.7962 | 0%
2028-12-28 | 2028 | 12 | Dec | 28 | 4 | 1 | 22.69% | 6.7962 | 0%
2028-12-29 | 2028 | 12 | Dec | 29 | 5 | 1 | 22.69% | 6.7962 | 0%
2028-12-30 | 2028 | 12 | Dec | 30 | 6 | 0 | 22.69% | 6.7962 | 0%
2028-12-31 | 2028 | 12 | Dec | 31 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-01-01 | 2029 | 1 | Jan | 1 | 1 | 1 | 19.46% | 7.0276 | 0%
2029-01-02 | 2029 | 1 | Jan | 2 | 2 | 1 | 19.46% | 7.0276 | 0%
2029-01-03 | 2029 | 1 | Jan | 3 | 3 | 1 | 19.46% | 7.0276 | 0%
2029-01-04 | 2029 | 1 | Jan | 4 | 4 | 1 | 19.46% | 7.0276 | 0%
2029-01-05 | 2029 | 1 | Jan | 5 | 5 | 1 | 19.46% | 7.0276 | 0%
2029-01-06 | 2029 | 1 | Jan | 6 | 6 | 0 | 19.46% | 7.0276 | 0%
2029-01-07 | 2029 | 1 | Jan | 7 | 7 | 0 | 19.46% | 7.0276 | 0%
2029-01-08 | 2029 | 1 | Jan | 8 | 1 | 1 | 19.46% | 7.0276 | 0%
2029-01-09 | 2029 | 1 | Jan | 9 | 2 | 1 | 19.46% | 7.0276 | 0%
2029-01-10 | 2029 | 1 | Jan | 10 | 3 | 1 | 19.46% | 7.0276 | 0%
2029-01-11 | 2029 | 1 | Jan | 11 | 4 | 1 | 19.46% | 7.0276 | 0%
2029-01-12 | 2029 | 1 | Jan | 12 | 5 | 1 | 19.46% | 7.0276 | 0%
2029-01-13 | 2029 | 1 | Jan | 13 | 6 | 0 | 19.46% | 7.0276 | 0%
2029-01-14 | 2029 | 1 | Jan | 14 | 7 | 0 | 19.46% | 7.0276 | 0%
2029-01-15 | 2029 | 1 | Jan | 15 | 1 | 1 | 19.46% | 7.0276 | 0%
2029-01-16 | 2029 | 1 | Jan | 16 | 2 | 1 | 19.46% | 7.0276 | 0%
2029-01-17 | 2029 | 1 | Jan | 17 | 3 | 1 | 19.46% | 7.0276 | 0%
2029-01-18 | 2029 | 1 | Jan | 18 | 4 | 1 | 19.46% | 7.0276 | 0%
2029-01-19 | 2029 | 1 | Jan | 19 | 5 | 1 | 19.46% | 7.0276 | 0%
2029-01-20 | 2029 | 1 | Jan | 20 | 6 | 0 | 19.46% | 7.0276 | 0%
2029-01-21 | 2029 | 1 | Jan | 21 | 7 | 0 | 19.46% | 7.0276 | 0%
2029-01-22 | 2029 | 1 | Jan | 22 | 1 | 1 | 19.46% | 7.0276 | 0%
2029-01-23 | 2029 | 1 | Jan | 23 | 2 | 1 | 19.46% | 7.0276 | 0%
2029-01-24 | 2029 | 1 | Jan | 24 | 3 | 1 | 19.46% | 7.0276 | 0%
2029-01-25 | 2029 | 1 | Jan | 25 | 4 | 1 | 19.46% | 7.0276 | 0%
2029-01-26 | 2029 | 1 | Jan | 26 | 5 | 1 | 19.46% | 7.0276 | 0%
2029-01-27 | 2029 | 1 | Jan | 27 | 6 | 0 | 19.46% | 7.0276 | 0%
2029-01-28 | 2029 | 1 | Jan | 28 | 7 | 0 | 19.46% | 7.0276 | 0%
2029-01-29 | 2029 | 1 | Jan | 29 | 1 | 1 | 19.46% | 7.0276 | 0%
2029-01-30 | 2029 | 1 | Jan | 30 | 2 | 1 | 19.46% | 7.0276 | 0%
2029-01-31 | 2029 | 1 | Jan | 31 | 3 | 1 | 19.46% | 7.0276 | 0%
2029-02-01 | 2029 | 2 | Feb | 1 | 4 | 1 | 18.87% | 7.4625 | 0%
2029-02-02 | 2029 | 2 | Feb | 2 | 5 | 1 | 18.87% | 7.4625 | 0%
2029-02-03 | 2029 | 2 | Feb | 3 | 6 | 0 | 18.87% | 7.4625 | 0%
2029-02-04 | 2029 | 2 | Feb | 4 | 7 | 0 | 18.87% | 7.4625 | 0%
2029-02-05 | 2029 | 2 | Feb | 5 | 1 | 1 | 18.87% | 7.4625 | 0%
2029-02-06 | 2029 | 2 | Feb | 6 | 2 | 1 | 18.87% | 7.4625 | 0%
2029-02-07 | 2029 | 2 | Feb | 7 | 3 | 1 | 18.87% | 7.4625 | 0%
2029-02-08 | 2029 | 2 | Feb | 8 | 4 | 1 | 18.87% | 7.4625 | 0%
2029-02-09 | 2029 | 2 | Feb | 9 | 5 | 1 | 18.87% | 7.4625 | 0%
2029-02-10 | 2029 | 2 | Feb | 10 | 6 | 0 | 18.87% | 7.4625 | 0%
2029-02-11 | 2029 | 2 | Feb | 11 | 7 | 0 | 18.87% | 7.4625 | 0%
2029-02-12 | 2029 | 2 | Feb | 12 | 1 | 1 | 18.87% | 7.4625 | 0%
2029-02-13 | 2029 | 2 | Feb | 13 | 2 | 1 | 18.87% | 7.4625 | 0%
2029-02-14 | 2029 | 2 | Feb | 14 | 3 | 1 | 18.87% | 7.4625 | 0%
2029-02-15 | 2029 | 2 | Feb | 15 | 4 | 1 | 18.87% | 7.4625 | 0%
2029-02-16 | 2029 | 2 | Feb | 16 | 5 | 1 | 18.87% | 7.4625 | 0%
2029-02-17 | 2029 | 2 | Feb | 17 | 6 | 0 | 18.87% | 7.4625 | 0%
2029-02-18 | 2029 | 2 | Feb | 18 | 7 | 0 | 18.87% | 7.4625 | 0%
2029-02-19 | 2029 | 2 | Feb | 19 | 1 | 1 | 18.87% | 7.4625 | 0%
2029-02-20 | 2029 | 2 | Feb | 20 | 2 | 1 | 18.87% | 7.4625 | 0%
2029-02-21 | 2029 | 2 | Feb | 21 | 3 | 1 | 18.87% | 7.4625 | 0%
2029-02-22 | 2029 | 2 | Feb | 22 | 4 | 1 | 18.87% | 7.4625 | 0%
2029-02-23 | 2029 | 2 | Feb | 23 | 5 | 1 | 18.87% | 7.4625 | 0%
2029-02-24 | 2029 | 2 | Feb | 24 | 6 | 0 | 18.87% | 7.4625 | 0%
2029-02-25 | 2029 | 2 | Feb | 25 | 7 | 0 | 18.87% | 7.4625 | 0%
2029-02-26 | 2029 | 2 | Feb | 26 | 1 | 1 | 18.87% | 7.4625 | 0%
2029-02-27 | 2029 | 2 | Feb | 27 | 2 | 1 | 18.87% | 7.4625 | 0%
2029-02-28 | 2029 | 2 | Feb | 28 | 3 | 1 | 18.87% | 7.4625 | 0%
2029-03-01 | 2029 | 3 | Mar | 1 | 4 | 1 | 18.49% | 7.8663 | 0%
2029-03-02 | 2029 | 3 | Mar | 2 | 5 | 1 | 18.49% | 7.8663 | 0%
2029-03-03 | 2029 | 3 | Mar | 3 | 6 | 0 | 18.49% | 7.8663 | 0%
2029-03-04 | 2029 | 3 | Mar | 4 | 7 | 0 | 18.49% | 7.8663 | 0%
2029-03-05 | 2029 | 3 | Mar | 5 | 1 | 1 | 18.49% | 7.8663 | 0%
2029-03-06 | 2029 | 3 | Mar | 6 | 2 | 1 | 18.49% | 7.8663 | 0%
2029-03-07 | 2029 | 3 | Mar | 7 | 3 | 1 | 18.49% | 7.8663 | 0%
2029-03-08 | 2029 | 3 | Mar | 8 | 4 | 1 | 18.49% | 7.8663 | 0%
2029-03-09 | 2029 | 3 | Mar | 9 | 5 | 1 | 18.49% | 7.8663 | 0%
2029-03-10 | 2029 | 3 | Mar | 10 | 6 | 0 | 18.49% | 7.8663 | 0%
2029-03-11 | 2029 | 3 | Mar | 11 | 7 | 0 | 18.49% | 7.8663 | 0%
2029-03-12 | 2029 | 3 | Mar | 12 | 1 | 1 | 18.49% | 7.8663 | 0%
2029-03-13 | 2029 | 3 | Mar | 13 | 2 | 1 | 18.49% | 7.8663 | 0%
2029-03-14 | 2029 | 3 | Mar | 14 | 3 | 1 | 18.49% | 7.8663 | 0%
2029-03-15 | 2029 | 3 | Mar | 15 | 4 | 1 | 18.49% | 7.8663 | 0%
2029-03-16 | 2029 | 3 | Mar | 16 | 5 | 1 | 18.49% | 7.8663 | 0%
2029-03-17 | 2029 | 3 | Mar | 17 | 6 | 0 | 18.49% | 7.8663 | 0%
2029-03-18 | 2029 | 3 | Mar | 18 | 7 | 0 | 18.49% | 7.8663 | 0%
2029-03-19 | 2029 | 3 | Mar | 19 | 1 | 1 | 18.49% | 7.8663 | 0%
2029-03-20 | 2029 | 3 | Mar | 20 | 2 | 1 | 18.49% | 7.8663 | 0%
2029-03-21 | 2029 | 3 | Mar | 21 | 3 | 1 | 18.49% | 7.8663 | 0%
2029-03-22 | 2029 | 3 | Mar | 22 | 4 | 1 | 18.49% | 7.8663 | 0%
2029-03-23 | 2029 | 3 | Mar | 23 | 5 | 1 | 18.49% | 7.8663 | 0%
2029-03-24 | 2029 | 3 | Mar | 24 | 6 | 0 | 18.49% | 7.8663 | 0%
2029-03-25 | 2029 | 3 | Mar | 25 | 7 | 0 | 18.49% | 7.8663 | 0%
2029-03-26 | 2029 | 3 | Mar | 26 | 1 | 1 | 18.49% | 7.8663 | 0%
2029-03-27 | 2029 | 3 | Mar | 27 | 2 | 1 | 18.49% | 7.8663 | 0%
2029-03-28 | 2029 | 3 | Mar | 28 | 3 | 1 | 18.49% | 7.8663 | 0%
2029-03-29 | 2029 | 3 | Mar | 29 | 4 | 1 | 18.49% | 7.8663 | 0%
2029-03-30 | 2029 | 3 | Mar | 30 | 5 | 1 | 18.49% | 7.8663 | 0%
2029-03-31 | 2029 | 3 | Mar | 31 | 6 | 0 | 18.49% | 7.8663 | 0%
2029-04-01 | 2029 | 4 | Apr | 1 | 7 | 0 | 25.56% | 7.5 | 0%
2029-04-02 | 2029 | 4 | Apr | 2 | 1 | 1 | 25.56% | 7.5 | 0%
2029-04-03 | 2029 | 4 | Apr | 3 | 2 | 1 | 25.56% | 7.5 | 0%
2029-04-04 | 2029 | 4 | Apr | 4 | 3 | 1 | 25.56% | 7.5 | 0%
2029-04-05 | 2029 | 4 | Apr | 5 | 4 | 1 | 25.56% | 7.5 | 0%
2029-04-06 | 2029 | 4 | Apr | 6 | 5 | 1 | 25.56% | 7.5 | 0%
2029-04-07 | 2029 | 4 | Apr | 7 | 6 | 0 | 25.56% | 7.5 | 0%
2029-04-08 | 2029 | 4 | Apr | 8 | 7 | 0 | 25.56% | 7.5 | 0%
2029-04-09 | 2029 | 4 | Apr | 9 | 1 | 1 | 25.56% | 7.5 | 0%
2029-04-10 | 2029 | 4 | Apr | 10 | 2 | 1 | 25.56% | 7.5 | 0%
2029-04-11 | 2029 | 4 | Apr | 11 | 3 | 1 | 25.56% | 7.5 | 0%
2029-04-12 | 2029 | 4 | Apr | 12 | 4 | 1 | 25.56% | 7.5 | 0%
2029-04-13 | 2029 | 4 | Apr | 13 | 5 | 1 | 25.56% | 7.5 | 0%
2029-04-14 | 2029 | 4 | Apr | 14 | 6 | 0 | 25.56% | 7.5 | 0%
2029-04-15 | 2029 | 4 | Apr | 15 | 7 | 0 | 25.56% | 7.5 | 0%
2029-04-16 | 2029 | 4 | Apr | 16 | 1 | 1 | 25.56% | 7.5 | 0%
2029-04-17 | 2029 | 4 | Apr | 17 | 2 | 1 | 25.56% | 7.5 | 0%
2029-04-18 | 2029 | 4 | Apr | 18 | 3 | 1 | 25.56% | 7.5 | 0%
2029-04-19 | 2029 | 4 | Apr | 19 | 4 | 1 | 25.56% | 7.5 | 0%
2029-04-20 | 2029 | 4 | Apr | 20 | 5 | 1 | 25.56% | 7.5 | 0%
2029-04-21 | 2029 | 4 | Apr | 21 | 6 | 0 | 25.56% | 7.5 | 0%
2029-04-22 | 2029 | 4 | Apr | 22 | 7 | 0 | 25.56% | 7.5 | 0%
2029-04-23 | 2029 | 4 | Apr | 23 | 1 | 1 | 25.56% | 7.5 | 0%
2029-04-24 | 2029 | 4 | Apr | 24 | 2 | 1 | 25.56% | 7.5 | 0%
2029-04-25 | 2029 | 4 | Apr | 25 | 3 | 1 | 25.56% | 7.5 | 0%
2029-04-26 | 2029 | 4 | Apr | 26 | 4 | 1 | 25.56% | 7.5 | 0%
2029-04-27 | 2029 | 4 | Apr | 27 | 5 | 1 | 25.56% | 7.5 | 0%
2029-04-28 | 2029 | 4 | Apr | 28 | 6 | 0 | 25.56% | 7.5 | 0%
2029-04-29 | 2029 | 4 | Apr | 29 | 7 | 0 | 25.56% | 7.5 | 0%
2029-04-30 | 2029 | 4 | Apr | 30 | 1 | 1 | 25.56% | 7.5 | 0%
2029-05-01 | 2029 | 5 | May | 1 | 2 | 1 | 23.01% | 8.1449 | 0%
2029-05-02 | 2029 | 5 | May | 2 | 3 | 1 | 23.01% | 8.1449 | 0%
2029-05-03 | 2029 | 5 | May | 3 | 4 | 1 | 23.01% | 8.1449 | 0%
2029-05-04 | 2029 | 5 | May | 4 | 5 | 1 | 23.01% | 8.1449 | 0%
2029-05-05 | 2029 | 5 | May | 5 | 6 | 0 | 23.01% | 8.1449 | 0%
2029-05-06 | 2029 | 5 | May | 6 | 7 | 0 | 23.01% | 8.1449 | 0%
2029-05-07 | 2029 | 5 | May | 7 | 1 | 1 | 23.01% | 8.1449 | 0%
2029-05-08 | 2029 | 5 | May | 8 | 2 | 1 | 23.01% | 8.1449 | 0%
2029-05-09 | 2029 | 5 | May | 9 | 3 | 1 | 23.01% | 8.1449 | 0%
2029-05-10 | 2029 | 5 | May | 10 | 4 | 1 | 23.01% | 8.1449 | 0%
2029-05-11 | 2029 | 5 | May | 11 | 5 | 1 | 23.01% | 8.1449 | 0%
2029-05-12 | 2029 | 5 | May | 12 | 6 | 0 | 23.01% | 8.1449 | 0%
2029-05-13 | 2029 | 5 | May | 13 | 7 | 0 | 23.01% | 8.1449 | 0%
2029-05-14 | 2029 | 5 | May | 14 | 1 | 1 | 23.01% | 8.1449 | 0%
2029-05-15 | 2029 | 5 | May | 15 | 2 | 1 | 23.01% | 8.1449 | 0%
2029-05-16 | 2029 | 5 | May | 16 | 3 | 1 | 23.01% | 8.1449 | 0%
2029-05-17 | 2029 | 5 | May | 17 | 4 | 1 | 23.01% | 8.1449 | 0%
2029-05-18 | 2029 | 5 | May | 18 | 5 | 1 | 23.01% | 8.1449 | 0%
2029-05-19 | 2029 | 5 | May | 19 | 6 | 0 | 23.01% | 8.1449 | 0%
2029-05-20 | 2029 | 5 | May | 20 | 7 | 0 | 23.01% | 8.1449 | 0%
2029-05-21 | 2029 | 5 | May | 21 | 1 | 1 | 23.01% | 8.1449 | 0%
2029-05-22 | 2029 | 5 | May | 22 | 2 | 1 | 23.01% | 8.1449 | 0%
2029-05-23 | 2029 | 5 | May | 23 | 3 | 1 | 23.01% | 8.1449 | 0%
2029-05-24 | 2029 | 5 | May | 24 | 4 | 1 | 23.01% | 8.1449 | 0%
2029-05-25 | 2029 | 5 | May | 25 | 5 | 1 | 23.01% | 8.1449 | 0%
2029-05-26 | 2029 | 5 | May | 26 | 6 | 0 | 23.01% | 8.1449 | 0%
2029-05-27 | 2029 | 5 | May | 27 | 7 | 0 | 23.01% | 8.1449 | 0%
2029-05-28 | 2029 | 5 | May | 28 | 1 | 1 | 23.01% | 8.1449 | 0%
2029-05-29 | 2029 | 5 | May | 29 | 2 | 1 | 23.01% | 8.1449 | 0%
2029-05-30 | 2029 | 5 | May | 30 | 3 | 1 | 23.01% | 8.1449 | 0%
2029-05-31 | 2029 | 5 | May | 31 | 4 | 1 | 23.01% | 8.1449 | 0%
2029-06-01 | 2029 | 6 | Jun | 1 | 5 | 1 | 28.67% | 7.9419 | 0%
2029-06-02 | 2029 | 6 | Jun | 2 | 6 | 0 | 28.67% | 7.9419 | 0%
2029-06-03 | 2029 | 6 | Jun | 3 | 7 | 0 | 28.67% | 7.9419 | 0%
2029-06-04 | 2029 | 6 | Jun | 4 | 1 | 1 | 28.67% | 7.9419 | 0%
2029-06-05 | 2029 | 6 | Jun | 5 | 2 | 1 | 28.67% | 7.9419 | 0%
2029-06-06 | 2029 | 6 | Jun | 6 | 3 | 1 | 28.67% | 7.9419 | 0%
2029-06-07 | 2029 | 6 | Jun | 7 | 4 | 1 | 28.67% | 7.9419 | 0%
2029-06-08 | 2029 | 6 | Jun | 8 | 5 | 1 | 28.67% | 7.9419 | 0%
2029-06-09 | 2029 | 6 | Jun | 9 | 6 | 0 | 28.67% | 7.9419 | 0%
2029-06-10 | 2029 | 6 | Jun | 10 | 7 | 0 | 28.67% | 7.9419 | 0%
2029-06-11 | 2029 | 6 | Jun | 11 | 1 | 1 | 28.67% | 7.9419 | 0%
2029-06-12 | 2029 | 6 | Jun | 12 | 2 | 1 | 28.67% | 7.9419 | 0%
2029-06-13 | 2029 | 6 | Jun | 13 | 3 | 1 | 28.67% | 7.9419 | 0%
2029-06-14 | 2029 | 6 | Jun | 14 | 4 | 1 | 28.67% | 7.9419 | 0%
2029-06-15 | 2029 | 6 | Jun | 15 | 5 | 1 | 28.67% | 7.9419 | 0%
2029-06-16 | 2029 | 6 | Jun | 16 | 6 | 0 | 28.67% | 7.9419 | 0%
2029-06-17 | 2029 | 6 | Jun | 17 | 7 | 0 | 28.67% | 7.9419 | 0%
2029-06-18 | 2029 | 6 | Jun | 18 | 1 | 1 | 28.67% | 7.9419 | 0%
2029-06-19 | 2029 | 6 | Jun | 19 | 2 | 1 | 28.67% | 7.9419 | 0%
2029-06-20 | 2029 | 6 | Jun | 20 | 3 | 1 | 28.67% | 7.9419 | 0%
2029-06-21 | 2029 | 6 | Jun | 21 | 4 | 1 | 28.67% | 7.9419 | 0%
2029-06-22 | 2029 | 6 | Jun | 22 | 5 | 1 | 28.67% | 7.9419 | 0%
2029-06-23 | 2029 | 6 | Jun | 23 | 6 | 0 | 28.67% | 7.9419 | 0%
2029-06-24 | 2029 | 6 | Jun | 24 | 7 | 0 | 28.67% | 7.9419 | 0%
2029-06-25 | 2029 | 6 | Jun | 25 | 1 | 1 | 28.67% | 7.9419 | 0%
2029-06-26 | 2029 | 6 | Jun | 26 | 2 | 1 | 28.67% | 7.9419 | 0%
2029-06-27 | 2029 | 6 | Jun | 27 | 3 | 1 | 28.67% | 7.9419 | 0%
2029-06-28 | 2029 | 6 | Jun | 28 | 4 | 1 | 28.67% | 7.9419 | 0%
2029-06-29 | 2029 | 6 | Jun | 29 | 5 | 1 | 28.67% | 7.9419 | 0%
2029-06-30 | 2029 | 6 | Jun | 30 | 6 | 0 | 28.67% | 7.9419 | 0%
2029-07-01 | 2029 | 7 | Jul | 1 | 7 | 0 | 24.73% | 8.3739 | 0%
2029-07-02 | 2029 | 7 | Jul | 2 | 1 | 1 | 24.73% | 8.3739 | 0%
2029-07-03 | 2029 | 7 | Jul | 3 | 2 | 1 | 24.73% | 8.3739 | 0%
2029-07-04 | 2029 | 7 | Jul | 4 | 3 | 1 | 24.73% | 8.3739 | 0%
2029-07-05 | 2029 | 7 | Jul | 5 | 4 | 1 | 24.73% | 8.3739 | 0%
2029-07-06 | 2029 | 7 | Jul | 6 | 5 | 1 | 24.73% | 8.3739 | 0%
2029-07-07 | 2029 | 7 | Jul | 7 | 6 | 0 | 24.73% | 8.3739 | 0%
2029-07-08 | 2029 | 7 | Jul | 8 | 7 | 0 | 24.73% | 8.3739 | 0%
2029-07-09 | 2029 | 7 | Jul | 9 | 1 | 1 | 24.73% | 8.3739 | 0%
2029-07-10 | 2029 | 7 | Jul | 10 | 2 | 1 | 24.73% | 8.3739 | 0%
2029-07-11 | 2029 | 7 | Jul | 11 | 3 | 1 | 24.73% | 8.3739 | 0%
2029-07-12 | 2029 | 7 | Jul | 12 | 4 | 1 | 24.73% | 8.3739 | 0%
2029-07-13 | 2029 | 7 | Jul | 13 | 5 | 1 | 24.73% | 8.3739 | 0%
2029-07-14 | 2029 | 7 | Jul | 14 | 6 | 0 | 24.73% | 8.3739 | 0%
2029-07-15 | 2029 | 7 | Jul | 15 | 7 | 0 | 24.73% | 8.3739 | 0%
2029-07-16 | 2029 | 7 | Jul | 16 | 1 | 1 | 24.73% | 8.3739 | 0%
2029-07-17 | 2029 | 7 | Jul | 17 | 2 | 1 | 24.73% | 8.3739 | 0%
2029-07-18 | 2029 | 7 | Jul | 18 | 3 | 1 | 24.73% | 8.3739 | 0%
2029-07-19 | 2029 | 7 | Jul | 19 | 4 | 1 | 24.73% | 8.3739 | 0%
2029-07-20 | 2029 | 7 | Jul | 20 | 5 | 1 | 24.73% | 8.3739 | 0%
2029-07-21 | 2029 | 7 | Jul | 21 | 6 | 0 | 24.73% | 8.3739 | 0%
2029-07-22 | 2029 | 7 | Jul | 22 | 7 | 0 | 24.73% | 8.3739 | 0%
2029-07-23 | 2029 | 7 | Jul | 23 | 1 | 1 | 24.73% | 8.3739 | 0%
2029-07-24 | 2029 | 7 | Jul | 24 | 2 | 1 | 24.73% | 8.3739 | 0%
2029-07-25 | 2029 | 7 | Jul | 25 | 3 | 1 | 24.73% | 8.3739 | 0%
2029-07-26 | 2029 | 7 | Jul | 26 | 4 | 1 | 24.73% | 8.3739 | 0%
2029-07-27 | 2029 | 7 | Jul | 27 | 5 | 1 | 24.73% | 8.3739 | 0%
2029-07-28 | 2029 | 7 | Jul | 28 | 6 | 0 | 24.73% | 8.3739 | 0%
2029-07-29 | 2029 | 7 | Jul | 29 | 7 | 0 | 24.73% | 8.3739 | 0%
2029-07-30 | 2029 | 7 | Jul | 30 | 1 | 1 | 24.73% | 8.3739 | 0%
2029-07-31 | 2029 | 7 | Jul | 31 | 2 | 1 | 24.73% | 8.3739 | 0%
2029-08-01 | 2029 | 8 | Aug | 1 | 3 | 1 | 23.55% | 7.9589 | 0%
2029-08-02 | 2029 | 8 | Aug | 2 | 4 | 1 | 23.55% | 7.9589 | 0%
2029-08-03 | 2029 | 8 | Aug | 3 | 5 | 1 | 23.55% | 7.9589 | 0%
2029-08-04 | 2029 | 8 | Aug | 4 | 6 | 0 | 23.55% | 7.9589 | 0%
2029-08-05 | 2029 | 8 | Aug | 5 | 7 | 0 | 23.55% | 7.9589 | 0%
2029-08-06 | 2029 | 8 | Aug | 6 | 1 | 1 | 23.55% | 7.9589 | 0%
2029-08-07 | 2029 | 8 | Aug | 7 | 2 | 1 | 23.55% | 7.9589 | 0%
2029-08-08 | 2029 | 8 | Aug | 8 | 3 | 1 | 23.55% | 7.9589 | 0%
2029-08-09 | 2029 | 8 | Aug | 9 | 4 | 1 | 23.55% | 7.9589 | 0%
2029-08-10 | 2029 | 8 | Aug | 10 | 5 | 1 | 23.55% | 7.9589 | 0%
2029-08-11 | 2029 | 8 | Aug | 11 | 6 | 0 | 23.55% | 7.9589 | 0%
2029-08-12 | 2029 | 8 | Aug | 12 | 7 | 0 | 23.55% | 7.9589 | 0%
2029-08-13 | 2029 | 8 | Aug | 13 | 1 | 1 | 23.55% | 7.9589 | 0%
2029-08-14 | 2029 | 8 | Aug | 14 | 2 | 1 | 23.55% | 7.9589 | 0%
2029-08-15 | 2029 | 8 | Aug | 15 | 3 | 1 | 23.55% | 7.9589 | 0%
2029-08-16 | 2029 | 8 | Aug | 16 | 4 | 1 | 23.55% | 7.9589 | 0%
2029-08-17 | 2029 | 8 | Aug | 17 | 5 | 1 | 23.55% | 7.9589 | 0%
2029-08-18 | 2029 | 8 | Aug | 18 | 6 | 0 | 23.55% | 7.9589 | 0%
2029-08-19 | 2029 | 8 | Aug | 19 | 7 | 0 | 23.55% | 7.9589 | 0%
2029-08-20 | 2029 | 8 | Aug | 20 | 1 | 1 | 23.55% | 7.9589 | 0%
2029-08-21 | 2029 | 8 | Aug | 21 | 2 | 1 | 23.55% | 7.9589 | 0%
2029-08-22 | 2029 | 8 | Aug | 22 | 3 | 1 | 23.55% | 7.9589 | 0%
2029-08-23 | 2029 | 8 | Aug | 23 | 4 | 1 | 23.55% | 7.9589 | 0%
2029-08-24 | 2029 | 8 | Aug | 24 | 5 | 1 | 23.55% | 7.9589 | 0%
2029-08-25 | 2029 | 8 | Aug | 25 | 6 | 0 | 23.55% | 7.9589 | 0%
2029-08-26 | 2029 | 8 | Aug | 26 | 7 | 0 | 23.55% | 7.9589 | 0%
2029-08-27 | 2029 | 8 | Aug | 27 | 1 | 1 | 23.55% | 7.9589 | 0%
2029-08-28 | 2029 | 8 | Aug | 28 | 2 | 1 | 23.55% | 7.9589 | 0%
2029-08-29 | 2029 | 8 | Aug | 29 | 3 | 1 | 23.55% | 7.9589 | 0%
2029-08-30 | 2029 | 8 | Aug | 30 | 4 | 1 | 23.55% | 7.9589 | 0%
2029-08-31 | 2029 | 8 | Aug | 31 | 5 | 1 | 23.55% | 7.9589 | 0%
2029-09-01 | 2029 | 9 | Sep | 1 | 6 | 0 | 20.67% | 6.8065 | 0%
2029-09-02 | 2029 | 9 | Sep | 2 | 7 | 0 | 20.67% | 6.8065 | 0%
2029-09-03 | 2029 | 9 | Sep | 3 | 1 | 1 | 20.67% | 6.8065 | 0%
2029-09-04 | 2029 | 9 | Sep | 4 | 2 | 1 | 20.67% | 6.8065 | 0%
2029-09-05 | 2029 | 9 | Sep | 5 | 3 | 1 | 20.67% | 6.8065 | 0%
2029-09-06 | 2029 | 9 | Sep | 6 | 4 | 1 | 20.67% | 6.8065 | 0%
2029-09-07 | 2029 | 9 | Sep | 7 | 5 | 1 | 20.67% | 6.8065 | 0%
2029-09-08 | 2029 | 9 | Sep | 8 | 6 | 0 | 20.67% | 6.8065 | 0%
2029-09-09 | 2029 | 9 | Sep | 9 | 7 | 0 | 20.67% | 6.8065 | 0%
2029-09-10 | 2029 | 9 | Sep | 10 | 1 | 1 | 20.67% | 6.8065 | 0%
2029-09-11 | 2029 | 9 | Sep | 11 | 2 | 1 | 20.67% | 6.8065 | 0%
2029-09-12 | 2029 | 9 | Sep | 12 | 3 | 1 | 20.67% | 6.8065 | 0%
2029-09-13 | 2029 | 9 | Sep | 13 | 4 | 1 | 20.67% | 6.8065 | 0%
2029-09-14 | 2029 | 9 | Sep | 14 | 5 | 1 | 20.67% | 6.8065 | 0%
2029-09-15 | 2029 | 9 | Sep | 15 | 6 | 0 | 20.67% | 6.8065 | 0%
2029-09-16 | 2029 | 9 | Sep | 16 | 7 | 0 | 20.67% | 6.8065 | 0%
2029-09-17 | 2029 | 9 | Sep | 17 | 1 | 1 | 20.67% | 6.8065 | 0%
2029-09-18 | 2029 | 9 | Sep | 18 | 2 | 1 | 20.67% | 6.8065 | 0%
2029-09-19 | 2029 | 9 | Sep | 19 | 3 | 1 | 20.67% | 6.8065 | 0%
2029-09-20 | 2029 | 9 | Sep | 20 | 4 | 1 | 20.67% | 6.8065 | 0%
2029-09-21 | 2029 | 9 | Sep | 21 | 5 | 1 | 20.67% | 6.8065 | 0%
2029-09-22 | 2029 | 9 | Sep | 22 | 6 | 0 | 20.67% | 6.8065 | 0%
2029-09-23 | 2029 | 9 | Sep | 23 | 7 | 0 | 20.67% | 6.8065 | 0%
2029-09-24 | 2029 | 9 | Sep | 24 | 1 | 1 | 20.67% | 6.8065 | 0%
2029-09-25 | 2029 | 9 | Sep | 25 | 2 | 1 | 20.67% | 6.8065 | 0%
2029-09-26 | 2029 | 9 | Sep | 26 | 3 | 1 | 20.67% | 6.8065 | 0%
2029-09-27 | 2029 | 9 | Sep | 27 | 4 | 1 | 20.67% | 6.8065 | 0%
2029-09-28 | 2029 | 9 | Sep | 28 | 5 | 1 | 20.67% | 6.8065 | 0%
2029-09-29 | 2029 | 9 | Sep | 29 | 6 | 0 | 20.67% | 6.8065 | 0%
2029-09-30 | 2029 | 9 | Sep | 30 | 7 | 0 | 20.67% | 6.8065 | 0%
2029-10-01 | 2029 | 10 | Oct | 1 | 1 | 1 | 23.23% | 6.8194 | 0%
2029-10-02 | 2029 | 10 | Oct | 2 | 2 | 1 | 23.23% | 6.8194 | 0%
2029-10-03 | 2029 | 10 | Oct | 3 | 3 | 1 | 23.23% | 6.8194 | 0%
2029-10-04 | 2029 | 10 | Oct | 4 | 4 | 1 | 23.23% | 6.8194 | 0%
2029-10-05 | 2029 | 10 | Oct | 5 | 5 | 1 | 23.23% | 6.8194 | 0%
2029-10-06 | 2029 | 10 | Oct | 6 | 6 | 0 | 23.23% | 6.8194 | 0%
2029-10-07 | 2029 | 10 | Oct | 7 | 7 | 0 | 23.23% | 6.8194 | 0%
2029-10-08 | 2029 | 10 | Oct | 8 | 1 | 1 | 23.23% | 6.8194 | 0%
2029-10-09 | 2029 | 10 | Oct | 9 | 2 | 1 | 23.23% | 6.8194 | 0%
2029-10-10 | 2029 | 10 | Oct | 10 | 3 | 1 | 23.23% | 6.8194 | 0%
2029-10-11 | 2029 | 10 | Oct | 11 | 4 | 1 | 23.23% | 6.8194 | 0%
2029-10-12 | 2029 | 10 | Oct | 12 | 5 | 1 | 23.23% | 6.8194 | 0%
2029-10-13 | 2029 | 10 | Oct | 13 | 6 | 0 | 23.23% | 6.8194 | 0%
2029-10-14 | 2029 | 10 | Oct | 14 | 7 | 0 | 23.23% | 6.8194 | 0%
2029-10-15 | 2029 | 10 | Oct | 15 | 1 | 1 | 23.23% | 6.8194 | 0%
2029-10-16 | 2029 | 10 | Oct | 16 | 2 | 1 | 23.23% | 6.8194 | 0%
2029-10-17 | 2029 | 10 | Oct | 17 | 3 | 1 | 23.23% | 6.8194 | 0%
2029-10-18 | 2029 | 10 | Oct | 18 | 4 | 1 | 23.23% | 6.8194 | 0%
2029-10-19 | 2029 | 10 | Oct | 19 | 5 | 1 | 23.23% | 6.8194 | 0%
2029-10-20 | 2029 | 10 | Oct | 20 | 6 | 0 | 23.23% | 6.8194 | 0%
2029-10-21 | 2029 | 10 | Oct | 21 | 7 | 0 | 23.23% | 6.8194 | 0%
2029-10-22 | 2029 | 10 | Oct | 22 | 1 | 1 | 23.23% | 6.8194 | 0%
2029-10-23 | 2029 | 10 | Oct | 23 | 2 | 1 | 23.23% | 6.8194 | 0%
2029-10-24 | 2029 | 10 | Oct | 24 | 3 | 1 | 23.23% | 6.8194 | 0%
2029-10-25 | 2029 | 10 | Oct | 25 | 4 | 1 | 23.23% | 6.8194 | 0%
2029-10-26 | 2029 | 10 | Oct | 26 | 5 | 1 | 23.23% | 6.8194 | 0%
2029-10-27 | 2029 | 10 | Oct | 27 | 6 | 0 | 23.23% | 6.8194 | 0%
2029-10-28 | 2029 | 10 | Oct | 28 | 7 | 0 | 23.23% | 6.8194 | 0%
2029-10-29 | 2029 | 10 | Oct | 29 | 1 | 1 | 23.23% | 6.8194 | 0%
2029-10-30 | 2029 | 10 | Oct | 30 | 2 | 1 | 23.23% | 6.8194 | 0%
2029-10-31 | 2029 | 10 | Oct | 31 | 3 | 1 | 23.23% | 6.8194 | 0%
2029-11-01 | 2029 | 11 | Nov | 1 | 4 | 1 | 23.33% | 6.4429 | 0%
2029-11-02 | 2029 | 11 | Nov | 2 | 5 | 1 | 23.33% | 6.4429 | 0%
2029-11-03 | 2029 | 11 | Nov | 3 | 6 | 0 | 23.33% | 6.4429 | 0%
2029-11-04 | 2029 | 11 | Nov | 4 | 7 | 0 | 23.33% | 6.4429 | 0%
2029-11-05 | 2029 | 11 | Nov | 5 | 1 | 1 | 23.33% | 6.4429 | 0%
2029-11-06 | 2029 | 11 | Nov | 6 | 2 | 1 | 23.33% | 6.4429 | 0%
2029-11-07 | 2029 | 11 | Nov | 7 | 3 | 1 | 23.33% | 6.4429 | 0%
2029-11-08 | 2029 | 11 | Nov | 8 | 4 | 1 | 23.33% | 6.4429 | 0%
2029-11-09 | 2029 | 11 | Nov | 9 | 5 | 1 | 23.33% | 6.4429 | 0%
2029-11-10 | 2029 | 11 | Nov | 10 | 6 | 0 | 23.33% | 6.4429 | 0%
2029-11-11 | 2029 | 11 | Nov | 11 | 7 | 0 | 23.33% | 6.4429 | 0%
2029-11-12 | 2029 | 11 | Nov | 12 | 1 | 1 | 23.33% | 6.4429 | 0%
2029-11-13 | 2029 | 11 | Nov | 13 | 2 | 1 | 23.33% | 6.4429 | 0%
2029-11-14 | 2029 | 11 | Nov | 14 | 3 | 1 | 23.33% | 6.4429 | 0%
2029-11-15 | 2029 | 11 | Nov | 15 | 4 | 1 | 23.33% | 6.4429 | 0%
2029-11-16 | 2029 | 11 | Nov | 16 | 5 | 1 | 23.33% | 6.4429 | 0%
2029-11-17 | 2029 | 11 | Nov | 17 | 6 | 0 | 23.33% | 6.4429 | 0%
2029-11-18 | 2029 | 11 | Nov | 18 | 7 | 0 | 23.33% | 6.4429 | 0%
2029-11-19 | 2029 | 11 | Nov | 19 | 1 | 1 | 23.33% | 6.4429 | 0%
2029-11-20 | 2029 | 11 | Nov | 20 | 2 | 1 | 23.33% | 6.4429 | 0%
2029-11-21 | 2029 | 11 | Nov | 21 | 3 | 1 | 23.33% | 6.4429 | 0%
2029-11-22 | 2029 | 11 | Nov | 22 | 4 | 1 | 23.33% | 6.4429 | 0%
2029-11-23 | 2029 | 11 | Nov | 23 | 5 | 1 | 23.33% | 6.4429 | 0%
2029-11-24 | 2029 | 11 | Nov | 24 | 6 | 0 | 23.33% | 6.4429 | 0%
2029-11-25 | 2029 | 11 | Nov | 25 | 7 | 0 | 23.33% | 6.4429 | 0%
2029-11-26 | 2029 | 11 | Nov | 26 | 1 | 1 | 23.33% | 6.4429 | 0%
2029-11-27 | 2029 | 11 | Nov | 27 | 2 | 1 | 23.33% | 6.4429 | 0%
2029-11-28 | 2029 | 11 | Nov | 28 | 3 | 1 | 23.33% | 6.4429 | 0%
2029-11-29 | 2029 | 11 | Nov | 29 | 4 | 1 | 23.33% | 6.4429 | 0%
2029-11-30 | 2029 | 11 | Nov | 30 | 5 | 1 | 23.33% | 6.4429 | 0%
2029-12-01 | 2029 | 12 | Dec | 1 | 6 | 0 | 22.69% | 6.7962 | 0%
2029-12-02 | 2029 | 12 | Dec | 2 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-12-03 | 2029 | 12 | Dec | 3 | 1 | 1 | 22.69% | 6.7962 | 0%
2029-12-04 | 2029 | 12 | Dec | 4 | 2 | 1 | 22.69% | 6.7962 | 0%
2029-12-05 | 2029 | 12 | Dec | 5 | 3 | 1 | 22.69% | 6.7962 | 0%
2029-12-06 | 2029 | 12 | Dec | 6 | 4 | 1 | 22.69% | 6.7962 | 0%
2029-12-07 | 2029 | 12 | Dec | 7 | 5 | 1 | 22.69% | 6.7962 | 0%
2029-12-08 | 2029 | 12 | Dec | 8 | 6 | 0 | 22.69% | 6.7962 | 0%
2029-12-09 | 2029 | 12 | Dec | 9 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-12-10 | 2029 | 12 | Dec | 10 | 1 | 1 | 22.69% | 6.7962 | 0%
2029-12-11 | 2029 | 12 | Dec | 11 | 2 | 1 | 22.69% | 6.7962 | 0%
2029-12-12 | 2029 | 12 | Dec | 12 | 3 | 1 | 22.69% | 6.7962 | 0%
2029-12-13 | 2029 | 12 | Dec | 13 | 4 | 1 | 22.69% | 6.7962 | 0%
2029-12-14 | 2029 | 12 | Dec | 14 | 5 | 1 | 22.69% | 6.7962 | 0%
2029-12-15 | 2029 | 12 | Dec | 15 | 6 | 0 | 22.69% | 6.7962 | 0%
2029-12-16 | 2029 | 12 | Dec | 16 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-12-17 | 2029 | 12 | Dec | 17 | 1 | 1 | 22.69% | 6.7962 | 0%
2029-12-18 | 2029 | 12 | Dec | 18 | 2 | 1 | 22.69% | 6.7962 | 0%
2029-12-19 | 2029 | 12 | Dec | 19 | 3 | 1 | 22.69% | 6.7962 | 0%
2029-12-20 | 2029 | 12 | Dec | 20 | 4 | 1 | 22.69% | 6.7962 | 0%
2029-12-21 | 2029 | 12 | Dec | 21 | 5 | 1 | 22.69% | 6.7962 | 0%
2029-12-22 | 2029 | 12 | Dec | 22 | 6 | 0 | 22.69% | 6.7962 | 0%
2029-12-23 | 2029 | 12 | Dec | 23 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-12-24 | 2029 | 12 | Dec | 24 | 1 | 1 | 22.69% | 6.7962 | 0%
2029-12-25 | 2029 | 12 | Dec | 25 | 2 | 1 | 22.69% | 6.7962 | 0%
2029-12-26 | 2029 | 12 | Dec | 26 | 3 | 1 | 22.69% | 6.7962 | 0%
2029-12-27 | 2029 | 12 | Dec | 27 | 4 | 1 | 22.69% | 6.7962 | 0%
2029-12-28 | 2029 | 12 | Dec | 28 | 5 | 1 | 22.69% | 6.7962 | 0%
2029-12-29 | 2029 | 12 | Dec | 29 | 6 | 0 | 22.69% | 6.7962 | 0%
2029-12-30 | 2029 | 12 | Dec | 30 | 7 | 0 | 22.69% | 6.7962 | 0%
2029-12-31 | 2029 | 12 | Dec | 31 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-01-01 | 2030 | 1 | Jan | 1 | 2 | 1 | 19.46% | 7.0276 | 0%
2030-01-02 | 2030 | 1 | Jan | 2 | 3 | 1 | 19.46% | 7.0276 | 0%
2030-01-03 | 2030 | 1 | Jan | 3 | 4 | 1 | 19.46% | 7.0276 | 0%
2030-01-04 | 2030 | 1 | Jan | 4 | 5 | 1 | 19.46% | 7.0276 | 0%
2030-01-05 | 2030 | 1 | Jan | 5 | 6 | 0 | 19.46% | 7.0276 | 0%
2030-01-06 | 2030 | 1 | Jan | 6 | 7 | 0 | 19.46% | 7.0276 | 0%
2030-01-07 | 2030 | 1 | Jan | 7 | 1 | 1 | 19.46% | 7.0276 | 0%
2030-01-08 | 2030 | 1 | Jan | 8 | 2 | 1 | 19.46% | 7.0276 | 0%
2030-01-09 | 2030 | 1 | Jan | 9 | 3 | 1 | 19.46% | 7.0276 | 0%
2030-01-10 | 2030 | 1 | Jan | 10 | 4 | 1 | 19.46% | 7.0276 | 0%
2030-01-11 | 2030 | 1 | Jan | 11 | 5 | 1 | 19.46% | 7.0276 | 0%
2030-01-12 | 2030 | 1 | Jan | 12 | 6 | 0 | 19.46% | 7.0276 | 0%
2030-01-13 | 2030 | 1 | Jan | 13 | 7 | 0 | 19.46% | 7.0276 | 0%
2030-01-14 | 2030 | 1 | Jan | 14 | 1 | 1 | 19.46% | 7.0276 | 0%
2030-01-15 | 2030 | 1 | Jan | 15 | 2 | 1 | 19.46% | 7.0276 | 0%
2030-01-16 | 2030 | 1 | Jan | 16 | 3 | 1 | 19.46% | 7.0276 | 0%
2030-01-17 | 2030 | 1 | Jan | 17 | 4 | 1 | 19.46% | 7.0276 | 0%
2030-01-18 | 2030 | 1 | Jan | 18 | 5 | 1 | 19.46% | 7.0276 | 0%
2030-01-19 | 2030 | 1 | Jan | 19 | 6 | 0 | 19.46% | 7.0276 | 0%
2030-01-20 | 2030 | 1 | Jan | 20 | 7 | 0 | 19.46% | 7.0276 | 0%
2030-01-21 | 2030 | 1 | Jan | 21 | 1 | 1 | 19.46% | 7.0276 | 0%
2030-01-22 | 2030 | 1 | Jan | 22 | 2 | 1 | 19.46% | 7.0276 | 0%
2030-01-23 | 2030 | 1 | Jan | 23 | 3 | 1 | 19.46% | 7.0276 | 0%
2030-01-24 | 2030 | 1 | Jan | 24 | 4 | 1 | 19.46% | 7.0276 | 0%
2030-01-25 | 2030 | 1 | Jan | 25 | 5 | 1 | 19.46% | 7.0276 | 0%
2030-01-26 | 2030 | 1 | Jan | 26 | 6 | 0 | 19.46% | 7.0276 | 0%
2030-01-27 | 2030 | 1 | Jan | 27 | 7 | 0 | 19.46% | 7.0276 | 0%
2030-01-28 | 2030 | 1 | Jan | 28 | 1 | 1 | 19.46% | 7.0276 | 0%
2030-01-29 | 2030 | 1 | Jan | 29 | 2 | 1 | 19.46% | 7.0276 | 0%
2030-01-30 | 2030 | 1 | Jan | 30 | 3 | 1 | 19.46% | 7.0276 | 0%
2030-01-31 | 2030 | 1 | Jan | 31 | 4 | 1 | 19.46% | 7.0276 | 0%
2030-02-01 | 2030 | 2 | Feb | 1 | 5 | 1 | 18.87% | 7.4625 | 0%
2030-02-02 | 2030 | 2 | Feb | 2 | 6 | 0 | 18.87% | 7.4625 | 0%
2030-02-03 | 2030 | 2 | Feb | 3 | 7 | 0 | 18.87% | 7.4625 | 0%
2030-02-04 | 2030 | 2 | Feb | 4 | 1 | 1 | 18.87% | 7.4625 | 0%
2030-02-05 | 2030 | 2 | Feb | 5 | 2 | 1 | 18.87% | 7.4625 | 0%
2030-02-06 | 2030 | 2 | Feb | 6 | 3 | 1 | 18.87% | 7.4625 | 0%
2030-02-07 | 2030 | 2 | Feb | 7 | 4 | 1 | 18.87% | 7.4625 | 0%
2030-02-08 | 2030 | 2 | Feb | 8 | 5 | 1 | 18.87% | 7.4625 | 0%
2030-02-09 | 2030 | 2 | Feb | 9 | 6 | 0 | 18.87% | 7.4625 | 0%
2030-02-10 | 2030 | 2 | Feb | 10 | 7 | 0 | 18.87% | 7.4625 | 0%
2030-02-11 | 2030 | 2 | Feb | 11 | 1 | 1 | 18.87% | 7.4625 | 0%
2030-02-12 | 2030 | 2 | Feb | 12 | 2 | 1 | 18.87% | 7.4625 | 0%
2030-02-13 | 2030 | 2 | Feb | 13 | 3 | 1 | 18.87% | 7.4625 | 0%
2030-02-14 | 2030 | 2 | Feb | 14 | 4 | 1 | 18.87% | 7.4625 | 0%
2030-02-15 | 2030 | 2 | Feb | 15 | 5 | 1 | 18.87% | 7.4625 | 0%
2030-02-16 | 2030 | 2 | Feb | 16 | 6 | 0 | 18.87% | 7.4625 | 0%
2030-02-17 | 2030 | 2 | Feb | 17 | 7 | 0 | 18.87% | 7.4625 | 0%
2030-02-18 | 2030 | 2 | Feb | 18 | 1 | 1 | 18.87% | 7.4625 | 0%
2030-02-19 | 2030 | 2 | Feb | 19 | 2 | 1 | 18.87% | 7.4625 | 0%
2030-02-20 | 2030 | 2 | Feb | 20 | 3 | 1 | 18.87% | 7.4625 | 0%
2030-02-21 | 2030 | 2 | Feb | 21 | 4 | 1 | 18.87% | 7.4625 | 0%
2030-02-22 | 2030 | 2 | Feb | 22 | 5 | 1 | 18.87% | 7.4625 | 0%
2030-02-23 | 2030 | 2 | Feb | 23 | 6 | 0 | 18.87% | 7.4625 | 0%
2030-02-24 | 2030 | 2 | Feb | 24 | 7 | 0 | 18.87% | 7.4625 | 0%
2030-02-25 | 2030 | 2 | Feb | 25 | 1 | 1 | 18.87% | 7.4625 | 0%
2030-02-26 | 2030 | 2 | Feb | 26 | 2 | 1 | 18.87% | 7.4625 | 0%
2030-02-27 | 2030 | 2 | Feb | 27 | 3 | 1 | 18.87% | 7.4625 | 0%
2030-02-28 | 2030 | 2 | Feb | 28 | 4 | 1 | 18.87% | 7.4625 | 0%
2030-03-01 | 2030 | 3 | Mar | 1 | 5 | 1 | 18.49% | 7.8663 | 0%
2030-03-02 | 2030 | 3 | Mar | 2 | 6 | 0 | 18.49% | 7.8663 | 0%
2030-03-03 | 2030 | 3 | Mar | 3 | 7 | 0 | 18.49% | 7.8663 | 0%
2030-03-04 | 2030 | 3 | Mar | 4 | 1 | 1 | 18.49% | 7.8663 | 0%
2030-03-05 | 2030 | 3 | Mar | 5 | 2 | 1 | 18.49% | 7.8663 | 0%
2030-03-06 | 2030 | 3 | Mar | 6 | 3 | 1 | 18.49% | 7.8663 | 0%
2030-03-07 | 2030 | 3 | Mar | 7 | 4 | 1 | 18.49% | 7.8663 | 0%
2030-03-08 | 2030 | 3 | Mar | 8 | 5 | 1 | 18.49% | 7.8663 | 0%
2030-03-09 | 2030 | 3 | Mar | 9 | 6 | 0 | 18.49% | 7.8663 | 0%
2030-03-10 | 2030 | 3 | Mar | 10 | 7 | 0 | 18.49% | 7.8663 | 0%
2030-03-11 | 2030 | 3 | Mar | 11 | 1 | 1 | 18.49% | 7.8663 | 0%
2030-03-12 | 2030 | 3 | Mar | 12 | 2 | 1 | 18.49% | 7.8663 | 0%
2030-03-13 | 2030 | 3 | Mar | 13 | 3 | 1 | 18.49% | 7.8663 | 0%
2030-03-14 | 2030 | 3 | Mar | 14 | 4 | 1 | 18.49% | 7.8663 | 0%
2030-03-15 | 2030 | 3 | Mar | 15 | 5 | 1 | 18.49% | 7.8663 | 0%
2030-03-16 | 2030 | 3 | Mar | 16 | 6 | 0 | 18.49% | 7.8663 | 0%
2030-03-17 | 2030 | 3 | Mar | 17 | 7 | 0 | 18.49% | 7.8663 | 0%
2030-03-18 | 2030 | 3 | Mar | 18 | 1 | 1 | 18.49% | 7.8663 | 0%
2030-03-19 | 2030 | 3 | Mar | 19 | 2 | 1 | 18.49% | 7.8663 | 0%
2030-03-20 | 2030 | 3 | Mar | 20 | 3 | 1 | 18.49% | 7.8663 | 0%
2030-03-21 | 2030 | 3 | Mar | 21 | 4 | 1 | 18.49% | 7.8663 | 0%
2030-03-22 | 2030 | 3 | Mar | 22 | 5 | 1 | 18.49% | 7.8663 | 0%
2030-03-23 | 2030 | 3 | Mar | 23 | 6 | 0 | 18.49% | 7.8663 | 0%
2030-03-24 | 2030 | 3 | Mar | 24 | 7 | 0 | 18.49% | 7.8663 | 0%
2030-03-25 | 2030 | 3 | Mar | 25 | 1 | 1 | 18.49% | 7.8663 | 0%
2030-03-26 | 2030 | 3 | Mar | 26 | 2 | 1 | 18.49% | 7.8663 | 0%
2030-03-27 | 2030 | 3 | Mar | 27 | 3 | 1 | 18.49% | 7.8663 | 0%
2030-03-28 | 2030 | 3 | Mar | 28 | 4 | 1 | 18.49% | 7.8663 | 0%
2030-03-29 | 2030 | 3 | Mar | 29 | 5 | 1 | 18.49% | 7.8663 | 0%
2030-03-30 | 2030 | 3 | Mar | 30 | 6 | 0 | 18.49% | 7.8663 | 0%
2030-03-31 | 2030 | 3 | Mar | 31 | 7 | 0 | 18.49% | 7.8663 | 0%
2030-04-01 | 2030 | 4 | Apr | 1 | 1 | 1 | 25.56% | 7.5 | 0%
2030-04-02 | 2030 | 4 | Apr | 2 | 2 | 1 | 25.56% | 7.5 | 0%
2030-04-03 | 2030 | 4 | Apr | 3 | 3 | 1 | 25.56% | 7.5 | 0%
2030-04-04 | 2030 | 4 | Apr | 4 | 4 | 1 | 25.56% | 7.5 | 0%
2030-04-05 | 2030 | 4 | Apr | 5 | 5 | 1 | 25.56% | 7.5 | 0%
2030-04-06 | 2030 | 4 | Apr | 6 | 6 | 0 | 25.56% | 7.5 | 0%
2030-04-07 | 2030 | 4 | Apr | 7 | 7 | 0 | 25.56% | 7.5 | 0%
2030-04-08 | 2030 | 4 | Apr | 8 | 1 | 1 | 25.56% | 7.5 | 0%
2030-04-09 | 2030 | 4 | Apr | 9 | 2 | 1 | 25.56% | 7.5 | 0%
2030-04-10 | 2030 | 4 | Apr | 10 | 3 | 1 | 25.56% | 7.5 | 0%
2030-04-11 | 2030 | 4 | Apr | 11 | 4 | 1 | 25.56% | 7.5 | 0%
2030-04-12 | 2030 | 4 | Apr | 12 | 5 | 1 | 25.56% | 7.5 | 0%
2030-04-13 | 2030 | 4 | Apr | 13 | 6 | 0 | 25.56% | 7.5 | 0%
2030-04-14 | 2030 | 4 | Apr | 14 | 7 | 0 | 25.56% | 7.5 | 0%
2030-04-15 | 2030 | 4 | Apr | 15 | 1 | 1 | 25.56% | 7.5 | 0%
2030-04-16 | 2030 | 4 | Apr | 16 | 2 | 1 | 25.56% | 7.5 | 0%
2030-04-17 | 2030 | 4 | Apr | 17 | 3 | 1 | 25.56% | 7.5 | 0%
2030-04-18 | 2030 | 4 | Apr | 18 | 4 | 1 | 25.56% | 7.5 | 0%
2030-04-19 | 2030 | 4 | Apr | 19 | 5 | 1 | 25.56% | 7.5 | 0%
2030-04-20 | 2030 | 4 | Apr | 20 | 6 | 0 | 25.56% | 7.5 | 0%
2030-04-21 | 2030 | 4 | Apr | 21 | 7 | 0 | 25.56% | 7.5 | 0%
2030-04-22 | 2030 | 4 | Apr | 22 | 1 | 1 | 25.56% | 7.5 | 0%
2030-04-23 | 2030 | 4 | Apr | 23 | 2 | 1 | 25.56% | 7.5 | 0%
2030-04-24 | 2030 | 4 | Apr | 24 | 3 | 1 | 25.56% | 7.5 | 0%
2030-04-25 | 2030 | 4 | Apr | 25 | 4 | 1 | 25.56% | 7.5 | 0%
2030-04-26 | 2030 | 4 | Apr | 26 | 5 | 1 | 25.56% | 7.5 | 0%
2030-04-27 | 2030 | 4 | Apr | 27 | 6 | 0 | 25.56% | 7.5 | 0%
2030-04-28 | 2030 | 4 | Apr | 28 | 7 | 0 | 25.56% | 7.5 | 0%
2030-04-29 | 2030 | 4 | Apr | 29 | 1 | 1 | 25.56% | 7.5 | 0%
2030-04-30 | 2030 | 4 | Apr | 30 | 2 | 1 | 25.56% | 7.5 | 0%
2030-05-01 | 2030 | 5 | May | 1 | 3 | 1 | 23.01% | 8.1449 | 0%
2030-05-02 | 2030 | 5 | May | 2 | 4 | 1 | 23.01% | 8.1449 | 0%
2030-05-03 | 2030 | 5 | May | 3 | 5 | 1 | 23.01% | 8.1449 | 0%
2030-05-04 | 2030 | 5 | May | 4 | 6 | 0 | 23.01% | 8.1449 | 0%
2030-05-05 | 2030 | 5 | May | 5 | 7 | 0 | 23.01% | 8.1449 | 0%
2030-05-06 | 2030 | 5 | May | 6 | 1 | 1 | 23.01% | 8.1449 | 0%
2030-05-07 | 2030 | 5 | May | 7 | 2 | 1 | 23.01% | 8.1449 | 0%
2030-05-08 | 2030 | 5 | May | 8 | 3 | 1 | 23.01% | 8.1449 | 0%
2030-05-09 | 2030 | 5 | May | 9 | 4 | 1 | 23.01% | 8.1449 | 0%
2030-05-10 | 2030 | 5 | May | 10 | 5 | 1 | 23.01% | 8.1449 | 0%
2030-05-11 | 2030 | 5 | May | 11 | 6 | 0 | 23.01% | 8.1449 | 0%
2030-05-12 | 2030 | 5 | May | 12 | 7 | 0 | 23.01% | 8.1449 | 0%
2030-05-13 | 2030 | 5 | May | 13 | 1 | 1 | 23.01% | 8.1449 | 0%
2030-05-14 | 2030 | 5 | May | 14 | 2 | 1 | 23.01% | 8.1449 | 0%
2030-05-15 | 2030 | 5 | May | 15 | 3 | 1 | 23.01% | 8.1449 | 0%
2030-05-16 | 2030 | 5 | May | 16 | 4 | 1 | 23.01% | 8.1449 | 0%
2030-05-17 | 2030 | 5 | May | 17 | 5 | 1 | 23.01% | 8.1449 | 0%
2030-05-18 | 2030 | 5 | May | 18 | 6 | 0 | 23.01% | 8.1449 | 0%
2030-05-19 | 2030 | 5 | May | 19 | 7 | 0 | 23.01% | 8.1449 | 0%
2030-05-20 | 2030 | 5 | May | 20 | 1 | 1 | 23.01% | 8.1449 | 0%
2030-05-21 | 2030 | 5 | May | 21 | 2 | 1 | 23.01% | 8.1449 | 0%
2030-05-22 | 2030 | 5 | May | 22 | 3 | 1 | 23.01% | 8.1449 | 0%
2030-05-23 | 2030 | 5 | May | 23 | 4 | 1 | 23.01% | 8.1449 | 0%
2030-05-24 | 2030 | 5 | May | 24 | 5 | 1 | 23.01% | 8.1449 | 0%
2030-05-25 | 2030 | 5 | May | 25 | 6 | 0 | 23.01% | 8.1449 | 0%
2030-05-26 | 2030 | 5 | May | 26 | 7 | 0 | 23.01% | 8.1449 | 0%
2030-05-27 | 2030 | 5 | May | 27 | 1 | 1 | 23.01% | 8.1449 | 0%
2030-05-28 | 2030 | 5 | May | 28 | 2 | 1 | 23.01% | 8.1449 | 0%
2030-05-29 | 2030 | 5 | May | 29 | 3 | 1 | 23.01% | 8.1449 | 0%
2030-05-30 | 2030 | 5 | May | 30 | 4 | 1 | 23.01% | 8.1449 | 0%
2030-05-31 | 2030 | 5 | May | 31 | 5 | 1 | 23.01% | 8.1449 | 0%
2030-06-01 | 2030 | 6 | Jun | 1 | 6 | 0 | 28.67% | 7.9419 | 0%
2030-06-02 | 2030 | 6 | Jun | 2 | 7 | 0 | 28.67% | 7.9419 | 0%
2030-06-03 | 2030 | 6 | Jun | 3 | 1 | 1 | 28.67% | 7.9419 | 0%
2030-06-04 | 2030 | 6 | Jun | 4 | 2 | 1 | 28.67% | 7.9419 | 0%
2030-06-05 | 2030 | 6 | Jun | 5 | 3 | 1 | 28.67% | 7.9419 | 0%
2030-06-06 | 2030 | 6 | Jun | 6 | 4 | 1 | 28.67% | 7.9419 | 0%
2030-06-07 | 2030 | 6 | Jun | 7 | 5 | 1 | 28.67% | 7.9419 | 0%
2030-06-08 | 2030 | 6 | Jun | 8 | 6 | 0 | 28.67% | 7.9419 | 0%
2030-06-09 | 2030 | 6 | Jun | 9 | 7 | 0 | 28.67% | 7.9419 | 0%
2030-06-10 | 2030 | 6 | Jun | 10 | 1 | 1 | 28.67% | 7.9419 | 0%
2030-06-11 | 2030 | 6 | Jun | 11 | 2 | 1 | 28.67% | 7.9419 | 0%
2030-06-12 | 2030 | 6 | Jun | 12 | 3 | 1 | 28.67% | 7.9419 | 0%
2030-06-13 | 2030 | 6 | Jun | 13 | 4 | 1 | 28.67% | 7.9419 | 0%
2030-06-14 | 2030 | 6 | Jun | 14 | 5 | 1 | 28.67% | 7.9419 | 0%
2030-06-15 | 2030 | 6 | Jun | 15 | 6 | 0 | 28.67% | 7.9419 | 0%
2030-06-16 | 2030 | 6 | Jun | 16 | 7 | 0 | 28.67% | 7.9419 | 0%
2030-06-17 | 2030 | 6 | Jun | 17 | 1 | 1 | 28.67% | 7.9419 | 0%
2030-06-18 | 2030 | 6 | Jun | 18 | 2 | 1 | 28.67% | 7.9419 | 0%
2030-06-19 | 2030 | 6 | Jun | 19 | 3 | 1 | 28.67% | 7.9419 | 0%
2030-06-20 | 2030 | 6 | Jun | 20 | 4 | 1 | 28.67% | 7.9419 | 0%
2030-06-21 | 2030 | 6 | Jun | 21 | 5 | 1 | 28.67% | 7.9419 | 0%
2030-06-22 | 2030 | 6 | Jun | 22 | 6 | 0 | 28.67% | 7.9419 | 0%
2030-06-23 | 2030 | 6 | Jun | 23 | 7 | 0 | 28.67% | 7.9419 | 0%
2030-06-24 | 2030 | 6 | Jun | 24 | 1 | 1 | 28.67% | 7.9419 | 0%
2030-06-25 | 2030 | 6 | Jun | 25 | 2 | 1 | 28.67% | 7.9419 | 0%
2030-06-26 | 2030 | 6 | Jun | 26 | 3 | 1 | 28.67% | 7.9419 | 0%
2030-06-27 | 2030 | 6 | Jun | 27 | 4 | 1 | 28.67% | 7.9419 | 0%
2030-06-28 | 2030 | 6 | Jun | 28 | 5 | 1 | 28.67% | 7.9419 | 0%
2030-06-29 | 2030 | 6 | Jun | 29 | 6 | 0 | 28.67% | 7.9419 | 0%
2030-06-30 | 2030 | 6 | Jun | 30 | 7 | 0 | 28.67% | 7.9419 | 0%
2030-07-01 | 2030 | 7 | Jul | 1 | 1 | 1 | 24.73% | 8.3739 | 0%
2030-07-02 | 2030 | 7 | Jul | 2 | 2 | 1 | 24.73% | 8.3739 | 0%
2030-07-03 | 2030 | 7 | Jul | 3 | 3 | 1 | 24.73% | 8.3739 | 0%
2030-07-04 | 2030 | 7 | Jul | 4 | 4 | 1 | 24.73% | 8.3739 | 0%
2030-07-05 | 2030 | 7 | Jul | 5 | 5 | 1 | 24.73% | 8.3739 | 0%
2030-07-06 | 2030 | 7 | Jul | 6 | 6 | 0 | 24.73% | 8.3739 | 0%
2030-07-07 | 2030 | 7 | Jul | 7 | 7 | 0 | 24.73% | 8.3739 | 0%
2030-07-08 | 2030 | 7 | Jul | 8 | 1 | 1 | 24.73% | 8.3739 | 0%
2030-07-09 | 2030 | 7 | Jul | 9 | 2 | 1 | 24.73% | 8.3739 | 0%
2030-07-10 | 2030 | 7 | Jul | 10 | 3 | 1 | 24.73% | 8.3739 | 0%
2030-07-11 | 2030 | 7 | Jul | 11 | 4 | 1 | 24.73% | 8.3739 | 0%
2030-07-12 | 2030 | 7 | Jul | 12 | 5 | 1 | 24.73% | 8.3739 | 0%
2030-07-13 | 2030 | 7 | Jul | 13 | 6 | 0 | 24.73% | 8.3739 | 0%
2030-07-14 | 2030 | 7 | Jul | 14 | 7 | 0 | 24.73% | 8.3739 | 0%
2030-07-15 | 2030 | 7 | Jul | 15 | 1 | 1 | 24.73% | 8.3739 | 0%
2030-07-16 | 2030 | 7 | Jul | 16 | 2 | 1 | 24.73% | 8.3739 | 0%
2030-07-17 | 2030 | 7 | Jul | 17 | 3 | 1 | 24.73% | 8.3739 | 0%
2030-07-18 | 2030 | 7 | Jul | 18 | 4 | 1 | 24.73% | 8.3739 | 0%
2030-07-19 | 2030 | 7 | Jul | 19 | 5 | 1 | 24.73% | 8.3739 | 0%
2030-07-20 | 2030 | 7 | Jul | 20 | 6 | 0 | 24.73% | 8.3739 | 0%
2030-07-21 | 2030 | 7 | Jul | 21 | 7 | 0 | 24.73% | 8.3739 | 0%
2030-07-22 | 2030 | 7 | Jul | 22 | 1 | 1 | 24.73% | 8.3739 | 0%
2030-07-23 | 2030 | 7 | Jul | 23 | 2 | 1 | 24.73% | 8.3739 | 0%
2030-07-24 | 2030 | 7 | Jul | 24 | 3 | 1 | 24.73% | 8.3739 | 0%
2030-07-25 | 2030 | 7 | Jul | 25 | 4 | 1 | 24.73% | 8.3739 | 0%
2030-07-26 | 2030 | 7 | Jul | 26 | 5 | 1 | 24.73% | 8.3739 | 0%
2030-07-27 | 2030 | 7 | Jul | 27 | 6 | 0 | 24.73% | 8.3739 | 0%
2030-07-28 | 2030 | 7 | Jul | 28 | 7 | 0 | 24.73% | 8.3739 | 0%
2030-07-29 | 2030 | 7 | Jul | 29 | 1 | 1 | 24.73% | 8.3739 | 0%
2030-07-30 | 2030 | 7 | Jul | 30 | 2 | 1 | 24.73% | 8.3739 | 0%
2030-07-31 | 2030 | 7 | Jul | 31 | 3 | 1 | 24.73% | 8.3739 | 0%
2030-08-01 | 2030 | 8 | Aug | 1 | 4 | 1 | 23.55% | 7.9589 | 0%
2030-08-02 | 2030 | 8 | Aug | 2 | 5 | 1 | 23.55% | 7.9589 | 0%
2030-08-03 | 2030 | 8 | Aug | 3 | 6 | 0 | 23.55% | 7.9589 | 0%
2030-08-04 | 2030 | 8 | Aug | 4 | 7 | 0 | 23.55% | 7.9589 | 0%
2030-08-05 | 2030 | 8 | Aug | 5 | 1 | 1 | 23.55% | 7.9589 | 0%
2030-08-06 | 2030 | 8 | Aug | 6 | 2 | 1 | 23.55% | 7.9589 | 0%
2030-08-07 | 2030 | 8 | Aug | 7 | 3 | 1 | 23.55% | 7.9589 | 0%
2030-08-08 | 2030 | 8 | Aug | 8 | 4 | 1 | 23.55% | 7.9589 | 0%
2030-08-09 | 2030 | 8 | Aug | 9 | 5 | 1 | 23.55% | 7.9589 | 0%
2030-08-10 | 2030 | 8 | Aug | 10 | 6 | 0 | 23.55% | 7.9589 | 0%
2030-08-11 | 2030 | 8 | Aug | 11 | 7 | 0 | 23.55% | 7.9589 | 0%
2030-08-12 | 2030 | 8 | Aug | 12 | 1 | 1 | 23.55% | 7.9589 | 0%
2030-08-13 | 2030 | 8 | Aug | 13 | 2 | 1 | 23.55% | 7.9589 | 0%
2030-08-14 | 2030 | 8 | Aug | 14 | 3 | 1 | 23.55% | 7.9589 | 0%
2030-08-15 | 2030 | 8 | Aug | 15 | 4 | 1 | 23.55% | 7.9589 | 0%
2030-08-16 | 2030 | 8 | Aug | 16 | 5 | 1 | 23.55% | 7.9589 | 0%
2030-08-17 | 2030 | 8 | Aug | 17 | 6 | 0 | 23.55% | 7.9589 | 0%
2030-08-18 | 2030 | 8 | Aug | 18 | 7 | 0 | 23.55% | 7.9589 | 0%
2030-08-19 | 2030 | 8 | Aug | 19 | 1 | 1 | 23.55% | 7.9589 | 0%
2030-08-20 | 2030 | 8 | Aug | 20 | 2 | 1 | 23.55% | 7.9589 | 0%
2030-08-21 | 2030 | 8 | Aug | 21 | 3 | 1 | 23.55% | 7.9589 | 0%
2030-08-22 | 2030 | 8 | Aug | 22 | 4 | 1 | 23.55% | 7.9589 | 0%
2030-08-23 | 2030 | 8 | Aug | 23 | 5 | 1 | 23.55% | 7.9589 | 0%
2030-08-24 | 2030 | 8 | Aug | 24 | 6 | 0 | 23.55% | 7.9589 | 0%
2030-08-25 | 2030 | 8 | Aug | 25 | 7 | 0 | 23.55% | 7.9589 | 0%
2030-08-26 | 2030 | 8 | Aug | 26 | 1 | 1 | 23.55% | 7.9589 | 0%
2030-08-27 | 2030 | 8 | Aug | 27 | 2 | 1 | 23.55% | 7.9589 | 0%
2030-08-28 | 2030 | 8 | Aug | 28 | 3 | 1 | 23.55% | 7.9589 | 0%
2030-08-29 | 2030 | 8 | Aug | 29 | 4 | 1 | 23.55% | 7.9589 | 0%
2030-08-30 | 2030 | 8 | Aug | 30 | 5 | 1 | 23.55% | 7.9589 | 0%
2030-08-31 | 2030 | 8 | Aug | 31 | 6 | 0 | 23.55% | 7.9589 | 0%
2030-09-01 | 2030 | 9 | Sep | 1 | 7 | 0 | 20.67% | 6.8065 | 0%
2030-09-02 | 2030 | 9 | Sep | 2 | 1 | 1 | 20.67% | 6.8065 | 0%
2030-09-03 | 2030 | 9 | Sep | 3 | 2 | 1 | 20.67% | 6.8065 | 0%
2030-09-04 | 2030 | 9 | Sep | 4 | 3 | 1 | 20.67% | 6.8065 | 0%
2030-09-05 | 2030 | 9 | Sep | 5 | 4 | 1 | 20.67% | 6.8065 | 0%
2030-09-06 | 2030 | 9 | Sep | 6 | 5 | 1 | 20.67% | 6.8065 | 0%
2030-09-07 | 2030 | 9 | Sep | 7 | 6 | 0 | 20.67% | 6.8065 | 0%
2030-09-08 | 2030 | 9 | Sep | 8 | 7 | 0 | 20.67% | 6.8065 | 0%
2030-09-09 | 2030 | 9 | Sep | 9 | 1 | 1 | 20.67% | 6.8065 | 0%
2030-09-10 | 2030 | 9 | Sep | 10 | 2 | 1 | 20.67% | 6.8065 | 0%
2030-09-11 | 2030 | 9 | Sep | 11 | 3 | 1 | 20.67% | 6.8065 | 0%
2030-09-12 | 2030 | 9 | Sep | 12 | 4 | 1 | 20.67% | 6.8065 | 0%
2030-09-13 | 2030 | 9 | Sep | 13 | 5 | 1 | 20.67% | 6.8065 | 0%
2030-09-14 | 2030 | 9 | Sep | 14 | 6 | 0 | 20.67% | 6.8065 | 0%
2030-09-15 | 2030 | 9 | Sep | 15 | 7 | 0 | 20.67% | 6.8065 | 0%
2030-09-16 | 2030 | 9 | Sep | 16 | 1 | 1 | 20.67% | 6.8065 | 0%
2030-09-17 | 2030 | 9 | Sep | 17 | 2 | 1 | 20.67% | 6.8065 | 0%
2030-09-18 | 2030 | 9 | Sep | 18 | 3 | 1 | 20.67% | 6.8065 | 0%
2030-09-19 | 2030 | 9 | Sep | 19 | 4 | 1 | 20.67% | 6.8065 | 0%
2030-09-20 | 2030 | 9 | Sep | 20 | 5 | 1 | 20.67% | 6.8065 | 0%
2030-09-21 | 2030 | 9 | Sep | 21 | 6 | 0 | 20.67% | 6.8065 | 0%
2030-09-22 | 2030 | 9 | Sep | 22 | 7 | 0 | 20.67% | 6.8065 | 0%
2030-09-23 | 2030 | 9 | Sep | 23 | 1 | 1 | 20.67% | 6.8065 | 0%
2030-09-24 | 2030 | 9 | Sep | 24 | 2 | 1 | 20.67% | 6.8065 | 0%
2030-09-25 | 2030 | 9 | Sep | 25 | 3 | 1 | 20.67% | 6.8065 | 0%
2030-09-26 | 2030 | 9 | Sep | 26 | 4 | 1 | 20.67% | 6.8065 | 0%
2030-09-27 | 2030 | 9 | Sep | 27 | 5 | 1 | 20.67% | 6.8065 | 0%
2030-09-28 | 2030 | 9 | Sep | 28 | 6 | 0 | 20.67% | 6.8065 | 0%
2030-09-29 | 2030 | 9 | Sep | 29 | 7 | 0 | 20.67% | 6.8065 | 0%
2030-09-30 | 2030 | 9 | Sep | 30 | 1 | 1 | 20.67% | 6.8065 | 0%
2030-10-01 | 2030 | 10 | Oct | 1 | 2 | 1 | 23.23% | 6.8194 | 0%
2030-10-02 | 2030 | 10 | Oct | 2 | 3 | 1 | 23.23% | 6.8194 | 0%
2030-10-03 | 2030 | 10 | Oct | 3 | 4 | 1 | 23.23% | 6.8194 | 0%
2030-10-04 | 2030 | 10 | Oct | 4 | 5 | 1 | 23.23% | 6.8194 | 0%
2030-10-05 | 2030 | 10 | Oct | 5 | 6 | 0 | 23.23% | 6.8194 | 0%
2030-10-06 | 2030 | 10 | Oct | 6 | 7 | 0 | 23.23% | 6.8194 | 0%
2030-10-07 | 2030 | 10 | Oct | 7 | 1 | 1 | 23.23% | 6.8194 | 0%
2030-10-08 | 2030 | 10 | Oct | 8 | 2 | 1 | 23.23% | 6.8194 | 0%
2030-10-09 | 2030 | 10 | Oct | 9 | 3 | 1 | 23.23% | 6.8194 | 0%
2030-10-10 | 2030 | 10 | Oct | 10 | 4 | 1 | 23.23% | 6.8194 | 0%
2030-10-11 | 2030 | 10 | Oct | 11 | 5 | 1 | 23.23% | 6.8194 | 0%
2030-10-12 | 2030 | 10 | Oct | 12 | 6 | 0 | 23.23% | 6.8194 | 0%
2030-10-13 | 2030 | 10 | Oct | 13 | 7 | 0 | 23.23% | 6.8194 | 0%
2030-10-14 | 2030 | 10 | Oct | 14 | 1 | 1 | 23.23% | 6.8194 | 0%
2030-10-15 | 2030 | 10 | Oct | 15 | 2 | 1 | 23.23% | 6.8194 | 0%
2030-10-16 | 2030 | 10 | Oct | 16 | 3 | 1 | 23.23% | 6.8194 | 0%
2030-10-17 | 2030 | 10 | Oct | 17 | 4 | 1 | 23.23% | 6.8194 | 0%
2030-10-18 | 2030 | 10 | Oct | 18 | 5 | 1 | 23.23% | 6.8194 | 0%
2030-10-19 | 2030 | 10 | Oct | 19 | 6 | 0 | 23.23% | 6.8194 | 0%
2030-10-20 | 2030 | 10 | Oct | 20 | 7 | 0 | 23.23% | 6.8194 | 0%
2030-10-21 | 2030 | 10 | Oct | 21 | 1 | 1 | 23.23% | 6.8194 | 0%
2030-10-22 | 2030 | 10 | Oct | 22 | 2 | 1 | 23.23% | 6.8194 | 0%
2030-10-23 | 2030 | 10 | Oct | 23 | 3 | 1 | 23.23% | 6.8194 | 0%
2030-10-24 | 2030 | 10 | Oct | 24 | 4 | 1 | 23.23% | 6.8194 | 0%
2030-10-25 | 2030 | 10 | Oct | 25 | 5 | 1 | 23.23% | 6.8194 | 0%
2030-10-26 | 2030 | 10 | Oct | 26 | 6 | 0 | 23.23% | 6.8194 | 0%
2030-10-27 | 2030 | 10 | Oct | 27 | 7 | 0 | 23.23% | 6.8194 | 0%
2030-10-28 | 2030 | 10 | Oct | 28 | 1 | 1 | 23.23% | 6.8194 | 0%
2030-10-29 | 2030 | 10 | Oct | 29 | 2 | 1 | 23.23% | 6.8194 | 0%
2030-10-30 | 2030 | 10 | Oct | 30 | 3 | 1 | 23.23% | 6.8194 | 0%
2030-10-31 | 2030 | 10 | Oct | 31 | 4 | 1 | 23.23% | 6.8194 | 0%
2030-11-01 | 2030 | 11 | Nov | 1 | 5 | 1 | 23.33% | 6.4429 | 0%
2030-11-02 | 2030 | 11 | Nov | 2 | 6 | 0 | 23.33% | 6.4429 | 0%
2030-11-03 | 2030 | 11 | Nov | 3 | 7 | 0 | 23.33% | 6.4429 | 0%
2030-11-04 | 2030 | 11 | Nov | 4 | 1 | 1 | 23.33% | 6.4429 | 0%
2030-11-05 | 2030 | 11 | Nov | 5 | 2 | 1 | 23.33% | 6.4429 | 0%
2030-11-06 | 2030 | 11 | Nov | 6 | 3 | 1 | 23.33% | 6.4429 | 0%
2030-11-07 | 2030 | 11 | Nov | 7 | 4 | 1 | 23.33% | 6.4429 | 0%
2030-11-08 | 2030 | 11 | Nov | 8 | 5 | 1 | 23.33% | 6.4429 | 0%
2030-11-09 | 2030 | 11 | Nov | 9 | 6 | 0 | 23.33% | 6.4429 | 0%
2030-11-10 | 2030 | 11 | Nov | 10 | 7 | 0 | 23.33% | 6.4429 | 0%
2030-11-11 | 2030 | 11 | Nov | 11 | 1 | 1 | 23.33% | 6.4429 | 0%
2030-11-12 | 2030 | 11 | Nov | 12 | 2 | 1 | 23.33% | 6.4429 | 0%
2030-11-13 | 2030 | 11 | Nov | 13 | 3 | 1 | 23.33% | 6.4429 | 0%
2030-11-14 | 2030 | 11 | Nov | 14 | 4 | 1 | 23.33% | 6.4429 | 0%
2030-11-15 | 2030 | 11 | Nov | 15 | 5 | 1 | 23.33% | 6.4429 | 0%
2030-11-16 | 2030 | 11 | Nov | 16 | 6 | 0 | 23.33% | 6.4429 | 0%
2030-11-17 | 2030 | 11 | Nov | 17 | 7 | 0 | 23.33% | 6.4429 | 0%
2030-11-18 | 2030 | 11 | Nov | 18 | 1 | 1 | 23.33% | 6.4429 | 0%
2030-11-19 | 2030 | 11 | Nov | 19 | 2 | 1 | 23.33% | 6.4429 | 0%
2030-11-20 | 2030 | 11 | Nov | 20 | 3 | 1 | 23.33% | 6.4429 | 0%
2030-11-21 | 2030 | 11 | Nov | 21 | 4 | 1 | 23.33% | 6.4429 | 0%
2030-11-22 | 2030 | 11 | Nov | 22 | 5 | 1 | 23.33% | 6.4429 | 0%
2030-11-23 | 2030 | 11 | Nov | 23 | 6 | 0 | 23.33% | 6.4429 | 0%
2030-11-24 | 2030 | 11 | Nov | 24 | 7 | 0 | 23.33% | 6.4429 | 0%
2030-11-25 | 2030 | 11 | Nov | 25 | 1 | 1 | 23.33% | 6.4429 | 0%
2030-11-26 | 2030 | 11 | Nov | 26 | 2 | 1 | 23.33% | 6.4429 | 0%
2030-11-27 | 2030 | 11 | Nov | 27 | 3 | 1 | 23.33% | 6.4429 | 0%
2030-11-28 | 2030 | 11 | Nov | 28 | 4 | 1 | 23.33% | 6.4429 | 0%
2030-11-29 | 2030 | 11 | Nov | 29 | 5 | 1 | 23.33% | 6.4429 | 0%
2030-11-30 | 2030 | 11 | Nov | 30 | 6 | 0 | 23.33% | 6.4429 | 0%
2030-12-01 | 2030 | 12 | Dec | 1 | 7 | 0 | 22.69% | 6.7962 | 0%
2030-12-02 | 2030 | 12 | Dec | 2 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-12-03 | 2030 | 12 | Dec | 3 | 2 | 1 | 22.69% | 6.7962 | 0%
2030-12-04 | 2030 | 12 | Dec | 4 | 3 | 1 | 22.69% | 6.7962 | 0%
2030-12-05 | 2030 | 12 | Dec | 5 | 4 | 1 | 22.69% | 6.7962 | 0%
2030-12-06 | 2030 | 12 | Dec | 6 | 5 | 1 | 22.69% | 6.7962 | 0%
2030-12-07 | 2030 | 12 | Dec | 7 | 6 | 0 | 22.69% | 6.7962 | 0%
2030-12-08 | 2030 | 12 | Dec | 8 | 7 | 0 | 22.69% | 6.7962 | 0%
2030-12-09 | 2030 | 12 | Dec | 9 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-12-10 | 2030 | 12 | Dec | 10 | 2 | 1 | 22.69% | 6.7962 | 0%
2030-12-11 | 2030 | 12 | Dec | 11 | 3 | 1 | 22.69% | 6.7962 | 0%
2030-12-12 | 2030 | 12 | Dec | 12 | 4 | 1 | 22.69% | 6.7962 | 0%
2030-12-13 | 2030 | 12 | Dec | 13 | 5 | 1 | 22.69% | 6.7962 | 0%
2030-12-14 | 2030 | 12 | Dec | 14 | 6 | 0 | 22.69% | 6.7962 | 0%
2030-12-15 | 2030 | 12 | Dec | 15 | 7 | 0 | 22.69% | 6.7962 | 0%
2030-12-16 | 2030 | 12 | Dec | 16 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-12-17 | 2030 | 12 | Dec | 17 | 2 | 1 | 22.69% | 6.7962 | 0%
2030-12-18 | 2030 | 12 | Dec | 18 | 3 | 1 | 22.69% | 6.7962 | 0%
2030-12-19 | 2030 | 12 | Dec | 19 | 4 | 1 | 22.69% | 6.7962 | 0%
2030-12-20 | 2030 | 12 | Dec | 20 | 5 | 1 | 22.69% | 6.7962 | 0%
2030-12-21 | 2030 | 12 | Dec | 21 | 6 | 0 | 22.69% | 6.7962 | 0%
2030-12-22 | 2030 | 12 | Dec | 22 | 7 | 0 | 22.69% | 6.7962 | 0%
2030-12-23 | 2030 | 12 | Dec | 23 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-12-24 | 2030 | 12 | Dec | 24 | 2 | 1 | 22.69% | 6.7962 | 0%
2030-12-25 | 2030 | 12 | Dec | 25 | 3 | 1 | 22.69% | 6.7962 | 0%
2030-12-26 | 2030 | 12 | Dec | 26 | 4 | 1 | 22.69% | 6.7962 | 0%
2030-12-27 | 2030 | 12 | Dec | 27 | 5 | 1 | 22.69% | 6.7962 | 0%
2030-12-28 | 2030 | 12 | Dec | 28 | 6 | 0 | 22.69% | 6.7962 | 0%
2030-12-29 | 2030 | 12 | Dec | 29 | 7 | 0 | 22.69% | 6.7962 | 0%
2030-12-30 | 2030 | 12 | Dec | 30 | 1 | 1 | 22.69% | 6.7962 | 0%
2030-12-31 | 2030 | 12 | Dec | 31 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-01-01 | 2031 | 1 | Jan | 1 | 3 | 1 | 19.46% | 7.0276 | 0%
2031-01-02 | 2031 | 1 | Jan | 2 | 4 | 1 | 19.46% | 7.0276 | 0%
2031-01-03 | 2031 | 1 | Jan | 3 | 5 | 1 | 19.46% | 7.0276 | 0%
2031-01-04 | 2031 | 1 | Jan | 4 | 6 | 0 | 19.46% | 7.0276 | 0%
2031-01-05 | 2031 | 1 | Jan | 5 | 7 | 0 | 19.46% | 7.0276 | 0%
2031-01-06 | 2031 | 1 | Jan | 6 | 1 | 1 | 19.46% | 7.0276 | 0%
2031-01-07 | 2031 | 1 | Jan | 7 | 2 | 1 | 19.46% | 7.0276 | 0%
2031-01-08 | 2031 | 1 | Jan | 8 | 3 | 1 | 19.46% | 7.0276 | 0%
2031-01-09 | 2031 | 1 | Jan | 9 | 4 | 1 | 19.46% | 7.0276 | 0%
2031-01-10 | 2031 | 1 | Jan | 10 | 5 | 1 | 19.46% | 7.0276 | 0%
2031-01-11 | 2031 | 1 | Jan | 11 | 6 | 0 | 19.46% | 7.0276 | 0%
2031-01-12 | 2031 | 1 | Jan | 12 | 7 | 0 | 19.46% | 7.0276 | 0%
2031-01-13 | 2031 | 1 | Jan | 13 | 1 | 1 | 19.46% | 7.0276 | 0%
2031-01-14 | 2031 | 1 | Jan | 14 | 2 | 1 | 19.46% | 7.0276 | 0%
2031-01-15 | 2031 | 1 | Jan | 15 | 3 | 1 | 19.46% | 7.0276 | 0%
2031-01-16 | 2031 | 1 | Jan | 16 | 4 | 1 | 19.46% | 7.0276 | 0%
2031-01-17 | 2031 | 1 | Jan | 17 | 5 | 1 | 19.46% | 7.0276 | 0%
2031-01-18 | 2031 | 1 | Jan | 18 | 6 | 0 | 19.46% | 7.0276 | 0%
2031-01-19 | 2031 | 1 | Jan | 19 | 7 | 0 | 19.46% | 7.0276 | 0%
2031-01-20 | 2031 | 1 | Jan | 20 | 1 | 1 | 19.46% | 7.0276 | 0%
2031-01-21 | 2031 | 1 | Jan | 21 | 2 | 1 | 19.46% | 7.0276 | 0%
2031-01-22 | 2031 | 1 | Jan | 22 | 3 | 1 | 19.46% | 7.0276 | 0%
2031-01-23 | 2031 | 1 | Jan | 23 | 4 | 1 | 19.46% | 7.0276 | 0%
2031-01-24 | 2031 | 1 | Jan | 24 | 5 | 1 | 19.46% | 7.0276 | 0%
2031-01-25 | 2031 | 1 | Jan | 25 | 6 | 0 | 19.46% | 7.0276 | 0%
2031-01-26 | 2031 | 1 | Jan | 26 | 7 | 0 | 19.46% | 7.0276 | 0%
2031-01-27 | 2031 | 1 | Jan | 27 | 1 | 1 | 19.46% | 7.0276 | 0%
2031-01-28 | 2031 | 1 | Jan | 28 | 2 | 1 | 19.46% | 7.0276 | 0%
2031-01-29 | 2031 | 1 | Jan | 29 | 3 | 1 | 19.46% | 7.0276 | 0%
2031-01-30 | 2031 | 1 | Jan | 30 | 4 | 1 | 19.46% | 7.0276 | 0%
2031-01-31 | 2031 | 1 | Jan | 31 | 5 | 1 | 19.46% | 7.0276 | 0%
2031-02-01 | 2031 | 2 | Feb | 1 | 6 | 0 | 18.87% | 7.4625 | 0%
2031-02-02 | 2031 | 2 | Feb | 2 | 7 | 0 | 18.87% | 7.4625 | 0%
2031-02-03 | 2031 | 2 | Feb | 3 | 1 | 1 | 18.87% | 7.4625 | 0%
2031-02-04 | 2031 | 2 | Feb | 4 | 2 | 1 | 18.87% | 7.4625 | 0%
2031-02-05 | 2031 | 2 | Feb | 5 | 3 | 1 | 18.87% | 7.4625 | 0%
2031-02-06 | 2031 | 2 | Feb | 6 | 4 | 1 | 18.87% | 7.4625 | 0%
2031-02-07 | 2031 | 2 | Feb | 7 | 5 | 1 | 18.87% | 7.4625 | 0%
2031-02-08 | 2031 | 2 | Feb | 8 | 6 | 0 | 18.87% | 7.4625 | 0%
2031-02-09 | 2031 | 2 | Feb | 9 | 7 | 0 | 18.87% | 7.4625 | 0%
2031-02-10 | 2031 | 2 | Feb | 10 | 1 | 1 | 18.87% | 7.4625 | 0%
2031-02-11 | 2031 | 2 | Feb | 11 | 2 | 1 | 18.87% | 7.4625 | 0%
2031-02-12 | 2031 | 2 | Feb | 12 | 3 | 1 | 18.87% | 7.4625 | 0%
2031-02-13 | 2031 | 2 | Feb | 13 | 4 | 1 | 18.87% | 7.4625 | 0%
2031-02-14 | 2031 | 2 | Feb | 14 | 5 | 1 | 18.87% | 7.4625 | 0%
2031-02-15 | 2031 | 2 | Feb | 15 | 6 | 0 | 18.87% | 7.4625 | 0%
2031-02-16 | 2031 | 2 | Feb | 16 | 7 | 0 | 18.87% | 7.4625 | 0%
2031-02-17 | 2031 | 2 | Feb | 17 | 1 | 1 | 18.87% | 7.4625 | 0%
2031-02-18 | 2031 | 2 | Feb | 18 | 2 | 1 | 18.87% | 7.4625 | 0%
2031-02-19 | 2031 | 2 | Feb | 19 | 3 | 1 | 18.87% | 7.4625 | 0%
2031-02-20 | 2031 | 2 | Feb | 20 | 4 | 1 | 18.87% | 7.4625 | 0%
2031-02-21 | 2031 | 2 | Feb | 21 | 5 | 1 | 18.87% | 7.4625 | 0%
2031-02-22 | 2031 | 2 | Feb | 22 | 6 | 0 | 18.87% | 7.4625 | 0%
2031-02-23 | 2031 | 2 | Feb | 23 | 7 | 0 | 18.87% | 7.4625 | 0%
2031-02-24 | 2031 | 2 | Feb | 24 | 1 | 1 | 18.87% | 7.4625 | 0%
2031-02-25 | 2031 | 2 | Feb | 25 | 2 | 1 | 18.87% | 7.4625 | 0%
2031-02-26 | 2031 | 2 | Feb | 26 | 3 | 1 | 18.87% | 7.4625 | 0%
2031-02-27 | 2031 | 2 | Feb | 27 | 4 | 1 | 18.87% | 7.4625 | 0%
2031-02-28 | 2031 | 2 | Feb | 28 | 5 | 1 | 18.87% | 7.4625 | 0%
2031-03-01 | 2031 | 3 | Mar | 1 | 6 | 0 | 18.49% | 7.8663 | 0%
2031-03-02 | 2031 | 3 | Mar | 2 | 7 | 0 | 18.49% | 7.8663 | 0%
2031-03-03 | 2031 | 3 | Mar | 3 | 1 | 1 | 18.49% | 7.8663 | 0%
2031-03-04 | 2031 | 3 | Mar | 4 | 2 | 1 | 18.49% | 7.8663 | 0%
2031-03-05 | 2031 | 3 | Mar | 5 | 3 | 1 | 18.49% | 7.8663 | 0%
2031-03-06 | 2031 | 3 | Mar | 6 | 4 | 1 | 18.49% | 7.8663 | 0%
2031-03-07 | 2031 | 3 | Mar | 7 | 5 | 1 | 18.49% | 7.8663 | 0%
2031-03-08 | 2031 | 3 | Mar | 8 | 6 | 0 | 18.49% | 7.8663 | 0%
2031-03-09 | 2031 | 3 | Mar | 9 | 7 | 0 | 18.49% | 7.8663 | 0%
2031-03-10 | 2031 | 3 | Mar | 10 | 1 | 1 | 18.49% | 7.8663 | 0%
2031-03-11 | 2031 | 3 | Mar | 11 | 2 | 1 | 18.49% | 7.8663 | 0%
2031-03-12 | 2031 | 3 | Mar | 12 | 3 | 1 | 18.49% | 7.8663 | 0%
2031-03-13 | 2031 | 3 | Mar | 13 | 4 | 1 | 18.49% | 7.8663 | 0%
2031-03-14 | 2031 | 3 | Mar | 14 | 5 | 1 | 18.49% | 7.8663 | 0%
2031-03-15 | 2031 | 3 | Mar | 15 | 6 | 0 | 18.49% | 7.8663 | 0%
2031-03-16 | 2031 | 3 | Mar | 16 | 7 | 0 | 18.49% | 7.8663 | 0%
2031-03-17 | 2031 | 3 | Mar | 17 | 1 | 1 | 18.49% | 7.8663 | 0%
2031-03-18 | 2031 | 3 | Mar | 18 | 2 | 1 | 18.49% | 7.8663 | 0%
2031-03-19 | 2031 | 3 | Mar | 19 | 3 | 1 | 18.49% | 7.8663 | 0%
2031-03-20 | 2031 | 3 | Mar | 20 | 4 | 1 | 18.49% | 7.8663 | 0%
2031-03-21 | 2031 | 3 | Mar | 21 | 5 | 1 | 18.49% | 7.8663 | 0%
2031-03-22 | 2031 | 3 | Mar | 22 | 6 | 0 | 18.49% | 7.8663 | 0%
2031-03-23 | 2031 | 3 | Mar | 23 | 7 | 0 | 18.49% | 7.8663 | 0%
2031-03-24 | 2031 | 3 | Mar | 24 | 1 | 1 | 18.49% | 7.8663 | 0%
2031-03-25 | 2031 | 3 | Mar | 25 | 2 | 1 | 18.49% | 7.8663 | 0%
2031-03-26 | 2031 | 3 | Mar | 26 | 3 | 1 | 18.49% | 7.8663 | 0%
2031-03-27 | 2031 | 3 | Mar | 27 | 4 | 1 | 18.49% | 7.8663 | 0%
2031-03-28 | 2031 | 3 | Mar | 28 | 5 | 1 | 18.49% | 7.8663 | 0%
2031-03-29 | 2031 | 3 | Mar | 29 | 6 | 0 | 18.49% | 7.8663 | 0%
2031-03-30 | 2031 | 3 | Mar | 30 | 7 | 0 | 18.49% | 7.8663 | 0%
2031-03-31 | 2031 | 3 | Mar | 31 | 1 | 1 | 18.49% | 7.8663 | 0%
2031-04-01 | 2031 | 4 | Apr | 1 | 2 | 1 | 25.56% | 7.5 | 0%
2031-04-02 | 2031 | 4 | Apr | 2 | 3 | 1 | 25.56% | 7.5 | 0%
2031-04-03 | 2031 | 4 | Apr | 3 | 4 | 1 | 25.56% | 7.5 | 0%
2031-04-04 | 2031 | 4 | Apr | 4 | 5 | 1 | 25.56% | 7.5 | 0%
2031-04-05 | 2031 | 4 | Apr | 5 | 6 | 0 | 25.56% | 7.5 | 0%
2031-04-06 | 2031 | 4 | Apr | 6 | 7 | 0 | 25.56% | 7.5 | 0%
2031-04-07 | 2031 | 4 | Apr | 7 | 1 | 1 | 25.56% | 7.5 | 0%
2031-04-08 | 2031 | 4 | Apr | 8 | 2 | 1 | 25.56% | 7.5 | 0%
2031-04-09 | 2031 | 4 | Apr | 9 | 3 | 1 | 25.56% | 7.5 | 0%
2031-04-10 | 2031 | 4 | Apr | 10 | 4 | 1 | 25.56% | 7.5 | 0%
2031-04-11 | 2031 | 4 | Apr | 11 | 5 | 1 | 25.56% | 7.5 | 0%
2031-04-12 | 2031 | 4 | Apr | 12 | 6 | 0 | 25.56% | 7.5 | 0%
2031-04-13 | 2031 | 4 | Apr | 13 | 7 | 0 | 25.56% | 7.5 | 0%
2031-04-14 | 2031 | 4 | Apr | 14 | 1 | 1 | 25.56% | 7.5 | 0%
2031-04-15 | 2031 | 4 | Apr | 15 | 2 | 1 | 25.56% | 7.5 | 0%
2031-04-16 | 2031 | 4 | Apr | 16 | 3 | 1 | 25.56% | 7.5 | 0%
2031-04-17 | 2031 | 4 | Apr | 17 | 4 | 1 | 25.56% | 7.5 | 0%
2031-04-18 | 2031 | 4 | Apr | 18 | 5 | 1 | 25.56% | 7.5 | 0%
2031-04-19 | 2031 | 4 | Apr | 19 | 6 | 0 | 25.56% | 7.5 | 0%
2031-04-20 | 2031 | 4 | Apr | 20 | 7 | 0 | 25.56% | 7.5 | 0%
2031-04-21 | 2031 | 4 | Apr | 21 | 1 | 1 | 25.56% | 7.5 | 0%
2031-04-22 | 2031 | 4 | Apr | 22 | 2 | 1 | 25.56% | 7.5 | 0%
2031-04-23 | 2031 | 4 | Apr | 23 | 3 | 1 | 25.56% | 7.5 | 0%
2031-04-24 | 2031 | 4 | Apr | 24 | 4 | 1 | 25.56% | 7.5 | 0%
2031-04-25 | 2031 | 4 | Apr | 25 | 5 | 1 | 25.56% | 7.5 | 0%
2031-04-26 | 2031 | 4 | Apr | 26 | 6 | 0 | 25.56% | 7.5 | 0%
2031-04-27 | 2031 | 4 | Apr | 27 | 7 | 0 | 25.56% | 7.5 | 0%
2031-04-28 | 2031 | 4 | Apr | 28 | 1 | 1 | 25.56% | 7.5 | 0%
2031-04-29 | 2031 | 4 | Apr | 29 | 2 | 1 | 25.56% | 7.5 | 0%
2031-04-30 | 2031 | 4 | Apr | 30 | 3 | 1 | 25.56% | 7.5 | 0%
2031-05-01 | 2031 | 5 | May | 1 | 4 | 1 | 23.01% | 8.1449 | 0%
2031-05-02 | 2031 | 5 | May | 2 | 5 | 1 | 23.01% | 8.1449 | 0%
2031-05-03 | 2031 | 5 | May | 3 | 6 | 0 | 23.01% | 8.1449 | 0%
2031-05-04 | 2031 | 5 | May | 4 | 7 | 0 | 23.01% | 8.1449 | 0%
2031-05-05 | 2031 | 5 | May | 5 | 1 | 1 | 23.01% | 8.1449 | 0%
2031-05-06 | 2031 | 5 | May | 6 | 2 | 1 | 23.01% | 8.1449 | 0%
2031-05-07 | 2031 | 5 | May | 7 | 3 | 1 | 23.01% | 8.1449 | 0%
2031-05-08 | 2031 | 5 | May | 8 | 4 | 1 | 23.01% | 8.1449 | 0%
2031-05-09 | 2031 | 5 | May | 9 | 5 | 1 | 23.01% | 8.1449 | 0%
2031-05-10 | 2031 | 5 | May | 10 | 6 | 0 | 23.01% | 8.1449 | 0%
2031-05-11 | 2031 | 5 | May | 11 | 7 | 0 | 23.01% | 8.1449 | 0%
2031-05-12 | 2031 | 5 | May | 12 | 1 | 1 | 23.01% | 8.1449 | 0%
2031-05-13 | 2031 | 5 | May | 13 | 2 | 1 | 23.01% | 8.1449 | 0%
2031-05-14 | 2031 | 5 | May | 14 | 3 | 1 | 23.01% | 8.1449 | 0%
2031-05-15 | 2031 | 5 | May | 15 | 4 | 1 | 23.01% | 8.1449 | 0%
2031-05-16 | 2031 | 5 | May | 16 | 5 | 1 | 23.01% | 8.1449 | 0%
2031-05-17 | 2031 | 5 | May | 17 | 6 | 0 | 23.01% | 8.1449 | 0%
2031-05-18 | 2031 | 5 | May | 18 | 7 | 0 | 23.01% | 8.1449 | 0%
2031-05-19 | 2031 | 5 | May | 19 | 1 | 1 | 23.01% | 8.1449 | 0%
2031-05-20 | 2031 | 5 | May | 20 | 2 | 1 | 23.01% | 8.1449 | 0%
2031-05-21 | 2031 | 5 | May | 21 | 3 | 1 | 23.01% | 8.1449 | 0%
2031-05-22 | 2031 | 5 | May | 22 | 4 | 1 | 23.01% | 8.1449 | 0%
2031-05-23 | 2031 | 5 | May | 23 | 5 | 1 | 23.01% | 8.1449 | 0%
2031-05-24 | 2031 | 5 | May | 24 | 6 | 0 | 23.01% | 8.1449 | 0%
2031-05-25 | 2031 | 5 | May | 25 | 7 | 0 | 23.01% | 8.1449 | 0%
2031-05-26 | 2031 | 5 | May | 26 | 1 | 1 | 23.01% | 8.1449 | 0%
2031-05-27 | 2031 | 5 | May | 27 | 2 | 1 | 23.01% | 8.1449 | 0%
2031-05-28 | 2031 | 5 | May | 28 | 3 | 1 | 23.01% | 8.1449 | 0%
2031-05-29 | 2031 | 5 | May | 29 | 4 | 1 | 23.01% | 8.1449 | 0%
2031-05-30 | 2031 | 5 | May | 30 | 5 | 1 | 23.01% | 8.1449 | 0%
2031-05-31 | 2031 | 5 | May | 31 | 6 | 0 | 23.01% | 8.1449 | 0%
2031-06-01 | 2031 | 6 | Jun | 1 | 7 | 0 | 28.67% | 7.9419 | 0%
2031-06-02 | 2031 | 6 | Jun | 2 | 1 | 1 | 28.67% | 7.9419 | 0%
2031-06-03 | 2031 | 6 | Jun | 3 | 2 | 1 | 28.67% | 7.9419 | 0%
2031-06-04 | 2031 | 6 | Jun | 4 | 3 | 1 | 28.67% | 7.9419 | 0%
2031-06-05 | 2031 | 6 | Jun | 5 | 4 | 1 | 28.67% | 7.9419 | 0%
2031-06-06 | 2031 | 6 | Jun | 6 | 5 | 1 | 28.67% | 7.9419 | 0%
2031-06-07 | 2031 | 6 | Jun | 7 | 6 | 0 | 28.67% | 7.9419 | 0%
2031-06-08 | 2031 | 6 | Jun | 8 | 7 | 0 | 28.67% | 7.9419 | 0%
2031-06-09 | 2031 | 6 | Jun | 9 | 1 | 1 | 28.67% | 7.9419 | 0%
2031-06-10 | 2031 | 6 | Jun | 10 | 2 | 1 | 28.67% | 7.9419 | 0%
2031-06-11 | 2031 | 6 | Jun | 11 | 3 | 1 | 28.67% | 7.9419 | 0%
2031-06-12 | 2031 | 6 | Jun | 12 | 4 | 1 | 28.67% | 7.9419 | 0%
2031-06-13 | 2031 | 6 | Jun | 13 | 5 | 1 | 28.67% | 7.9419 | 0%
2031-06-14 | 2031 | 6 | Jun | 14 | 6 | 0 | 28.67% | 7.9419 | 0%
2031-06-15 | 2031 | 6 | Jun | 15 | 7 | 0 | 28.67% | 7.9419 | 0%
2031-06-16 | 2031 | 6 | Jun | 16 | 1 | 1 | 28.67% | 7.9419 | 0%
2031-06-17 | 2031 | 6 | Jun | 17 | 2 | 1 | 28.67% | 7.9419 | 0%
2031-06-18 | 2031 | 6 | Jun | 18 | 3 | 1 | 28.67% | 7.9419 | 0%
2031-06-19 | 2031 | 6 | Jun | 19 | 4 | 1 | 28.67% | 7.9419 | 0%
2031-06-20 | 2031 | 6 | Jun | 20 | 5 | 1 | 28.67% | 7.9419 | 0%
2031-06-21 | 2031 | 6 | Jun | 21 | 6 | 0 | 28.67% | 7.9419 | 0%
2031-06-22 | 2031 | 6 | Jun | 22 | 7 | 0 | 28.67% | 7.9419 | 0%
2031-06-23 | 2031 | 6 | Jun | 23 | 1 | 1 | 28.67% | 7.9419 | 0%
2031-06-24 | 2031 | 6 | Jun | 24 | 2 | 1 | 28.67% | 7.9419 | 0%
2031-06-25 | 2031 | 6 | Jun | 25 | 3 | 1 | 28.67% | 7.9419 | 0%
2031-06-26 | 2031 | 6 | Jun | 26 | 4 | 1 | 28.67% | 7.9419 | 0%
2031-06-27 | 2031 | 6 | Jun | 27 | 5 | 1 | 28.67% | 7.9419 | 0%
2031-06-28 | 2031 | 6 | Jun | 28 | 6 | 0 | 28.67% | 7.9419 | 0%
2031-06-29 | 2031 | 6 | Jun | 29 | 7 | 0 | 28.67% | 7.9419 | 0%
2031-06-30 | 2031 | 6 | Jun | 30 | 1 | 1 | 28.67% | 7.9419 | 0%
2031-07-01 | 2031 | 7 | Jul | 1 | 2 | 1 | 24.73% | 8.3739 | 0%
2031-07-02 | 2031 | 7 | Jul | 2 | 3 | 1 | 24.73% | 8.3739 | 0%
2031-07-03 | 2031 | 7 | Jul | 3 | 4 | 1 | 24.73% | 8.3739 | 0%
2031-07-04 | 2031 | 7 | Jul | 4 | 5 | 1 | 24.73% | 8.3739 | 0%
2031-07-05 | 2031 | 7 | Jul | 5 | 6 | 0 | 24.73% | 8.3739 | 0%
2031-07-06 | 2031 | 7 | Jul | 6 | 7 | 0 | 24.73% | 8.3739 | 0%
2031-07-07 | 2031 | 7 | Jul | 7 | 1 | 1 | 24.73% | 8.3739 | 0%
2031-07-08 | 2031 | 7 | Jul | 8 | 2 | 1 | 24.73% | 8.3739 | 0%
2031-07-09 | 2031 | 7 | Jul | 9 | 3 | 1 | 24.73% | 8.3739 | 0%
2031-07-10 | 2031 | 7 | Jul | 10 | 4 | 1 | 24.73% | 8.3739 | 0%
2031-07-11 | 2031 | 7 | Jul | 11 | 5 | 1 | 24.73% | 8.3739 | 0%
2031-07-12 | 2031 | 7 | Jul | 12 | 6 | 0 | 24.73% | 8.3739 | 0%
2031-07-13 | 2031 | 7 | Jul | 13 | 7 | 0 | 24.73% | 8.3739 | 0%
2031-07-14 | 2031 | 7 | Jul | 14 | 1 | 1 | 24.73% | 8.3739 | 0%
2031-07-15 | 2031 | 7 | Jul | 15 | 2 | 1 | 24.73% | 8.3739 | 0%
2031-07-16 | 2031 | 7 | Jul | 16 | 3 | 1 | 24.73% | 8.3739 | 0%
2031-07-17 | 2031 | 7 | Jul | 17 | 4 | 1 | 24.73% | 8.3739 | 0%
2031-07-18 | 2031 | 7 | Jul | 18 | 5 | 1 | 24.73% | 8.3739 | 0%
2031-07-19 | 2031 | 7 | Jul | 19 | 6 | 0 | 24.73% | 8.3739 | 0%
2031-07-20 | 2031 | 7 | Jul | 20 | 7 | 0 | 24.73% | 8.3739 | 0%
2031-07-21 | 2031 | 7 | Jul | 21 | 1 | 1 | 24.73% | 8.3739 | 0%
2031-07-22 | 2031 | 7 | Jul | 22 | 2 | 1 | 24.73% | 8.3739 | 0%
2031-07-23 | 2031 | 7 | Jul | 23 | 3 | 1 | 24.73% | 8.3739 | 0%
2031-07-24 | 2031 | 7 | Jul | 24 | 4 | 1 | 24.73% | 8.3739 | 0%
2031-07-25 | 2031 | 7 | Jul | 25 | 5 | 1 | 24.73% | 8.3739 | 0%
2031-07-26 | 2031 | 7 | Jul | 26 | 6 | 0 | 24.73% | 8.3739 | 0%
2031-07-27 | 2031 | 7 | Jul | 27 | 7 | 0 | 24.73% | 8.3739 | 0%
2031-07-28 | 2031 | 7 | Jul | 28 | 1 | 1 | 24.73% | 8.3739 | 0%
2031-07-29 | 2031 | 7 | Jul | 29 | 2 | 1 | 24.73% | 8.3739 | 0%
2031-07-30 | 2031 | 7 | Jul | 30 | 3 | 1 | 24.73% | 8.3739 | 0%
2031-07-31 | 2031 | 7 | Jul | 31 | 4 | 1 | 24.73% | 8.3739 | 0%
2031-08-01 | 2031 | 8 | Aug | 1 | 5 | 1 | 23.55% | 7.9589 | 0%
2031-08-02 | 2031 | 8 | Aug | 2 | 6 | 0 | 23.55% | 7.9589 | 0%
2031-08-03 | 2031 | 8 | Aug | 3 | 7 | 0 | 23.55% | 7.9589 | 0%
2031-08-04 | 2031 | 8 | Aug | 4 | 1 | 1 | 23.55% | 7.9589 | 0%
2031-08-05 | 2031 | 8 | Aug | 5 | 2 | 1 | 23.55% | 7.9589 | 0%
2031-08-06 | 2031 | 8 | Aug | 6 | 3 | 1 | 23.55% | 7.9589 | 0%
2031-08-07 | 2031 | 8 | Aug | 7 | 4 | 1 | 23.55% | 7.9589 | 0%
2031-08-08 | 2031 | 8 | Aug | 8 | 5 | 1 | 23.55% | 7.9589 | 0%
2031-08-09 | 2031 | 8 | Aug | 9 | 6 | 0 | 23.55% | 7.9589 | 0%
2031-08-10 | 2031 | 8 | Aug | 10 | 7 | 0 | 23.55% | 7.9589 | 0%
2031-08-11 | 2031 | 8 | Aug | 11 | 1 | 1 | 23.55% | 7.9589 | 0%
2031-08-12 | 2031 | 8 | Aug | 12 | 2 | 1 | 23.55% | 7.9589 | 0%
2031-08-13 | 2031 | 8 | Aug | 13 | 3 | 1 | 23.55% | 7.9589 | 0%
2031-08-14 | 2031 | 8 | Aug | 14 | 4 | 1 | 23.55% | 7.9589 | 0%
2031-08-15 | 2031 | 8 | Aug | 15 | 5 | 1 | 23.55% | 7.9589 | 0%
2031-08-16 | 2031 | 8 | Aug | 16 | 6 | 0 | 23.55% | 7.9589 | 0%
2031-08-17 | 2031 | 8 | Aug | 17 | 7 | 0 | 23.55% | 7.9589 | 0%
2031-08-18 | 2031 | 8 | Aug | 18 | 1 | 1 | 23.55% | 7.9589 | 0%
2031-08-19 | 2031 | 8 | Aug | 19 | 2 | 1 | 23.55% | 7.9589 | 0%
2031-08-20 | 2031 | 8 | Aug | 20 | 3 | 1 | 23.55% | 7.9589 | 0%
2031-08-21 | 2031 | 8 | Aug | 21 | 4 | 1 | 23.55% | 7.9589 | 0%
2031-08-22 | 2031 | 8 | Aug | 22 | 5 | 1 | 23.55% | 7.9589 | 0%
2031-08-23 | 2031 | 8 | Aug | 23 | 6 | 0 | 23.55% | 7.9589 | 0%
2031-08-24 | 2031 | 8 | Aug | 24 | 7 | 0 | 23.55% | 7.9589 | 0%
2031-08-25 | 2031 | 8 | Aug | 25 | 1 | 1 | 23.55% | 7.9589 | 0%
2031-08-26 | 2031 | 8 | Aug | 26 | 2 | 1 | 23.55% | 7.9589 | 0%
2031-08-27 | 2031 | 8 | Aug | 27 | 3 | 1 | 23.55% | 7.9589 | 0%
2031-08-28 | 2031 | 8 | Aug | 28 | 4 | 1 | 23.55% | 7.9589 | 0%
2031-08-29 | 2031 | 8 | Aug | 29 | 5 | 1 | 23.55% | 7.9589 | 0%
2031-08-30 | 2031 | 8 | Aug | 30 | 6 | 0 | 23.55% | 7.9589 | 0%
2031-08-31 | 2031 | 8 | Aug | 31 | 7 | 0 | 23.55% | 7.9589 | 0%
2031-09-01 | 2031 | 9 | Sep | 1 | 1 | 1 | 20.67% | 6.8065 | 0%
2031-09-02 | 2031 | 9 | Sep | 2 | 2 | 1 | 20.67% | 6.8065 | 0%
2031-09-03 | 2031 | 9 | Sep | 3 | 3 | 1 | 20.67% | 6.8065 | 0%
2031-09-04 | 2031 | 9 | Sep | 4 | 4 | 1 | 20.67% | 6.8065 | 0%
2031-09-05 | 2031 | 9 | Sep | 5 | 5 | 1 | 20.67% | 6.8065 | 0%
2031-09-06 | 2031 | 9 | Sep | 6 | 6 | 0 | 20.67% | 6.8065 | 0%
2031-09-07 | 2031 | 9 | Sep | 7 | 7 | 0 | 20.67% | 6.8065 | 0%
2031-09-08 | 2031 | 9 | Sep | 8 | 1 | 1 | 20.67% | 6.8065 | 0%
2031-09-09 | 2031 | 9 | Sep | 9 | 2 | 1 | 20.67% | 6.8065 | 0%
2031-09-10 | 2031 | 9 | Sep | 10 | 3 | 1 | 20.67% | 6.8065 | 0%
2031-09-11 | 2031 | 9 | Sep | 11 | 4 | 1 | 20.67% | 6.8065 | 0%
2031-09-12 | 2031 | 9 | Sep | 12 | 5 | 1 | 20.67% | 6.8065 | 0%
2031-09-13 | 2031 | 9 | Sep | 13 | 6 | 0 | 20.67% | 6.8065 | 0%
2031-09-14 | 2031 | 9 | Sep | 14 | 7 | 0 | 20.67% | 6.8065 | 0%
2031-09-15 | 2031 | 9 | Sep | 15 | 1 | 1 | 20.67% | 6.8065 | 0%
2031-09-16 | 2031 | 9 | Sep | 16 | 2 | 1 | 20.67% | 6.8065 | 0%
2031-09-17 | 2031 | 9 | Sep | 17 | 3 | 1 | 20.67% | 6.8065 | 0%
2031-09-18 | 2031 | 9 | Sep | 18 | 4 | 1 | 20.67% | 6.8065 | 0%
2031-09-19 | 2031 | 9 | Sep | 19 | 5 | 1 | 20.67% | 6.8065 | 0%
2031-09-20 | 2031 | 9 | Sep | 20 | 6 | 0 | 20.67% | 6.8065 | 0%
2031-09-21 | 2031 | 9 | Sep | 21 | 7 | 0 | 20.67% | 6.8065 | 0%
2031-09-22 | 2031 | 9 | Sep | 22 | 1 | 1 | 20.67% | 6.8065 | 0%
2031-09-23 | 2031 | 9 | Sep | 23 | 2 | 1 | 20.67% | 6.8065 | 0%
2031-09-24 | 2031 | 9 | Sep | 24 | 3 | 1 | 20.67% | 6.8065 | 0%
2031-09-25 | 2031 | 9 | Sep | 25 | 4 | 1 | 20.67% | 6.8065 | 0%
2031-09-26 | 2031 | 9 | Sep | 26 | 5 | 1 | 20.67% | 6.8065 | 0%
2031-09-27 | 2031 | 9 | Sep | 27 | 6 | 0 | 20.67% | 6.8065 | 0%
2031-09-28 | 2031 | 9 | Sep | 28 | 7 | 0 | 20.67% | 6.8065 | 0%
2031-09-29 | 2031 | 9 | Sep | 29 | 1 | 1 | 20.67% | 6.8065 | 0%
2031-09-30 | 2031 | 9 | Sep | 30 | 2 | 1 | 20.67% | 6.8065 | 0%
2031-10-01 | 2031 | 10 | Oct | 1 | 3 | 1 | 23.23% | 6.8194 | 0%
2031-10-02 | 2031 | 10 | Oct | 2 | 4 | 1 | 23.23% | 6.8194 | 0%
2031-10-03 | 2031 | 10 | Oct | 3 | 5 | 1 | 23.23% | 6.8194 | 0%
2031-10-04 | 2031 | 10 | Oct | 4 | 6 | 0 | 23.23% | 6.8194 | 0%
2031-10-05 | 2031 | 10 | Oct | 5 | 7 | 0 | 23.23% | 6.8194 | 0%
2031-10-06 | 2031 | 10 | Oct | 6 | 1 | 1 | 23.23% | 6.8194 | 0%
2031-10-07 | 2031 | 10 | Oct | 7 | 2 | 1 | 23.23% | 6.8194 | 0%
2031-10-08 | 2031 | 10 | Oct | 8 | 3 | 1 | 23.23% | 6.8194 | 0%
2031-10-09 | 2031 | 10 | Oct | 9 | 4 | 1 | 23.23% | 6.8194 | 0%
2031-10-10 | 2031 | 10 | Oct | 10 | 5 | 1 | 23.23% | 6.8194 | 0%
2031-10-11 | 2031 | 10 | Oct | 11 | 6 | 0 | 23.23% | 6.8194 | 0%
2031-10-12 | 2031 | 10 | Oct | 12 | 7 | 0 | 23.23% | 6.8194 | 0%
2031-10-13 | 2031 | 10 | Oct | 13 | 1 | 1 | 23.23% | 6.8194 | 0%
2031-10-14 | 2031 | 10 | Oct | 14 | 2 | 1 | 23.23% | 6.8194 | 0%
2031-10-15 | 2031 | 10 | Oct | 15 | 3 | 1 | 23.23% | 6.8194 | 0%
2031-10-16 | 2031 | 10 | Oct | 16 | 4 | 1 | 23.23% | 6.8194 | 0%
2031-10-17 | 2031 | 10 | Oct | 17 | 5 | 1 | 23.23% | 6.8194 | 0%
2031-10-18 | 2031 | 10 | Oct | 18 | 6 | 0 | 23.23% | 6.8194 | 0%
2031-10-19 | 2031 | 10 | Oct | 19 | 7 | 0 | 23.23% | 6.8194 | 0%
2031-10-20 | 2031 | 10 | Oct | 20 | 1 | 1 | 23.23% | 6.8194 | 0%
2031-10-21 | 2031 | 10 | Oct | 21 | 2 | 1 | 23.23% | 6.8194 | 0%
2031-10-22 | 2031 | 10 | Oct | 22 | 3 | 1 | 23.23% | 6.8194 | 0%
2031-10-23 | 2031 | 10 | Oct | 23 | 4 | 1 | 23.23% | 6.8194 | 0%
2031-10-24 | 2031 | 10 | Oct | 24 | 5 | 1 | 23.23% | 6.8194 | 0%
2031-10-25 | 2031 | 10 | Oct | 25 | 6 | 0 | 23.23% | 6.8194 | 0%
2031-10-26 | 2031 | 10 | Oct | 26 | 7 | 0 | 23.23% | 6.8194 | 0%
2031-10-27 | 2031 | 10 | Oct | 27 | 1 | 1 | 23.23% | 6.8194 | 0%
2031-10-28 | 2031 | 10 | Oct | 28 | 2 | 1 | 23.23% | 6.8194 | 0%
2031-10-29 | 2031 | 10 | Oct | 29 | 3 | 1 | 23.23% | 6.8194 | 0%
2031-10-30 | 2031 | 10 | Oct | 30 | 4 | 1 | 23.23% | 6.8194 | 0%
2031-10-31 | 2031 | 10 | Oct | 31 | 5 | 1 | 23.23% | 6.8194 | 0%
2031-11-01 | 2031 | 11 | Nov | 1 | 6 | 0 | 23.33% | 6.4429 | 0%
2031-11-02 | 2031 | 11 | Nov | 2 | 7 | 0 | 23.33% | 6.4429 | 0%
2031-11-03 | 2031 | 11 | Nov | 3 | 1 | 1 | 23.33% | 6.4429 | 0%
2031-11-04 | 2031 | 11 | Nov | 4 | 2 | 1 | 23.33% | 6.4429 | 0%
2031-11-05 | 2031 | 11 | Nov | 5 | 3 | 1 | 23.33% | 6.4429 | 0%
2031-11-06 | 2031 | 11 | Nov | 6 | 4 | 1 | 23.33% | 6.4429 | 0%
2031-11-07 | 2031 | 11 | Nov | 7 | 5 | 1 | 23.33% | 6.4429 | 0%
2031-11-08 | 2031 | 11 | Nov | 8 | 6 | 0 | 23.33% | 6.4429 | 0%
2031-11-09 | 2031 | 11 | Nov | 9 | 7 | 0 | 23.33% | 6.4429 | 0%
2031-11-10 | 2031 | 11 | Nov | 10 | 1 | 1 | 23.33% | 6.4429 | 0%
2031-11-11 | 2031 | 11 | Nov | 11 | 2 | 1 | 23.33% | 6.4429 | 0%
2031-11-12 | 2031 | 11 | Nov | 12 | 3 | 1 | 23.33% | 6.4429 | 0%
2031-11-13 | 2031 | 11 | Nov | 13 | 4 | 1 | 23.33% | 6.4429 | 0%
2031-11-14 | 2031 | 11 | Nov | 14 | 5 | 1 | 23.33% | 6.4429 | 0%
2031-11-15 | 2031 | 11 | Nov | 15 | 6 | 0 | 23.33% | 6.4429 | 0%
2031-11-16 | 2031 | 11 | Nov | 16 | 7 | 0 | 23.33% | 6.4429 | 0%
2031-11-17 | 2031 | 11 | Nov | 17 | 1 | 1 | 23.33% | 6.4429 | 0%
2031-11-18 | 2031 | 11 | Nov | 18 | 2 | 1 | 23.33% | 6.4429 | 0%
2031-11-19 | 2031 | 11 | Nov | 19 | 3 | 1 | 23.33% | 6.4429 | 0%
2031-11-20 | 2031 | 11 | Nov | 20 | 4 | 1 | 23.33% | 6.4429 | 0%
2031-11-21 | 2031 | 11 | Nov | 21 | 5 | 1 | 23.33% | 6.4429 | 0%
2031-11-22 | 2031 | 11 | Nov | 22 | 6 | 0 | 23.33% | 6.4429 | 0%
2031-11-23 | 2031 | 11 | Nov | 23 | 7 | 0 | 23.33% | 6.4429 | 0%
2031-11-24 | 2031 | 11 | Nov | 24 | 1 | 1 | 23.33% | 6.4429 | 0%
2031-11-25 | 2031 | 11 | Nov | 25 | 2 | 1 | 23.33% | 6.4429 | 0%
2031-11-26 | 2031 | 11 | Nov | 26 | 3 | 1 | 23.33% | 6.4429 | 0%
2031-11-27 | 2031 | 11 | Nov | 27 | 4 | 1 | 23.33% | 6.4429 | 0%
2031-11-28 | 2031 | 11 | Nov | 28 | 5 | 1 | 23.33% | 6.4429 | 0%
2031-11-29 | 2031 | 11 | Nov | 29 | 6 | 0 | 23.33% | 6.4429 | 0%
2031-11-30 | 2031 | 11 | Nov | 30 | 7 | 0 | 23.33% | 6.4429 | 0%
2031-12-01 | 2031 | 12 | Dec | 1 | 1 | 1 | 22.69% | 6.7962 | 0%
2031-12-02 | 2031 | 12 | Dec | 2 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-12-03 | 2031 | 12 | Dec | 3 | 3 | 1 | 22.69% | 6.7962 | 0%
2031-12-04 | 2031 | 12 | Dec | 4 | 4 | 1 | 22.69% | 6.7962 | 0%
2031-12-05 | 2031 | 12 | Dec | 5 | 5 | 1 | 22.69% | 6.7962 | 0%
2031-12-06 | 2031 | 12 | Dec | 6 | 6 | 0 | 22.69% | 6.7962 | 0%
2031-12-07 | 2031 | 12 | Dec | 7 | 7 | 0 | 22.69% | 6.7962 | 0%
2031-12-08 | 2031 | 12 | Dec | 8 | 1 | 1 | 22.69% | 6.7962 | 0%
2031-12-09 | 2031 | 12 | Dec | 9 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-12-10 | 2031 | 12 | Dec | 10 | 3 | 1 | 22.69% | 6.7962 | 0%
2031-12-11 | 2031 | 12 | Dec | 11 | 4 | 1 | 22.69% | 6.7962 | 0%
2031-12-12 | 2031 | 12 | Dec | 12 | 5 | 1 | 22.69% | 6.7962 | 0%
2031-12-13 | 2031 | 12 | Dec | 13 | 6 | 0 | 22.69% | 6.7962 | 0%
2031-12-14 | 2031 | 12 | Dec | 14 | 7 | 0 | 22.69% | 6.7962 | 0%
2031-12-15 | 2031 | 12 | Dec | 15 | 1 | 1 | 22.69% | 6.7962 | 0%
2031-12-16 | 2031 | 12 | Dec | 16 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-12-17 | 2031 | 12 | Dec | 17 | 3 | 1 | 22.69% | 6.7962 | 0%
2031-12-18 | 2031 | 12 | Dec | 18 | 4 | 1 | 22.69% | 6.7962 | 0%
2031-12-19 | 2031 | 12 | Dec | 19 | 5 | 1 | 22.69% | 6.7962 | 0%
2031-12-20 | 2031 | 12 | Dec | 20 | 6 | 0 | 22.69% | 6.7962 | 0%
2031-12-21 | 2031 | 12 | Dec | 21 | 7 | 0 | 22.69% | 6.7962 | 0%
2031-12-22 | 2031 | 12 | Dec | 22 | 1 | 1 | 22.69% | 6.7962 | 0%
2031-12-23 | 2031 | 12 | Dec | 23 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-12-24 | 2031 | 12 | Dec | 24 | 3 | 1 | 22.69% | 6.7962 | 0%
2031-12-25 | 2031 | 12 | Dec | 25 | 4 | 1 | 22.69% | 6.7962 | 0%
2031-12-26 | 2031 | 12 | Dec | 26 | 5 | 1 | 22.69% | 6.7962 | 0%
2031-12-27 | 2031 | 12 | Dec | 27 | 6 | 0 | 22.69% | 6.7962 | 0%
2031-12-28 | 2031 | 12 | Dec | 28 | 7 | 0 | 22.69% | 6.7962 | 0%
2031-12-29 | 2031 | 12 | Dec | 29 | 1 | 1 | 22.69% | 6.7962 | 0%
2031-12-30 | 2031 | 12 | Dec | 30 | 2 | 1 | 22.69% | 6.7962 | 0%
2031-12-31 | 2031 | 12 | Dec | 31 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-01-01 | 2032 | 1 | Jan | 1 | 4 | 1 | 19.46% | 7.0276 | 0%
2032-01-02 | 2032 | 1 | Jan | 2 | 5 | 1 | 19.46% | 7.0276 | 0%
2032-01-03 | 2032 | 1 | Jan | 3 | 6 | 0 | 19.46% | 7.0276 | 0%
2032-01-04 | 2032 | 1 | Jan | 4 | 7 | 0 | 19.46% | 7.0276 | 0%
2032-01-05 | 2032 | 1 | Jan | 5 | 1 | 1 | 19.46% | 7.0276 | 0%
2032-01-06 | 2032 | 1 | Jan | 6 | 2 | 1 | 19.46% | 7.0276 | 0%
2032-01-07 | 2032 | 1 | Jan | 7 | 3 | 1 | 19.46% | 7.0276 | 0%
2032-01-08 | 2032 | 1 | Jan | 8 | 4 | 1 | 19.46% | 7.0276 | 0%
2032-01-09 | 2032 | 1 | Jan | 9 | 5 | 1 | 19.46% | 7.0276 | 0%
2032-01-10 | 2032 | 1 | Jan | 10 | 6 | 0 | 19.46% | 7.0276 | 0%
2032-01-11 | 2032 | 1 | Jan | 11 | 7 | 0 | 19.46% | 7.0276 | 0%
2032-01-12 | 2032 | 1 | Jan | 12 | 1 | 1 | 19.46% | 7.0276 | 0%
2032-01-13 | 2032 | 1 | Jan | 13 | 2 | 1 | 19.46% | 7.0276 | 0%
2032-01-14 | 2032 | 1 | Jan | 14 | 3 | 1 | 19.46% | 7.0276 | 0%
2032-01-15 | 2032 | 1 | Jan | 15 | 4 | 1 | 19.46% | 7.0276 | 0%
2032-01-16 | 2032 | 1 | Jan | 16 | 5 | 1 | 19.46% | 7.0276 | 0%
2032-01-17 | 2032 | 1 | Jan | 17 | 6 | 0 | 19.46% | 7.0276 | 0%
2032-01-18 | 2032 | 1 | Jan | 18 | 7 | 0 | 19.46% | 7.0276 | 0%
2032-01-19 | 2032 | 1 | Jan | 19 | 1 | 1 | 19.46% | 7.0276 | 0%
2032-01-20 | 2032 | 1 | Jan | 20 | 2 | 1 | 19.46% | 7.0276 | 0%
2032-01-21 | 2032 | 1 | Jan | 21 | 3 | 1 | 19.46% | 7.0276 | 0%
2032-01-22 | 2032 | 1 | Jan | 22 | 4 | 1 | 19.46% | 7.0276 | 0%
2032-01-23 | 2032 | 1 | Jan | 23 | 5 | 1 | 19.46% | 7.0276 | 0%
2032-01-24 | 2032 | 1 | Jan | 24 | 6 | 0 | 19.46% | 7.0276 | 0%
2032-01-25 | 2032 | 1 | Jan | 25 | 7 | 0 | 19.46% | 7.0276 | 0%
2032-01-26 | 2032 | 1 | Jan | 26 | 1 | 1 | 19.46% | 7.0276 | 0%
2032-01-27 | 2032 | 1 | Jan | 27 | 2 | 1 | 19.46% | 7.0276 | 0%
2032-01-28 | 2032 | 1 | Jan | 28 | 3 | 1 | 19.46% | 7.0276 | 0%
2032-01-29 | 2032 | 1 | Jan | 29 | 4 | 1 | 19.46% | 7.0276 | 0%
2032-01-30 | 2032 | 1 | Jan | 30 | 5 | 1 | 19.46% | 7.0276 | 0%
2032-01-31 | 2032 | 1 | Jan | 31 | 6 | 0 | 19.46% | 7.0276 | 0%
2032-02-01 | 2032 | 2 | Feb | 1 | 7 | 0 | 18.87% | 7.4625 | 0%
2032-02-02 | 2032 | 2 | Feb | 2 | 1 | 1 | 18.87% | 7.4625 | 0%
2032-02-03 | 2032 | 2 | Feb | 3 | 2 | 1 | 18.87% | 7.4625 | 0%
2032-02-04 | 2032 | 2 | Feb | 4 | 3 | 1 | 18.87% | 7.4625 | 0%
2032-02-05 | 2032 | 2 | Feb | 5 | 4 | 1 | 18.87% | 7.4625 | 0%
2032-02-06 | 2032 | 2 | Feb | 6 | 5 | 1 | 18.87% | 7.4625 | 0%
2032-02-07 | 2032 | 2 | Feb | 7 | 6 | 0 | 18.87% | 7.4625 | 0%
2032-02-08 | 2032 | 2 | Feb | 8 | 7 | 0 | 18.87% | 7.4625 | 0%
2032-02-09 | 2032 | 2 | Feb | 9 | 1 | 1 | 18.87% | 7.4625 | 0%
2032-02-10 | 2032 | 2 | Feb | 10 | 2 | 1 | 18.87% | 7.4625 | 0%
2032-02-11 | 2032 | 2 | Feb | 11 | 3 | 1 | 18.87% | 7.4625 | 0%
2032-02-12 | 2032 | 2 | Feb | 12 | 4 | 1 | 18.87% | 7.4625 | 0%
2032-02-13 | 2032 | 2 | Feb | 13 | 5 | 1 | 18.87% | 7.4625 | 0%
2032-02-14 | 2032 | 2 | Feb | 14 | 6 | 0 | 18.87% | 7.4625 | 0%
2032-02-15 | 2032 | 2 | Feb | 15 | 7 | 0 | 18.87% | 7.4625 | 0%
2032-02-16 | 2032 | 2 | Feb | 16 | 1 | 1 | 18.87% | 7.4625 | 0%
2032-02-17 | 2032 | 2 | Feb | 17 | 2 | 1 | 18.87% | 7.4625 | 0%
2032-02-18 | 2032 | 2 | Feb | 18 | 3 | 1 | 18.87% | 7.4625 | 0%
2032-02-19 | 2032 | 2 | Feb | 19 | 4 | 1 | 18.87% | 7.4625 | 0%
2032-02-20 | 2032 | 2 | Feb | 20 | 5 | 1 | 18.87% | 7.4625 | 0%
2032-02-21 | 2032 | 2 | Feb | 21 | 6 | 0 | 18.87% | 7.4625 | 0%
2032-02-22 | 2032 | 2 | Feb | 22 | 7 | 0 | 18.87% | 7.4625 | 0%
2032-02-23 | 2032 | 2 | Feb | 23 | 1 | 1 | 18.87% | 7.4625 | 0%
2032-02-24 | 2032 | 2 | Feb | 24 | 2 | 1 | 18.87% | 7.4625 | 0%
2032-02-25 | 2032 | 2 | Feb | 25 | 3 | 1 | 18.87% | 7.4625 | 0%
2032-02-26 | 2032 | 2 | Feb | 26 | 4 | 1 | 18.87% | 7.4625 | 0%
2032-02-27 | 2032 | 2 | Feb | 27 | 5 | 1 | 18.87% | 7.4625 | 0%
2032-02-28 | 2032 | 2 | Feb | 28 | 6 | 0 | 18.87% | 7.4625 | 0%
2032-02-29 | 2032 | 2 | Feb | 29 | 7 | 0 | 18.87% | 7.4625 | 0%
2032-03-01 | 2032 | 3 | Mar | 1 | 1 | 1 | 18.49% | 7.8663 | 0%
2032-03-02 | 2032 | 3 | Mar | 2 | 2 | 1 | 18.49% | 7.8663 | 0%
2032-03-03 | 2032 | 3 | Mar | 3 | 3 | 1 | 18.49% | 7.8663 | 0%
2032-03-04 | 2032 | 3 | Mar | 4 | 4 | 1 | 18.49% | 7.8663 | 0%
2032-03-05 | 2032 | 3 | Mar | 5 | 5 | 1 | 18.49% | 7.8663 | 0%
2032-03-06 | 2032 | 3 | Mar | 6 | 6 | 0 | 18.49% | 7.8663 | 0%
2032-03-07 | 2032 | 3 | Mar | 7 | 7 | 0 | 18.49% | 7.8663 | 0%
2032-03-08 | 2032 | 3 | Mar | 8 | 1 | 1 | 18.49% | 7.8663 | 0%
2032-03-09 | 2032 | 3 | Mar | 9 | 2 | 1 | 18.49% | 7.8663 | 0%
2032-03-10 | 2032 | 3 | Mar | 10 | 3 | 1 | 18.49% | 7.8663 | 0%
2032-03-11 | 2032 | 3 | Mar | 11 | 4 | 1 | 18.49% | 7.8663 | 0%
2032-03-12 | 2032 | 3 | Mar | 12 | 5 | 1 | 18.49% | 7.8663 | 0%
2032-03-13 | 2032 | 3 | Mar | 13 | 6 | 0 | 18.49% | 7.8663 | 0%
2032-03-14 | 2032 | 3 | Mar | 14 | 7 | 0 | 18.49% | 7.8663 | 0%
2032-03-15 | 2032 | 3 | Mar | 15 | 1 | 1 | 18.49% | 7.8663 | 0%
2032-03-16 | 2032 | 3 | Mar | 16 | 2 | 1 | 18.49% | 7.8663 | 0%
2032-03-17 | 2032 | 3 | Mar | 17 | 3 | 1 | 18.49% | 7.8663 | 0%
2032-03-18 | 2032 | 3 | Mar | 18 | 4 | 1 | 18.49% | 7.8663 | 0%
2032-03-19 | 2032 | 3 | Mar | 19 | 5 | 1 | 18.49% | 7.8663 | 0%
2032-03-20 | 2032 | 3 | Mar | 20 | 6 | 0 | 18.49% | 7.8663 | 0%
2032-03-21 | 2032 | 3 | Mar | 21 | 7 | 0 | 18.49% | 7.8663 | 0%
2032-03-22 | 2032 | 3 | Mar | 22 | 1 | 1 | 18.49% | 7.8663 | 0%
2032-03-23 | 2032 | 3 | Mar | 23 | 2 | 1 | 18.49% | 7.8663 | 0%
2032-03-24 | 2032 | 3 | Mar | 24 | 3 | 1 | 18.49% | 7.8663 | 0%
2032-03-25 | 2032 | 3 | Mar | 25 | 4 | 1 | 18.49% | 7.8663 | 0%
2032-03-26 | 2032 | 3 | Mar | 26 | 5 | 1 | 18.49% | 7.8663 | 0%
2032-03-27 | 2032 | 3 | Mar | 27 | 6 | 0 | 18.49% | 7.8663 | 0%
2032-03-28 | 2032 | 3 | Mar | 28 | 7 | 0 | 18.49% | 7.8663 | 0%
2032-03-29 | 2032 | 3 | Mar | 29 | 1 | 1 | 18.49% | 7.8663 | 0%
2032-03-30 | 2032 | 3 | Mar | 30 | 2 | 1 | 18.49% | 7.8663 | 0%
2032-03-31 | 2032 | 3 | Mar | 31 | 3 | 1 | 18.49% | 7.8663 | 0%
2032-04-01 | 2032 | 4 | Apr | 1 | 4 | 1 | 25.56% | 7.5 | 0%
2032-04-02 | 2032 | 4 | Apr | 2 | 5 | 1 | 25.56% | 7.5 | 0%
2032-04-03 | 2032 | 4 | Apr | 3 | 6 | 0 | 25.56% | 7.5 | 0%
2032-04-04 | 2032 | 4 | Apr | 4 | 7 | 0 | 25.56% | 7.5 | 0%
2032-04-05 | 2032 | 4 | Apr | 5 | 1 | 1 | 25.56% | 7.5 | 0%
2032-04-06 | 2032 | 4 | Apr | 6 | 2 | 1 | 25.56% | 7.5 | 0%
2032-04-07 | 2032 | 4 | Apr | 7 | 3 | 1 | 25.56% | 7.5 | 0%
2032-04-08 | 2032 | 4 | Apr | 8 | 4 | 1 | 25.56% | 7.5 | 0%
2032-04-09 | 2032 | 4 | Apr | 9 | 5 | 1 | 25.56% | 7.5 | 0%
2032-04-10 | 2032 | 4 | Apr | 10 | 6 | 0 | 25.56% | 7.5 | 0%
2032-04-11 | 2032 | 4 | Apr | 11 | 7 | 0 | 25.56% | 7.5 | 0%
2032-04-12 | 2032 | 4 | Apr | 12 | 1 | 1 | 25.56% | 7.5 | 0%
2032-04-13 | 2032 | 4 | Apr | 13 | 2 | 1 | 25.56% | 7.5 | 0%
2032-04-14 | 2032 | 4 | Apr | 14 | 3 | 1 | 25.56% | 7.5 | 0%
2032-04-15 | 2032 | 4 | Apr | 15 | 4 | 1 | 25.56% | 7.5 | 0%
2032-04-16 | 2032 | 4 | Apr | 16 | 5 | 1 | 25.56% | 7.5 | 0%
2032-04-17 | 2032 | 4 | Apr | 17 | 6 | 0 | 25.56% | 7.5 | 0%
2032-04-18 | 2032 | 4 | Apr | 18 | 7 | 0 | 25.56% | 7.5 | 0%
2032-04-19 | 2032 | 4 | Apr | 19 | 1 | 1 | 25.56% | 7.5 | 0%
2032-04-20 | 2032 | 4 | Apr | 20 | 2 | 1 | 25.56% | 7.5 | 0%
2032-04-21 | 2032 | 4 | Apr | 21 | 3 | 1 | 25.56% | 7.5 | 0%
2032-04-22 | 2032 | 4 | Apr | 22 | 4 | 1 | 25.56% | 7.5 | 0%
2032-04-23 | 2032 | 4 | Apr | 23 | 5 | 1 | 25.56% | 7.5 | 0%
2032-04-24 | 2032 | 4 | Apr | 24 | 6 | 0 | 25.56% | 7.5 | 0%
2032-04-25 | 2032 | 4 | Apr | 25 | 7 | 0 | 25.56% | 7.5 | 0%
2032-04-26 | 2032 | 4 | Apr | 26 | 1 | 1 | 25.56% | 7.5 | 0%
2032-04-27 | 2032 | 4 | Apr | 27 | 2 | 1 | 25.56% | 7.5 | 0%
2032-04-28 | 2032 | 4 | Apr | 28 | 3 | 1 | 25.56% | 7.5 | 0%
2032-04-29 | 2032 | 4 | Apr | 29 | 4 | 1 | 25.56% | 7.5 | 0%
2032-04-30 | 2032 | 4 | Apr | 30 | 5 | 1 | 25.56% | 7.5 | 0%
2032-05-01 | 2032 | 5 | May | 1 | 6 | 0 | 23.01% | 8.1449 | 0%
2032-05-02 | 2032 | 5 | May | 2 | 7 | 0 | 23.01% | 8.1449 | 0%
2032-05-03 | 2032 | 5 | May | 3 | 1 | 1 | 23.01% | 8.1449 | 0%
2032-05-04 | 2032 | 5 | May | 4 | 2 | 1 | 23.01% | 8.1449 | 0%
2032-05-05 | 2032 | 5 | May | 5 | 3 | 1 | 23.01% | 8.1449 | 0%
2032-05-06 | 2032 | 5 | May | 6 | 4 | 1 | 23.01% | 8.1449 | 0%
2032-05-07 | 2032 | 5 | May | 7 | 5 | 1 | 23.01% | 8.1449 | 0%
2032-05-08 | 2032 | 5 | May | 8 | 6 | 0 | 23.01% | 8.1449 | 0%
2032-05-09 | 2032 | 5 | May | 9 | 7 | 0 | 23.01% | 8.1449 | 0%
2032-05-10 | 2032 | 5 | May | 10 | 1 | 1 | 23.01% | 8.1449 | 0%
2032-05-11 | 2032 | 5 | May | 11 | 2 | 1 | 23.01% | 8.1449 | 0%
2032-05-12 | 2032 | 5 | May | 12 | 3 | 1 | 23.01% | 8.1449 | 0%
2032-05-13 | 2032 | 5 | May | 13 | 4 | 1 | 23.01% | 8.1449 | 0%
2032-05-14 | 2032 | 5 | May | 14 | 5 | 1 | 23.01% | 8.1449 | 0%
2032-05-15 | 2032 | 5 | May | 15 | 6 | 0 | 23.01% | 8.1449 | 0%
2032-05-16 | 2032 | 5 | May | 16 | 7 | 0 | 23.01% | 8.1449 | 0%
2032-05-17 | 2032 | 5 | May | 17 | 1 | 1 | 23.01% | 8.1449 | 0%
2032-05-18 | 2032 | 5 | May | 18 | 2 | 1 | 23.01% | 8.1449 | 0%
2032-05-19 | 2032 | 5 | May | 19 | 3 | 1 | 23.01% | 8.1449 | 0%
2032-05-20 | 2032 | 5 | May | 20 | 4 | 1 | 23.01% | 8.1449 | 0%
2032-05-21 | 2032 | 5 | May | 21 | 5 | 1 | 23.01% | 8.1449 | 0%
2032-05-22 | 2032 | 5 | May | 22 | 6 | 0 | 23.01% | 8.1449 | 0%
2032-05-23 | 2032 | 5 | May | 23 | 7 | 0 | 23.01% | 8.1449 | 0%
2032-05-24 | 2032 | 5 | May | 24 | 1 | 1 | 23.01% | 8.1449 | 0%
2032-05-25 | 2032 | 5 | May | 25 | 2 | 1 | 23.01% | 8.1449 | 0%
2032-05-26 | 2032 | 5 | May | 26 | 3 | 1 | 23.01% | 8.1449 | 0%
2032-05-27 | 2032 | 5 | May | 27 | 4 | 1 | 23.01% | 8.1449 | 0%
2032-05-28 | 2032 | 5 | May | 28 | 5 | 1 | 23.01% | 8.1449 | 0%
2032-05-29 | 2032 | 5 | May | 29 | 6 | 0 | 23.01% | 8.1449 | 0%
2032-05-30 | 2032 | 5 | May | 30 | 7 | 0 | 23.01% | 8.1449 | 0%
2032-05-31 | 2032 | 5 | May | 31 | 1 | 1 | 23.01% | 8.1449 | 0%
2032-06-01 | 2032 | 6 | Jun | 1 | 2 | 1 | 28.67% | 7.9419 | 0%
2032-06-02 | 2032 | 6 | Jun | 2 | 3 | 1 | 28.67% | 7.9419 | 0%
2032-06-03 | 2032 | 6 | Jun | 3 | 4 | 1 | 28.67% | 7.9419 | 0%
2032-06-04 | 2032 | 6 | Jun | 4 | 5 | 1 | 28.67% | 7.9419 | 0%
2032-06-05 | 2032 | 6 | Jun | 5 | 6 | 0 | 28.67% | 7.9419 | 0%
2032-06-06 | 2032 | 6 | Jun | 6 | 7 | 0 | 28.67% | 7.9419 | 0%
2032-06-07 | 2032 | 6 | Jun | 7 | 1 | 1 | 28.67% | 7.9419 | 0%
2032-06-08 | 2032 | 6 | Jun | 8 | 2 | 1 | 28.67% | 7.9419 | 0%
2032-06-09 | 2032 | 6 | Jun | 9 | 3 | 1 | 28.67% | 7.9419 | 0%
2032-06-10 | 2032 | 6 | Jun | 10 | 4 | 1 | 28.67% | 7.9419 | 0%
2032-06-11 | 2032 | 6 | Jun | 11 | 5 | 1 | 28.67% | 7.9419 | 0%
2032-06-12 | 2032 | 6 | Jun | 12 | 6 | 0 | 28.67% | 7.9419 | 0%
2032-06-13 | 2032 | 6 | Jun | 13 | 7 | 0 | 28.67% | 7.9419 | 0%
2032-06-14 | 2032 | 6 | Jun | 14 | 1 | 1 | 28.67% | 7.9419 | 0%
2032-06-15 | 2032 | 6 | Jun | 15 | 2 | 1 | 28.67% | 7.9419 | 0%
2032-06-16 | 2032 | 6 | Jun | 16 | 3 | 1 | 28.67% | 7.9419 | 0%
2032-06-17 | 2032 | 6 | Jun | 17 | 4 | 1 | 28.67% | 7.9419 | 0%
2032-06-18 | 2032 | 6 | Jun | 18 | 5 | 1 | 28.67% | 7.9419 | 0%
2032-06-19 | 2032 | 6 | Jun | 19 | 6 | 0 | 28.67% | 7.9419 | 0%
2032-06-20 | 2032 | 6 | Jun | 20 | 7 | 0 | 28.67% | 7.9419 | 0%
2032-06-21 | 2032 | 6 | Jun | 21 | 1 | 1 | 28.67% | 7.9419 | 0%
2032-06-22 | 2032 | 6 | Jun | 22 | 2 | 1 | 28.67% | 7.9419 | 0%
2032-06-23 | 2032 | 6 | Jun | 23 | 3 | 1 | 28.67% | 7.9419 | 0%
2032-06-24 | 2032 | 6 | Jun | 24 | 4 | 1 | 28.67% | 7.9419 | 0%
2032-06-25 | 2032 | 6 | Jun | 25 | 5 | 1 | 28.67% | 7.9419 | 0%
2032-06-26 | 2032 | 6 | Jun | 26 | 6 | 0 | 28.67% | 7.9419 | 0%
2032-06-27 | 2032 | 6 | Jun | 27 | 7 | 0 | 28.67% | 7.9419 | 0%
2032-06-28 | 2032 | 6 | Jun | 28 | 1 | 1 | 28.67% | 7.9419 | 0%
2032-06-29 | 2032 | 6 | Jun | 29 | 2 | 1 | 28.67% | 7.9419 | 0%
2032-06-30 | 2032 | 6 | Jun | 30 | 3 | 1 | 28.67% | 7.9419 | 0%
2032-07-01 | 2032 | 7 | Jul | 1 | 4 | 1 | 24.73% | 8.3739 | 0%
2032-07-02 | 2032 | 7 | Jul | 2 | 5 | 1 | 24.73% | 8.3739 | 0%
2032-07-03 | 2032 | 7 | Jul | 3 | 6 | 0 | 24.73% | 8.3739 | 0%
2032-07-04 | 2032 | 7 | Jul | 4 | 7 | 0 | 24.73% | 8.3739 | 0%
2032-07-05 | 2032 | 7 | Jul | 5 | 1 | 1 | 24.73% | 8.3739 | 0%
2032-07-06 | 2032 | 7 | Jul | 6 | 2 | 1 | 24.73% | 8.3739 | 0%
2032-07-07 | 2032 | 7 | Jul | 7 | 3 | 1 | 24.73% | 8.3739 | 0%
2032-07-08 | 2032 | 7 | Jul | 8 | 4 | 1 | 24.73% | 8.3739 | 0%
2032-07-09 | 2032 | 7 | Jul | 9 | 5 | 1 | 24.73% | 8.3739 | 0%
2032-07-10 | 2032 | 7 | Jul | 10 | 6 | 0 | 24.73% | 8.3739 | 0%
2032-07-11 | 2032 | 7 | Jul | 11 | 7 | 0 | 24.73% | 8.3739 | 0%
2032-07-12 | 2032 | 7 | Jul | 12 | 1 | 1 | 24.73% | 8.3739 | 0%
2032-07-13 | 2032 | 7 | Jul | 13 | 2 | 1 | 24.73% | 8.3739 | 0%
2032-07-14 | 2032 | 7 | Jul | 14 | 3 | 1 | 24.73% | 8.3739 | 0%
2032-07-15 | 2032 | 7 | Jul | 15 | 4 | 1 | 24.73% | 8.3739 | 0%
2032-07-16 | 2032 | 7 | Jul | 16 | 5 | 1 | 24.73% | 8.3739 | 0%
2032-07-17 | 2032 | 7 | Jul | 17 | 6 | 0 | 24.73% | 8.3739 | 0%
2032-07-18 | 2032 | 7 | Jul | 18 | 7 | 0 | 24.73% | 8.3739 | 0%
2032-07-19 | 2032 | 7 | Jul | 19 | 1 | 1 | 24.73% | 8.3739 | 0%
2032-07-20 | 2032 | 7 | Jul | 20 | 2 | 1 | 24.73% | 8.3739 | 0%
2032-07-21 | 2032 | 7 | Jul | 21 | 3 | 1 | 24.73% | 8.3739 | 0%
2032-07-22 | 2032 | 7 | Jul | 22 | 4 | 1 | 24.73% | 8.3739 | 0%
2032-07-23 | 2032 | 7 | Jul | 23 | 5 | 1 | 24.73% | 8.3739 | 0%
2032-07-24 | 2032 | 7 | Jul | 24 | 6 | 0 | 24.73% | 8.3739 | 0%
2032-07-25 | 2032 | 7 | Jul | 25 | 7 | 0 | 24.73% | 8.3739 | 0%
2032-07-26 | 2032 | 7 | Jul | 26 | 1 | 1 | 24.73% | 8.3739 | 0%
2032-07-27 | 2032 | 7 | Jul | 27 | 2 | 1 | 24.73% | 8.3739 | 0%
2032-07-28 | 2032 | 7 | Jul | 28 | 3 | 1 | 24.73% | 8.3739 | 0%
2032-07-29 | 2032 | 7 | Jul | 29 | 4 | 1 | 24.73% | 8.3739 | 0%
2032-07-30 | 2032 | 7 | Jul | 30 | 5 | 1 | 24.73% | 8.3739 | 0%
2032-07-31 | 2032 | 7 | Jul | 31 | 6 | 0 | 24.73% | 8.3739 | 0%
2032-08-01 | 2032 | 8 | Aug | 1 | 7 | 0 | 23.55% | 7.9589 | 0%
2032-08-02 | 2032 | 8 | Aug | 2 | 1 | 1 | 23.55% | 7.9589 | 0%
2032-08-03 | 2032 | 8 | Aug | 3 | 2 | 1 | 23.55% | 7.9589 | 0%
2032-08-04 | 2032 | 8 | Aug | 4 | 3 | 1 | 23.55% | 7.9589 | 0%
2032-08-05 | 2032 | 8 | Aug | 5 | 4 | 1 | 23.55% | 7.9589 | 0%
2032-08-06 | 2032 | 8 | Aug | 6 | 5 | 1 | 23.55% | 7.9589 | 0%
2032-08-07 | 2032 | 8 | Aug | 7 | 6 | 0 | 23.55% | 7.9589 | 0%
2032-08-08 | 2032 | 8 | Aug | 8 | 7 | 0 | 23.55% | 7.9589 | 0%
2032-08-09 | 2032 | 8 | Aug | 9 | 1 | 1 | 23.55% | 7.9589 | 0%
2032-08-10 | 2032 | 8 | Aug | 10 | 2 | 1 | 23.55% | 7.9589 | 0%
2032-08-11 | 2032 | 8 | Aug | 11 | 3 | 1 | 23.55% | 7.9589 | 0%
2032-08-12 | 2032 | 8 | Aug | 12 | 4 | 1 | 23.55% | 7.9589 | 0%
2032-08-13 | 2032 | 8 | Aug | 13 | 5 | 1 | 23.55% | 7.9589 | 0%
2032-08-14 | 2032 | 8 | Aug | 14 | 6 | 0 | 23.55% | 7.9589 | 0%
2032-08-15 | 2032 | 8 | Aug | 15 | 7 | 0 | 23.55% | 7.9589 | 0%
2032-08-16 | 2032 | 8 | Aug | 16 | 1 | 1 | 23.55% | 7.9589 | 0%
2032-08-17 | 2032 | 8 | Aug | 17 | 2 | 1 | 23.55% | 7.9589 | 0%
2032-08-18 | 2032 | 8 | Aug | 18 | 3 | 1 | 23.55% | 7.9589 | 0%
2032-08-19 | 2032 | 8 | Aug | 19 | 4 | 1 | 23.55% | 7.9589 | 0%
2032-08-20 | 2032 | 8 | Aug | 20 | 5 | 1 | 23.55% | 7.9589 | 0%
2032-08-21 | 2032 | 8 | Aug | 21 | 6 | 0 | 23.55% | 7.9589 | 0%
2032-08-22 | 2032 | 8 | Aug | 22 | 7 | 0 | 23.55% | 7.9589 | 0%
2032-08-23 | 2032 | 8 | Aug | 23 | 1 | 1 | 23.55% | 7.9589 | 0%
2032-08-24 | 2032 | 8 | Aug | 24 | 2 | 1 | 23.55% | 7.9589 | 0%
2032-08-25 | 2032 | 8 | Aug | 25 | 3 | 1 | 23.55% | 7.9589 | 0%
2032-08-26 | 2032 | 8 | Aug | 26 | 4 | 1 | 23.55% | 7.9589 | 0%
2032-08-27 | 2032 | 8 | Aug | 27 | 5 | 1 | 23.55% | 7.9589 | 0%
2032-08-28 | 2032 | 8 | Aug | 28 | 6 | 0 | 23.55% | 7.9589 | 0%
2032-08-29 | 2032 | 8 | Aug | 29 | 7 | 0 | 23.55% | 7.9589 | 0%
2032-08-30 | 2032 | 8 | Aug | 30 | 1 | 1 | 23.55% | 7.9589 | 0%
2032-08-31 | 2032 | 8 | Aug | 31 | 2 | 1 | 23.55% | 7.9589 | 0%
2032-09-01 | 2032 | 9 | Sep | 1 | 3 | 1 | 20.67% | 6.8065 | 0%
2032-09-02 | 2032 | 9 | Sep | 2 | 4 | 1 | 20.67% | 6.8065 | 0%
2032-09-03 | 2032 | 9 | Sep | 3 | 5 | 1 | 20.67% | 6.8065 | 0%
2032-09-04 | 2032 | 9 | Sep | 4 | 6 | 0 | 20.67% | 6.8065 | 0%
2032-09-05 | 2032 | 9 | Sep | 5 | 7 | 0 | 20.67% | 6.8065 | 0%
2032-09-06 | 2032 | 9 | Sep | 6 | 1 | 1 | 20.67% | 6.8065 | 0%
2032-09-07 | 2032 | 9 | Sep | 7 | 2 | 1 | 20.67% | 6.8065 | 0%
2032-09-08 | 2032 | 9 | Sep | 8 | 3 | 1 | 20.67% | 6.8065 | 0%
2032-09-09 | 2032 | 9 | Sep | 9 | 4 | 1 | 20.67% | 6.8065 | 0%
2032-09-10 | 2032 | 9 | Sep | 10 | 5 | 1 | 20.67% | 6.8065 | 0%
2032-09-11 | 2032 | 9 | Sep | 11 | 6 | 0 | 20.67% | 6.8065 | 0%
2032-09-12 | 2032 | 9 | Sep | 12 | 7 | 0 | 20.67% | 6.8065 | 0%
2032-09-13 | 2032 | 9 | Sep | 13 | 1 | 1 | 20.67% | 6.8065 | 0%
2032-09-14 | 2032 | 9 | Sep | 14 | 2 | 1 | 20.67% | 6.8065 | 0%
2032-09-15 | 2032 | 9 | Sep | 15 | 3 | 1 | 20.67% | 6.8065 | 0%
2032-09-16 | 2032 | 9 | Sep | 16 | 4 | 1 | 20.67% | 6.8065 | 0%
2032-09-17 | 2032 | 9 | Sep | 17 | 5 | 1 | 20.67% | 6.8065 | 0%
2032-09-18 | 2032 | 9 | Sep | 18 | 6 | 0 | 20.67% | 6.8065 | 0%
2032-09-19 | 2032 | 9 | Sep | 19 | 7 | 0 | 20.67% | 6.8065 | 0%
2032-09-20 | 2032 | 9 | Sep | 20 | 1 | 1 | 20.67% | 6.8065 | 0%
2032-09-21 | 2032 | 9 | Sep | 21 | 2 | 1 | 20.67% | 6.8065 | 0%
2032-09-22 | 2032 | 9 | Sep | 22 | 3 | 1 | 20.67% | 6.8065 | 0%
2032-09-23 | 2032 | 9 | Sep | 23 | 4 | 1 | 20.67% | 6.8065 | 0%
2032-09-24 | 2032 | 9 | Sep | 24 | 5 | 1 | 20.67% | 6.8065 | 0%
2032-09-25 | 2032 | 9 | Sep | 25 | 6 | 0 | 20.67% | 6.8065 | 0%
2032-09-26 | 2032 | 9 | Sep | 26 | 7 | 0 | 20.67% | 6.8065 | 0%
2032-09-27 | 2032 | 9 | Sep | 27 | 1 | 1 | 20.67% | 6.8065 | 0%
2032-09-28 | 2032 | 9 | Sep | 28 | 2 | 1 | 20.67% | 6.8065 | 0%
2032-09-29 | 2032 | 9 | Sep | 29 | 3 | 1 | 20.67% | 6.8065 | 0%
2032-09-30 | 2032 | 9 | Sep | 30 | 4 | 1 | 20.67% | 6.8065 | 0%
2032-10-01 | 2032 | 10 | Oct | 1 | 5 | 1 | 23.23% | 6.8194 | 0%
2032-10-02 | 2032 | 10 | Oct | 2 | 6 | 0 | 23.23% | 6.8194 | 0%
2032-10-03 | 2032 | 10 | Oct | 3 | 7 | 0 | 23.23% | 6.8194 | 0%
2032-10-04 | 2032 | 10 | Oct | 4 | 1 | 1 | 23.23% | 6.8194 | 0%
2032-10-05 | 2032 | 10 | Oct | 5 | 2 | 1 | 23.23% | 6.8194 | 0%
2032-10-06 | 2032 | 10 | Oct | 6 | 3 | 1 | 23.23% | 6.8194 | 0%
2032-10-07 | 2032 | 10 | Oct | 7 | 4 | 1 | 23.23% | 6.8194 | 0%
2032-10-08 | 2032 | 10 | Oct | 8 | 5 | 1 | 23.23% | 6.8194 | 0%
2032-10-09 | 2032 | 10 | Oct | 9 | 6 | 0 | 23.23% | 6.8194 | 0%
2032-10-10 | 2032 | 10 | Oct | 10 | 7 | 0 | 23.23% | 6.8194 | 0%
2032-10-11 | 2032 | 10 | Oct | 11 | 1 | 1 | 23.23% | 6.8194 | 0%
2032-10-12 | 2032 | 10 | Oct | 12 | 2 | 1 | 23.23% | 6.8194 | 0%
2032-10-13 | 2032 | 10 | Oct | 13 | 3 | 1 | 23.23% | 6.8194 | 0%
2032-10-14 | 2032 | 10 | Oct | 14 | 4 | 1 | 23.23% | 6.8194 | 0%
2032-10-15 | 2032 | 10 | Oct | 15 | 5 | 1 | 23.23% | 6.8194 | 0%
2032-10-16 | 2032 | 10 | Oct | 16 | 6 | 0 | 23.23% | 6.8194 | 0%
2032-10-17 | 2032 | 10 | Oct | 17 | 7 | 0 | 23.23% | 6.8194 | 0%
2032-10-18 | 2032 | 10 | Oct | 18 | 1 | 1 | 23.23% | 6.8194 | 0%
2032-10-19 | 2032 | 10 | Oct | 19 | 2 | 1 | 23.23% | 6.8194 | 0%
2032-10-20 | 2032 | 10 | Oct | 20 | 3 | 1 | 23.23% | 6.8194 | 0%
2032-10-21 | 2032 | 10 | Oct | 21 | 4 | 1 | 23.23% | 6.8194 | 0%
2032-10-22 | 2032 | 10 | Oct | 22 | 5 | 1 | 23.23% | 6.8194 | 0%
2032-10-23 | 2032 | 10 | Oct | 23 | 6 | 0 | 23.23% | 6.8194 | 0%
2032-10-24 | 2032 | 10 | Oct | 24 | 7 | 0 | 23.23% | 6.8194 | 0%
2032-10-25 | 2032 | 10 | Oct | 25 | 1 | 1 | 23.23% | 6.8194 | 0%
2032-10-26 | 2032 | 10 | Oct | 26 | 2 | 1 | 23.23% | 6.8194 | 0%
2032-10-27 | 2032 | 10 | Oct | 27 | 3 | 1 | 23.23% | 6.8194 | 0%
2032-10-28 | 2032 | 10 | Oct | 28 | 4 | 1 | 23.23% | 6.8194 | 0%
2032-10-29 | 2032 | 10 | Oct | 29 | 5 | 1 | 23.23% | 6.8194 | 0%
2032-10-30 | 2032 | 10 | Oct | 30 | 6 | 0 | 23.23% | 6.8194 | 0%
2032-10-31 | 2032 | 10 | Oct | 31 | 7 | 0 | 23.23% | 6.8194 | 0%
2032-11-01 | 2032 | 11 | Nov | 1 | 1 | 1 | 23.33% | 6.4429 | 0%
2032-11-02 | 2032 | 11 | Nov | 2 | 2 | 1 | 23.33% | 6.4429 | 0%
2032-11-03 | 2032 | 11 | Nov | 3 | 3 | 1 | 23.33% | 6.4429 | 0%
2032-11-04 | 2032 | 11 | Nov | 4 | 4 | 1 | 23.33% | 6.4429 | 0%
2032-11-05 | 2032 | 11 | Nov | 5 | 5 | 1 | 23.33% | 6.4429 | 0%
2032-11-06 | 2032 | 11 | Nov | 6 | 6 | 0 | 23.33% | 6.4429 | 0%
2032-11-07 | 2032 | 11 | Nov | 7 | 7 | 0 | 23.33% | 6.4429 | 0%
2032-11-08 | 2032 | 11 | Nov | 8 | 1 | 1 | 23.33% | 6.4429 | 0%
2032-11-09 | 2032 | 11 | Nov | 9 | 2 | 1 | 23.33% | 6.4429 | 0%
2032-11-10 | 2032 | 11 | Nov | 10 | 3 | 1 | 23.33% | 6.4429 | 0%
2032-11-11 | 2032 | 11 | Nov | 11 | 4 | 1 | 23.33% | 6.4429 | 0%
2032-11-12 | 2032 | 11 | Nov | 12 | 5 | 1 | 23.33% | 6.4429 | 0%
2032-11-13 | 2032 | 11 | Nov | 13 | 6 | 0 | 23.33% | 6.4429 | 0%
2032-11-14 | 2032 | 11 | Nov | 14 | 7 | 0 | 23.33% | 6.4429 | 0%
2032-11-15 | 2032 | 11 | Nov | 15 | 1 | 1 | 23.33% | 6.4429 | 0%
2032-11-16 | 2032 | 11 | Nov | 16 | 2 | 1 | 23.33% | 6.4429 | 0%
2032-11-17 | 2032 | 11 | Nov | 17 | 3 | 1 | 23.33% | 6.4429 | 0%
2032-11-18 | 2032 | 11 | Nov | 18 | 4 | 1 | 23.33% | 6.4429 | 0%
2032-11-19 | 2032 | 11 | Nov | 19 | 5 | 1 | 23.33% | 6.4429 | 0%
2032-11-20 | 2032 | 11 | Nov | 20 | 6 | 0 | 23.33% | 6.4429 | 0%
2032-11-21 | 2032 | 11 | Nov | 21 | 7 | 0 | 23.33% | 6.4429 | 0%
2032-11-22 | 2032 | 11 | Nov | 22 | 1 | 1 | 23.33% | 6.4429 | 0%
2032-11-23 | 2032 | 11 | Nov | 23 | 2 | 1 | 23.33% | 6.4429 | 0%
2032-11-24 | 2032 | 11 | Nov | 24 | 3 | 1 | 23.33% | 6.4429 | 0%
2032-11-25 | 2032 | 11 | Nov | 25 | 4 | 1 | 23.33% | 6.4429 | 0%
2032-11-26 | 2032 | 11 | Nov | 26 | 5 | 1 | 23.33% | 6.4429 | 0%
2032-11-27 | 2032 | 11 | Nov | 27 | 6 | 0 | 23.33% | 6.4429 | 0%
2032-11-28 | 2032 | 11 | Nov | 28 | 7 | 0 | 23.33% | 6.4429 | 0%
2032-11-29 | 2032 | 11 | Nov | 29 | 1 | 1 | 23.33% | 6.4429 | 0%
2032-11-30 | 2032 | 11 | Nov | 30 | 2 | 1 | 23.33% | 6.4429 | 0%
2032-12-01 | 2032 | 12 | Dec | 1 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-12-02 | 2032 | 12 | Dec | 2 | 4 | 1 | 22.69% | 6.7962 | 0%
2032-12-03 | 2032 | 12 | Dec | 3 | 5 | 1 | 22.69% | 6.7962 | 0%
2032-12-04 | 2032 | 12 | Dec | 4 | 6 | 0 | 22.69% | 6.7962 | 0%
2032-12-05 | 2032 | 12 | Dec | 5 | 7 | 0 | 22.69% | 6.7962 | 0%
2032-12-06 | 2032 | 12 | Dec | 6 | 1 | 1 | 22.69% | 6.7962 | 0%
2032-12-07 | 2032 | 12 | Dec | 7 | 2 | 1 | 22.69% | 6.7962 | 0%
2032-12-08 | 2032 | 12 | Dec | 8 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-12-09 | 2032 | 12 | Dec | 9 | 4 | 1 | 22.69% | 6.7962 | 0%
2032-12-10 | 2032 | 12 | Dec | 10 | 5 | 1 | 22.69% | 6.7962 | 0%
2032-12-11 | 2032 | 12 | Dec | 11 | 6 | 0 | 22.69% | 6.7962 | 0%
2032-12-12 | 2032 | 12 | Dec | 12 | 7 | 0 | 22.69% | 6.7962 | 0%
2032-12-13 | 2032 | 12 | Dec | 13 | 1 | 1 | 22.69% | 6.7962 | 0%
2032-12-14 | 2032 | 12 | Dec | 14 | 2 | 1 | 22.69% | 6.7962 | 0%
2032-12-15 | 2032 | 12 | Dec | 15 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-12-16 | 2032 | 12 | Dec | 16 | 4 | 1 | 22.69% | 6.7962 | 0%
2032-12-17 | 2032 | 12 | Dec | 17 | 5 | 1 | 22.69% | 6.7962 | 0%
2032-12-18 | 2032 | 12 | Dec | 18 | 6 | 0 | 22.69% | 6.7962 | 0%
2032-12-19 | 2032 | 12 | Dec | 19 | 7 | 0 | 22.69% | 6.7962 | 0%
2032-12-20 | 2032 | 12 | Dec | 20 | 1 | 1 | 22.69% | 6.7962 | 0%
2032-12-21 | 2032 | 12 | Dec | 21 | 2 | 1 | 22.69% | 6.7962 | 0%
2032-12-22 | 2032 | 12 | Dec | 22 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-12-23 | 2032 | 12 | Dec | 23 | 4 | 1 | 22.69% | 6.7962 | 0%
2032-12-24 | 2032 | 12 | Dec | 24 | 5 | 1 | 22.69% | 6.7962 | 0%
2032-12-25 | 2032 | 12 | Dec | 25 | 6 | 0 | 22.69% | 6.7962 | 0%
2032-12-26 | 2032 | 12 | Dec | 26 | 7 | 0 | 22.69% | 6.7962 | 0%
2032-12-27 | 2032 | 12 | Dec | 27 | 1 | 1 | 22.69% | 6.7962 | 0%
2032-12-28 | 2032 | 12 | Dec | 28 | 2 | 1 | 22.69% | 6.7962 | 0%
2032-12-29 | 2032 | 12 | Dec | 29 | 3 | 1 | 22.69% | 6.7962 | 0%
2032-12-30 | 2032 | 12 | Dec | 30 | 4 | 1 | 22.69% | 6.7962 | 0%
2032-12-31 | 2032 | 12 | Dec | 31 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-01-01 | 2033 | 1 | Jan | 1 | 6 | 0 | 19.46% | 7.0276 | 0%
2033-01-02 | 2033 | 1 | Jan | 2 | 7 | 0 | 19.46% | 7.0276 | 0%
2033-01-03 | 2033 | 1 | Jan | 3 | 1 | 1 | 19.46% | 7.0276 | 0%
2033-01-04 | 2033 | 1 | Jan | 4 | 2 | 1 | 19.46% | 7.0276 | 0%
2033-01-05 | 2033 | 1 | Jan | 5 | 3 | 1 | 19.46% | 7.0276 | 0%
2033-01-06 | 2033 | 1 | Jan | 6 | 4 | 1 | 19.46% | 7.0276 | 0%
2033-01-07 | 2033 | 1 | Jan | 7 | 5 | 1 | 19.46% | 7.0276 | 0%
2033-01-08 | 2033 | 1 | Jan | 8 | 6 | 0 | 19.46% | 7.0276 | 0%
2033-01-09 | 2033 | 1 | Jan | 9 | 7 | 0 | 19.46% | 7.0276 | 0%
2033-01-10 | 2033 | 1 | Jan | 10 | 1 | 1 | 19.46% | 7.0276 | 0%
2033-01-11 | 2033 | 1 | Jan | 11 | 2 | 1 | 19.46% | 7.0276 | 0%
2033-01-12 | 2033 | 1 | Jan | 12 | 3 | 1 | 19.46% | 7.0276 | 0%
2033-01-13 | 2033 | 1 | Jan | 13 | 4 | 1 | 19.46% | 7.0276 | 0%
2033-01-14 | 2033 | 1 | Jan | 14 | 5 | 1 | 19.46% | 7.0276 | 0%
2033-01-15 | 2033 | 1 | Jan | 15 | 6 | 0 | 19.46% | 7.0276 | 0%
2033-01-16 | 2033 | 1 | Jan | 16 | 7 | 0 | 19.46% | 7.0276 | 0%
2033-01-17 | 2033 | 1 | Jan | 17 | 1 | 1 | 19.46% | 7.0276 | 0%
2033-01-18 | 2033 | 1 | Jan | 18 | 2 | 1 | 19.46% | 7.0276 | 0%
2033-01-19 | 2033 | 1 | Jan | 19 | 3 | 1 | 19.46% | 7.0276 | 0%
2033-01-20 | 2033 | 1 | Jan | 20 | 4 | 1 | 19.46% | 7.0276 | 0%
2033-01-21 | 2033 | 1 | Jan | 21 | 5 | 1 | 19.46% | 7.0276 | 0%
2033-01-22 | 2033 | 1 | Jan | 22 | 6 | 0 | 19.46% | 7.0276 | 0%
2033-01-23 | 2033 | 1 | Jan | 23 | 7 | 0 | 19.46% | 7.0276 | 0%
2033-01-24 | 2033 | 1 | Jan | 24 | 1 | 1 | 19.46% | 7.0276 | 0%
2033-01-25 | 2033 | 1 | Jan | 25 | 2 | 1 | 19.46% | 7.0276 | 0%
2033-01-26 | 2033 | 1 | Jan | 26 | 3 | 1 | 19.46% | 7.0276 | 0%
2033-01-27 | 2033 | 1 | Jan | 27 | 4 | 1 | 19.46% | 7.0276 | 0%
2033-01-28 | 2033 | 1 | Jan | 28 | 5 | 1 | 19.46% | 7.0276 | 0%
2033-01-29 | 2033 | 1 | Jan | 29 | 6 | 0 | 19.46% | 7.0276 | 0%
2033-01-30 | 2033 | 1 | Jan | 30 | 7 | 0 | 19.46% | 7.0276 | 0%
2033-01-31 | 2033 | 1 | Jan | 31 | 1 | 1 | 19.46% | 7.0276 | 0%
2033-02-01 | 2033 | 2 | Feb | 1 | 2 | 1 | 18.87% | 7.4625 | 0%
2033-02-02 | 2033 | 2 | Feb | 2 | 3 | 1 | 18.87% | 7.4625 | 0%
2033-02-03 | 2033 | 2 | Feb | 3 | 4 | 1 | 18.87% | 7.4625 | 0%
2033-02-04 | 2033 | 2 | Feb | 4 | 5 | 1 | 18.87% | 7.4625 | 0%
2033-02-05 | 2033 | 2 | Feb | 5 | 6 | 0 | 18.87% | 7.4625 | 0%
2033-02-06 | 2033 | 2 | Feb | 6 | 7 | 0 | 18.87% | 7.4625 | 0%
2033-02-07 | 2033 | 2 | Feb | 7 | 1 | 1 | 18.87% | 7.4625 | 0%
2033-02-08 | 2033 | 2 | Feb | 8 | 2 | 1 | 18.87% | 7.4625 | 0%
2033-02-09 | 2033 | 2 | Feb | 9 | 3 | 1 | 18.87% | 7.4625 | 0%
2033-02-10 | 2033 | 2 | Feb | 10 | 4 | 1 | 18.87% | 7.4625 | 0%
2033-02-11 | 2033 | 2 | Feb | 11 | 5 | 1 | 18.87% | 7.4625 | 0%
2033-02-12 | 2033 | 2 | Feb | 12 | 6 | 0 | 18.87% | 7.4625 | 0%
2033-02-13 | 2033 | 2 | Feb | 13 | 7 | 0 | 18.87% | 7.4625 | 0%
2033-02-14 | 2033 | 2 | Feb | 14 | 1 | 1 | 18.87% | 7.4625 | 0%
2033-02-15 | 2033 | 2 | Feb | 15 | 2 | 1 | 18.87% | 7.4625 | 0%
2033-02-16 | 2033 | 2 | Feb | 16 | 3 | 1 | 18.87% | 7.4625 | 0%
2033-02-17 | 2033 | 2 | Feb | 17 | 4 | 1 | 18.87% | 7.4625 | 0%
2033-02-18 | 2033 | 2 | Feb | 18 | 5 | 1 | 18.87% | 7.4625 | 0%
2033-02-19 | 2033 | 2 | Feb | 19 | 6 | 0 | 18.87% | 7.4625 | 0%
2033-02-20 | 2033 | 2 | Feb | 20 | 7 | 0 | 18.87% | 7.4625 | 0%
2033-02-21 | 2033 | 2 | Feb | 21 | 1 | 1 | 18.87% | 7.4625 | 0%
2033-02-22 | 2033 | 2 | Feb | 22 | 2 | 1 | 18.87% | 7.4625 | 0%
2033-02-23 | 2033 | 2 | Feb | 23 | 3 | 1 | 18.87% | 7.4625 | 0%
2033-02-24 | 2033 | 2 | Feb | 24 | 4 | 1 | 18.87% | 7.4625 | 0%
2033-02-25 | 2033 | 2 | Feb | 25 | 5 | 1 | 18.87% | 7.4625 | 0%
2033-02-26 | 2033 | 2 | Feb | 26 | 6 | 0 | 18.87% | 7.4625 | 0%
2033-02-27 | 2033 | 2 | Feb | 27 | 7 | 0 | 18.87% | 7.4625 | 0%
2033-02-28 | 2033 | 2 | Feb | 28 | 1 | 1 | 18.87% | 7.4625 | 0%
2033-03-01 | 2033 | 3 | Mar | 1 | 2 | 1 | 18.49% | 7.8663 | 0%
2033-03-02 | 2033 | 3 | Mar | 2 | 3 | 1 | 18.49% | 7.8663 | 0%
2033-03-03 | 2033 | 3 | Mar | 3 | 4 | 1 | 18.49% | 7.8663 | 0%
2033-03-04 | 2033 | 3 | Mar | 4 | 5 | 1 | 18.49% | 7.8663 | 0%
2033-03-05 | 2033 | 3 | Mar | 5 | 6 | 0 | 18.49% | 7.8663 | 0%
2033-03-06 | 2033 | 3 | Mar | 6 | 7 | 0 | 18.49% | 7.8663 | 0%
2033-03-07 | 2033 | 3 | Mar | 7 | 1 | 1 | 18.49% | 7.8663 | 0%
2033-03-08 | 2033 | 3 | Mar | 8 | 2 | 1 | 18.49% | 7.8663 | 0%
2033-03-09 | 2033 | 3 | Mar | 9 | 3 | 1 | 18.49% | 7.8663 | 0%
2033-03-10 | 2033 | 3 | Mar | 10 | 4 | 1 | 18.49% | 7.8663 | 0%
2033-03-11 | 2033 | 3 | Mar | 11 | 5 | 1 | 18.49% | 7.8663 | 0%
2033-03-12 | 2033 | 3 | Mar | 12 | 6 | 0 | 18.49% | 7.8663 | 0%
2033-03-13 | 2033 | 3 | Mar | 13 | 7 | 0 | 18.49% | 7.8663 | 0%
2033-03-14 | 2033 | 3 | Mar | 14 | 1 | 1 | 18.49% | 7.8663 | 0%
2033-03-15 | 2033 | 3 | Mar | 15 | 2 | 1 | 18.49% | 7.8663 | 0%
2033-03-16 | 2033 | 3 | Mar | 16 | 3 | 1 | 18.49% | 7.8663 | 0%
2033-03-17 | 2033 | 3 | Mar | 17 | 4 | 1 | 18.49% | 7.8663 | 0%
2033-03-18 | 2033 | 3 | Mar | 18 | 5 | 1 | 18.49% | 7.8663 | 0%
2033-03-19 | 2033 | 3 | Mar | 19 | 6 | 0 | 18.49% | 7.8663 | 0%
2033-03-20 | 2033 | 3 | Mar | 20 | 7 | 0 | 18.49% | 7.8663 | 0%
2033-03-21 | 2033 | 3 | Mar | 21 | 1 | 1 | 18.49% | 7.8663 | 0%
2033-03-22 | 2033 | 3 | Mar | 22 | 2 | 1 | 18.49% | 7.8663 | 0%
2033-03-23 | 2033 | 3 | Mar | 23 | 3 | 1 | 18.49% | 7.8663 | 0%
2033-03-24 | 2033 | 3 | Mar | 24 | 4 | 1 | 18.49% | 7.8663 | 0%
2033-03-25 | 2033 | 3 | Mar | 25 | 5 | 1 | 18.49% | 7.8663 | 0%
2033-03-26 | 2033 | 3 | Mar | 26 | 6 | 0 | 18.49% | 7.8663 | 0%
2033-03-27 | 2033 | 3 | Mar | 27 | 7 | 0 | 18.49% | 7.8663 | 0%
2033-03-28 | 2033 | 3 | Mar | 28 | 1 | 1 | 18.49% | 7.8663 | 0%
2033-03-29 | 2033 | 3 | Mar | 29 | 2 | 1 | 18.49% | 7.8663 | 0%
2033-03-30 | 2033 | 3 | Mar | 30 | 3 | 1 | 18.49% | 7.8663 | 0%
2033-03-31 | 2033 | 3 | Mar | 31 | 4 | 1 | 18.49% | 7.8663 | 0%
2033-04-01 | 2033 | 4 | Apr | 1 | 5 | 1 | 25.56% | 7.5 | 0%
2033-04-02 | 2033 | 4 | Apr | 2 | 6 | 0 | 25.56% | 7.5 | 0%
2033-04-03 | 2033 | 4 | Apr | 3 | 7 | 0 | 25.56% | 7.5 | 0%
2033-04-04 | 2033 | 4 | Apr | 4 | 1 | 1 | 25.56% | 7.5 | 0%
2033-04-05 | 2033 | 4 | Apr | 5 | 2 | 1 | 25.56% | 7.5 | 0%
2033-04-06 | 2033 | 4 | Apr | 6 | 3 | 1 | 25.56% | 7.5 | 0%
2033-04-07 | 2033 | 4 | Apr | 7 | 4 | 1 | 25.56% | 7.5 | 0%
2033-04-08 | 2033 | 4 | Apr | 8 | 5 | 1 | 25.56% | 7.5 | 0%
2033-04-09 | 2033 | 4 | Apr | 9 | 6 | 0 | 25.56% | 7.5 | 0%
2033-04-10 | 2033 | 4 | Apr | 10 | 7 | 0 | 25.56% | 7.5 | 0%
2033-04-11 | 2033 | 4 | Apr | 11 | 1 | 1 | 25.56% | 7.5 | 0%
2033-04-12 | 2033 | 4 | Apr | 12 | 2 | 1 | 25.56% | 7.5 | 0%
2033-04-13 | 2033 | 4 | Apr | 13 | 3 | 1 | 25.56% | 7.5 | 0%
2033-04-14 | 2033 | 4 | Apr | 14 | 4 | 1 | 25.56% | 7.5 | 0%
2033-04-15 | 2033 | 4 | Apr | 15 | 5 | 1 | 25.56% | 7.5 | 0%
2033-04-16 | 2033 | 4 | Apr | 16 | 6 | 0 | 25.56% | 7.5 | 0%
2033-04-17 | 2033 | 4 | Apr | 17 | 7 | 0 | 25.56% | 7.5 | 0%
2033-04-18 | 2033 | 4 | Apr | 18 | 1 | 1 | 25.56% | 7.5 | 0%
2033-04-19 | 2033 | 4 | Apr | 19 | 2 | 1 | 25.56% | 7.5 | 0%
2033-04-20 | 2033 | 4 | Apr | 20 | 3 | 1 | 25.56% | 7.5 | 0%
2033-04-21 | 2033 | 4 | Apr | 21 | 4 | 1 | 25.56% | 7.5 | 0%
2033-04-22 | 2033 | 4 | Apr | 22 | 5 | 1 | 25.56% | 7.5 | 0%
2033-04-23 | 2033 | 4 | Apr | 23 | 6 | 0 | 25.56% | 7.5 | 0%
2033-04-24 | 2033 | 4 | Apr | 24 | 7 | 0 | 25.56% | 7.5 | 0%
2033-04-25 | 2033 | 4 | Apr | 25 | 1 | 1 | 25.56% | 7.5 | 0%
2033-04-26 | 2033 | 4 | Apr | 26 | 2 | 1 | 25.56% | 7.5 | 0%
2033-04-27 | 2033 | 4 | Apr | 27 | 3 | 1 | 25.56% | 7.5 | 0%
2033-04-28 | 2033 | 4 | Apr | 28 | 4 | 1 | 25.56% | 7.5 | 0%
2033-04-29 | 2033 | 4 | Apr | 29 | 5 | 1 | 25.56% | 7.5 | 0%
2033-04-30 | 2033 | 4 | Apr | 30 | 6 | 0 | 25.56% | 7.5 | 0%
2033-05-01 | 2033 | 5 | May | 1 | 7 | 0 | 23.01% | 8.1449 | 0%
2033-05-02 | 2033 | 5 | May | 2 | 1 | 1 | 23.01% | 8.1449 | 0%
2033-05-03 | 2033 | 5 | May | 3 | 2 | 1 | 23.01% | 8.1449 | 0%
2033-05-04 | 2033 | 5 | May | 4 | 3 | 1 | 23.01% | 8.1449 | 0%
2033-05-05 | 2033 | 5 | May | 5 | 4 | 1 | 23.01% | 8.1449 | 0%
2033-05-06 | 2033 | 5 | May | 6 | 5 | 1 | 23.01% | 8.1449 | 0%
2033-05-07 | 2033 | 5 | May | 7 | 6 | 0 | 23.01% | 8.1449 | 0%
2033-05-08 | 2033 | 5 | May | 8 | 7 | 0 | 23.01% | 8.1449 | 0%
2033-05-09 | 2033 | 5 | May | 9 | 1 | 1 | 23.01% | 8.1449 | 0%
2033-05-10 | 2033 | 5 | May | 10 | 2 | 1 | 23.01% | 8.1449 | 0%
2033-05-11 | 2033 | 5 | May | 11 | 3 | 1 | 23.01% | 8.1449 | 0%
2033-05-12 | 2033 | 5 | May | 12 | 4 | 1 | 23.01% | 8.1449 | 0%
2033-05-13 | 2033 | 5 | May | 13 | 5 | 1 | 23.01% | 8.1449 | 0%
2033-05-14 | 2033 | 5 | May | 14 | 6 | 0 | 23.01% | 8.1449 | 0%
2033-05-15 | 2033 | 5 | May | 15 | 7 | 0 | 23.01% | 8.1449 | 0%
2033-05-16 | 2033 | 5 | May | 16 | 1 | 1 | 23.01% | 8.1449 | 0%
2033-05-17 | 2033 | 5 | May | 17 | 2 | 1 | 23.01% | 8.1449 | 0%
2033-05-18 | 2033 | 5 | May | 18 | 3 | 1 | 23.01% | 8.1449 | 0%
2033-05-19 | 2033 | 5 | May | 19 | 4 | 1 | 23.01% | 8.1449 | 0%
2033-05-20 | 2033 | 5 | May | 20 | 5 | 1 | 23.01% | 8.1449 | 0%
2033-05-21 | 2033 | 5 | May | 21 | 6 | 0 | 23.01% | 8.1449 | 0%
2033-05-22 | 2033 | 5 | May | 22 | 7 | 0 | 23.01% | 8.1449 | 0%
2033-05-23 | 2033 | 5 | May | 23 | 1 | 1 | 23.01% | 8.1449 | 0%
2033-05-24 | 2033 | 5 | May | 24 | 2 | 1 | 23.01% | 8.1449 | 0%
2033-05-25 | 2033 | 5 | May | 25 | 3 | 1 | 23.01% | 8.1449 | 0%
2033-05-26 | 2033 | 5 | May | 26 | 4 | 1 | 23.01% | 8.1449 | 0%
2033-05-27 | 2033 | 5 | May | 27 | 5 | 1 | 23.01% | 8.1449 | 0%
2033-05-28 | 2033 | 5 | May | 28 | 6 | 0 | 23.01% | 8.1449 | 0%
2033-05-29 | 2033 | 5 | May | 29 | 7 | 0 | 23.01% | 8.1449 | 0%
2033-05-30 | 2033 | 5 | May | 30 | 1 | 1 | 23.01% | 8.1449 | 0%
2033-05-31 | 2033 | 5 | May | 31 | 2 | 1 | 23.01% | 8.1449 | 0%
2033-06-01 | 2033 | 6 | Jun | 1 | 3 | 1 | 28.67% | 7.9419 | 0%
2033-06-02 | 2033 | 6 | Jun | 2 | 4 | 1 | 28.67% | 7.9419 | 0%
2033-06-03 | 2033 | 6 | Jun | 3 | 5 | 1 | 28.67% | 7.9419 | 0%
2033-06-04 | 2033 | 6 | Jun | 4 | 6 | 0 | 28.67% | 7.9419 | 0%
2033-06-05 | 2033 | 6 | Jun | 5 | 7 | 0 | 28.67% | 7.9419 | 0%
2033-06-06 | 2033 | 6 | Jun | 6 | 1 | 1 | 28.67% | 7.9419 | 0%
2033-06-07 | 2033 | 6 | Jun | 7 | 2 | 1 | 28.67% | 7.9419 | 0%
2033-06-08 | 2033 | 6 | Jun | 8 | 3 | 1 | 28.67% | 7.9419 | 0%
2033-06-09 | 2033 | 6 | Jun | 9 | 4 | 1 | 28.67% | 7.9419 | 0%
2033-06-10 | 2033 | 6 | Jun | 10 | 5 | 1 | 28.67% | 7.9419 | 0%
2033-06-11 | 2033 | 6 | Jun | 11 | 6 | 0 | 28.67% | 7.9419 | 0%
2033-06-12 | 2033 | 6 | Jun | 12 | 7 | 0 | 28.67% | 7.9419 | 0%
2033-06-13 | 2033 | 6 | Jun | 13 | 1 | 1 | 28.67% | 7.9419 | 0%
2033-06-14 | 2033 | 6 | Jun | 14 | 2 | 1 | 28.67% | 7.9419 | 0%
2033-06-15 | 2033 | 6 | Jun | 15 | 3 | 1 | 28.67% | 7.9419 | 0%
2033-06-16 | 2033 | 6 | Jun | 16 | 4 | 1 | 28.67% | 7.9419 | 0%
2033-06-17 | 2033 | 6 | Jun | 17 | 5 | 1 | 28.67% | 7.9419 | 0%
2033-06-18 | 2033 | 6 | Jun | 18 | 6 | 0 | 28.67% | 7.9419 | 0%
2033-06-19 | 2033 | 6 | Jun | 19 | 7 | 0 | 28.67% | 7.9419 | 0%
2033-06-20 | 2033 | 6 | Jun | 20 | 1 | 1 | 28.67% | 7.9419 | 0%
2033-06-21 | 2033 | 6 | Jun | 21 | 2 | 1 | 28.67% | 7.9419 | 0%
2033-06-22 | 2033 | 6 | Jun | 22 | 3 | 1 | 28.67% | 7.9419 | 0%
2033-06-23 | 2033 | 6 | Jun | 23 | 4 | 1 | 28.67% | 7.9419 | 0%
2033-06-24 | 2033 | 6 | Jun | 24 | 5 | 1 | 28.67% | 7.9419 | 0%
2033-06-25 | 2033 | 6 | Jun | 25 | 6 | 0 | 28.67% | 7.9419 | 0%
2033-06-26 | 2033 | 6 | Jun | 26 | 7 | 0 | 28.67% | 7.9419 | 0%
2033-06-27 | 2033 | 6 | Jun | 27 | 1 | 1 | 28.67% | 7.9419 | 0%
2033-06-28 | 2033 | 6 | Jun | 28 | 2 | 1 | 28.67% | 7.9419 | 0%
2033-06-29 | 2033 | 6 | Jun | 29 | 3 | 1 | 28.67% | 7.9419 | 0%
2033-06-30 | 2033 | 6 | Jun | 30 | 4 | 1 | 28.67% | 7.9419 | 0%
2033-07-01 | 2033 | 7 | Jul | 1 | 5 | 1 | 24.73% | 8.3739 | 0%
2033-07-02 | 2033 | 7 | Jul | 2 | 6 | 0 | 24.73% | 8.3739 | 0%
2033-07-03 | 2033 | 7 | Jul | 3 | 7 | 0 | 24.73% | 8.3739 | 0%
2033-07-04 | 2033 | 7 | Jul | 4 | 1 | 1 | 24.73% | 8.3739 | 0%
2033-07-05 | 2033 | 7 | Jul | 5 | 2 | 1 | 24.73% | 8.3739 | 0%
2033-07-06 | 2033 | 7 | Jul | 6 | 3 | 1 | 24.73% | 8.3739 | 0%
2033-07-07 | 2033 | 7 | Jul | 7 | 4 | 1 | 24.73% | 8.3739 | 0%
2033-07-08 | 2033 | 7 | Jul | 8 | 5 | 1 | 24.73% | 8.3739 | 0%
2033-07-09 | 2033 | 7 | Jul | 9 | 6 | 0 | 24.73% | 8.3739 | 0%
2033-07-10 | 2033 | 7 | Jul | 10 | 7 | 0 | 24.73% | 8.3739 | 0%
2033-07-11 | 2033 | 7 | Jul | 11 | 1 | 1 | 24.73% | 8.3739 | 0%
2033-07-12 | 2033 | 7 | Jul | 12 | 2 | 1 | 24.73% | 8.3739 | 0%
2033-07-13 | 2033 | 7 | Jul | 13 | 3 | 1 | 24.73% | 8.3739 | 0%
2033-07-14 | 2033 | 7 | Jul | 14 | 4 | 1 | 24.73% | 8.3739 | 0%
2033-07-15 | 2033 | 7 | Jul | 15 | 5 | 1 | 24.73% | 8.3739 | 0%
2033-07-16 | 2033 | 7 | Jul | 16 | 6 | 0 | 24.73% | 8.3739 | 0%
2033-07-17 | 2033 | 7 | Jul | 17 | 7 | 0 | 24.73% | 8.3739 | 0%
2033-07-18 | 2033 | 7 | Jul | 18 | 1 | 1 | 24.73% | 8.3739 | 0%
2033-07-19 | 2033 | 7 | Jul | 19 | 2 | 1 | 24.73% | 8.3739 | 0%
2033-07-20 | 2033 | 7 | Jul | 20 | 3 | 1 | 24.73% | 8.3739 | 0%
2033-07-21 | 2033 | 7 | Jul | 21 | 4 | 1 | 24.73% | 8.3739 | 0%
2033-07-22 | 2033 | 7 | Jul | 22 | 5 | 1 | 24.73% | 8.3739 | 0%
2033-07-23 | 2033 | 7 | Jul | 23 | 6 | 0 | 24.73% | 8.3739 | 0%
2033-07-24 | 2033 | 7 | Jul | 24 | 7 | 0 | 24.73% | 8.3739 | 0%
2033-07-25 | 2033 | 7 | Jul | 25 | 1 | 1 | 24.73% | 8.3739 | 0%
2033-07-26 | 2033 | 7 | Jul | 26 | 2 | 1 | 24.73% | 8.3739 | 0%
2033-07-27 | 2033 | 7 | Jul | 27 | 3 | 1 | 24.73% | 8.3739 | 0%
2033-07-28 | 2033 | 7 | Jul | 28 | 4 | 1 | 24.73% | 8.3739 | 0%
2033-07-29 | 2033 | 7 | Jul | 29 | 5 | 1 | 24.73% | 8.3739 | 0%
2033-07-30 | 2033 | 7 | Jul | 30 | 6 | 0 | 24.73% | 8.3739 | 0%
2033-07-31 | 2033 | 7 | Jul | 31 | 7 | 0 | 24.73% | 8.3739 | 0%
2033-08-01 | 2033 | 8 | Aug | 1 | 1 | 1 | 23.55% | 7.9589 | 0%
2033-08-02 | 2033 | 8 | Aug | 2 | 2 | 1 | 23.55% | 7.9589 | 0%
2033-08-03 | 2033 | 8 | Aug | 3 | 3 | 1 | 23.55% | 7.9589 | 0%
2033-08-04 | 2033 | 8 | Aug | 4 | 4 | 1 | 23.55% | 7.9589 | 0%
2033-08-05 | 2033 | 8 | Aug | 5 | 5 | 1 | 23.55% | 7.9589 | 0%
2033-08-06 | 2033 | 8 | Aug | 6 | 6 | 0 | 23.55% | 7.9589 | 0%
2033-08-07 | 2033 | 8 | Aug | 7 | 7 | 0 | 23.55% | 7.9589 | 0%
2033-08-08 | 2033 | 8 | Aug | 8 | 1 | 1 | 23.55% | 7.9589 | 0%
2033-08-09 | 2033 | 8 | Aug | 9 | 2 | 1 | 23.55% | 7.9589 | 0%
2033-08-10 | 2033 | 8 | Aug | 10 | 3 | 1 | 23.55% | 7.9589 | 0%
2033-08-11 | 2033 | 8 | Aug | 11 | 4 | 1 | 23.55% | 7.9589 | 0%
2033-08-12 | 2033 | 8 | Aug | 12 | 5 | 1 | 23.55% | 7.9589 | 0%
2033-08-13 | 2033 | 8 | Aug | 13 | 6 | 0 | 23.55% | 7.9589 | 0%
2033-08-14 | 2033 | 8 | Aug | 14 | 7 | 0 | 23.55% | 7.9589 | 0%
2033-08-15 | 2033 | 8 | Aug | 15 | 1 | 1 | 23.55% | 7.9589 | 0%
2033-08-16 | 2033 | 8 | Aug | 16 | 2 | 1 | 23.55% | 7.9589 | 0%
2033-08-17 | 2033 | 8 | Aug | 17 | 3 | 1 | 23.55% | 7.9589 | 0%
2033-08-18 | 2033 | 8 | Aug | 18 | 4 | 1 | 23.55% | 7.9589 | 0%
2033-08-19 | 2033 | 8 | Aug | 19 | 5 | 1 | 23.55% | 7.9589 | 0%
2033-08-20 | 2033 | 8 | Aug | 20 | 6 | 0 | 23.55% | 7.9589 | 0%
2033-08-21 | 2033 | 8 | Aug | 21 | 7 | 0 | 23.55% | 7.9589 | 0%
2033-08-22 | 2033 | 8 | Aug | 22 | 1 | 1 | 23.55% | 7.9589 | 0%
2033-08-23 | 2033 | 8 | Aug | 23 | 2 | 1 | 23.55% | 7.9589 | 0%
2033-08-24 | 2033 | 8 | Aug | 24 | 3 | 1 | 23.55% | 7.9589 | 0%
2033-08-25 | 2033 | 8 | Aug | 25 | 4 | 1 | 23.55% | 7.9589 | 0%
2033-08-26 | 2033 | 8 | Aug | 26 | 5 | 1 | 23.55% | 7.9589 | 0%
2033-08-27 | 2033 | 8 | Aug | 27 | 6 | 0 | 23.55% | 7.9589 | 0%
2033-08-28 | 2033 | 8 | Aug | 28 | 7 | 0 | 23.55% | 7.9589 | 0%
2033-08-29 | 2033 | 8 | Aug | 29 | 1 | 1 | 23.55% | 7.9589 | 0%
2033-08-30 | 2033 | 8 | Aug | 30 | 2 | 1 | 23.55% | 7.9589 | 0%
2033-08-31 | 2033 | 8 | Aug | 31 | 3 | 1 | 23.55% | 7.9589 | 0%
2033-09-01 | 2033 | 9 | Sep | 1 | 4 | 1 | 20.67% | 6.8065 | 0%
2033-09-02 | 2033 | 9 | Sep | 2 | 5 | 1 | 20.67% | 6.8065 | 0%
2033-09-03 | 2033 | 9 | Sep | 3 | 6 | 0 | 20.67% | 6.8065 | 0%
2033-09-04 | 2033 | 9 | Sep | 4 | 7 | 0 | 20.67% | 6.8065 | 0%
2033-09-05 | 2033 | 9 | Sep | 5 | 1 | 1 | 20.67% | 6.8065 | 0%
2033-09-06 | 2033 | 9 | Sep | 6 | 2 | 1 | 20.67% | 6.8065 | 0%
2033-09-07 | 2033 | 9 | Sep | 7 | 3 | 1 | 20.67% | 6.8065 | 0%
2033-09-08 | 2033 | 9 | Sep | 8 | 4 | 1 | 20.67% | 6.8065 | 0%
2033-09-09 | 2033 | 9 | Sep | 9 | 5 | 1 | 20.67% | 6.8065 | 0%
2033-09-10 | 2033 | 9 | Sep | 10 | 6 | 0 | 20.67% | 6.8065 | 0%
2033-09-11 | 2033 | 9 | Sep | 11 | 7 | 0 | 20.67% | 6.8065 | 0%
2033-09-12 | 2033 | 9 | Sep | 12 | 1 | 1 | 20.67% | 6.8065 | 0%
2033-09-13 | 2033 | 9 | Sep | 13 | 2 | 1 | 20.67% | 6.8065 | 0%
2033-09-14 | 2033 | 9 | Sep | 14 | 3 | 1 | 20.67% | 6.8065 | 0%
2033-09-15 | 2033 | 9 | Sep | 15 | 4 | 1 | 20.67% | 6.8065 | 0%
2033-09-16 | 2033 | 9 | Sep | 16 | 5 | 1 | 20.67% | 6.8065 | 0%
2033-09-17 | 2033 | 9 | Sep | 17 | 6 | 0 | 20.67% | 6.8065 | 0%
2033-09-18 | 2033 | 9 | Sep | 18 | 7 | 0 | 20.67% | 6.8065 | 0%
2033-09-19 | 2033 | 9 | Sep | 19 | 1 | 1 | 20.67% | 6.8065 | 0%
2033-09-20 | 2033 | 9 | Sep | 20 | 2 | 1 | 20.67% | 6.8065 | 0%
2033-09-21 | 2033 | 9 | Sep | 21 | 3 | 1 | 20.67% | 6.8065 | 0%
2033-09-22 | 2033 | 9 | Sep | 22 | 4 | 1 | 20.67% | 6.8065 | 0%
2033-09-23 | 2033 | 9 | Sep | 23 | 5 | 1 | 20.67% | 6.8065 | 0%
2033-09-24 | 2033 | 9 | Sep | 24 | 6 | 0 | 20.67% | 6.8065 | 0%
2033-09-25 | 2033 | 9 | Sep | 25 | 7 | 0 | 20.67% | 6.8065 | 0%
2033-09-26 | 2033 | 9 | Sep | 26 | 1 | 1 | 20.67% | 6.8065 | 0%
2033-09-27 | 2033 | 9 | Sep | 27 | 2 | 1 | 20.67% | 6.8065 | 0%
2033-09-28 | 2033 | 9 | Sep | 28 | 3 | 1 | 20.67% | 6.8065 | 0%
2033-09-29 | 2033 | 9 | Sep | 29 | 4 | 1 | 20.67% | 6.8065 | 0%
2033-09-30 | 2033 | 9 | Sep | 30 | 5 | 1 | 20.67% | 6.8065 | 0%
2033-10-01 | 2033 | 10 | Oct | 1 | 6 | 0 | 23.23% | 6.8194 | 0%
2033-10-02 | 2033 | 10 | Oct | 2 | 7 | 0 | 23.23% | 6.8194 | 0%
2033-10-03 | 2033 | 10 | Oct | 3 | 1 | 1 | 23.23% | 6.8194 | 0%
2033-10-04 | 2033 | 10 | Oct | 4 | 2 | 1 | 23.23% | 6.8194 | 0%
2033-10-05 | 2033 | 10 | Oct | 5 | 3 | 1 | 23.23% | 6.8194 | 0%
2033-10-06 | 2033 | 10 | Oct | 6 | 4 | 1 | 23.23% | 6.8194 | 0%
2033-10-07 | 2033 | 10 | Oct | 7 | 5 | 1 | 23.23% | 6.8194 | 0%
2033-10-08 | 2033 | 10 | Oct | 8 | 6 | 0 | 23.23% | 6.8194 | 0%
2033-10-09 | 2033 | 10 | Oct | 9 | 7 | 0 | 23.23% | 6.8194 | 0%
2033-10-10 | 2033 | 10 | Oct | 10 | 1 | 1 | 23.23% | 6.8194 | 0%
2033-10-11 | 2033 | 10 | Oct | 11 | 2 | 1 | 23.23% | 6.8194 | 0%
2033-10-12 | 2033 | 10 | Oct | 12 | 3 | 1 | 23.23% | 6.8194 | 0%
2033-10-13 | 2033 | 10 | Oct | 13 | 4 | 1 | 23.23% | 6.8194 | 0%
2033-10-14 | 2033 | 10 | Oct | 14 | 5 | 1 | 23.23% | 6.8194 | 0%
2033-10-15 | 2033 | 10 | Oct | 15 | 6 | 0 | 23.23% | 6.8194 | 0%
2033-10-16 | 2033 | 10 | Oct | 16 | 7 | 0 | 23.23% | 6.8194 | 0%
2033-10-17 | 2033 | 10 | Oct | 17 | 1 | 1 | 23.23% | 6.8194 | 0%
2033-10-18 | 2033 | 10 | Oct | 18 | 2 | 1 | 23.23% | 6.8194 | 0%
2033-10-19 | 2033 | 10 | Oct | 19 | 3 | 1 | 23.23% | 6.8194 | 0%
2033-10-20 | 2033 | 10 | Oct | 20 | 4 | 1 | 23.23% | 6.8194 | 0%
2033-10-21 | 2033 | 10 | Oct | 21 | 5 | 1 | 23.23% | 6.8194 | 0%
2033-10-22 | 2033 | 10 | Oct | 22 | 6 | 0 | 23.23% | 6.8194 | 0%
2033-10-23 | 2033 | 10 | Oct | 23 | 7 | 0 | 23.23% | 6.8194 | 0%
2033-10-24 | 2033 | 10 | Oct | 24 | 1 | 1 | 23.23% | 6.8194 | 0%
2033-10-25 | 2033 | 10 | Oct | 25 | 2 | 1 | 23.23% | 6.8194 | 0%
2033-10-26 | 2033 | 10 | Oct | 26 | 3 | 1 | 23.23% | 6.8194 | 0%
2033-10-27 | 2033 | 10 | Oct | 27 | 4 | 1 | 23.23% | 6.8194 | 0%
2033-10-28 | 2033 | 10 | Oct | 28 | 5 | 1 | 23.23% | 6.8194 | 0%
2033-10-29 | 2033 | 10 | Oct | 29 | 6 | 0 | 23.23% | 6.8194 | 0%
2033-10-30 | 2033 | 10 | Oct | 30 | 7 | 0 | 23.23% | 6.8194 | 0%
2033-10-31 | 2033 | 10 | Oct | 31 | 1 | 1 | 23.23% | 6.8194 | 0%
2033-11-01 | 2033 | 11 | Nov | 1 | 2 | 1 | 23.33% | 6.4429 | 0%
2033-11-02 | 2033 | 11 | Nov | 2 | 3 | 1 | 23.33% | 6.4429 | 0%
2033-11-03 | 2033 | 11 | Nov | 3 | 4 | 1 | 23.33% | 6.4429 | 0%
2033-11-04 | 2033 | 11 | Nov | 4 | 5 | 1 | 23.33% | 6.4429 | 0%
2033-11-05 | 2033 | 11 | Nov | 5 | 6 | 0 | 23.33% | 6.4429 | 0%
2033-11-06 | 2033 | 11 | Nov | 6 | 7 | 0 | 23.33% | 6.4429 | 0%
2033-11-07 | 2033 | 11 | Nov | 7 | 1 | 1 | 23.33% | 6.4429 | 0%
2033-11-08 | 2033 | 11 | Nov | 8 | 2 | 1 | 23.33% | 6.4429 | 0%
2033-11-09 | 2033 | 11 | Nov | 9 | 3 | 1 | 23.33% | 6.4429 | 0%
2033-11-10 | 2033 | 11 | Nov | 10 | 4 | 1 | 23.33% | 6.4429 | 0%
2033-11-11 | 2033 | 11 | Nov | 11 | 5 | 1 | 23.33% | 6.4429 | 0%
2033-11-12 | 2033 | 11 | Nov | 12 | 6 | 0 | 23.33% | 6.4429 | 0%
2033-11-13 | 2033 | 11 | Nov | 13 | 7 | 0 | 23.33% | 6.4429 | 0%
2033-11-14 | 2033 | 11 | Nov | 14 | 1 | 1 | 23.33% | 6.4429 | 0%
2033-11-15 | 2033 | 11 | Nov | 15 | 2 | 1 | 23.33% | 6.4429 | 0%
2033-11-16 | 2033 | 11 | Nov | 16 | 3 | 1 | 23.33% | 6.4429 | 0%
2033-11-17 | 2033 | 11 | Nov | 17 | 4 | 1 | 23.33% | 6.4429 | 0%
2033-11-18 | 2033 | 11 | Nov | 18 | 5 | 1 | 23.33% | 6.4429 | 0%
2033-11-19 | 2033 | 11 | Nov | 19 | 6 | 0 | 23.33% | 6.4429 | 0%
2033-11-20 | 2033 | 11 | Nov | 20 | 7 | 0 | 23.33% | 6.4429 | 0%
2033-11-21 | 2033 | 11 | Nov | 21 | 1 | 1 | 23.33% | 6.4429 | 0%
2033-11-22 | 2033 | 11 | Nov | 22 | 2 | 1 | 23.33% | 6.4429 | 0%
2033-11-23 | 2033 | 11 | Nov | 23 | 3 | 1 | 23.33% | 6.4429 | 0%
2033-11-24 | 2033 | 11 | Nov | 24 | 4 | 1 | 23.33% | 6.4429 | 0%
2033-11-25 | 2033 | 11 | Nov | 25 | 5 | 1 | 23.33% | 6.4429 | 0%
2033-11-26 | 2033 | 11 | Nov | 26 | 6 | 0 | 23.33% | 6.4429 | 0%
2033-11-27 | 2033 | 11 | Nov | 27 | 7 | 0 | 23.33% | 6.4429 | 0%
2033-11-28 | 2033 | 11 | Nov | 28 | 1 | 1 | 23.33% | 6.4429 | 0%
2033-11-29 | 2033 | 11 | Nov | 29 | 2 | 1 | 23.33% | 6.4429 | 0%
2033-11-30 | 2033 | 11 | Nov | 30 | 3 | 1 | 23.33% | 6.4429 | 0%
2033-12-01 | 2033 | 12 | Dec | 1 | 4 | 1 | 22.69% | 6.7962 | 0%
2033-12-02 | 2033 | 12 | Dec | 2 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-12-03 | 2033 | 12 | Dec | 3 | 6 | 0 | 22.69% | 6.7962 | 0%
2033-12-04 | 2033 | 12 | Dec | 4 | 7 | 0 | 22.69% | 6.7962 | 0%
2033-12-05 | 2033 | 12 | Dec | 5 | 1 | 1 | 22.69% | 6.7962 | 0%
2033-12-06 | 2033 | 12 | Dec | 6 | 2 | 1 | 22.69% | 6.7962 | 0%
2033-12-07 | 2033 | 12 | Dec | 7 | 3 | 1 | 22.69% | 6.7962 | 0%
2033-12-08 | 2033 | 12 | Dec | 8 | 4 | 1 | 22.69% | 6.7962 | 0%
2033-12-09 | 2033 | 12 | Dec | 9 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-12-10 | 2033 | 12 | Dec | 10 | 6 | 0 | 22.69% | 6.7962 | 0%
2033-12-11 | 2033 | 12 | Dec | 11 | 7 | 0 | 22.69% | 6.7962 | 0%
2033-12-12 | 2033 | 12 | Dec | 12 | 1 | 1 | 22.69% | 6.7962 | 0%
2033-12-13 | 2033 | 12 | Dec | 13 | 2 | 1 | 22.69% | 6.7962 | 0%
2033-12-14 | 2033 | 12 | Dec | 14 | 3 | 1 | 22.69% | 6.7962 | 0%
2033-12-15 | 2033 | 12 | Dec | 15 | 4 | 1 | 22.69% | 6.7962 | 0%
2033-12-16 | 2033 | 12 | Dec | 16 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-12-17 | 2033 | 12 | Dec | 17 | 6 | 0 | 22.69% | 6.7962 | 0%
2033-12-18 | 2033 | 12 | Dec | 18 | 7 | 0 | 22.69% | 6.7962 | 0%
2033-12-19 | 2033 | 12 | Dec | 19 | 1 | 1 | 22.69% | 6.7962 | 0%
2033-12-20 | 2033 | 12 | Dec | 20 | 2 | 1 | 22.69% | 6.7962 | 0%
2033-12-21 | 2033 | 12 | Dec | 21 | 3 | 1 | 22.69% | 6.7962 | 0%
2033-12-22 | 2033 | 12 | Dec | 22 | 4 | 1 | 22.69% | 6.7962 | 0%
2033-12-23 | 2033 | 12 | Dec | 23 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-12-24 | 2033 | 12 | Dec | 24 | 6 | 0 | 22.69% | 6.7962 | 0%
2033-12-25 | 2033 | 12 | Dec | 25 | 7 | 0 | 22.69% | 6.7962 | 0%
2033-12-26 | 2033 | 12 | Dec | 26 | 1 | 1 | 22.69% | 6.7962 | 0%
2033-12-27 | 2033 | 12 | Dec | 27 | 2 | 1 | 22.69% | 6.7962 | 0%
2033-12-28 | 2033 | 12 | Dec | 28 | 3 | 1 | 22.69% | 6.7962 | 0%
2033-12-29 | 2033 | 12 | Dec | 29 | 4 | 1 | 22.69% | 6.7962 | 0%
2033-12-30 | 2033 | 12 | Dec | 30 | 5 | 1 | 22.69% | 6.7962 | 0%
2033-12-31 | 2033 | 12 | Dec | 31 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-01-01 | 2034 | 1 | Jan | 1 | 7 | 0 | 19.46% | 7.0276 | 0%
2034-01-02 | 2034 | 1 | Jan | 2 | 1 | 1 | 19.46% | 7.0276 | 0%
2034-01-03 | 2034 | 1 | Jan | 3 | 2 | 1 | 19.46% | 7.0276 | 0%
2034-01-04 | 2034 | 1 | Jan | 4 | 3 | 1 | 19.46% | 7.0276 | 0%
2034-01-05 | 2034 | 1 | Jan | 5 | 4 | 1 | 19.46% | 7.0276 | 0%
2034-01-06 | 2034 | 1 | Jan | 6 | 5 | 1 | 19.46% | 7.0276 | 0%
2034-01-07 | 2034 | 1 | Jan | 7 | 6 | 0 | 19.46% | 7.0276 | 0%
2034-01-08 | 2034 | 1 | Jan | 8 | 7 | 0 | 19.46% | 7.0276 | 0%
2034-01-09 | 2034 | 1 | Jan | 9 | 1 | 1 | 19.46% | 7.0276 | 0%
2034-01-10 | 2034 | 1 | Jan | 10 | 2 | 1 | 19.46% | 7.0276 | 0%
2034-01-11 | 2034 | 1 | Jan | 11 | 3 | 1 | 19.46% | 7.0276 | 0%
2034-01-12 | 2034 | 1 | Jan | 12 | 4 | 1 | 19.46% | 7.0276 | 0%
2034-01-13 | 2034 | 1 | Jan | 13 | 5 | 1 | 19.46% | 7.0276 | 0%
2034-01-14 | 2034 | 1 | Jan | 14 | 6 | 0 | 19.46% | 7.0276 | 0%
2034-01-15 | 2034 | 1 | Jan | 15 | 7 | 0 | 19.46% | 7.0276 | 0%
2034-01-16 | 2034 | 1 | Jan | 16 | 1 | 1 | 19.46% | 7.0276 | 0%
2034-01-17 | 2034 | 1 | Jan | 17 | 2 | 1 | 19.46% | 7.0276 | 0%
2034-01-18 | 2034 | 1 | Jan | 18 | 3 | 1 | 19.46% | 7.0276 | 0%
2034-01-19 | 2034 | 1 | Jan | 19 | 4 | 1 | 19.46% | 7.0276 | 0%
2034-01-20 | 2034 | 1 | Jan | 20 | 5 | 1 | 19.46% | 7.0276 | 0%
2034-01-21 | 2034 | 1 | Jan | 21 | 6 | 0 | 19.46% | 7.0276 | 0%
2034-01-22 | 2034 | 1 | Jan | 22 | 7 | 0 | 19.46% | 7.0276 | 0%
2034-01-23 | 2034 | 1 | Jan | 23 | 1 | 1 | 19.46% | 7.0276 | 0%
2034-01-24 | 2034 | 1 | Jan | 24 | 2 | 1 | 19.46% | 7.0276 | 0%
2034-01-25 | 2034 | 1 | Jan | 25 | 3 | 1 | 19.46% | 7.0276 | 0%
2034-01-26 | 2034 | 1 | Jan | 26 | 4 | 1 | 19.46% | 7.0276 | 0%
2034-01-27 | 2034 | 1 | Jan | 27 | 5 | 1 | 19.46% | 7.0276 | 0%
2034-01-28 | 2034 | 1 | Jan | 28 | 6 | 0 | 19.46% | 7.0276 | 0%
2034-01-29 | 2034 | 1 | Jan | 29 | 7 | 0 | 19.46% | 7.0276 | 0%
2034-01-30 | 2034 | 1 | Jan | 30 | 1 | 1 | 19.46% | 7.0276 | 0%
2034-01-31 | 2034 | 1 | Jan | 31 | 2 | 1 | 19.46% | 7.0276 | 0%
2034-02-01 | 2034 | 2 | Feb | 1 | 3 | 1 | 18.87% | 7.4625 | 0%
2034-02-02 | 2034 | 2 | Feb | 2 | 4 | 1 | 18.87% | 7.4625 | 0%
2034-02-03 | 2034 | 2 | Feb | 3 | 5 | 1 | 18.87% | 7.4625 | 0%
2034-02-04 | 2034 | 2 | Feb | 4 | 6 | 0 | 18.87% | 7.4625 | 0%
2034-02-05 | 2034 | 2 | Feb | 5 | 7 | 0 | 18.87% | 7.4625 | 0%
2034-02-06 | 2034 | 2 | Feb | 6 | 1 | 1 | 18.87% | 7.4625 | 0%
2034-02-07 | 2034 | 2 | Feb | 7 | 2 | 1 | 18.87% | 7.4625 | 0%
2034-02-08 | 2034 | 2 | Feb | 8 | 3 | 1 | 18.87% | 7.4625 | 0%
2034-02-09 | 2034 | 2 | Feb | 9 | 4 | 1 | 18.87% | 7.4625 | 0%
2034-02-10 | 2034 | 2 | Feb | 10 | 5 | 1 | 18.87% | 7.4625 | 0%
2034-02-11 | 2034 | 2 | Feb | 11 | 6 | 0 | 18.87% | 7.4625 | 0%
2034-02-12 | 2034 | 2 | Feb | 12 | 7 | 0 | 18.87% | 7.4625 | 0%
2034-02-13 | 2034 | 2 | Feb | 13 | 1 | 1 | 18.87% | 7.4625 | 0%
2034-02-14 | 2034 | 2 | Feb | 14 | 2 | 1 | 18.87% | 7.4625 | 0%
2034-02-15 | 2034 | 2 | Feb | 15 | 3 | 1 | 18.87% | 7.4625 | 0%
2034-02-16 | 2034 | 2 | Feb | 16 | 4 | 1 | 18.87% | 7.4625 | 0%
2034-02-17 | 2034 | 2 | Feb | 17 | 5 | 1 | 18.87% | 7.4625 | 0%
2034-02-18 | 2034 | 2 | Feb | 18 | 6 | 0 | 18.87% | 7.4625 | 0%
2034-02-19 | 2034 | 2 | Feb | 19 | 7 | 0 | 18.87% | 7.4625 | 0%
2034-02-20 | 2034 | 2 | Feb | 20 | 1 | 1 | 18.87% | 7.4625 | 0%
2034-02-21 | 2034 | 2 | Feb | 21 | 2 | 1 | 18.87% | 7.4625 | 0%
2034-02-22 | 2034 | 2 | Feb | 22 | 3 | 1 | 18.87% | 7.4625 | 0%
2034-02-23 | 2034 | 2 | Feb | 23 | 4 | 1 | 18.87% | 7.4625 | 0%
2034-02-24 | 2034 | 2 | Feb | 24 | 5 | 1 | 18.87% | 7.4625 | 0%
2034-02-25 | 2034 | 2 | Feb | 25 | 6 | 0 | 18.87% | 7.4625 | 0%
2034-02-26 | 2034 | 2 | Feb | 26 | 7 | 0 | 18.87% | 7.4625 | 0%
2034-02-27 | 2034 | 2 | Feb | 27 | 1 | 1 | 18.87% | 7.4625 | 0%
2034-02-28 | 2034 | 2 | Feb | 28 | 2 | 1 | 18.87% | 7.4625 | 0%
2034-03-01 | 2034 | 3 | Mar | 1 | 3 | 1 | 18.49% | 7.8663 | 0%
2034-03-02 | 2034 | 3 | Mar | 2 | 4 | 1 | 18.49% | 7.8663 | 0%
2034-03-03 | 2034 | 3 | Mar | 3 | 5 | 1 | 18.49% | 7.8663 | 0%
2034-03-04 | 2034 | 3 | Mar | 4 | 6 | 0 | 18.49% | 7.8663 | 0%
2034-03-05 | 2034 | 3 | Mar | 5 | 7 | 0 | 18.49% | 7.8663 | 0%
2034-03-06 | 2034 | 3 | Mar | 6 | 1 | 1 | 18.49% | 7.8663 | 0%
2034-03-07 | 2034 | 3 | Mar | 7 | 2 | 1 | 18.49% | 7.8663 | 0%
2034-03-08 | 2034 | 3 | Mar | 8 | 3 | 1 | 18.49% | 7.8663 | 0%
2034-03-09 | 2034 | 3 | Mar | 9 | 4 | 1 | 18.49% | 7.8663 | 0%
2034-03-10 | 2034 | 3 | Mar | 10 | 5 | 1 | 18.49% | 7.8663 | 0%
2034-03-11 | 2034 | 3 | Mar | 11 | 6 | 0 | 18.49% | 7.8663 | 0%
2034-03-12 | 2034 | 3 | Mar | 12 | 7 | 0 | 18.49% | 7.8663 | 0%
2034-03-13 | 2034 | 3 | Mar | 13 | 1 | 1 | 18.49% | 7.8663 | 0%
2034-03-14 | 2034 | 3 | Mar | 14 | 2 | 1 | 18.49% | 7.8663 | 0%
2034-03-15 | 2034 | 3 | Mar | 15 | 3 | 1 | 18.49% | 7.8663 | 0%
2034-03-16 | 2034 | 3 | Mar | 16 | 4 | 1 | 18.49% | 7.8663 | 0%
2034-03-17 | 2034 | 3 | Mar | 17 | 5 | 1 | 18.49% | 7.8663 | 0%
2034-03-18 | 2034 | 3 | Mar | 18 | 6 | 0 | 18.49% | 7.8663 | 0%
2034-03-19 | 2034 | 3 | Mar | 19 | 7 | 0 | 18.49% | 7.8663 | 0%
2034-03-20 | 2034 | 3 | Mar | 20 | 1 | 1 | 18.49% | 7.8663 | 0%
2034-03-21 | 2034 | 3 | Mar | 21 | 2 | 1 | 18.49% | 7.8663 | 0%
2034-03-22 | 2034 | 3 | Mar | 22 | 3 | 1 | 18.49% | 7.8663 | 0%
2034-03-23 | 2034 | 3 | Mar | 23 | 4 | 1 | 18.49% | 7.8663 | 0%
2034-03-24 | 2034 | 3 | Mar | 24 | 5 | 1 | 18.49% | 7.8663 | 0%
2034-03-25 | 2034 | 3 | Mar | 25 | 6 | 0 | 18.49% | 7.8663 | 0%
2034-03-26 | 2034 | 3 | Mar | 26 | 7 | 0 | 18.49% | 7.8663 | 0%
2034-03-27 | 2034 | 3 | Mar | 27 | 1 | 1 | 18.49% | 7.8663 | 0%
2034-03-28 | 2034 | 3 | Mar | 28 | 2 | 1 | 18.49% | 7.8663 | 0%
2034-03-29 | 2034 | 3 | Mar | 29 | 3 | 1 | 18.49% | 7.8663 | 0%
2034-03-30 | 2034 | 3 | Mar | 30 | 4 | 1 | 18.49% | 7.8663 | 0%
2034-03-31 | 2034 | 3 | Mar | 31 | 5 | 1 | 18.49% | 7.8663 | 0%
2034-04-01 | 2034 | 4 | Apr | 1 | 6 | 0 | 25.56% | 7.5 | 0%
2034-04-02 | 2034 | 4 | Apr | 2 | 7 | 0 | 25.56% | 7.5 | 0%
2034-04-03 | 2034 | 4 | Apr | 3 | 1 | 1 | 25.56% | 7.5 | 0%
2034-04-04 | 2034 | 4 | Apr | 4 | 2 | 1 | 25.56% | 7.5 | 0%
2034-04-05 | 2034 | 4 | Apr | 5 | 3 | 1 | 25.56% | 7.5 | 0%
2034-04-06 | 2034 | 4 | Apr | 6 | 4 | 1 | 25.56% | 7.5 | 0%
2034-04-07 | 2034 | 4 | Apr | 7 | 5 | 1 | 25.56% | 7.5 | 0%
2034-04-08 | 2034 | 4 | Apr | 8 | 6 | 0 | 25.56% | 7.5 | 0%
2034-04-09 | 2034 | 4 | Apr | 9 | 7 | 0 | 25.56% | 7.5 | 0%
2034-04-10 | 2034 | 4 | Apr | 10 | 1 | 1 | 25.56% | 7.5 | 0%
2034-04-11 | 2034 | 4 | Apr | 11 | 2 | 1 | 25.56% | 7.5 | 0%
2034-04-12 | 2034 | 4 | Apr | 12 | 3 | 1 | 25.56% | 7.5 | 0%
2034-04-13 | 2034 | 4 | Apr | 13 | 4 | 1 | 25.56% | 7.5 | 0%
2034-04-14 | 2034 | 4 | Apr | 14 | 5 | 1 | 25.56% | 7.5 | 0%
2034-04-15 | 2034 | 4 | Apr | 15 | 6 | 0 | 25.56% | 7.5 | 0%
2034-04-16 | 2034 | 4 | Apr | 16 | 7 | 0 | 25.56% | 7.5 | 0%
2034-04-17 | 2034 | 4 | Apr | 17 | 1 | 1 | 25.56% | 7.5 | 0%
2034-04-18 | 2034 | 4 | Apr | 18 | 2 | 1 | 25.56% | 7.5 | 0%
2034-04-19 | 2034 | 4 | Apr | 19 | 3 | 1 | 25.56% | 7.5 | 0%
2034-04-20 | 2034 | 4 | Apr | 20 | 4 | 1 | 25.56% | 7.5 | 0%
2034-04-21 | 2034 | 4 | Apr | 21 | 5 | 1 | 25.56% | 7.5 | 0%
2034-04-22 | 2034 | 4 | Apr | 22 | 6 | 0 | 25.56% | 7.5 | 0%
2034-04-23 | 2034 | 4 | Apr | 23 | 7 | 0 | 25.56% | 7.5 | 0%
2034-04-24 | 2034 | 4 | Apr | 24 | 1 | 1 | 25.56% | 7.5 | 0%
2034-04-25 | 2034 | 4 | Apr | 25 | 2 | 1 | 25.56% | 7.5 | 0%
2034-04-26 | 2034 | 4 | Apr | 26 | 3 | 1 | 25.56% | 7.5 | 0%
2034-04-27 | 2034 | 4 | Apr | 27 | 4 | 1 | 25.56% | 7.5 | 0%
2034-04-28 | 2034 | 4 | Apr | 28 | 5 | 1 | 25.56% | 7.5 | 0%
2034-04-29 | 2034 | 4 | Apr | 29 | 6 | 0 | 25.56% | 7.5 | 0%
2034-04-30 | 2034 | 4 | Apr | 30 | 7 | 0 | 25.56% | 7.5 | 0%
2034-05-01 | 2034 | 5 | May | 1 | 1 | 1 | 23.01% | 8.1449 | 0%
2034-05-02 | 2034 | 5 | May | 2 | 2 | 1 | 23.01% | 8.1449 | 0%
2034-05-03 | 2034 | 5 | May | 3 | 3 | 1 | 23.01% | 8.1449 | 0%
2034-05-04 | 2034 | 5 | May | 4 | 4 | 1 | 23.01% | 8.1449 | 0%
2034-05-05 | 2034 | 5 | May | 5 | 5 | 1 | 23.01% | 8.1449 | 0%
2034-05-06 | 2034 | 5 | May | 6 | 6 | 0 | 23.01% | 8.1449 | 0%
2034-05-07 | 2034 | 5 | May | 7 | 7 | 0 | 23.01% | 8.1449 | 0%
2034-05-08 | 2034 | 5 | May | 8 | 1 | 1 | 23.01% | 8.1449 | 0%
2034-05-09 | 2034 | 5 | May | 9 | 2 | 1 | 23.01% | 8.1449 | 0%
2034-05-10 | 2034 | 5 | May | 10 | 3 | 1 | 23.01% | 8.1449 | 0%
2034-05-11 | 2034 | 5 | May | 11 | 4 | 1 | 23.01% | 8.1449 | 0%
2034-05-12 | 2034 | 5 | May | 12 | 5 | 1 | 23.01% | 8.1449 | 0%
2034-05-13 | 2034 | 5 | May | 13 | 6 | 0 | 23.01% | 8.1449 | 0%
2034-05-14 | 2034 | 5 | May | 14 | 7 | 0 | 23.01% | 8.1449 | 0%
2034-05-15 | 2034 | 5 | May | 15 | 1 | 1 | 23.01% | 8.1449 | 0%
2034-05-16 | 2034 | 5 | May | 16 | 2 | 1 | 23.01% | 8.1449 | 0%
2034-05-17 | 2034 | 5 | May | 17 | 3 | 1 | 23.01% | 8.1449 | 0%
2034-05-18 | 2034 | 5 | May | 18 | 4 | 1 | 23.01% | 8.1449 | 0%
2034-05-19 | 2034 | 5 | May | 19 | 5 | 1 | 23.01% | 8.1449 | 0%
2034-05-20 | 2034 | 5 | May | 20 | 6 | 0 | 23.01% | 8.1449 | 0%
2034-05-21 | 2034 | 5 | May | 21 | 7 | 0 | 23.01% | 8.1449 | 0%
2034-05-22 | 2034 | 5 | May | 22 | 1 | 1 | 23.01% | 8.1449 | 0%
2034-05-23 | 2034 | 5 | May | 23 | 2 | 1 | 23.01% | 8.1449 | 0%
2034-05-24 | 2034 | 5 | May | 24 | 3 | 1 | 23.01% | 8.1449 | 0%
2034-05-25 | 2034 | 5 | May | 25 | 4 | 1 | 23.01% | 8.1449 | 0%
2034-05-26 | 2034 | 5 | May | 26 | 5 | 1 | 23.01% | 8.1449 | 0%
2034-05-27 | 2034 | 5 | May | 27 | 6 | 0 | 23.01% | 8.1449 | 0%
2034-05-28 | 2034 | 5 | May | 28 | 7 | 0 | 23.01% | 8.1449 | 0%
2034-05-29 | 2034 | 5 | May | 29 | 1 | 1 | 23.01% | 8.1449 | 0%
2034-05-30 | 2034 | 5 | May | 30 | 2 | 1 | 23.01% | 8.1449 | 0%
2034-05-31 | 2034 | 5 | May | 31 | 3 | 1 | 23.01% | 8.1449 | 0%
2034-06-01 | 2034 | 6 | Jun | 1 | 4 | 1 | 28.67% | 7.9419 | 0%
2034-06-02 | 2034 | 6 | Jun | 2 | 5 | 1 | 28.67% | 7.9419 | 0%
2034-06-03 | 2034 | 6 | Jun | 3 | 6 | 0 | 28.67% | 7.9419 | 0%
2034-06-04 | 2034 | 6 | Jun | 4 | 7 | 0 | 28.67% | 7.9419 | 0%
2034-06-05 | 2034 | 6 | Jun | 5 | 1 | 1 | 28.67% | 7.9419 | 0%
2034-06-06 | 2034 | 6 | Jun | 6 | 2 | 1 | 28.67% | 7.9419 | 0%
2034-06-07 | 2034 | 6 | Jun | 7 | 3 | 1 | 28.67% | 7.9419 | 0%
2034-06-08 | 2034 | 6 | Jun | 8 | 4 | 1 | 28.67% | 7.9419 | 0%
2034-06-09 | 2034 | 6 | Jun | 9 | 5 | 1 | 28.67% | 7.9419 | 0%
2034-06-10 | 2034 | 6 | Jun | 10 | 6 | 0 | 28.67% | 7.9419 | 0%
2034-06-11 | 2034 | 6 | Jun | 11 | 7 | 0 | 28.67% | 7.9419 | 0%
2034-06-12 | 2034 | 6 | Jun | 12 | 1 | 1 | 28.67% | 7.9419 | 0%
2034-06-13 | 2034 | 6 | Jun | 13 | 2 | 1 | 28.67% | 7.9419 | 0%
2034-06-14 | 2034 | 6 | Jun | 14 | 3 | 1 | 28.67% | 7.9419 | 0%
2034-06-15 | 2034 | 6 | Jun | 15 | 4 | 1 | 28.67% | 7.9419 | 0%
2034-06-16 | 2034 | 6 | Jun | 16 | 5 | 1 | 28.67% | 7.9419 | 0%
2034-06-17 | 2034 | 6 | Jun | 17 | 6 | 0 | 28.67% | 7.9419 | 0%
2034-06-18 | 2034 | 6 | Jun | 18 | 7 | 0 | 28.67% | 7.9419 | 0%
2034-06-19 | 2034 | 6 | Jun | 19 | 1 | 1 | 28.67% | 7.9419 | 0%
2034-06-20 | 2034 | 6 | Jun | 20 | 2 | 1 | 28.67% | 7.9419 | 0%
2034-06-21 | 2034 | 6 | Jun | 21 | 3 | 1 | 28.67% | 7.9419 | 0%
2034-06-22 | 2034 | 6 | Jun | 22 | 4 | 1 | 28.67% | 7.9419 | 0%
2034-06-23 | 2034 | 6 | Jun | 23 | 5 | 1 | 28.67% | 7.9419 | 0%
2034-06-24 | 2034 | 6 | Jun | 24 | 6 | 0 | 28.67% | 7.9419 | 0%
2034-06-25 | 2034 | 6 | Jun | 25 | 7 | 0 | 28.67% | 7.9419 | 0%
2034-06-26 | 2034 | 6 | Jun | 26 | 1 | 1 | 28.67% | 7.9419 | 0%
2034-06-27 | 2034 | 6 | Jun | 27 | 2 | 1 | 28.67% | 7.9419 | 0%
2034-06-28 | 2034 | 6 | Jun | 28 | 3 | 1 | 28.67% | 7.9419 | 0%
2034-06-29 | 2034 | 6 | Jun | 29 | 4 | 1 | 28.67% | 7.9419 | 0%
2034-06-30 | 2034 | 6 | Jun | 30 | 5 | 1 | 28.67% | 7.9419 | 0%
2034-07-01 | 2034 | 7 | Jul | 1 | 6 | 0 | 24.73% | 8.3739 | 0%
2034-07-02 | 2034 | 7 | Jul | 2 | 7 | 0 | 24.73% | 8.3739 | 0%
2034-07-03 | 2034 | 7 | Jul | 3 | 1 | 1 | 24.73% | 8.3739 | 0%
2034-07-04 | 2034 | 7 | Jul | 4 | 2 | 1 | 24.73% | 8.3739 | 0%
2034-07-05 | 2034 | 7 | Jul | 5 | 3 | 1 | 24.73% | 8.3739 | 0%
2034-07-06 | 2034 | 7 | Jul | 6 | 4 | 1 | 24.73% | 8.3739 | 0%
2034-07-07 | 2034 | 7 | Jul | 7 | 5 | 1 | 24.73% | 8.3739 | 0%
2034-07-08 | 2034 | 7 | Jul | 8 | 6 | 0 | 24.73% | 8.3739 | 0%
2034-07-09 | 2034 | 7 | Jul | 9 | 7 | 0 | 24.73% | 8.3739 | 0%
2034-07-10 | 2034 | 7 | Jul | 10 | 1 | 1 | 24.73% | 8.3739 | 0%
2034-07-11 | 2034 | 7 | Jul | 11 | 2 | 1 | 24.73% | 8.3739 | 0%
2034-07-12 | 2034 | 7 | Jul | 12 | 3 | 1 | 24.73% | 8.3739 | 0%
2034-07-13 | 2034 | 7 | Jul | 13 | 4 | 1 | 24.73% | 8.3739 | 0%
2034-07-14 | 2034 | 7 | Jul | 14 | 5 | 1 | 24.73% | 8.3739 | 0%
2034-07-15 | 2034 | 7 | Jul | 15 | 6 | 0 | 24.73% | 8.3739 | 0%
2034-07-16 | 2034 | 7 | Jul | 16 | 7 | 0 | 24.73% | 8.3739 | 0%
2034-07-17 | 2034 | 7 | Jul | 17 | 1 | 1 | 24.73% | 8.3739 | 0%
2034-07-18 | 2034 | 7 | Jul | 18 | 2 | 1 | 24.73% | 8.3739 | 0%
2034-07-19 | 2034 | 7 | Jul | 19 | 3 | 1 | 24.73% | 8.3739 | 0%
2034-07-20 | 2034 | 7 | Jul | 20 | 4 | 1 | 24.73% | 8.3739 | 0%
2034-07-21 | 2034 | 7 | Jul | 21 | 5 | 1 | 24.73% | 8.3739 | 0%
2034-07-22 | 2034 | 7 | Jul | 22 | 6 | 0 | 24.73% | 8.3739 | 0%
2034-07-23 | 2034 | 7 | Jul | 23 | 7 | 0 | 24.73% | 8.3739 | 0%
2034-07-24 | 2034 | 7 | Jul | 24 | 1 | 1 | 24.73% | 8.3739 | 0%
2034-07-25 | 2034 | 7 | Jul | 25 | 2 | 1 | 24.73% | 8.3739 | 0%
2034-07-26 | 2034 | 7 | Jul | 26 | 3 | 1 | 24.73% | 8.3739 | 0%
2034-07-27 | 2034 | 7 | Jul | 27 | 4 | 1 | 24.73% | 8.3739 | 0%
2034-07-28 | 2034 | 7 | Jul | 28 | 5 | 1 | 24.73% | 8.3739 | 0%
2034-07-29 | 2034 | 7 | Jul | 29 | 6 | 0 | 24.73% | 8.3739 | 0%
2034-07-30 | 2034 | 7 | Jul | 30 | 7 | 0 | 24.73% | 8.3739 | 0%
2034-07-31 | 2034 | 7 | Jul | 31 | 1 | 1 | 24.73% | 8.3739 | 0%
2034-08-01 | 2034 | 8 | Aug | 1 | 2 | 1 | 23.55% | 7.9589 | 0%
2034-08-02 | 2034 | 8 | Aug | 2 | 3 | 1 | 23.55% | 7.9589 | 0%
2034-08-03 | 2034 | 8 | Aug | 3 | 4 | 1 | 23.55% | 7.9589 | 0%
2034-08-04 | 2034 | 8 | Aug | 4 | 5 | 1 | 23.55% | 7.9589 | 0%
2034-08-05 | 2034 | 8 | Aug | 5 | 6 | 0 | 23.55% | 7.9589 | 0%
2034-08-06 | 2034 | 8 | Aug | 6 | 7 | 0 | 23.55% | 7.9589 | 0%
2034-08-07 | 2034 | 8 | Aug | 7 | 1 | 1 | 23.55% | 7.9589 | 0%
2034-08-08 | 2034 | 8 | Aug | 8 | 2 | 1 | 23.55% | 7.9589 | 0%
2034-08-09 | 2034 | 8 | Aug | 9 | 3 | 1 | 23.55% | 7.9589 | 0%
2034-08-10 | 2034 | 8 | Aug | 10 | 4 | 1 | 23.55% | 7.9589 | 0%
2034-08-11 | 2034 | 8 | Aug | 11 | 5 | 1 | 23.55% | 7.9589 | 0%
2034-08-12 | 2034 | 8 | Aug | 12 | 6 | 0 | 23.55% | 7.9589 | 0%
2034-08-13 | 2034 | 8 | Aug | 13 | 7 | 0 | 23.55% | 7.9589 | 0%
2034-08-14 | 2034 | 8 | Aug | 14 | 1 | 1 | 23.55% | 7.9589 | 0%
2034-08-15 | 2034 | 8 | Aug | 15 | 2 | 1 | 23.55% | 7.9589 | 0%
2034-08-16 | 2034 | 8 | Aug | 16 | 3 | 1 | 23.55% | 7.9589 | 0%
2034-08-17 | 2034 | 8 | Aug | 17 | 4 | 1 | 23.55% | 7.9589 | 0%
2034-08-18 | 2034 | 8 | Aug | 18 | 5 | 1 | 23.55% | 7.9589 | 0%
2034-08-19 | 2034 | 8 | Aug | 19 | 6 | 0 | 23.55% | 7.9589 | 0%
2034-08-20 | 2034 | 8 | Aug | 20 | 7 | 0 | 23.55% | 7.9589 | 0%
2034-08-21 | 2034 | 8 | Aug | 21 | 1 | 1 | 23.55% | 7.9589 | 0%
2034-08-22 | 2034 | 8 | Aug | 22 | 2 | 1 | 23.55% | 7.9589 | 0%
2034-08-23 | 2034 | 8 | Aug | 23 | 3 | 1 | 23.55% | 7.9589 | 0%
2034-08-24 | 2034 | 8 | Aug | 24 | 4 | 1 | 23.55% | 7.9589 | 0%
2034-08-25 | 2034 | 8 | Aug | 25 | 5 | 1 | 23.55% | 7.9589 | 0%
2034-08-26 | 2034 | 8 | Aug | 26 | 6 | 0 | 23.55% | 7.9589 | 0%
2034-08-27 | 2034 | 8 | Aug | 27 | 7 | 0 | 23.55% | 7.9589 | 0%
2034-08-28 | 2034 | 8 | Aug | 28 | 1 | 1 | 23.55% | 7.9589 | 0%
2034-08-29 | 2034 | 8 | Aug | 29 | 2 | 1 | 23.55% | 7.9589 | 0%
2034-08-30 | 2034 | 8 | Aug | 30 | 3 | 1 | 23.55% | 7.9589 | 0%
2034-08-31 | 2034 | 8 | Aug | 31 | 4 | 1 | 23.55% | 7.9589 | 0%
2034-09-01 | 2034 | 9 | Sep | 1 | 5 | 1 | 20.67% | 6.8065 | 0%
2034-09-02 | 2034 | 9 | Sep | 2 | 6 | 0 | 20.67% | 6.8065 | 0%
2034-09-03 | 2034 | 9 | Sep | 3 | 7 | 0 | 20.67% | 6.8065 | 0%
2034-09-04 | 2034 | 9 | Sep | 4 | 1 | 1 | 20.67% | 6.8065 | 0%
2034-09-05 | 2034 | 9 | Sep | 5 | 2 | 1 | 20.67% | 6.8065 | 0%
2034-09-06 | 2034 | 9 | Sep | 6 | 3 | 1 | 20.67% | 6.8065 | 0%
2034-09-07 | 2034 | 9 | Sep | 7 | 4 | 1 | 20.67% | 6.8065 | 0%
2034-09-08 | 2034 | 9 | Sep | 8 | 5 | 1 | 20.67% | 6.8065 | 0%
2034-09-09 | 2034 | 9 | Sep | 9 | 6 | 0 | 20.67% | 6.8065 | 0%
2034-09-10 | 2034 | 9 | Sep | 10 | 7 | 0 | 20.67% | 6.8065 | 0%
2034-09-11 | 2034 | 9 | Sep | 11 | 1 | 1 | 20.67% | 6.8065 | 0%
2034-09-12 | 2034 | 9 | Sep | 12 | 2 | 1 | 20.67% | 6.8065 | 0%
2034-09-13 | 2034 | 9 | Sep | 13 | 3 | 1 | 20.67% | 6.8065 | 0%
2034-09-14 | 2034 | 9 | Sep | 14 | 4 | 1 | 20.67% | 6.8065 | 0%
2034-09-15 | 2034 | 9 | Sep | 15 | 5 | 1 | 20.67% | 6.8065 | 0%
2034-09-16 | 2034 | 9 | Sep | 16 | 6 | 0 | 20.67% | 6.8065 | 0%
2034-09-17 | 2034 | 9 | Sep | 17 | 7 | 0 | 20.67% | 6.8065 | 0%
2034-09-18 | 2034 | 9 | Sep | 18 | 1 | 1 | 20.67% | 6.8065 | 0%
2034-09-19 | 2034 | 9 | Sep | 19 | 2 | 1 | 20.67% | 6.8065 | 0%
2034-09-20 | 2034 | 9 | Sep | 20 | 3 | 1 | 20.67% | 6.8065 | 0%
2034-09-21 | 2034 | 9 | Sep | 21 | 4 | 1 | 20.67% | 6.8065 | 0%
2034-09-22 | 2034 | 9 | Sep | 22 | 5 | 1 | 20.67% | 6.8065 | 0%
2034-09-23 | 2034 | 9 | Sep | 23 | 6 | 0 | 20.67% | 6.8065 | 0%
2034-09-24 | 2034 | 9 | Sep | 24 | 7 | 0 | 20.67% | 6.8065 | 0%
2034-09-25 | 2034 | 9 | Sep | 25 | 1 | 1 | 20.67% | 6.8065 | 0%
2034-09-26 | 2034 | 9 | Sep | 26 | 2 | 1 | 20.67% | 6.8065 | 0%
2034-09-27 | 2034 | 9 | Sep | 27 | 3 | 1 | 20.67% | 6.8065 | 0%
2034-09-28 | 2034 | 9 | Sep | 28 | 4 | 1 | 20.67% | 6.8065 | 0%
2034-09-29 | 2034 | 9 | Sep | 29 | 5 | 1 | 20.67% | 6.8065 | 0%
2034-09-30 | 2034 | 9 | Sep | 30 | 6 | 0 | 20.67% | 6.8065 | 0%
2034-10-01 | 2034 | 10 | Oct | 1 | 7 | 0 | 23.23% | 6.8194 | 0%
2034-10-02 | 2034 | 10 | Oct | 2 | 1 | 1 | 23.23% | 6.8194 | 0%
2034-10-03 | 2034 | 10 | Oct | 3 | 2 | 1 | 23.23% | 6.8194 | 0%
2034-10-04 | 2034 | 10 | Oct | 4 | 3 | 1 | 23.23% | 6.8194 | 0%
2034-10-05 | 2034 | 10 | Oct | 5 | 4 | 1 | 23.23% | 6.8194 | 0%
2034-10-06 | 2034 | 10 | Oct | 6 | 5 | 1 | 23.23% | 6.8194 | 0%
2034-10-07 | 2034 | 10 | Oct | 7 | 6 | 0 | 23.23% | 6.8194 | 0%
2034-10-08 | 2034 | 10 | Oct | 8 | 7 | 0 | 23.23% | 6.8194 | 0%
2034-10-09 | 2034 | 10 | Oct | 9 | 1 | 1 | 23.23% | 6.8194 | 0%
2034-10-10 | 2034 | 10 | Oct | 10 | 2 | 1 | 23.23% | 6.8194 | 0%
2034-10-11 | 2034 | 10 | Oct | 11 | 3 | 1 | 23.23% | 6.8194 | 0%
2034-10-12 | 2034 | 10 | Oct | 12 | 4 | 1 | 23.23% | 6.8194 | 0%
2034-10-13 | 2034 | 10 | Oct | 13 | 5 | 1 | 23.23% | 6.8194 | 0%
2034-10-14 | 2034 | 10 | Oct | 14 | 6 | 0 | 23.23% | 6.8194 | 0%
2034-10-15 | 2034 | 10 | Oct | 15 | 7 | 0 | 23.23% | 6.8194 | 0%
2034-10-16 | 2034 | 10 | Oct | 16 | 1 | 1 | 23.23% | 6.8194 | 0%
2034-10-17 | 2034 | 10 | Oct | 17 | 2 | 1 | 23.23% | 6.8194 | 0%
2034-10-18 | 2034 | 10 | Oct | 18 | 3 | 1 | 23.23% | 6.8194 | 0%
2034-10-19 | 2034 | 10 | Oct | 19 | 4 | 1 | 23.23% | 6.8194 | 0%
2034-10-20 | 2034 | 10 | Oct | 20 | 5 | 1 | 23.23% | 6.8194 | 0%
2034-10-21 | 2034 | 10 | Oct | 21 | 6 | 0 | 23.23% | 6.8194 | 0%
2034-10-22 | 2034 | 10 | Oct | 22 | 7 | 0 | 23.23% | 6.8194 | 0%
2034-10-23 | 2034 | 10 | Oct | 23 | 1 | 1 | 23.23% | 6.8194 | 0%
2034-10-24 | 2034 | 10 | Oct | 24 | 2 | 1 | 23.23% | 6.8194 | 0%
2034-10-25 | 2034 | 10 | Oct | 25 | 3 | 1 | 23.23% | 6.8194 | 0%
2034-10-26 | 2034 | 10 | Oct | 26 | 4 | 1 | 23.23% | 6.8194 | 0%
2034-10-27 | 2034 | 10 | Oct | 27 | 5 | 1 | 23.23% | 6.8194 | 0%
2034-10-28 | 2034 | 10 | Oct | 28 | 6 | 0 | 23.23% | 6.8194 | 0%
2034-10-29 | 2034 | 10 | Oct | 29 | 7 | 0 | 23.23% | 6.8194 | 0%
2034-10-30 | 2034 | 10 | Oct | 30 | 1 | 1 | 23.23% | 6.8194 | 0%
2034-10-31 | 2034 | 10 | Oct | 31 | 2 | 1 | 23.23% | 6.8194 | 0%
2034-11-01 | 2034 | 11 | Nov | 1 | 3 | 1 | 23.33% | 6.4429 | 0%
2034-11-02 | 2034 | 11 | Nov | 2 | 4 | 1 | 23.33% | 6.4429 | 0%
2034-11-03 | 2034 | 11 | Nov | 3 | 5 | 1 | 23.33% | 6.4429 | 0%
2034-11-04 | 2034 | 11 | Nov | 4 | 6 | 0 | 23.33% | 6.4429 | 0%
2034-11-05 | 2034 | 11 | Nov | 5 | 7 | 0 | 23.33% | 6.4429 | 0%
2034-11-06 | 2034 | 11 | Nov | 6 | 1 | 1 | 23.33% | 6.4429 | 0%
2034-11-07 | 2034 | 11 | Nov | 7 | 2 | 1 | 23.33% | 6.4429 | 0%
2034-11-08 | 2034 | 11 | Nov | 8 | 3 | 1 | 23.33% | 6.4429 | 0%
2034-11-09 | 2034 | 11 | Nov | 9 | 4 | 1 | 23.33% | 6.4429 | 0%
2034-11-10 | 2034 | 11 | Nov | 10 | 5 | 1 | 23.33% | 6.4429 | 0%
2034-11-11 | 2034 | 11 | Nov | 11 | 6 | 0 | 23.33% | 6.4429 | 0%
2034-11-12 | 2034 | 11 | Nov | 12 | 7 | 0 | 23.33% | 6.4429 | 0%
2034-11-13 | 2034 | 11 | Nov | 13 | 1 | 1 | 23.33% | 6.4429 | 0%
2034-11-14 | 2034 | 11 | Nov | 14 | 2 | 1 | 23.33% | 6.4429 | 0%
2034-11-15 | 2034 | 11 | Nov | 15 | 3 | 1 | 23.33% | 6.4429 | 0%
2034-11-16 | 2034 | 11 | Nov | 16 | 4 | 1 | 23.33% | 6.4429 | 0%
2034-11-17 | 2034 | 11 | Nov | 17 | 5 | 1 | 23.33% | 6.4429 | 0%
2034-11-18 | 2034 | 11 | Nov | 18 | 6 | 0 | 23.33% | 6.4429 | 0%
2034-11-19 | 2034 | 11 | Nov | 19 | 7 | 0 | 23.33% | 6.4429 | 0%
2034-11-20 | 2034 | 11 | Nov | 20 | 1 | 1 | 23.33% | 6.4429 | 0%
2034-11-21 | 2034 | 11 | Nov | 21 | 2 | 1 | 23.33% | 6.4429 | 0%
2034-11-22 | 2034 | 11 | Nov | 22 | 3 | 1 | 23.33% | 6.4429 | 0%
2034-11-23 | 2034 | 11 | Nov | 23 | 4 | 1 | 23.33% | 6.4429 | 0%
2034-11-24 | 2034 | 11 | Nov | 24 | 5 | 1 | 23.33% | 6.4429 | 0%
2034-11-25 | 2034 | 11 | Nov | 25 | 6 | 0 | 23.33% | 6.4429 | 0%
2034-11-26 | 2034 | 11 | Nov | 26 | 7 | 0 | 23.33% | 6.4429 | 0%
2034-11-27 | 2034 | 11 | Nov | 27 | 1 | 1 | 23.33% | 6.4429 | 0%
2034-11-28 | 2034 | 11 | Nov | 28 | 2 | 1 | 23.33% | 6.4429 | 0%
2034-11-29 | 2034 | 11 | Nov | 29 | 3 | 1 | 23.33% | 6.4429 | 0%
2034-11-30 | 2034 | 11 | Nov | 30 | 4 | 1 | 23.33% | 6.4429 | 0%
2034-12-01 | 2034 | 12 | Dec | 1 | 5 | 1 | 22.69% | 6.7962 | 0%
2034-12-02 | 2034 | 12 | Dec | 2 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-12-03 | 2034 | 12 | Dec | 3 | 7 | 0 | 22.69% | 6.7962 | 0%
2034-12-04 | 2034 | 12 | Dec | 4 | 1 | 1 | 22.69% | 6.7962 | 0%
2034-12-05 | 2034 | 12 | Dec | 5 | 2 | 1 | 22.69% | 6.7962 | 0%
2034-12-06 | 2034 | 12 | Dec | 6 | 3 | 1 | 22.69% | 6.7962 | 0%
2034-12-07 | 2034 | 12 | Dec | 7 | 4 | 1 | 22.69% | 6.7962 | 0%
2034-12-08 | 2034 | 12 | Dec | 8 | 5 | 1 | 22.69% | 6.7962 | 0%
2034-12-09 | 2034 | 12 | Dec | 9 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-12-10 | 2034 | 12 | Dec | 10 | 7 | 0 | 22.69% | 6.7962 | 0%
2034-12-11 | 2034 | 12 | Dec | 11 | 1 | 1 | 22.69% | 6.7962 | 0%
2034-12-12 | 2034 | 12 | Dec | 12 | 2 | 1 | 22.69% | 6.7962 | 0%
2034-12-13 | 2034 | 12 | Dec | 13 | 3 | 1 | 22.69% | 6.7962 | 0%
2034-12-14 | 2034 | 12 | Dec | 14 | 4 | 1 | 22.69% | 6.7962 | 0%
2034-12-15 | 2034 | 12 | Dec | 15 | 5 | 1 | 22.69% | 6.7962 | 0%
2034-12-16 | 2034 | 12 | Dec | 16 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-12-17 | 2034 | 12 | Dec | 17 | 7 | 0 | 22.69% | 6.7962 | 0%
2034-12-18 | 2034 | 12 | Dec | 18 | 1 | 1 | 22.69% | 6.7962 | 0%
2034-12-19 | 2034 | 12 | Dec | 19 | 2 | 1 | 22.69% | 6.7962 | 0%
2034-12-20 | 2034 | 12 | Dec | 20 | 3 | 1 | 22.69% | 6.7962 | 0%
2034-12-21 | 2034 | 12 | Dec | 21 | 4 | 1 | 22.69% | 6.7962 | 0%
2034-12-22 | 2034 | 12 | Dec | 22 | 5 | 1 | 22.69% | 6.7962 | 0%
2034-12-23 | 2034 | 12 | Dec | 23 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-12-24 | 2034 | 12 | Dec | 24 | 7 | 0 | 22.69% | 6.7962 | 0%
2034-12-25 | 2034 | 12 | Dec | 25 | 1 | 1 | 22.69% | 6.7962 | 0%
2034-12-26 | 2034 | 12 | Dec | 26 | 2 | 1 | 22.69% | 6.7962 | 0%
2034-12-27 | 2034 | 12 | Dec | 27 | 3 | 1 | 22.69% | 6.7962 | 0%
2034-12-28 | 2034 | 12 | Dec | 28 | 4 | 1 | 22.69% | 6.7962 | 0%
2034-12-29 | 2034 | 12 | Dec | 29 | 5 | 1 | 22.69% | 6.7962 | 0%
2034-12-30 | 2034 | 12 | Dec | 30 | 6 | 0 | 22.69% | 6.7962 | 0%
2034-12-31 | 2034 | 12 | Dec | 31 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-01-01 | 2035 | 1 | Jan | 1 | 1 | 1 | 19.46% | 7.0276 | 0%
2035-01-02 | 2035 | 1 | Jan | 2 | 2 | 1 | 19.46% | 7.0276 | 0%
2035-01-03 | 2035 | 1 | Jan | 3 | 3 | 1 | 19.46% | 7.0276 | 0%
2035-01-04 | 2035 | 1 | Jan | 4 | 4 | 1 | 19.46% | 7.0276 | 0%
2035-01-05 | 2035 | 1 | Jan | 5 | 5 | 1 | 19.46% | 7.0276 | 0%
2035-01-06 | 2035 | 1 | Jan | 6 | 6 | 0 | 19.46% | 7.0276 | 0%
2035-01-07 | 2035 | 1 | Jan | 7 | 7 | 0 | 19.46% | 7.0276 | 0%
2035-01-08 | 2035 | 1 | Jan | 8 | 1 | 1 | 19.46% | 7.0276 | 0%
2035-01-09 | 2035 | 1 | Jan | 9 | 2 | 1 | 19.46% | 7.0276 | 0%
2035-01-10 | 2035 | 1 | Jan | 10 | 3 | 1 | 19.46% | 7.0276 | 0%
2035-01-11 | 2035 | 1 | Jan | 11 | 4 | 1 | 19.46% | 7.0276 | 0%
2035-01-12 | 2035 | 1 | Jan | 12 | 5 | 1 | 19.46% | 7.0276 | 0%
2035-01-13 | 2035 | 1 | Jan | 13 | 6 | 0 | 19.46% | 7.0276 | 0%
2035-01-14 | 2035 | 1 | Jan | 14 | 7 | 0 | 19.46% | 7.0276 | 0%
2035-01-15 | 2035 | 1 | Jan | 15 | 1 | 1 | 19.46% | 7.0276 | 0%
2035-01-16 | 2035 | 1 | Jan | 16 | 2 | 1 | 19.46% | 7.0276 | 0%
2035-01-17 | 2035 | 1 | Jan | 17 | 3 | 1 | 19.46% | 7.0276 | 0%
2035-01-18 | 2035 | 1 | Jan | 18 | 4 | 1 | 19.46% | 7.0276 | 0%
2035-01-19 | 2035 | 1 | Jan | 19 | 5 | 1 | 19.46% | 7.0276 | 0%
2035-01-20 | 2035 | 1 | Jan | 20 | 6 | 0 | 19.46% | 7.0276 | 0%
2035-01-21 | 2035 | 1 | Jan | 21 | 7 | 0 | 19.46% | 7.0276 | 0%
2035-01-22 | 2035 | 1 | Jan | 22 | 1 | 1 | 19.46% | 7.0276 | 0%
2035-01-23 | 2035 | 1 | Jan | 23 | 2 | 1 | 19.46% | 7.0276 | 0%
2035-01-24 | 2035 | 1 | Jan | 24 | 3 | 1 | 19.46% | 7.0276 | 0%
2035-01-25 | 2035 | 1 | Jan | 25 | 4 | 1 | 19.46% | 7.0276 | 0%
2035-01-26 | 2035 | 1 | Jan | 26 | 5 | 1 | 19.46% | 7.0276 | 0%
2035-01-27 | 2035 | 1 | Jan | 27 | 6 | 0 | 19.46% | 7.0276 | 0%
2035-01-28 | 2035 | 1 | Jan | 28 | 7 | 0 | 19.46% | 7.0276 | 0%
2035-01-29 | 2035 | 1 | Jan | 29 | 1 | 1 | 19.46% | 7.0276 | 0%
2035-01-30 | 2035 | 1 | Jan | 30 | 2 | 1 | 19.46% | 7.0276 | 0%
2035-01-31 | 2035 | 1 | Jan | 31 | 3 | 1 | 19.46% | 7.0276 | 0%
2035-02-01 | 2035 | 2 | Feb | 1 | 4 | 1 | 18.87% | 7.4625 | 0%
2035-02-02 | 2035 | 2 | Feb | 2 | 5 | 1 | 18.87% | 7.4625 | 0%
2035-02-03 | 2035 | 2 | Feb | 3 | 6 | 0 | 18.87% | 7.4625 | 0%
2035-02-04 | 2035 | 2 | Feb | 4 | 7 | 0 | 18.87% | 7.4625 | 0%
2035-02-05 | 2035 | 2 | Feb | 5 | 1 | 1 | 18.87% | 7.4625 | 0%
2035-02-06 | 2035 | 2 | Feb | 6 | 2 | 1 | 18.87% | 7.4625 | 0%
2035-02-07 | 2035 | 2 | Feb | 7 | 3 | 1 | 18.87% | 7.4625 | 0%
2035-02-08 | 2035 | 2 | Feb | 8 | 4 | 1 | 18.87% | 7.4625 | 0%
2035-02-09 | 2035 | 2 | Feb | 9 | 5 | 1 | 18.87% | 7.4625 | 0%
2035-02-10 | 2035 | 2 | Feb | 10 | 6 | 0 | 18.87% | 7.4625 | 0%
2035-02-11 | 2035 | 2 | Feb | 11 | 7 | 0 | 18.87% | 7.4625 | 0%
2035-02-12 | 2035 | 2 | Feb | 12 | 1 | 1 | 18.87% | 7.4625 | 0%
2035-02-13 | 2035 | 2 | Feb | 13 | 2 | 1 | 18.87% | 7.4625 | 0%
2035-02-14 | 2035 | 2 | Feb | 14 | 3 | 1 | 18.87% | 7.4625 | 0%
2035-02-15 | 2035 | 2 | Feb | 15 | 4 | 1 | 18.87% | 7.4625 | 0%
2035-02-16 | 2035 | 2 | Feb | 16 | 5 | 1 | 18.87% | 7.4625 | 0%
2035-02-17 | 2035 | 2 | Feb | 17 | 6 | 0 | 18.87% | 7.4625 | 0%
2035-02-18 | 2035 | 2 | Feb | 18 | 7 | 0 | 18.87% | 7.4625 | 0%
2035-02-19 | 2035 | 2 | Feb | 19 | 1 | 1 | 18.87% | 7.4625 | 0%
2035-02-20 | 2035 | 2 | Feb | 20 | 2 | 1 | 18.87% | 7.4625 | 0%
2035-02-21 | 2035 | 2 | Feb | 21 | 3 | 1 | 18.87% | 7.4625 | 0%
2035-02-22 | 2035 | 2 | Feb | 22 | 4 | 1 | 18.87% | 7.4625 | 0%
2035-02-23 | 2035 | 2 | Feb | 23 | 5 | 1 | 18.87% | 7.4625 | 0%
2035-02-24 | 2035 | 2 | Feb | 24 | 6 | 0 | 18.87% | 7.4625 | 0%
2035-02-25 | 2035 | 2 | Feb | 25 | 7 | 0 | 18.87% | 7.4625 | 0%
2035-02-26 | 2035 | 2 | Feb | 26 | 1 | 1 | 18.87% | 7.4625 | 0%
2035-02-27 | 2035 | 2 | Feb | 27 | 2 | 1 | 18.87% | 7.4625 | 0%
2035-02-28 | 2035 | 2 | Feb | 28 | 3 | 1 | 18.87% | 7.4625 | 0%
2035-03-01 | 2035 | 3 | Mar | 1 | 4 | 1 | 18.49% | 7.8663 | 0%
2035-03-02 | 2035 | 3 | Mar | 2 | 5 | 1 | 18.49% | 7.8663 | 0%
2035-03-03 | 2035 | 3 | Mar | 3 | 6 | 0 | 18.49% | 7.8663 | 0%
2035-03-04 | 2035 | 3 | Mar | 4 | 7 | 0 | 18.49% | 7.8663 | 0%
2035-03-05 | 2035 | 3 | Mar | 5 | 1 | 1 | 18.49% | 7.8663 | 0%
2035-03-06 | 2035 | 3 | Mar | 6 | 2 | 1 | 18.49% | 7.8663 | 0%
2035-03-07 | 2035 | 3 | Mar | 7 | 3 | 1 | 18.49% | 7.8663 | 0%
2035-03-08 | 2035 | 3 | Mar | 8 | 4 | 1 | 18.49% | 7.8663 | 0%
2035-03-09 | 2035 | 3 | Mar | 9 | 5 | 1 | 18.49% | 7.8663 | 0%
2035-03-10 | 2035 | 3 | Mar | 10 | 6 | 0 | 18.49% | 7.8663 | 0%
2035-03-11 | 2035 | 3 | Mar | 11 | 7 | 0 | 18.49% | 7.8663 | 0%
2035-03-12 | 2035 | 3 | Mar | 12 | 1 | 1 | 18.49% | 7.8663 | 0%
2035-03-13 | 2035 | 3 | Mar | 13 | 2 | 1 | 18.49% | 7.8663 | 0%
2035-03-14 | 2035 | 3 | Mar | 14 | 3 | 1 | 18.49% | 7.8663 | 0%
2035-03-15 | 2035 | 3 | Mar | 15 | 4 | 1 | 18.49% | 7.8663 | 0%
2035-03-16 | 2035 | 3 | Mar | 16 | 5 | 1 | 18.49% | 7.8663 | 0%
2035-03-17 | 2035 | 3 | Mar | 17 | 6 | 0 | 18.49% | 7.8663 | 0%
2035-03-18 | 2035 | 3 | Mar | 18 | 7 | 0 | 18.49% | 7.8663 | 0%
2035-03-19 | 2035 | 3 | Mar | 19 | 1 | 1 | 18.49% | 7.8663 | 0%
2035-03-20 | 2035 | 3 | Mar | 20 | 2 | 1 | 18.49% | 7.8663 | 0%
2035-03-21 | 2035 | 3 | Mar | 21 | 3 | 1 | 18.49% | 7.8663 | 0%
2035-03-22 | 2035 | 3 | Mar | 22 | 4 | 1 | 18.49% | 7.8663 | 0%
2035-03-23 | 2035 | 3 | Mar | 23 | 5 | 1 | 18.49% | 7.8663 | 0%
2035-03-24 | 2035 | 3 | Mar | 24 | 6 | 0 | 18.49% | 7.8663 | 0%
2035-03-25 | 2035 | 3 | Mar | 25 | 7 | 0 | 18.49% | 7.8663 | 0%
2035-03-26 | 2035 | 3 | Mar | 26 | 1 | 1 | 18.49% | 7.8663 | 0%
2035-03-27 | 2035 | 3 | Mar | 27 | 2 | 1 | 18.49% | 7.8663 | 0%
2035-03-28 | 2035 | 3 | Mar | 28 | 3 | 1 | 18.49% | 7.8663 | 0%
2035-03-29 | 2035 | 3 | Mar | 29 | 4 | 1 | 18.49% | 7.8663 | 0%
2035-03-30 | 2035 | 3 | Mar | 30 | 5 | 1 | 18.49% | 7.8663 | 0%
2035-03-31 | 2035 | 3 | Mar | 31 | 6 | 0 | 18.49% | 7.8663 | 0%
2035-04-01 | 2035 | 4 | Apr | 1 | 7 | 0 | 25.56% | 7.5 | 0%
2035-04-02 | 2035 | 4 | Apr | 2 | 1 | 1 | 25.56% | 7.5 | 0%
2035-04-03 | 2035 | 4 | Apr | 3 | 2 | 1 | 25.56% | 7.5 | 0%
2035-04-04 | 2035 | 4 | Apr | 4 | 3 | 1 | 25.56% | 7.5 | 0%
2035-04-05 | 2035 | 4 | Apr | 5 | 4 | 1 | 25.56% | 7.5 | 0%
2035-04-06 | 2035 | 4 | Apr | 6 | 5 | 1 | 25.56% | 7.5 | 0%
2035-04-07 | 2035 | 4 | Apr | 7 | 6 | 0 | 25.56% | 7.5 | 0%
2035-04-08 | 2035 | 4 | Apr | 8 | 7 | 0 | 25.56% | 7.5 | 0%
2035-04-09 | 2035 | 4 | Apr | 9 | 1 | 1 | 25.56% | 7.5 | 0%
2035-04-10 | 2035 | 4 | Apr | 10 | 2 | 1 | 25.56% | 7.5 | 0%
2035-04-11 | 2035 | 4 | Apr | 11 | 3 | 1 | 25.56% | 7.5 | 0%
2035-04-12 | 2035 | 4 | Apr | 12 | 4 | 1 | 25.56% | 7.5 | 0%
2035-04-13 | 2035 | 4 | Apr | 13 | 5 | 1 | 25.56% | 7.5 | 0%
2035-04-14 | 2035 | 4 | Apr | 14 | 6 | 0 | 25.56% | 7.5 | 0%
2035-04-15 | 2035 | 4 | Apr | 15 | 7 | 0 | 25.56% | 7.5 | 0%
2035-04-16 | 2035 | 4 | Apr | 16 | 1 | 1 | 25.56% | 7.5 | 0%
2035-04-17 | 2035 | 4 | Apr | 17 | 2 | 1 | 25.56% | 7.5 | 0%
2035-04-18 | 2035 | 4 | Apr | 18 | 3 | 1 | 25.56% | 7.5 | 0%
2035-04-19 | 2035 | 4 | Apr | 19 | 4 | 1 | 25.56% | 7.5 | 0%
2035-04-20 | 2035 | 4 | Apr | 20 | 5 | 1 | 25.56% | 7.5 | 0%
2035-04-21 | 2035 | 4 | Apr | 21 | 6 | 0 | 25.56% | 7.5 | 0%
2035-04-22 | 2035 | 4 | Apr | 22 | 7 | 0 | 25.56% | 7.5 | 0%
2035-04-23 | 2035 | 4 | Apr | 23 | 1 | 1 | 25.56% | 7.5 | 0%
2035-04-24 | 2035 | 4 | Apr | 24 | 2 | 1 | 25.56% | 7.5 | 0%
2035-04-25 | 2035 | 4 | Apr | 25 | 3 | 1 | 25.56% | 7.5 | 0%
2035-04-26 | 2035 | 4 | Apr | 26 | 4 | 1 | 25.56% | 7.5 | 0%
2035-04-27 | 2035 | 4 | Apr | 27 | 5 | 1 | 25.56% | 7.5 | 0%
2035-04-28 | 2035 | 4 | Apr | 28 | 6 | 0 | 25.56% | 7.5 | 0%
2035-04-29 | 2035 | 4 | Apr | 29 | 7 | 0 | 25.56% | 7.5 | 0%
2035-04-30 | 2035 | 4 | Apr | 30 | 1 | 1 | 25.56% | 7.5 | 0%
2035-05-01 | 2035 | 5 | May | 1 | 2 | 1 | 23.01% | 8.1449 | 0%
2035-05-02 | 2035 | 5 | May | 2 | 3 | 1 | 23.01% | 8.1449 | 0%
2035-05-03 | 2035 | 5 | May | 3 | 4 | 1 | 23.01% | 8.1449 | 0%
2035-05-04 | 2035 | 5 | May | 4 | 5 | 1 | 23.01% | 8.1449 | 0%
2035-05-05 | 2035 | 5 | May | 5 | 6 | 0 | 23.01% | 8.1449 | 0%
2035-05-06 | 2035 | 5 | May | 6 | 7 | 0 | 23.01% | 8.1449 | 0%
2035-05-07 | 2035 | 5 | May | 7 | 1 | 1 | 23.01% | 8.1449 | 0%
2035-05-08 | 2035 | 5 | May | 8 | 2 | 1 | 23.01% | 8.1449 | 0%
2035-05-09 | 2035 | 5 | May | 9 | 3 | 1 | 23.01% | 8.1449 | 0%
2035-05-10 | 2035 | 5 | May | 10 | 4 | 1 | 23.01% | 8.1449 | 0%
2035-05-11 | 2035 | 5 | May | 11 | 5 | 1 | 23.01% | 8.1449 | 0%
2035-05-12 | 2035 | 5 | May | 12 | 6 | 0 | 23.01% | 8.1449 | 0%
2035-05-13 | 2035 | 5 | May | 13 | 7 | 0 | 23.01% | 8.1449 | 0%
2035-05-14 | 2035 | 5 | May | 14 | 1 | 1 | 23.01% | 8.1449 | 0%
2035-05-15 | 2035 | 5 | May | 15 | 2 | 1 | 23.01% | 8.1449 | 0%
2035-05-16 | 2035 | 5 | May | 16 | 3 | 1 | 23.01% | 8.1449 | 0%
2035-05-17 | 2035 | 5 | May | 17 | 4 | 1 | 23.01% | 8.1449 | 0%
2035-05-18 | 2035 | 5 | May | 18 | 5 | 1 | 23.01% | 8.1449 | 0%
2035-05-19 | 2035 | 5 | May | 19 | 6 | 0 | 23.01% | 8.1449 | 0%
2035-05-20 | 2035 | 5 | May | 20 | 7 | 0 | 23.01% | 8.1449 | 0%
2035-05-21 | 2035 | 5 | May | 21 | 1 | 1 | 23.01% | 8.1449 | 0%
2035-05-22 | 2035 | 5 | May | 22 | 2 | 1 | 23.01% | 8.1449 | 0%
2035-05-23 | 2035 | 5 | May | 23 | 3 | 1 | 23.01% | 8.1449 | 0%
2035-05-24 | 2035 | 5 | May | 24 | 4 | 1 | 23.01% | 8.1449 | 0%
2035-05-25 | 2035 | 5 | May | 25 | 5 | 1 | 23.01% | 8.1449 | 0%
2035-05-26 | 2035 | 5 | May | 26 | 6 | 0 | 23.01% | 8.1449 | 0%
2035-05-27 | 2035 | 5 | May | 27 | 7 | 0 | 23.01% | 8.1449 | 0%
2035-05-28 | 2035 | 5 | May | 28 | 1 | 1 | 23.01% | 8.1449 | 0%
2035-05-29 | 2035 | 5 | May | 29 | 2 | 1 | 23.01% | 8.1449 | 0%
2035-05-30 | 2035 | 5 | May | 30 | 3 | 1 | 23.01% | 8.1449 | 0%
2035-05-31 | 2035 | 5 | May | 31 | 4 | 1 | 23.01% | 8.1449 | 0%
2035-06-01 | 2035 | 6 | Jun | 1 | 5 | 1 | 28.67% | 7.9419 | 0%
2035-06-02 | 2035 | 6 | Jun | 2 | 6 | 0 | 28.67% | 7.9419 | 0%
2035-06-03 | 2035 | 6 | Jun | 3 | 7 | 0 | 28.67% | 7.9419 | 0%
2035-06-04 | 2035 | 6 | Jun | 4 | 1 | 1 | 28.67% | 7.9419 | 0%
2035-06-05 | 2035 | 6 | Jun | 5 | 2 | 1 | 28.67% | 7.9419 | 0%
2035-06-06 | 2035 | 6 | Jun | 6 | 3 | 1 | 28.67% | 7.9419 | 0%
2035-06-07 | 2035 | 6 | Jun | 7 | 4 | 1 | 28.67% | 7.9419 | 0%
2035-06-08 | 2035 | 6 | Jun | 8 | 5 | 1 | 28.67% | 7.9419 | 0%
2035-06-09 | 2035 | 6 | Jun | 9 | 6 | 0 | 28.67% | 7.9419 | 0%
2035-06-10 | 2035 | 6 | Jun | 10 | 7 | 0 | 28.67% | 7.9419 | 0%
2035-06-11 | 2035 | 6 | Jun | 11 | 1 | 1 | 28.67% | 7.9419 | 0%
2035-06-12 | 2035 | 6 | Jun | 12 | 2 | 1 | 28.67% | 7.9419 | 0%
2035-06-13 | 2035 | 6 | Jun | 13 | 3 | 1 | 28.67% | 7.9419 | 0%
2035-06-14 | 2035 | 6 | Jun | 14 | 4 | 1 | 28.67% | 7.9419 | 0%
2035-06-15 | 2035 | 6 | Jun | 15 | 5 | 1 | 28.67% | 7.9419 | 0%
2035-06-16 | 2035 | 6 | Jun | 16 | 6 | 0 | 28.67% | 7.9419 | 0%
2035-06-17 | 2035 | 6 | Jun | 17 | 7 | 0 | 28.67% | 7.9419 | 0%
2035-06-18 | 2035 | 6 | Jun | 18 | 1 | 1 | 28.67% | 7.9419 | 0%
2035-06-19 | 2035 | 6 | Jun | 19 | 2 | 1 | 28.67% | 7.9419 | 0%
2035-06-20 | 2035 | 6 | Jun | 20 | 3 | 1 | 28.67% | 7.9419 | 0%
2035-06-21 | 2035 | 6 | Jun | 21 | 4 | 1 | 28.67% | 7.9419 | 0%
2035-06-22 | 2035 | 6 | Jun | 22 | 5 | 1 | 28.67% | 7.9419 | 0%
2035-06-23 | 2035 | 6 | Jun | 23 | 6 | 0 | 28.67% | 7.9419 | 0%
2035-06-24 | 2035 | 6 | Jun | 24 | 7 | 0 | 28.67% | 7.9419 | 0%
2035-06-25 | 2035 | 6 | Jun | 25 | 1 | 1 | 28.67% | 7.9419 | 0%
2035-06-26 | 2035 | 6 | Jun | 26 | 2 | 1 | 28.67% | 7.9419 | 0%
2035-06-27 | 2035 | 6 | Jun | 27 | 3 | 1 | 28.67% | 7.9419 | 0%
2035-06-28 | 2035 | 6 | Jun | 28 | 4 | 1 | 28.67% | 7.9419 | 0%
2035-06-29 | 2035 | 6 | Jun | 29 | 5 | 1 | 28.67% | 7.9419 | 0%
2035-06-30 | 2035 | 6 | Jun | 30 | 6 | 0 | 28.67% | 7.9419 | 0%
2035-07-01 | 2035 | 7 | Jul | 1 | 7 | 0 | 24.73% | 8.3739 | 0%
2035-07-02 | 2035 | 7 | Jul | 2 | 1 | 1 | 24.73% | 8.3739 | 0%
2035-07-03 | 2035 | 7 | Jul | 3 | 2 | 1 | 24.73% | 8.3739 | 0%
2035-07-04 | 2035 | 7 | Jul | 4 | 3 | 1 | 24.73% | 8.3739 | 0%
2035-07-05 | 2035 | 7 | Jul | 5 | 4 | 1 | 24.73% | 8.3739 | 0%
2035-07-06 | 2035 | 7 | Jul | 6 | 5 | 1 | 24.73% | 8.3739 | 0%
2035-07-07 | 2035 | 7 | Jul | 7 | 6 | 0 | 24.73% | 8.3739 | 0%
2035-07-08 | 2035 | 7 | Jul | 8 | 7 | 0 | 24.73% | 8.3739 | 0%
2035-07-09 | 2035 | 7 | Jul | 9 | 1 | 1 | 24.73% | 8.3739 | 0%
2035-07-10 | 2035 | 7 | Jul | 10 | 2 | 1 | 24.73% | 8.3739 | 0%
2035-07-11 | 2035 | 7 | Jul | 11 | 3 | 1 | 24.73% | 8.3739 | 0%
2035-07-12 | 2035 | 7 | Jul | 12 | 4 | 1 | 24.73% | 8.3739 | 0%
2035-07-13 | 2035 | 7 | Jul | 13 | 5 | 1 | 24.73% | 8.3739 | 0%
2035-07-14 | 2035 | 7 | Jul | 14 | 6 | 0 | 24.73% | 8.3739 | 0%
2035-07-15 | 2035 | 7 | Jul | 15 | 7 | 0 | 24.73% | 8.3739 | 0%
2035-07-16 | 2035 | 7 | Jul | 16 | 1 | 1 | 24.73% | 8.3739 | 0%
2035-07-17 | 2035 | 7 | Jul | 17 | 2 | 1 | 24.73% | 8.3739 | 0%
2035-07-18 | 2035 | 7 | Jul | 18 | 3 | 1 | 24.73% | 8.3739 | 0%
2035-07-19 | 2035 | 7 | Jul | 19 | 4 | 1 | 24.73% | 8.3739 | 0%
2035-07-20 | 2035 | 7 | Jul | 20 | 5 | 1 | 24.73% | 8.3739 | 0%
2035-07-21 | 2035 | 7 | Jul | 21 | 6 | 0 | 24.73% | 8.3739 | 0%
2035-07-22 | 2035 | 7 | Jul | 22 | 7 | 0 | 24.73% | 8.3739 | 0%
2035-07-23 | 2035 | 7 | Jul | 23 | 1 | 1 | 24.73% | 8.3739 | 0%
2035-07-24 | 2035 | 7 | Jul | 24 | 2 | 1 | 24.73% | 8.3739 | 0%
2035-07-25 | 2035 | 7 | Jul | 25 | 3 | 1 | 24.73% | 8.3739 | 0%
2035-07-26 | 2035 | 7 | Jul | 26 | 4 | 1 | 24.73% | 8.3739 | 0%
2035-07-27 | 2035 | 7 | Jul | 27 | 5 | 1 | 24.73% | 8.3739 | 0%
2035-07-28 | 2035 | 7 | Jul | 28 | 6 | 0 | 24.73% | 8.3739 | 0%
2035-07-29 | 2035 | 7 | Jul | 29 | 7 | 0 | 24.73% | 8.3739 | 0%
2035-07-30 | 2035 | 7 | Jul | 30 | 1 | 1 | 24.73% | 8.3739 | 0%
2035-07-31 | 2035 | 7 | Jul | 31 | 2 | 1 | 24.73% | 8.3739 | 0%
2035-08-01 | 2035 | 8 | Aug | 1 | 3 | 1 | 23.55% | 7.9589 | 0%
2035-08-02 | 2035 | 8 | Aug | 2 | 4 | 1 | 23.55% | 7.9589 | 0%
2035-08-03 | 2035 | 8 | Aug | 3 | 5 | 1 | 23.55% | 7.9589 | 0%
2035-08-04 | 2035 | 8 | Aug | 4 | 6 | 0 | 23.55% | 7.9589 | 0%
2035-08-05 | 2035 | 8 | Aug | 5 | 7 | 0 | 23.55% | 7.9589 | 0%
2035-08-06 | 2035 | 8 | Aug | 6 | 1 | 1 | 23.55% | 7.9589 | 0%
2035-08-07 | 2035 | 8 | Aug | 7 | 2 | 1 | 23.55% | 7.9589 | 0%
2035-08-08 | 2035 | 8 | Aug | 8 | 3 | 1 | 23.55% | 7.9589 | 0%
2035-08-09 | 2035 | 8 | Aug | 9 | 4 | 1 | 23.55% | 7.9589 | 0%
2035-08-10 | 2035 | 8 | Aug | 10 | 5 | 1 | 23.55% | 7.9589 | 0%
2035-08-11 | 2035 | 8 | Aug | 11 | 6 | 0 | 23.55% | 7.9589 | 0%
2035-08-12 | 2035 | 8 | Aug | 12 | 7 | 0 | 23.55% | 7.9589 | 0%
2035-08-13 | 2035 | 8 | Aug | 13 | 1 | 1 | 23.55% | 7.9589 | 0%
2035-08-14 | 2035 | 8 | Aug | 14 | 2 | 1 | 23.55% | 7.9589 | 0%
2035-08-15 | 2035 | 8 | Aug | 15 | 3 | 1 | 23.55% | 7.9589 | 0%
2035-08-16 | 2035 | 8 | Aug | 16 | 4 | 1 | 23.55% | 7.9589 | 0%
2035-08-17 | 2035 | 8 | Aug | 17 | 5 | 1 | 23.55% | 7.9589 | 0%
2035-08-18 | 2035 | 8 | Aug | 18 | 6 | 0 | 23.55% | 7.9589 | 0%
2035-08-19 | 2035 | 8 | Aug | 19 | 7 | 0 | 23.55% | 7.9589 | 0%
2035-08-20 | 2035 | 8 | Aug | 20 | 1 | 1 | 23.55% | 7.9589 | 0%
2035-08-21 | 2035 | 8 | Aug | 21 | 2 | 1 | 23.55% | 7.9589 | 0%
2035-08-22 | 2035 | 8 | Aug | 22 | 3 | 1 | 23.55% | 7.9589 | 0%
2035-08-23 | 2035 | 8 | Aug | 23 | 4 | 1 | 23.55% | 7.9589 | 0%
2035-08-24 | 2035 | 8 | Aug | 24 | 5 | 1 | 23.55% | 7.9589 | 0%
2035-08-25 | 2035 | 8 | Aug | 25 | 6 | 0 | 23.55% | 7.9589 | 0%
2035-08-26 | 2035 | 8 | Aug | 26 | 7 | 0 | 23.55% | 7.9589 | 0%
2035-08-27 | 2035 | 8 | Aug | 27 | 1 | 1 | 23.55% | 7.9589 | 0%
2035-08-28 | 2035 | 8 | Aug | 28 | 2 | 1 | 23.55% | 7.9589 | 0%
2035-08-29 | 2035 | 8 | Aug | 29 | 3 | 1 | 23.55% | 7.9589 | 0%
2035-08-30 | 2035 | 8 | Aug | 30 | 4 | 1 | 23.55% | 7.9589 | 0%
2035-08-31 | 2035 | 8 | Aug | 31 | 5 | 1 | 23.55% | 7.9589 | 0%
2035-09-01 | 2035 | 9 | Sep | 1 | 6 | 0 | 20.67% | 6.8065 | 0%
2035-09-02 | 2035 | 9 | Sep | 2 | 7 | 0 | 20.67% | 6.8065 | 0%
2035-09-03 | 2035 | 9 | Sep | 3 | 1 | 1 | 20.67% | 6.8065 | 0%
2035-09-04 | 2035 | 9 | Sep | 4 | 2 | 1 | 20.67% | 6.8065 | 0%
2035-09-05 | 2035 | 9 | Sep | 5 | 3 | 1 | 20.67% | 6.8065 | 0%
2035-09-06 | 2035 | 9 | Sep | 6 | 4 | 1 | 20.67% | 6.8065 | 0%
2035-09-07 | 2035 | 9 | Sep | 7 | 5 | 1 | 20.67% | 6.8065 | 0%
2035-09-08 | 2035 | 9 | Sep | 8 | 6 | 0 | 20.67% | 6.8065 | 0%
2035-09-09 | 2035 | 9 | Sep | 9 | 7 | 0 | 20.67% | 6.8065 | 0%
2035-09-10 | 2035 | 9 | Sep | 10 | 1 | 1 | 20.67% | 6.8065 | 0%
2035-09-11 | 2035 | 9 | Sep | 11 | 2 | 1 | 20.67% | 6.8065 | 0%
2035-09-12 | 2035 | 9 | Sep | 12 | 3 | 1 | 20.67% | 6.8065 | 0%
2035-09-13 | 2035 | 9 | Sep | 13 | 4 | 1 | 20.67% | 6.8065 | 0%
2035-09-14 | 2035 | 9 | Sep | 14 | 5 | 1 | 20.67% | 6.8065 | 0%
2035-09-15 | 2035 | 9 | Sep | 15 | 6 | 0 | 20.67% | 6.8065 | 0%
2035-09-16 | 2035 | 9 | Sep | 16 | 7 | 0 | 20.67% | 6.8065 | 0%
2035-09-17 | 2035 | 9 | Sep | 17 | 1 | 1 | 20.67% | 6.8065 | 0%
2035-09-18 | 2035 | 9 | Sep | 18 | 2 | 1 | 20.67% | 6.8065 | 0%
2035-09-19 | 2035 | 9 | Sep | 19 | 3 | 1 | 20.67% | 6.8065 | 0%
2035-09-20 | 2035 | 9 | Sep | 20 | 4 | 1 | 20.67% | 6.8065 | 0%
2035-09-21 | 2035 | 9 | Sep | 21 | 5 | 1 | 20.67% | 6.8065 | 0%
2035-09-22 | 2035 | 9 | Sep | 22 | 6 | 0 | 20.67% | 6.8065 | 0%
2035-09-23 | 2035 | 9 | Sep | 23 | 7 | 0 | 20.67% | 6.8065 | 0%
2035-09-24 | 2035 | 9 | Sep | 24 | 1 | 1 | 20.67% | 6.8065 | 0%
2035-09-25 | 2035 | 9 | Sep | 25 | 2 | 1 | 20.67% | 6.8065 | 0%
2035-09-26 | 2035 | 9 | Sep | 26 | 3 | 1 | 20.67% | 6.8065 | 0%
2035-09-27 | 2035 | 9 | Sep | 27 | 4 | 1 | 20.67% | 6.8065 | 0%
2035-09-28 | 2035 | 9 | Sep | 28 | 5 | 1 | 20.67% | 6.8065 | 0%
2035-09-29 | 2035 | 9 | Sep | 29 | 6 | 0 | 20.67% | 6.8065 | 0%
2035-09-30 | 2035 | 9 | Sep | 30 | 7 | 0 | 20.67% | 6.8065 | 0%
2035-10-01 | 2035 | 10 | Oct | 1 | 1 | 1 | 23.23% | 6.8194 | 0%
2035-10-02 | 2035 | 10 | Oct | 2 | 2 | 1 | 23.23% | 6.8194 | 0%
2035-10-03 | 2035 | 10 | Oct | 3 | 3 | 1 | 23.23% | 6.8194 | 0%
2035-10-04 | 2035 | 10 | Oct | 4 | 4 | 1 | 23.23% | 6.8194 | 0%
2035-10-05 | 2035 | 10 | Oct | 5 | 5 | 1 | 23.23% | 6.8194 | 0%
2035-10-06 | 2035 | 10 | Oct | 6 | 6 | 0 | 23.23% | 6.8194 | 0%
2035-10-07 | 2035 | 10 | Oct | 7 | 7 | 0 | 23.23% | 6.8194 | 0%
2035-10-08 | 2035 | 10 | Oct | 8 | 1 | 1 | 23.23% | 6.8194 | 0%
2035-10-09 | 2035 | 10 | Oct | 9 | 2 | 1 | 23.23% | 6.8194 | 0%
2035-10-10 | 2035 | 10 | Oct | 10 | 3 | 1 | 23.23% | 6.8194 | 0%
2035-10-11 | 2035 | 10 | Oct | 11 | 4 | 1 | 23.23% | 6.8194 | 0%
2035-10-12 | 2035 | 10 | Oct | 12 | 5 | 1 | 23.23% | 6.8194 | 0%
2035-10-13 | 2035 | 10 | Oct | 13 | 6 | 0 | 23.23% | 6.8194 | 0%
2035-10-14 | 2035 | 10 | Oct | 14 | 7 | 0 | 23.23% | 6.8194 | 0%
2035-10-15 | 2035 | 10 | Oct | 15 | 1 | 1 | 23.23% | 6.8194 | 0%
2035-10-16 | 2035 | 10 | Oct | 16 | 2 | 1 | 23.23% | 6.8194 | 0%
2035-10-17 | 2035 | 10 | Oct | 17 | 3 | 1 | 23.23% | 6.8194 | 0%
2035-10-18 | 2035 | 10 | Oct | 18 | 4 | 1 | 23.23% | 6.8194 | 0%
2035-10-19 | 2035 | 10 | Oct | 19 | 5 | 1 | 23.23% | 6.8194 | 0%
2035-10-20 | 2035 | 10 | Oct | 20 | 6 | 0 | 23.23% | 6.8194 | 0%
2035-10-21 | 2035 | 10 | Oct | 21 | 7 | 0 | 23.23% | 6.8194 | 0%
2035-10-22 | 2035 | 10 | Oct | 22 | 1 | 1 | 23.23% | 6.8194 | 0%
2035-10-23 | 2035 | 10 | Oct | 23 | 2 | 1 | 23.23% | 6.8194 | 0%
2035-10-24 | 2035 | 10 | Oct | 24 | 3 | 1 | 23.23% | 6.8194 | 0%
2035-10-25 | 2035 | 10 | Oct | 25 | 4 | 1 | 23.23% | 6.8194 | 0%
2035-10-26 | 2035 | 10 | Oct | 26 | 5 | 1 | 23.23% | 6.8194 | 0%
2035-10-27 | 2035 | 10 | Oct | 27 | 6 | 0 | 23.23% | 6.8194 | 0%
2035-10-28 | 2035 | 10 | Oct | 28 | 7 | 0 | 23.23% | 6.8194 | 0%
2035-10-29 | 2035 | 10 | Oct | 29 | 1 | 1 | 23.23% | 6.8194 | 0%
2035-10-30 | 2035 | 10 | Oct | 30 | 2 | 1 | 23.23% | 6.8194 | 0%
2035-10-31 | 2035 | 10 | Oct | 31 | 3 | 1 | 23.23% | 6.8194 | 0%
2035-11-01 | 2035 | 11 | Nov | 1 | 4 | 1 | 23.33% | 6.4429 | 0%
2035-11-02 | 2035 | 11 | Nov | 2 | 5 | 1 | 23.33% | 6.4429 | 0%
2035-11-03 | 2035 | 11 | Nov | 3 | 6 | 0 | 23.33% | 6.4429 | 0%
2035-11-04 | 2035 | 11 | Nov | 4 | 7 | 0 | 23.33% | 6.4429 | 0%
2035-11-05 | 2035 | 11 | Nov | 5 | 1 | 1 | 23.33% | 6.4429 | 0%
2035-11-06 | 2035 | 11 | Nov | 6 | 2 | 1 | 23.33% | 6.4429 | 0%
2035-11-07 | 2035 | 11 | Nov | 7 | 3 | 1 | 23.33% | 6.4429 | 0%
2035-11-08 | 2035 | 11 | Nov | 8 | 4 | 1 | 23.33% | 6.4429 | 0%
2035-11-09 | 2035 | 11 | Nov | 9 | 5 | 1 | 23.33% | 6.4429 | 0%
2035-11-10 | 2035 | 11 | Nov | 10 | 6 | 0 | 23.33% | 6.4429 | 0%
2035-11-11 | 2035 | 11 | Nov | 11 | 7 | 0 | 23.33% | 6.4429 | 0%
2035-11-12 | 2035 | 11 | Nov | 12 | 1 | 1 | 23.33% | 6.4429 | 0%
2035-11-13 | 2035 | 11 | Nov | 13 | 2 | 1 | 23.33% | 6.4429 | 0%
2035-11-14 | 2035 | 11 | Nov | 14 | 3 | 1 | 23.33% | 6.4429 | 0%
2035-11-15 | 2035 | 11 | Nov | 15 | 4 | 1 | 23.33% | 6.4429 | 0%
2035-11-16 | 2035 | 11 | Nov | 16 | 5 | 1 | 23.33% | 6.4429 | 0%
2035-11-17 | 2035 | 11 | Nov | 17 | 6 | 0 | 23.33% | 6.4429 | 0%
2035-11-18 | 2035 | 11 | Nov | 18 | 7 | 0 | 23.33% | 6.4429 | 0%
2035-11-19 | 2035 | 11 | Nov | 19 | 1 | 1 | 23.33% | 6.4429 | 0%
2035-11-20 | 2035 | 11 | Nov | 20 | 2 | 1 | 23.33% | 6.4429 | 0%
2035-11-21 | 2035 | 11 | Nov | 21 | 3 | 1 | 23.33% | 6.4429 | 0%
2035-11-22 | 2035 | 11 | Nov | 22 | 4 | 1 | 23.33% | 6.4429 | 0%
2035-11-23 | 2035 | 11 | Nov | 23 | 5 | 1 | 23.33% | 6.4429 | 0%
2035-11-24 | 2035 | 11 | Nov | 24 | 6 | 0 | 23.33% | 6.4429 | 0%
2035-11-25 | 2035 | 11 | Nov | 25 | 7 | 0 | 23.33% | 6.4429 | 0%
2035-11-26 | 2035 | 11 | Nov | 26 | 1 | 1 | 23.33% | 6.4429 | 0%
2035-11-27 | 2035 | 11 | Nov | 27 | 2 | 1 | 23.33% | 6.4429 | 0%
2035-11-28 | 2035 | 11 | Nov | 28 | 3 | 1 | 23.33% | 6.4429 | 0%
2035-11-29 | 2035 | 11 | Nov | 29 | 4 | 1 | 23.33% | 6.4429 | 0%
2035-11-30 | 2035 | 11 | Nov | 30 | 5 | 1 | 23.33% | 6.4429 | 0%
2035-12-01 | 2035 | 12 | Dec | 1 | 6 | 0 | 22.69% | 6.7962 | 0%
2035-12-02 | 2035 | 12 | Dec | 2 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-12-03 | 2035 | 12 | Dec | 3 | 1 | 1 | 22.69% | 6.7962 | 0%
2035-12-04 | 2035 | 12 | Dec | 4 | 2 | 1 | 22.69% | 6.7962 | 0%
2035-12-05 | 2035 | 12 | Dec | 5 | 3 | 1 | 22.69% | 6.7962 | 0%
2035-12-06 | 2035 | 12 | Dec | 6 | 4 | 1 | 22.69% | 6.7962 | 0%
2035-12-07 | 2035 | 12 | Dec | 7 | 5 | 1 | 22.69% | 6.7962 | 0%
2035-12-08 | 2035 | 12 | Dec | 8 | 6 | 0 | 22.69% | 6.7962 | 0%
2035-12-09 | 2035 | 12 | Dec | 9 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-12-10 | 2035 | 12 | Dec | 10 | 1 | 1 | 22.69% | 6.7962 | 0%
2035-12-11 | 2035 | 12 | Dec | 11 | 2 | 1 | 22.69% | 6.7962 | 0%
2035-12-12 | 2035 | 12 | Dec | 12 | 3 | 1 | 22.69% | 6.7962 | 0%
2035-12-13 | 2035 | 12 | Dec | 13 | 4 | 1 | 22.69% | 6.7962 | 0%
2035-12-14 | 2035 | 12 | Dec | 14 | 5 | 1 | 22.69% | 6.7962 | 0%
2035-12-15 | 2035 | 12 | Dec | 15 | 6 | 0 | 22.69% | 6.7962 | 0%
2035-12-16 | 2035 | 12 | Dec | 16 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-12-17 | 2035 | 12 | Dec | 17 | 1 | 1 | 22.69% | 6.7962 | 0%
2035-12-18 | 2035 | 12 | Dec | 18 | 2 | 1 | 22.69% | 6.7962 | 0%
2035-12-19 | 2035 | 12 | Dec | 19 | 3 | 1 | 22.69% | 6.7962 | 0%
2035-12-20 | 2035 | 12 | Dec | 20 | 4 | 1 | 22.69% | 6.7962 | 0%
2035-12-21 | 2035 | 12 | Dec | 21 | 5 | 1 | 22.69% | 6.7962 | 0%
2035-12-22 | 2035 | 12 | Dec | 22 | 6 | 0 | 22.69% | 6.7962 | 0%
2035-12-23 | 2035 | 12 | Dec | 23 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-12-24 | 2035 | 12 | Dec | 24 | 1 | 1 | 22.69% | 6.7962 | 0%
2035-12-25 | 2035 | 12 | Dec | 25 | 2 | 1 | 22.69% | 6.7962 | 0%
2035-12-26 | 2035 | 12 | Dec | 26 | 3 | 1 | 22.69% | 6.7962 | 0%
2035-12-27 | 2035 | 12 | Dec | 27 | 4 | 1 | 22.69% | 6.7962 | 0%
2035-12-28 | 2035 | 12 | Dec | 28 | 5 | 1 | 22.69% | 6.7962 | 0%
2035-12-29 | 2035 | 12 | Dec | 29 | 6 | 0 | 22.69% | 6.7962 | 0%
2035-12-30 | 2035 | 12 | Dec | 30 | 7 | 0 | 22.69% | 6.7962 | 0%
2035-12-31 | 2035 | 12 | Dec | 31 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-01-01 | 2036 | 1 | Jan | 1 | 2 | 1 | 19.46% | 7.0276 | 0%
2036-01-02 | 2036 | 1 | Jan | 2 | 3 | 1 | 19.46% | 7.0276 | 0%
2036-01-03 | 2036 | 1 | Jan | 3 | 4 | 1 | 19.46% | 7.0276 | 0%
2036-01-04 | 2036 | 1 | Jan | 4 | 5 | 1 | 19.46% | 7.0276 | 0%
2036-01-05 | 2036 | 1 | Jan | 5 | 6 | 0 | 19.46% | 7.0276 | 0%
2036-01-06 | 2036 | 1 | Jan | 6 | 7 | 0 | 19.46% | 7.0276 | 0%
2036-01-07 | 2036 | 1 | Jan | 7 | 1 | 1 | 19.46% | 7.0276 | 0%
2036-01-08 | 2036 | 1 | Jan | 8 | 2 | 1 | 19.46% | 7.0276 | 0%
2036-01-09 | 2036 | 1 | Jan | 9 | 3 | 1 | 19.46% | 7.0276 | 0%
2036-01-10 | 2036 | 1 | Jan | 10 | 4 | 1 | 19.46% | 7.0276 | 0%
2036-01-11 | 2036 | 1 | Jan | 11 | 5 | 1 | 19.46% | 7.0276 | 0%
2036-01-12 | 2036 | 1 | Jan | 12 | 6 | 0 | 19.46% | 7.0276 | 0%
2036-01-13 | 2036 | 1 | Jan | 13 | 7 | 0 | 19.46% | 7.0276 | 0%
2036-01-14 | 2036 | 1 | Jan | 14 | 1 | 1 | 19.46% | 7.0276 | 0%
2036-01-15 | 2036 | 1 | Jan | 15 | 2 | 1 | 19.46% | 7.0276 | 0%
2036-01-16 | 2036 | 1 | Jan | 16 | 3 | 1 | 19.46% | 7.0276 | 0%
2036-01-17 | 2036 | 1 | Jan | 17 | 4 | 1 | 19.46% | 7.0276 | 0%
2036-01-18 | 2036 | 1 | Jan | 18 | 5 | 1 | 19.46% | 7.0276 | 0%
2036-01-19 | 2036 | 1 | Jan | 19 | 6 | 0 | 19.46% | 7.0276 | 0%
2036-01-20 | 2036 | 1 | Jan | 20 | 7 | 0 | 19.46% | 7.0276 | 0%
2036-01-21 | 2036 | 1 | Jan | 21 | 1 | 1 | 19.46% | 7.0276 | 0%
2036-01-22 | 2036 | 1 | Jan | 22 | 2 | 1 | 19.46% | 7.0276 | 0%
2036-01-23 | 2036 | 1 | Jan | 23 | 3 | 1 | 19.46% | 7.0276 | 0%
2036-01-24 | 2036 | 1 | Jan | 24 | 4 | 1 | 19.46% | 7.0276 | 0%
2036-01-25 | 2036 | 1 | Jan | 25 | 5 | 1 | 19.46% | 7.0276 | 0%
2036-01-26 | 2036 | 1 | Jan | 26 | 6 | 0 | 19.46% | 7.0276 | 0%
2036-01-27 | 2036 | 1 | Jan | 27 | 7 | 0 | 19.46% | 7.0276 | 0%
2036-01-28 | 2036 | 1 | Jan | 28 | 1 | 1 | 19.46% | 7.0276 | 0%
2036-01-29 | 2036 | 1 | Jan | 29 | 2 | 1 | 19.46% | 7.0276 | 0%
2036-01-30 | 2036 | 1 | Jan | 30 | 3 | 1 | 19.46% | 7.0276 | 0%
2036-01-31 | 2036 | 1 | Jan | 31 | 4 | 1 | 19.46% | 7.0276 | 0%
2036-02-01 | 2036 | 2 | Feb | 1 | 5 | 1 | 18.87% | 7.4625 | 0%
2036-02-02 | 2036 | 2 | Feb | 2 | 6 | 0 | 18.87% | 7.4625 | 0%
2036-02-03 | 2036 | 2 | Feb | 3 | 7 | 0 | 18.87% | 7.4625 | 0%
2036-02-04 | 2036 | 2 | Feb | 4 | 1 | 1 | 18.87% | 7.4625 | 0%
2036-02-05 | 2036 | 2 | Feb | 5 | 2 | 1 | 18.87% | 7.4625 | 0%
2036-02-06 | 2036 | 2 | Feb | 6 | 3 | 1 | 18.87% | 7.4625 | 0%
2036-02-07 | 2036 | 2 | Feb | 7 | 4 | 1 | 18.87% | 7.4625 | 0%
2036-02-08 | 2036 | 2 | Feb | 8 | 5 | 1 | 18.87% | 7.4625 | 0%
2036-02-09 | 2036 | 2 | Feb | 9 | 6 | 0 | 18.87% | 7.4625 | 0%
2036-02-10 | 2036 | 2 | Feb | 10 | 7 | 0 | 18.87% | 7.4625 | 0%
2036-02-11 | 2036 | 2 | Feb | 11 | 1 | 1 | 18.87% | 7.4625 | 0%
2036-02-12 | 2036 | 2 | Feb | 12 | 2 | 1 | 18.87% | 7.4625 | 0%
2036-02-13 | 2036 | 2 | Feb | 13 | 3 | 1 | 18.87% | 7.4625 | 0%
2036-02-14 | 2036 | 2 | Feb | 14 | 4 | 1 | 18.87% | 7.4625 | 0%
2036-02-15 | 2036 | 2 | Feb | 15 | 5 | 1 | 18.87% | 7.4625 | 0%
2036-02-16 | 2036 | 2 | Feb | 16 | 6 | 0 | 18.87% | 7.4625 | 0%
2036-02-17 | 2036 | 2 | Feb | 17 | 7 | 0 | 18.87% | 7.4625 | 0%
2036-02-18 | 2036 | 2 | Feb | 18 | 1 | 1 | 18.87% | 7.4625 | 0%
2036-02-19 | 2036 | 2 | Feb | 19 | 2 | 1 | 18.87% | 7.4625 | 0%
2036-02-20 | 2036 | 2 | Feb | 20 | 3 | 1 | 18.87% | 7.4625 | 0%
2036-02-21 | 2036 | 2 | Feb | 21 | 4 | 1 | 18.87% | 7.4625 | 0%
2036-02-22 | 2036 | 2 | Feb | 22 | 5 | 1 | 18.87% | 7.4625 | 0%
2036-02-23 | 2036 | 2 | Feb | 23 | 6 | 0 | 18.87% | 7.4625 | 0%
2036-02-24 | 2036 | 2 | Feb | 24 | 7 | 0 | 18.87% | 7.4625 | 0%
2036-02-25 | 2036 | 2 | Feb | 25 | 1 | 1 | 18.87% | 7.4625 | 0%
2036-02-26 | 2036 | 2 | Feb | 26 | 2 | 1 | 18.87% | 7.4625 | 0%
2036-02-27 | 2036 | 2 | Feb | 27 | 3 | 1 | 18.87% | 7.4625 | 0%
2036-02-28 | 2036 | 2 | Feb | 28 | 4 | 1 | 18.87% | 7.4625 | 0%
2036-02-29 | 2036 | 2 | Feb | 29 | 5 | 1 | 18.87% | 7.4625 | 0%
2036-03-01 | 2036 | 3 | Mar | 1 | 6 | 0 | 18.49% | 7.8663 | 0%
2036-03-02 | 2036 | 3 | Mar | 2 | 7 | 0 | 18.49% | 7.8663 | 0%
2036-03-03 | 2036 | 3 | Mar | 3 | 1 | 1 | 18.49% | 7.8663 | 0%
2036-03-04 | 2036 | 3 | Mar | 4 | 2 | 1 | 18.49% | 7.8663 | 0%
2036-03-05 | 2036 | 3 | Mar | 5 | 3 | 1 | 18.49% | 7.8663 | 0%
2036-03-06 | 2036 | 3 | Mar | 6 | 4 | 1 | 18.49% | 7.8663 | 0%
2036-03-07 | 2036 | 3 | Mar | 7 | 5 | 1 | 18.49% | 7.8663 | 0%
2036-03-08 | 2036 | 3 | Mar | 8 | 6 | 0 | 18.49% | 7.8663 | 0%
2036-03-09 | 2036 | 3 | Mar | 9 | 7 | 0 | 18.49% | 7.8663 | 0%
2036-03-10 | 2036 | 3 | Mar | 10 | 1 | 1 | 18.49% | 7.8663 | 0%
2036-03-11 | 2036 | 3 | Mar | 11 | 2 | 1 | 18.49% | 7.8663 | 0%
2036-03-12 | 2036 | 3 | Mar | 12 | 3 | 1 | 18.49% | 7.8663 | 0%
2036-03-13 | 2036 | 3 | Mar | 13 | 4 | 1 | 18.49% | 7.8663 | 0%
2036-03-14 | 2036 | 3 | Mar | 14 | 5 | 1 | 18.49% | 7.8663 | 0%
2036-03-15 | 2036 | 3 | Mar | 15 | 6 | 0 | 18.49% | 7.8663 | 0%
2036-03-16 | 2036 | 3 | Mar | 16 | 7 | 0 | 18.49% | 7.8663 | 0%
2036-03-17 | 2036 | 3 | Mar | 17 | 1 | 1 | 18.49% | 7.8663 | 0%
2036-03-18 | 2036 | 3 | Mar | 18 | 2 | 1 | 18.49% | 7.8663 | 0%
2036-03-19 | 2036 | 3 | Mar | 19 | 3 | 1 | 18.49% | 7.8663 | 0%
2036-03-20 | 2036 | 3 | Mar | 20 | 4 | 1 | 18.49% | 7.8663 | 0%
2036-03-21 | 2036 | 3 | Mar | 21 | 5 | 1 | 18.49% | 7.8663 | 0%
2036-03-22 | 2036 | 3 | Mar | 22 | 6 | 0 | 18.49% | 7.8663 | 0%
2036-03-23 | 2036 | 3 | Mar | 23 | 7 | 0 | 18.49% | 7.8663 | 0%
2036-03-24 | 2036 | 3 | Mar | 24 | 1 | 1 | 18.49% | 7.8663 | 0%
2036-03-25 | 2036 | 3 | Mar | 25 | 2 | 1 | 18.49% | 7.8663 | 0%
2036-03-26 | 2036 | 3 | Mar | 26 | 3 | 1 | 18.49% | 7.8663 | 0%
2036-03-27 | 2036 | 3 | Mar | 27 | 4 | 1 | 18.49% | 7.8663 | 0%
2036-03-28 | 2036 | 3 | Mar | 28 | 5 | 1 | 18.49% | 7.8663 | 0%
2036-03-29 | 2036 | 3 | Mar | 29 | 6 | 0 | 18.49% | 7.8663 | 0%
2036-03-30 | 2036 | 3 | Mar | 30 | 7 | 0 | 18.49% | 7.8663 | 0%
2036-03-31 | 2036 | 3 | Mar | 31 | 1 | 1 | 18.49% | 7.8663 | 0%
2036-04-01 | 2036 | 4 | Apr | 1 | 2 | 1 | 25.56% | 7.5 | 0%
2036-04-02 | 2036 | 4 | Apr | 2 | 3 | 1 | 25.56% | 7.5 | 0%
2036-04-03 | 2036 | 4 | Apr | 3 | 4 | 1 | 25.56% | 7.5 | 0%
2036-04-04 | 2036 | 4 | Apr | 4 | 5 | 1 | 25.56% | 7.5 | 0%
2036-04-05 | 2036 | 4 | Apr | 5 | 6 | 0 | 25.56% | 7.5 | 0%
2036-04-06 | 2036 | 4 | Apr | 6 | 7 | 0 | 25.56% | 7.5 | 0%
2036-04-07 | 2036 | 4 | Apr | 7 | 1 | 1 | 25.56% | 7.5 | 0%
2036-04-08 | 2036 | 4 | Apr | 8 | 2 | 1 | 25.56% | 7.5 | 0%
2036-04-09 | 2036 | 4 | Apr | 9 | 3 | 1 | 25.56% | 7.5 | 0%
2036-04-10 | 2036 | 4 | Apr | 10 | 4 | 1 | 25.56% | 7.5 | 0%
2036-04-11 | 2036 | 4 | Apr | 11 | 5 | 1 | 25.56% | 7.5 | 0%
2036-04-12 | 2036 | 4 | Apr | 12 | 6 | 0 | 25.56% | 7.5 | 0%
2036-04-13 | 2036 | 4 | Apr | 13 | 7 | 0 | 25.56% | 7.5 | 0%
2036-04-14 | 2036 | 4 | Apr | 14 | 1 | 1 | 25.56% | 7.5 | 0%
2036-04-15 | 2036 | 4 | Apr | 15 | 2 | 1 | 25.56% | 7.5 | 0%
2036-04-16 | 2036 | 4 | Apr | 16 | 3 | 1 | 25.56% | 7.5 | 0%
2036-04-17 | 2036 | 4 | Apr | 17 | 4 | 1 | 25.56% | 7.5 | 0%
2036-04-18 | 2036 | 4 | Apr | 18 | 5 | 1 | 25.56% | 7.5 | 0%
2036-04-19 | 2036 | 4 | Apr | 19 | 6 | 0 | 25.56% | 7.5 | 0%
2036-04-20 | 2036 | 4 | Apr | 20 | 7 | 0 | 25.56% | 7.5 | 0%
2036-04-21 | 2036 | 4 | Apr | 21 | 1 | 1 | 25.56% | 7.5 | 0%
2036-04-22 | 2036 | 4 | Apr | 22 | 2 | 1 | 25.56% | 7.5 | 0%
2036-04-23 | 2036 | 4 | Apr | 23 | 3 | 1 | 25.56% | 7.5 | 0%
2036-04-24 | 2036 | 4 | Apr | 24 | 4 | 1 | 25.56% | 7.5 | 0%
2036-04-25 | 2036 | 4 | Apr | 25 | 5 | 1 | 25.56% | 7.5 | 0%
2036-04-26 | 2036 | 4 | Apr | 26 | 6 | 0 | 25.56% | 7.5 | 0%
2036-04-27 | 2036 | 4 | Apr | 27 | 7 | 0 | 25.56% | 7.5 | 0%
2036-04-28 | 2036 | 4 | Apr | 28 | 1 | 1 | 25.56% | 7.5 | 0%
2036-04-29 | 2036 | 4 | Apr | 29 | 2 | 1 | 25.56% | 7.5 | 0%
2036-04-30 | 2036 | 4 | Apr | 30 | 3 | 1 | 25.56% | 7.5 | 0%
2036-05-01 | 2036 | 5 | May | 1 | 4 | 1 | 23.01% | 8.1449 | 0%
2036-05-02 | 2036 | 5 | May | 2 | 5 | 1 | 23.01% | 8.1449 | 0%
2036-05-03 | 2036 | 5 | May | 3 | 6 | 0 | 23.01% | 8.1449 | 0%
2036-05-04 | 2036 | 5 | May | 4 | 7 | 0 | 23.01% | 8.1449 | 0%
2036-05-05 | 2036 | 5 | May | 5 | 1 | 1 | 23.01% | 8.1449 | 0%
2036-05-06 | 2036 | 5 | May | 6 | 2 | 1 | 23.01% | 8.1449 | 0%
2036-05-07 | 2036 | 5 | May | 7 | 3 | 1 | 23.01% | 8.1449 | 0%
2036-05-08 | 2036 | 5 | May | 8 | 4 | 1 | 23.01% | 8.1449 | 0%
2036-05-09 | 2036 | 5 | May | 9 | 5 | 1 | 23.01% | 8.1449 | 0%
2036-05-10 | 2036 | 5 | May | 10 | 6 | 0 | 23.01% | 8.1449 | 0%
2036-05-11 | 2036 | 5 | May | 11 | 7 | 0 | 23.01% | 8.1449 | 0%
2036-05-12 | 2036 | 5 | May | 12 | 1 | 1 | 23.01% | 8.1449 | 0%
2036-05-13 | 2036 | 5 | May | 13 | 2 | 1 | 23.01% | 8.1449 | 0%
2036-05-14 | 2036 | 5 | May | 14 | 3 | 1 | 23.01% | 8.1449 | 0%
2036-05-15 | 2036 | 5 | May | 15 | 4 | 1 | 23.01% | 8.1449 | 0%
2036-05-16 | 2036 | 5 | May | 16 | 5 | 1 | 23.01% | 8.1449 | 0%
2036-05-17 | 2036 | 5 | May | 17 | 6 | 0 | 23.01% | 8.1449 | 0%
2036-05-18 | 2036 | 5 | May | 18 | 7 | 0 | 23.01% | 8.1449 | 0%
2036-05-19 | 2036 | 5 | May | 19 | 1 | 1 | 23.01% | 8.1449 | 0%
2036-05-20 | 2036 | 5 | May | 20 | 2 | 1 | 23.01% | 8.1449 | 0%
2036-05-21 | 2036 | 5 | May | 21 | 3 | 1 | 23.01% | 8.1449 | 0%
2036-05-22 | 2036 | 5 | May | 22 | 4 | 1 | 23.01% | 8.1449 | 0%
2036-05-23 | 2036 | 5 | May | 23 | 5 | 1 | 23.01% | 8.1449 | 0%
2036-05-24 | 2036 | 5 | May | 24 | 6 | 0 | 23.01% | 8.1449 | 0%
2036-05-25 | 2036 | 5 | May | 25 | 7 | 0 | 23.01% | 8.1449 | 0%
2036-05-26 | 2036 | 5 | May | 26 | 1 | 1 | 23.01% | 8.1449 | 0%
2036-05-27 | 2036 | 5 | May | 27 | 2 | 1 | 23.01% | 8.1449 | 0%
2036-05-28 | 2036 | 5 | May | 28 | 3 | 1 | 23.01% | 8.1449 | 0%
2036-05-29 | 2036 | 5 | May | 29 | 4 | 1 | 23.01% | 8.1449 | 0%
2036-05-30 | 2036 | 5 | May | 30 | 5 | 1 | 23.01% | 8.1449 | 0%
2036-05-31 | 2036 | 5 | May | 31 | 6 | 0 | 23.01% | 8.1449 | 0%
2036-06-01 | 2036 | 6 | Jun | 1 | 7 | 0 | 28.67% | 7.9419 | 0%
2036-06-02 | 2036 | 6 | Jun | 2 | 1 | 1 | 28.67% | 7.9419 | 0%
2036-06-03 | 2036 | 6 | Jun | 3 | 2 | 1 | 28.67% | 7.9419 | 0%
2036-06-04 | 2036 | 6 | Jun | 4 | 3 | 1 | 28.67% | 7.9419 | 0%
2036-06-05 | 2036 | 6 | Jun | 5 | 4 | 1 | 28.67% | 7.9419 | 0%
2036-06-06 | 2036 | 6 | Jun | 6 | 5 | 1 | 28.67% | 7.9419 | 0%
2036-06-07 | 2036 | 6 | Jun | 7 | 6 | 0 | 28.67% | 7.9419 | 0%
2036-06-08 | 2036 | 6 | Jun | 8 | 7 | 0 | 28.67% | 7.9419 | 0%
2036-06-09 | 2036 | 6 | Jun | 9 | 1 | 1 | 28.67% | 7.9419 | 0%
2036-06-10 | 2036 | 6 | Jun | 10 | 2 | 1 | 28.67% | 7.9419 | 0%
2036-06-11 | 2036 | 6 | Jun | 11 | 3 | 1 | 28.67% | 7.9419 | 0%
2036-06-12 | 2036 | 6 | Jun | 12 | 4 | 1 | 28.67% | 7.9419 | 0%
2036-06-13 | 2036 | 6 | Jun | 13 | 5 | 1 | 28.67% | 7.9419 | 0%
2036-06-14 | 2036 | 6 | Jun | 14 | 6 | 0 | 28.67% | 7.9419 | 0%
2036-06-15 | 2036 | 6 | Jun | 15 | 7 | 0 | 28.67% | 7.9419 | 0%
2036-06-16 | 2036 | 6 | Jun | 16 | 1 | 1 | 28.67% | 7.9419 | 0%
2036-06-17 | 2036 | 6 | Jun | 17 | 2 | 1 | 28.67% | 7.9419 | 0%
2036-06-18 | 2036 | 6 | Jun | 18 | 3 | 1 | 28.67% | 7.9419 | 0%
2036-06-19 | 2036 | 6 | Jun | 19 | 4 | 1 | 28.67% | 7.9419 | 0%
2036-06-20 | 2036 | 6 | Jun | 20 | 5 | 1 | 28.67% | 7.9419 | 0%
2036-06-21 | 2036 | 6 | Jun | 21 | 6 | 0 | 28.67% | 7.9419 | 0%
2036-06-22 | 2036 | 6 | Jun | 22 | 7 | 0 | 28.67% | 7.9419 | 0%
2036-06-23 | 2036 | 6 | Jun | 23 | 1 | 1 | 28.67% | 7.9419 | 0%
2036-06-24 | 2036 | 6 | Jun | 24 | 2 | 1 | 28.67% | 7.9419 | 0%
2036-06-25 | 2036 | 6 | Jun | 25 | 3 | 1 | 28.67% | 7.9419 | 0%
2036-06-26 | 2036 | 6 | Jun | 26 | 4 | 1 | 28.67% | 7.9419 | 0%
2036-06-27 | 2036 | 6 | Jun | 27 | 5 | 1 | 28.67% | 7.9419 | 0%
2036-06-28 | 2036 | 6 | Jun | 28 | 6 | 0 | 28.67% | 7.9419 | 0%
2036-06-29 | 2036 | 6 | Jun | 29 | 7 | 0 | 28.67% | 7.9419 | 0%
2036-06-30 | 2036 | 6 | Jun | 30 | 1 | 1 | 28.67% | 7.9419 | 0%
2036-07-01 | 2036 | 7 | Jul | 1 | 2 | 1 | 24.73% | 8.3739 | 0%
2036-07-02 | 2036 | 7 | Jul | 2 | 3 | 1 | 24.73% | 8.3739 | 0%
2036-07-03 | 2036 | 7 | Jul | 3 | 4 | 1 | 24.73% | 8.3739 | 0%
2036-07-04 | 2036 | 7 | Jul | 4 | 5 | 1 | 24.73% | 8.3739 | 0%
2036-07-05 | 2036 | 7 | Jul | 5 | 6 | 0 | 24.73% | 8.3739 | 0%
2036-07-06 | 2036 | 7 | Jul | 6 | 7 | 0 | 24.73% | 8.3739 | 0%
2036-07-07 | 2036 | 7 | Jul | 7 | 1 | 1 | 24.73% | 8.3739 | 0%
2036-07-08 | 2036 | 7 | Jul | 8 | 2 | 1 | 24.73% | 8.3739 | 0%
2036-07-09 | 2036 | 7 | Jul | 9 | 3 | 1 | 24.73% | 8.3739 | 0%
2036-07-10 | 2036 | 7 | Jul | 10 | 4 | 1 | 24.73% | 8.3739 | 0%
2036-07-11 | 2036 | 7 | Jul | 11 | 5 | 1 | 24.73% | 8.3739 | 0%
2036-07-12 | 2036 | 7 | Jul | 12 | 6 | 0 | 24.73% | 8.3739 | 0%
2036-07-13 | 2036 | 7 | Jul | 13 | 7 | 0 | 24.73% | 8.3739 | 0%
2036-07-14 | 2036 | 7 | Jul | 14 | 1 | 1 | 24.73% | 8.3739 | 0%
2036-07-15 | 2036 | 7 | Jul | 15 | 2 | 1 | 24.73% | 8.3739 | 0%
2036-07-16 | 2036 | 7 | Jul | 16 | 3 | 1 | 24.73% | 8.3739 | 0%
2036-07-17 | 2036 | 7 | Jul | 17 | 4 | 1 | 24.73% | 8.3739 | 0%
2036-07-18 | 2036 | 7 | Jul | 18 | 5 | 1 | 24.73% | 8.3739 | 0%
2036-07-19 | 2036 | 7 | Jul | 19 | 6 | 0 | 24.73% | 8.3739 | 0%
2036-07-20 | 2036 | 7 | Jul | 20 | 7 | 0 | 24.73% | 8.3739 | 0%
2036-07-21 | 2036 | 7 | Jul | 21 | 1 | 1 | 24.73% | 8.3739 | 0%
2036-07-22 | 2036 | 7 | Jul | 22 | 2 | 1 | 24.73% | 8.3739 | 0%
2036-07-23 | 2036 | 7 | Jul | 23 | 3 | 1 | 24.73% | 8.3739 | 0%
2036-07-24 | 2036 | 7 | Jul | 24 | 4 | 1 | 24.73% | 8.3739 | 0%
2036-07-25 | 2036 | 7 | Jul | 25 | 5 | 1 | 24.73% | 8.3739 | 0%
2036-07-26 | 2036 | 7 | Jul | 26 | 6 | 0 | 24.73% | 8.3739 | 0%
2036-07-27 | 2036 | 7 | Jul | 27 | 7 | 0 | 24.73% | 8.3739 | 0%
2036-07-28 | 2036 | 7 | Jul | 28 | 1 | 1 | 24.73% | 8.3739 | 0%
2036-07-29 | 2036 | 7 | Jul | 29 | 2 | 1 | 24.73% | 8.3739 | 0%
2036-07-30 | 2036 | 7 | Jul | 30 | 3 | 1 | 24.73% | 8.3739 | 0%
2036-07-31 | 2036 | 7 | Jul | 31 | 4 | 1 | 24.73% | 8.3739 | 0%
2036-08-01 | 2036 | 8 | Aug | 1 | 5 | 1 | 23.55% | 7.9589 | 0%
2036-08-02 | 2036 | 8 | Aug | 2 | 6 | 0 | 23.55% | 7.9589 | 0%
2036-08-03 | 2036 | 8 | Aug | 3 | 7 | 0 | 23.55% | 7.9589 | 0%
2036-08-04 | 2036 | 8 | Aug | 4 | 1 | 1 | 23.55% | 7.9589 | 0%
2036-08-05 | 2036 | 8 | Aug | 5 | 2 | 1 | 23.55% | 7.9589 | 0%
2036-08-06 | 2036 | 8 | Aug | 6 | 3 | 1 | 23.55% | 7.9589 | 0%
2036-08-07 | 2036 | 8 | Aug | 7 | 4 | 1 | 23.55% | 7.9589 | 0%
2036-08-08 | 2036 | 8 | Aug | 8 | 5 | 1 | 23.55% | 7.9589 | 0%
2036-08-09 | 2036 | 8 | Aug | 9 | 6 | 0 | 23.55% | 7.9589 | 0%
2036-08-10 | 2036 | 8 | Aug | 10 | 7 | 0 | 23.55% | 7.9589 | 0%
2036-08-11 | 2036 | 8 | Aug | 11 | 1 | 1 | 23.55% | 7.9589 | 0%
2036-08-12 | 2036 | 8 | Aug | 12 | 2 | 1 | 23.55% | 7.9589 | 0%
2036-08-13 | 2036 | 8 | Aug | 13 | 3 | 1 | 23.55% | 7.9589 | 0%
2036-08-14 | 2036 | 8 | Aug | 14 | 4 | 1 | 23.55% | 7.9589 | 0%
2036-08-15 | 2036 | 8 | Aug | 15 | 5 | 1 | 23.55% | 7.9589 | 0%
2036-08-16 | 2036 | 8 | Aug | 16 | 6 | 0 | 23.55% | 7.9589 | 0%
2036-08-17 | 2036 | 8 | Aug | 17 | 7 | 0 | 23.55% | 7.9589 | 0%
2036-08-18 | 2036 | 8 | Aug | 18 | 1 | 1 | 23.55% | 7.9589 | 0%
2036-08-19 | 2036 | 8 | Aug | 19 | 2 | 1 | 23.55% | 7.9589 | 0%
2036-08-20 | 2036 | 8 | Aug | 20 | 3 | 1 | 23.55% | 7.9589 | 0%
2036-08-21 | 2036 | 8 | Aug | 21 | 4 | 1 | 23.55% | 7.9589 | 0%
2036-08-22 | 2036 | 8 | Aug | 22 | 5 | 1 | 23.55% | 7.9589 | 0%
2036-08-23 | 2036 | 8 | Aug | 23 | 6 | 0 | 23.55% | 7.9589 | 0%
2036-08-24 | 2036 | 8 | Aug | 24 | 7 | 0 | 23.55% | 7.9589 | 0%
2036-08-25 | 2036 | 8 | Aug | 25 | 1 | 1 | 23.55% | 7.9589 | 0%
2036-08-26 | 2036 | 8 | Aug | 26 | 2 | 1 | 23.55% | 7.9589 | 0%
2036-08-27 | 2036 | 8 | Aug | 27 | 3 | 1 | 23.55% | 7.9589 | 0%
2036-08-28 | 2036 | 8 | Aug | 28 | 4 | 1 | 23.55% | 7.9589 | 0%
2036-08-29 | 2036 | 8 | Aug | 29 | 5 | 1 | 23.55% | 7.9589 | 0%
2036-08-30 | 2036 | 8 | Aug | 30 | 6 | 0 | 23.55% | 7.9589 | 0%
2036-08-31 | 2036 | 8 | Aug | 31 | 7 | 0 | 23.55% | 7.9589 | 0%
2036-09-01 | 2036 | 9 | Sep | 1 | 1 | 1 | 20.67% | 6.8065 | 0%
2036-09-02 | 2036 | 9 | Sep | 2 | 2 | 1 | 20.67% | 6.8065 | 0%
2036-09-03 | 2036 | 9 | Sep | 3 | 3 | 1 | 20.67% | 6.8065 | 0%
2036-09-04 | 2036 | 9 | Sep | 4 | 4 | 1 | 20.67% | 6.8065 | 0%
2036-09-05 | 2036 | 9 | Sep | 5 | 5 | 1 | 20.67% | 6.8065 | 0%
2036-09-06 | 2036 | 9 | Sep | 6 | 6 | 0 | 20.67% | 6.8065 | 0%
2036-09-07 | 2036 | 9 | Sep | 7 | 7 | 0 | 20.67% | 6.8065 | 0%
2036-09-08 | 2036 | 9 | Sep | 8 | 1 | 1 | 20.67% | 6.8065 | 0%
2036-09-09 | 2036 | 9 | Sep | 9 | 2 | 1 | 20.67% | 6.8065 | 0%
2036-09-10 | 2036 | 9 | Sep | 10 | 3 | 1 | 20.67% | 6.8065 | 0%
2036-09-11 | 2036 | 9 | Sep | 11 | 4 | 1 | 20.67% | 6.8065 | 0%
2036-09-12 | 2036 | 9 | Sep | 12 | 5 | 1 | 20.67% | 6.8065 | 0%
2036-09-13 | 2036 | 9 | Sep | 13 | 6 | 0 | 20.67% | 6.8065 | 0%
2036-09-14 | 2036 | 9 | Sep | 14 | 7 | 0 | 20.67% | 6.8065 | 0%
2036-09-15 | 2036 | 9 | Sep | 15 | 1 | 1 | 20.67% | 6.8065 | 0%
2036-09-16 | 2036 | 9 | Sep | 16 | 2 | 1 | 20.67% | 6.8065 | 0%
2036-09-17 | 2036 | 9 | Sep | 17 | 3 | 1 | 20.67% | 6.8065 | 0%
2036-09-18 | 2036 | 9 | Sep | 18 | 4 | 1 | 20.67% | 6.8065 | 0%
2036-09-19 | 2036 | 9 | Sep | 19 | 5 | 1 | 20.67% | 6.8065 | 0%
2036-09-20 | 2036 | 9 | Sep | 20 | 6 | 0 | 20.67% | 6.8065 | 0%
2036-09-21 | 2036 | 9 | Sep | 21 | 7 | 0 | 20.67% | 6.8065 | 0%
2036-09-22 | 2036 | 9 | Sep | 22 | 1 | 1 | 20.67% | 6.8065 | 0%
2036-09-23 | 2036 | 9 | Sep | 23 | 2 | 1 | 20.67% | 6.8065 | 0%
2036-09-24 | 2036 | 9 | Sep | 24 | 3 | 1 | 20.67% | 6.8065 | 0%
2036-09-25 | 2036 | 9 | Sep | 25 | 4 | 1 | 20.67% | 6.8065 | 0%
2036-09-26 | 2036 | 9 | Sep | 26 | 5 | 1 | 20.67% | 6.8065 | 0%
2036-09-27 | 2036 | 9 | Sep | 27 | 6 | 0 | 20.67% | 6.8065 | 0%
2036-09-28 | 2036 | 9 | Sep | 28 | 7 | 0 | 20.67% | 6.8065 | 0%
2036-09-29 | 2036 | 9 | Sep | 29 | 1 | 1 | 20.67% | 6.8065 | 0%
2036-09-30 | 2036 | 9 | Sep | 30 | 2 | 1 | 20.67% | 6.8065 | 0%
2036-10-01 | 2036 | 10 | Oct | 1 | 3 | 1 | 23.23% | 6.8194 | 0%
2036-10-02 | 2036 | 10 | Oct | 2 | 4 | 1 | 23.23% | 6.8194 | 0%
2036-10-03 | 2036 | 10 | Oct | 3 | 5 | 1 | 23.23% | 6.8194 | 0%
2036-10-04 | 2036 | 10 | Oct | 4 | 6 | 0 | 23.23% | 6.8194 | 0%
2036-10-05 | 2036 | 10 | Oct | 5 | 7 | 0 | 23.23% | 6.8194 | 0%
2036-10-06 | 2036 | 10 | Oct | 6 | 1 | 1 | 23.23% | 6.8194 | 0%
2036-10-07 | 2036 | 10 | Oct | 7 | 2 | 1 | 23.23% | 6.8194 | 0%
2036-10-08 | 2036 | 10 | Oct | 8 | 3 | 1 | 23.23% | 6.8194 | 0%
2036-10-09 | 2036 | 10 | Oct | 9 | 4 | 1 | 23.23% | 6.8194 | 0%
2036-10-10 | 2036 | 10 | Oct | 10 | 5 | 1 | 23.23% | 6.8194 | 0%
2036-10-11 | 2036 | 10 | Oct | 11 | 6 | 0 | 23.23% | 6.8194 | 0%
2036-10-12 | 2036 | 10 | Oct | 12 | 7 | 0 | 23.23% | 6.8194 | 0%
2036-10-13 | 2036 | 10 | Oct | 13 | 1 | 1 | 23.23% | 6.8194 | 0%
2036-10-14 | 2036 | 10 | Oct | 14 | 2 | 1 | 23.23% | 6.8194 | 0%
2036-10-15 | 2036 | 10 | Oct | 15 | 3 | 1 | 23.23% | 6.8194 | 0%
2036-10-16 | 2036 | 10 | Oct | 16 | 4 | 1 | 23.23% | 6.8194 | 0%
2036-10-17 | 2036 | 10 | Oct | 17 | 5 | 1 | 23.23% | 6.8194 | 0%
2036-10-18 | 2036 | 10 | Oct | 18 | 6 | 0 | 23.23% | 6.8194 | 0%
2036-10-19 | 2036 | 10 | Oct | 19 | 7 | 0 | 23.23% | 6.8194 | 0%
2036-10-20 | 2036 | 10 | Oct | 20 | 1 | 1 | 23.23% | 6.8194 | 0%
2036-10-21 | 2036 | 10 | Oct | 21 | 2 | 1 | 23.23% | 6.8194 | 0%
2036-10-22 | 2036 | 10 | Oct | 22 | 3 | 1 | 23.23% | 6.8194 | 0%
2036-10-23 | 2036 | 10 | Oct | 23 | 4 | 1 | 23.23% | 6.8194 | 0%
2036-10-24 | 2036 | 10 | Oct | 24 | 5 | 1 | 23.23% | 6.8194 | 0%
2036-10-25 | 2036 | 10 | Oct | 25 | 6 | 0 | 23.23% | 6.8194 | 0%
2036-10-26 | 2036 | 10 | Oct | 26 | 7 | 0 | 23.23% | 6.8194 | 0%
2036-10-27 | 2036 | 10 | Oct | 27 | 1 | 1 | 23.23% | 6.8194 | 0%
2036-10-28 | 2036 | 10 | Oct | 28 | 2 | 1 | 23.23% | 6.8194 | 0%
2036-10-29 | 2036 | 10 | Oct | 29 | 3 | 1 | 23.23% | 6.8194 | 0%
2036-10-30 | 2036 | 10 | Oct | 30 | 4 | 1 | 23.23% | 6.8194 | 0%
2036-10-31 | 2036 | 10 | Oct | 31 | 5 | 1 | 23.23% | 6.8194 | 0%
2036-11-01 | 2036 | 11 | Nov | 1 | 6 | 0 | 23.33% | 6.4429 | 0%
2036-11-02 | 2036 | 11 | Nov | 2 | 7 | 0 | 23.33% | 6.4429 | 0%
2036-11-03 | 2036 | 11 | Nov | 3 | 1 | 1 | 23.33% | 6.4429 | 0%
2036-11-04 | 2036 | 11 | Nov | 4 | 2 | 1 | 23.33% | 6.4429 | 0%
2036-11-05 | 2036 | 11 | Nov | 5 | 3 | 1 | 23.33% | 6.4429 | 0%
2036-11-06 | 2036 | 11 | Nov | 6 | 4 | 1 | 23.33% | 6.4429 | 0%
2036-11-07 | 2036 | 11 | Nov | 7 | 5 | 1 | 23.33% | 6.4429 | 0%
2036-11-08 | 2036 | 11 | Nov | 8 | 6 | 0 | 23.33% | 6.4429 | 0%
2036-11-09 | 2036 | 11 | Nov | 9 | 7 | 0 | 23.33% | 6.4429 | 0%
2036-11-10 | 2036 | 11 | Nov | 10 | 1 | 1 | 23.33% | 6.4429 | 0%
2036-11-11 | 2036 | 11 | Nov | 11 | 2 | 1 | 23.33% | 6.4429 | 0%
2036-11-12 | 2036 | 11 | Nov | 12 | 3 | 1 | 23.33% | 6.4429 | 0%
2036-11-13 | 2036 | 11 | Nov | 13 | 4 | 1 | 23.33% | 6.4429 | 0%
2036-11-14 | 2036 | 11 | Nov | 14 | 5 | 1 | 23.33% | 6.4429 | 0%
2036-11-15 | 2036 | 11 | Nov | 15 | 6 | 0 | 23.33% | 6.4429 | 0%
2036-11-16 | 2036 | 11 | Nov | 16 | 7 | 0 | 23.33% | 6.4429 | 0%
2036-11-17 | 2036 | 11 | Nov | 17 | 1 | 1 | 23.33% | 6.4429 | 0%
2036-11-18 | 2036 | 11 | Nov | 18 | 2 | 1 | 23.33% | 6.4429 | 0%
2036-11-19 | 2036 | 11 | Nov | 19 | 3 | 1 | 23.33% | 6.4429 | 0%
2036-11-20 | 2036 | 11 | Nov | 20 | 4 | 1 | 23.33% | 6.4429 | 0%
2036-11-21 | 2036 | 11 | Nov | 21 | 5 | 1 | 23.33% | 6.4429 | 0%
2036-11-22 | 2036 | 11 | Nov | 22 | 6 | 0 | 23.33% | 6.4429 | 0%
2036-11-23 | 2036 | 11 | Nov | 23 | 7 | 0 | 23.33% | 6.4429 | 0%
2036-11-24 | 2036 | 11 | Nov | 24 | 1 | 1 | 23.33% | 6.4429 | 0%
2036-11-25 | 2036 | 11 | Nov | 25 | 2 | 1 | 23.33% | 6.4429 | 0%
2036-11-26 | 2036 | 11 | Nov | 26 | 3 | 1 | 23.33% | 6.4429 | 0%
2036-11-27 | 2036 | 11 | Nov | 27 | 4 | 1 | 23.33% | 6.4429 | 0%
2036-11-28 | 2036 | 11 | Nov | 28 | 5 | 1 | 23.33% | 6.4429 | 0%
2036-11-29 | 2036 | 11 | Nov | 29 | 6 | 0 | 23.33% | 6.4429 | 0%
2036-11-30 | 2036 | 11 | Nov | 30 | 7 | 0 | 23.33% | 6.4429 | 0%
2036-12-01 | 2036 | 12 | Dec | 1 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-12-02 | 2036 | 12 | Dec | 2 | 2 | 1 | 22.69% | 6.7962 | 0%
2036-12-03 | 2036 | 12 | Dec | 3 | 3 | 1 | 22.69% | 6.7962 | 0%
2036-12-04 | 2036 | 12 | Dec | 4 | 4 | 1 | 22.69% | 6.7962 | 0%
2036-12-05 | 2036 | 12 | Dec | 5 | 5 | 1 | 22.69% | 6.7962 | 0%
2036-12-06 | 2036 | 12 | Dec | 6 | 6 | 0 | 22.69% | 6.7962 | 0%
2036-12-07 | 2036 | 12 | Dec | 7 | 7 | 0 | 22.69% | 6.7962 | 0%
2036-12-08 | 2036 | 12 | Dec | 8 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-12-09 | 2036 | 12 | Dec | 9 | 2 | 1 | 22.69% | 6.7962 | 0%
2036-12-10 | 2036 | 12 | Dec | 10 | 3 | 1 | 22.69% | 6.7962 | 0%
2036-12-11 | 2036 | 12 | Dec | 11 | 4 | 1 | 22.69% | 6.7962 | 0%
2036-12-12 | 2036 | 12 | Dec | 12 | 5 | 1 | 22.69% | 6.7962 | 0%
2036-12-13 | 2036 | 12 | Dec | 13 | 6 | 0 | 22.69% | 6.7962 | 0%
2036-12-14 | 2036 | 12 | Dec | 14 | 7 | 0 | 22.69% | 6.7962 | 0%
2036-12-15 | 2036 | 12 | Dec | 15 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-12-16 | 2036 | 12 | Dec | 16 | 2 | 1 | 22.69% | 6.7962 | 0%
2036-12-17 | 2036 | 12 | Dec | 17 | 3 | 1 | 22.69% | 6.7962 | 0%
2036-12-18 | 2036 | 12 | Dec | 18 | 4 | 1 | 22.69% | 6.7962 | 0%
2036-12-19 | 2036 | 12 | Dec | 19 | 5 | 1 | 22.69% | 6.7962 | 0%
2036-12-20 | 2036 | 12 | Dec | 20 | 6 | 0 | 22.69% | 6.7962 | 0%
2036-12-21 | 2036 | 12 | Dec | 21 | 7 | 0 | 22.69% | 6.7962 | 0%
2036-12-22 | 2036 | 12 | Dec | 22 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-12-23 | 2036 | 12 | Dec | 23 | 2 | 1 | 22.69% | 6.7962 | 0%
2036-12-24 | 2036 | 12 | Dec | 24 | 3 | 1 | 22.69% | 6.7962 | 0%
2036-12-25 | 2036 | 12 | Dec | 25 | 4 | 1 | 22.69% | 6.7962 | 0%
2036-12-26 | 2036 | 12 | Dec | 26 | 5 | 1 | 22.69% | 6.7962 | 0%
2036-12-27 | 2036 | 12 | Dec | 27 | 6 | 0 | 22.69% | 6.7962 | 0%
2036-12-28 | 2036 | 12 | Dec | 28 | 7 | 0 | 22.69% | 6.7962 | 0%
2036-12-29 | 2036 | 12 | Dec | 29 | 1 | 1 | 22.69% | 6.7962 | 0%
2036-12-30 | 2036 | 12 | Dec | 30 | 2 | 1 | 22.69% | 6.7962 | 0%
2036-12-31 | 2036 | 12 | Dec | 31 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-01-01 | 2037 | 1 | Jan | 1 | 4 | 1 | 19.46% | 7.0276 | 0%
2037-01-02 | 2037 | 1 | Jan | 2 | 5 | 1 | 19.46% | 7.0276 | 0%
2037-01-03 | 2037 | 1 | Jan | 3 | 6 | 0 | 19.46% | 7.0276 | 0%
2037-01-04 | 2037 | 1 | Jan | 4 | 7 | 0 | 19.46% | 7.0276 | 0%
2037-01-05 | 2037 | 1 | Jan | 5 | 1 | 1 | 19.46% | 7.0276 | 0%
2037-01-06 | 2037 | 1 | Jan | 6 | 2 | 1 | 19.46% | 7.0276 | 0%
2037-01-07 | 2037 | 1 | Jan | 7 | 3 | 1 | 19.46% | 7.0276 | 0%
2037-01-08 | 2037 | 1 | Jan | 8 | 4 | 1 | 19.46% | 7.0276 | 0%
2037-01-09 | 2037 | 1 | Jan | 9 | 5 | 1 | 19.46% | 7.0276 | 0%
2037-01-10 | 2037 | 1 | Jan | 10 | 6 | 0 | 19.46% | 7.0276 | 0%
2037-01-11 | 2037 | 1 | Jan | 11 | 7 | 0 | 19.46% | 7.0276 | 0%
2037-01-12 | 2037 | 1 | Jan | 12 | 1 | 1 | 19.46% | 7.0276 | 0%
2037-01-13 | 2037 | 1 | Jan | 13 | 2 | 1 | 19.46% | 7.0276 | 0%
2037-01-14 | 2037 | 1 | Jan | 14 | 3 | 1 | 19.46% | 7.0276 | 0%
2037-01-15 | 2037 | 1 | Jan | 15 | 4 | 1 | 19.46% | 7.0276 | 0%
2037-01-16 | 2037 | 1 | Jan | 16 | 5 | 1 | 19.46% | 7.0276 | 0%
2037-01-17 | 2037 | 1 | Jan | 17 | 6 | 0 | 19.46% | 7.0276 | 0%
2037-01-18 | 2037 | 1 | Jan | 18 | 7 | 0 | 19.46% | 7.0276 | 0%
2037-01-19 | 2037 | 1 | Jan | 19 | 1 | 1 | 19.46% | 7.0276 | 0%
2037-01-20 | 2037 | 1 | Jan | 20 | 2 | 1 | 19.46% | 7.0276 | 0%
2037-01-21 | 2037 | 1 | Jan | 21 | 3 | 1 | 19.46% | 7.0276 | 0%
2037-01-22 | 2037 | 1 | Jan | 22 | 4 | 1 | 19.46% | 7.0276 | 0%
2037-01-23 | 2037 | 1 | Jan | 23 | 5 | 1 | 19.46% | 7.0276 | 0%
2037-01-24 | 2037 | 1 | Jan | 24 | 6 | 0 | 19.46% | 7.0276 | 0%
2037-01-25 | 2037 | 1 | Jan | 25 | 7 | 0 | 19.46% | 7.0276 | 0%
2037-01-26 | 2037 | 1 | Jan | 26 | 1 | 1 | 19.46% | 7.0276 | 0%
2037-01-27 | 2037 | 1 | Jan | 27 | 2 | 1 | 19.46% | 7.0276 | 0%
2037-01-28 | 2037 | 1 | Jan | 28 | 3 | 1 | 19.46% | 7.0276 | 0%
2037-01-29 | 2037 | 1 | Jan | 29 | 4 | 1 | 19.46% | 7.0276 | 0%
2037-01-30 | 2037 | 1 | Jan | 30 | 5 | 1 | 19.46% | 7.0276 | 0%
2037-01-31 | 2037 | 1 | Jan | 31 | 6 | 0 | 19.46% | 7.0276 | 0%
2037-02-01 | 2037 | 2 | Feb | 1 | 7 | 0 | 18.87% | 7.4625 | 0%
2037-02-02 | 2037 | 2 | Feb | 2 | 1 | 1 | 18.87% | 7.4625 | 0%
2037-02-03 | 2037 | 2 | Feb | 3 | 2 | 1 | 18.87% | 7.4625 | 0%
2037-02-04 | 2037 | 2 | Feb | 4 | 3 | 1 | 18.87% | 7.4625 | 0%
2037-02-05 | 2037 | 2 | Feb | 5 | 4 | 1 | 18.87% | 7.4625 | 0%
2037-02-06 | 2037 | 2 | Feb | 6 | 5 | 1 | 18.87% | 7.4625 | 0%
2037-02-07 | 2037 | 2 | Feb | 7 | 6 | 0 | 18.87% | 7.4625 | 0%
2037-02-08 | 2037 | 2 | Feb | 8 | 7 | 0 | 18.87% | 7.4625 | 0%
2037-02-09 | 2037 | 2 | Feb | 9 | 1 | 1 | 18.87% | 7.4625 | 0%
2037-02-10 | 2037 | 2 | Feb | 10 | 2 | 1 | 18.87% | 7.4625 | 0%
2037-02-11 | 2037 | 2 | Feb | 11 | 3 | 1 | 18.87% | 7.4625 | 0%
2037-02-12 | 2037 | 2 | Feb | 12 | 4 | 1 | 18.87% | 7.4625 | 0%
2037-02-13 | 2037 | 2 | Feb | 13 | 5 | 1 | 18.87% | 7.4625 | 0%
2037-02-14 | 2037 | 2 | Feb | 14 | 6 | 0 | 18.87% | 7.4625 | 0%
2037-02-15 | 2037 | 2 | Feb | 15 | 7 | 0 | 18.87% | 7.4625 | 0%
2037-02-16 | 2037 | 2 | Feb | 16 | 1 | 1 | 18.87% | 7.4625 | 0%
2037-02-17 | 2037 | 2 | Feb | 17 | 2 | 1 | 18.87% | 7.4625 | 0%
2037-02-18 | 2037 | 2 | Feb | 18 | 3 | 1 | 18.87% | 7.4625 | 0%
2037-02-19 | 2037 | 2 | Feb | 19 | 4 | 1 | 18.87% | 7.4625 | 0%
2037-02-20 | 2037 | 2 | Feb | 20 | 5 | 1 | 18.87% | 7.4625 | 0%
2037-02-21 | 2037 | 2 | Feb | 21 | 6 | 0 | 18.87% | 7.4625 | 0%
2037-02-22 | 2037 | 2 | Feb | 22 | 7 | 0 | 18.87% | 7.4625 | 0%
2037-02-23 | 2037 | 2 | Feb | 23 | 1 | 1 | 18.87% | 7.4625 | 0%
2037-02-24 | 2037 | 2 | Feb | 24 | 2 | 1 | 18.87% | 7.4625 | 0%
2037-02-25 | 2037 | 2 | Feb | 25 | 3 | 1 | 18.87% | 7.4625 | 0%
2037-02-26 | 2037 | 2 | Feb | 26 | 4 | 1 | 18.87% | 7.4625 | 0%
2037-02-27 | 2037 | 2 | Feb | 27 | 5 | 1 | 18.87% | 7.4625 | 0%
2037-02-28 | 2037 | 2 | Feb | 28 | 6 | 0 | 18.87% | 7.4625 | 0%
2037-03-01 | 2037 | 3 | Mar | 1 | 7 | 0 | 18.49% | 7.8663 | 0%
2037-03-02 | 2037 | 3 | Mar | 2 | 1 | 1 | 18.49% | 7.8663 | 0%
2037-03-03 | 2037 | 3 | Mar | 3 | 2 | 1 | 18.49% | 7.8663 | 0%
2037-03-04 | 2037 | 3 | Mar | 4 | 3 | 1 | 18.49% | 7.8663 | 0%
2037-03-05 | 2037 | 3 | Mar | 5 | 4 | 1 | 18.49% | 7.8663 | 0%
2037-03-06 | 2037 | 3 | Mar | 6 | 5 | 1 | 18.49% | 7.8663 | 0%
2037-03-07 | 2037 | 3 | Mar | 7 | 6 | 0 | 18.49% | 7.8663 | 0%
2037-03-08 | 2037 | 3 | Mar | 8 | 7 | 0 | 18.49% | 7.8663 | 0%
2037-03-09 | 2037 | 3 | Mar | 9 | 1 | 1 | 18.49% | 7.8663 | 0%
2037-03-10 | 2037 | 3 | Mar | 10 | 2 | 1 | 18.49% | 7.8663 | 0%
2037-03-11 | 2037 | 3 | Mar | 11 | 3 | 1 | 18.49% | 7.8663 | 0%
2037-03-12 | 2037 | 3 | Mar | 12 | 4 | 1 | 18.49% | 7.8663 | 0%
2037-03-13 | 2037 | 3 | Mar | 13 | 5 | 1 | 18.49% | 7.8663 | 0%
2037-03-14 | 2037 | 3 | Mar | 14 | 6 | 0 | 18.49% | 7.8663 | 0%
2037-03-15 | 2037 | 3 | Mar | 15 | 7 | 0 | 18.49% | 7.8663 | 0%
2037-03-16 | 2037 | 3 | Mar | 16 | 1 | 1 | 18.49% | 7.8663 | 0%
2037-03-17 | 2037 | 3 | Mar | 17 | 2 | 1 | 18.49% | 7.8663 | 0%
2037-03-18 | 2037 | 3 | Mar | 18 | 3 | 1 | 18.49% | 7.8663 | 0%
2037-03-19 | 2037 | 3 | Mar | 19 | 4 | 1 | 18.49% | 7.8663 | 0%
2037-03-20 | 2037 | 3 | Mar | 20 | 5 | 1 | 18.49% | 7.8663 | 0%
2037-03-21 | 2037 | 3 | Mar | 21 | 6 | 0 | 18.49% | 7.8663 | 0%
2037-03-22 | 2037 | 3 | Mar | 22 | 7 | 0 | 18.49% | 7.8663 | 0%
2037-03-23 | 2037 | 3 | Mar | 23 | 1 | 1 | 18.49% | 7.8663 | 0%
2037-03-24 | 2037 | 3 | Mar | 24 | 2 | 1 | 18.49% | 7.8663 | 0%
2037-03-25 | 2037 | 3 | Mar | 25 | 3 | 1 | 18.49% | 7.8663 | 0%
2037-03-26 | 2037 | 3 | Mar | 26 | 4 | 1 | 18.49% | 7.8663 | 0%
2037-03-27 | 2037 | 3 | Mar | 27 | 5 | 1 | 18.49% | 7.8663 | 0%
2037-03-28 | 2037 | 3 | Mar | 28 | 6 | 0 | 18.49% | 7.8663 | 0%
2037-03-29 | 2037 | 3 | Mar | 29 | 7 | 0 | 18.49% | 7.8663 | 0%
2037-03-30 | 2037 | 3 | Mar | 30 | 1 | 1 | 18.49% | 7.8663 | 0%
2037-03-31 | 2037 | 3 | Mar | 31 | 2 | 1 | 18.49% | 7.8663 | 0%
2037-04-01 | 2037 | 4 | Apr | 1 | 3 | 1 | 25.56% | 7.5 | 0%
2037-04-02 | 2037 | 4 | Apr | 2 | 4 | 1 | 25.56% | 7.5 | 0%
2037-04-03 | 2037 | 4 | Apr | 3 | 5 | 1 | 25.56% | 7.5 | 0%
2037-04-04 | 2037 | 4 | Apr | 4 | 6 | 0 | 25.56% | 7.5 | 0%
2037-04-05 | 2037 | 4 | Apr | 5 | 7 | 0 | 25.56% | 7.5 | 0%
2037-04-06 | 2037 | 4 | Apr | 6 | 1 | 1 | 25.56% | 7.5 | 0%
2037-04-07 | 2037 | 4 | Apr | 7 | 2 | 1 | 25.56% | 7.5 | 0%
2037-04-08 | 2037 | 4 | Apr | 8 | 3 | 1 | 25.56% | 7.5 | 0%
2037-04-09 | 2037 | 4 | Apr | 9 | 4 | 1 | 25.56% | 7.5 | 0%
2037-04-10 | 2037 | 4 | Apr | 10 | 5 | 1 | 25.56% | 7.5 | 0%
2037-04-11 | 2037 | 4 | Apr | 11 | 6 | 0 | 25.56% | 7.5 | 0%
2037-04-12 | 2037 | 4 | Apr | 12 | 7 | 0 | 25.56% | 7.5 | 0%
2037-04-13 | 2037 | 4 | Apr | 13 | 1 | 1 | 25.56% | 7.5 | 0%
2037-04-14 | 2037 | 4 | Apr | 14 | 2 | 1 | 25.56% | 7.5 | 0%
2037-04-15 | 2037 | 4 | Apr | 15 | 3 | 1 | 25.56% | 7.5 | 0%
2037-04-16 | 2037 | 4 | Apr | 16 | 4 | 1 | 25.56% | 7.5 | 0%
2037-04-17 | 2037 | 4 | Apr | 17 | 5 | 1 | 25.56% | 7.5 | 0%
2037-04-18 | 2037 | 4 | Apr | 18 | 6 | 0 | 25.56% | 7.5 | 0%
2037-04-19 | 2037 | 4 | Apr | 19 | 7 | 0 | 25.56% | 7.5 | 0%
2037-04-20 | 2037 | 4 | Apr | 20 | 1 | 1 | 25.56% | 7.5 | 0%
2037-04-21 | 2037 | 4 | Apr | 21 | 2 | 1 | 25.56% | 7.5 | 0%
2037-04-22 | 2037 | 4 | Apr | 22 | 3 | 1 | 25.56% | 7.5 | 0%
2037-04-23 | 2037 | 4 | Apr | 23 | 4 | 1 | 25.56% | 7.5 | 0%
2037-04-24 | 2037 | 4 | Apr | 24 | 5 | 1 | 25.56% | 7.5 | 0%
2037-04-25 | 2037 | 4 | Apr | 25 | 6 | 0 | 25.56% | 7.5 | 0%
2037-04-26 | 2037 | 4 | Apr | 26 | 7 | 0 | 25.56% | 7.5 | 0%
2037-04-27 | 2037 | 4 | Apr | 27 | 1 | 1 | 25.56% | 7.5 | 0%
2037-04-28 | 2037 | 4 | Apr | 28 | 2 | 1 | 25.56% | 7.5 | 0%
2037-04-29 | 2037 | 4 | Apr | 29 | 3 | 1 | 25.56% | 7.5 | 0%
2037-04-30 | 2037 | 4 | Apr | 30 | 4 | 1 | 25.56% | 7.5 | 0%
2037-05-01 | 2037 | 5 | May | 1 | 5 | 1 | 23.01% | 8.1449 | 0%
2037-05-02 | 2037 | 5 | May | 2 | 6 | 0 | 23.01% | 8.1449 | 0%
2037-05-03 | 2037 | 5 | May | 3 | 7 | 0 | 23.01% | 8.1449 | 0%
2037-05-04 | 2037 | 5 | May | 4 | 1 | 1 | 23.01% | 8.1449 | 0%
2037-05-05 | 2037 | 5 | May | 5 | 2 | 1 | 23.01% | 8.1449 | 0%
2037-05-06 | 2037 | 5 | May | 6 | 3 | 1 | 23.01% | 8.1449 | 0%
2037-05-07 | 2037 | 5 | May | 7 | 4 | 1 | 23.01% | 8.1449 | 0%
2037-05-08 | 2037 | 5 | May | 8 | 5 | 1 | 23.01% | 8.1449 | 0%
2037-05-09 | 2037 | 5 | May | 9 | 6 | 0 | 23.01% | 8.1449 | 0%
2037-05-10 | 2037 | 5 | May | 10 | 7 | 0 | 23.01% | 8.1449 | 0%
2037-05-11 | 2037 | 5 | May | 11 | 1 | 1 | 23.01% | 8.1449 | 0%
2037-05-12 | 2037 | 5 | May | 12 | 2 | 1 | 23.01% | 8.1449 | 0%
2037-05-13 | 2037 | 5 | May | 13 | 3 | 1 | 23.01% | 8.1449 | 0%
2037-05-14 | 2037 | 5 | May | 14 | 4 | 1 | 23.01% | 8.1449 | 0%
2037-05-15 | 2037 | 5 | May | 15 | 5 | 1 | 23.01% | 8.1449 | 0%
2037-05-16 | 2037 | 5 | May | 16 | 6 | 0 | 23.01% | 8.1449 | 0%
2037-05-17 | 2037 | 5 | May | 17 | 7 | 0 | 23.01% | 8.1449 | 0%
2037-05-18 | 2037 | 5 | May | 18 | 1 | 1 | 23.01% | 8.1449 | 0%
2037-05-19 | 2037 | 5 | May | 19 | 2 | 1 | 23.01% | 8.1449 | 0%
2037-05-20 | 2037 | 5 | May | 20 | 3 | 1 | 23.01% | 8.1449 | 0%
2037-05-21 | 2037 | 5 | May | 21 | 4 | 1 | 23.01% | 8.1449 | 0%
2037-05-22 | 2037 | 5 | May | 22 | 5 | 1 | 23.01% | 8.1449 | 0%
2037-05-23 | 2037 | 5 | May | 23 | 6 | 0 | 23.01% | 8.1449 | 0%
2037-05-24 | 2037 | 5 | May | 24 | 7 | 0 | 23.01% | 8.1449 | 0%
2037-05-25 | 2037 | 5 | May | 25 | 1 | 1 | 23.01% | 8.1449 | 0%
2037-05-26 | 2037 | 5 | May | 26 | 2 | 1 | 23.01% | 8.1449 | 0%
2037-05-27 | 2037 | 5 | May | 27 | 3 | 1 | 23.01% | 8.1449 | 0%
2037-05-28 | 2037 | 5 | May | 28 | 4 | 1 | 23.01% | 8.1449 | 0%
2037-05-29 | 2037 | 5 | May | 29 | 5 | 1 | 23.01% | 8.1449 | 0%
2037-05-30 | 2037 | 5 | May | 30 | 6 | 0 | 23.01% | 8.1449 | 0%
2037-05-31 | 2037 | 5 | May | 31 | 7 | 0 | 23.01% | 8.1449 | 0%
2037-06-01 | 2037 | 6 | Jun | 1 | 1 | 1 | 28.67% | 7.9419 | 0%
2037-06-02 | 2037 | 6 | Jun | 2 | 2 | 1 | 28.67% | 7.9419 | 0%
2037-06-03 | 2037 | 6 | Jun | 3 | 3 | 1 | 28.67% | 7.9419 | 0%
2037-06-04 | 2037 | 6 | Jun | 4 | 4 | 1 | 28.67% | 7.9419 | 0%
2037-06-05 | 2037 | 6 | Jun | 5 | 5 | 1 | 28.67% | 7.9419 | 0%
2037-06-06 | 2037 | 6 | Jun | 6 | 6 | 0 | 28.67% | 7.9419 | 0%
2037-06-07 | 2037 | 6 | Jun | 7 | 7 | 0 | 28.67% | 7.9419 | 0%
2037-06-08 | 2037 | 6 | Jun | 8 | 1 | 1 | 28.67% | 7.9419 | 0%
2037-06-09 | 2037 | 6 | Jun | 9 | 2 | 1 | 28.67% | 7.9419 | 0%
2037-06-10 | 2037 | 6 | Jun | 10 | 3 | 1 | 28.67% | 7.9419 | 0%
2037-06-11 | 2037 | 6 | Jun | 11 | 4 | 1 | 28.67% | 7.9419 | 0%
2037-06-12 | 2037 | 6 | Jun | 12 | 5 | 1 | 28.67% | 7.9419 | 0%
2037-06-13 | 2037 | 6 | Jun | 13 | 6 | 0 | 28.67% | 7.9419 | 0%
2037-06-14 | 2037 | 6 | Jun | 14 | 7 | 0 | 28.67% | 7.9419 | 0%
2037-06-15 | 2037 | 6 | Jun | 15 | 1 | 1 | 28.67% | 7.9419 | 0%
2037-06-16 | 2037 | 6 | Jun | 16 | 2 | 1 | 28.67% | 7.9419 | 0%
2037-06-17 | 2037 | 6 | Jun | 17 | 3 | 1 | 28.67% | 7.9419 | 0%
2037-06-18 | 2037 | 6 | Jun | 18 | 4 | 1 | 28.67% | 7.9419 | 0%
2037-06-19 | 2037 | 6 | Jun | 19 | 5 | 1 | 28.67% | 7.9419 | 0%
2037-06-20 | 2037 | 6 | Jun | 20 | 6 | 0 | 28.67% | 7.9419 | 0%
2037-06-21 | 2037 | 6 | Jun | 21 | 7 | 0 | 28.67% | 7.9419 | 0%
2037-06-22 | 2037 | 6 | Jun | 22 | 1 | 1 | 28.67% | 7.9419 | 0%
2037-06-23 | 2037 | 6 | Jun | 23 | 2 | 1 | 28.67% | 7.9419 | 0%
2037-06-24 | 2037 | 6 | Jun | 24 | 3 | 1 | 28.67% | 7.9419 | 0%
2037-06-25 | 2037 | 6 | Jun | 25 | 4 | 1 | 28.67% | 7.9419 | 0%
2037-06-26 | 2037 | 6 | Jun | 26 | 5 | 1 | 28.67% | 7.9419 | 0%
2037-06-27 | 2037 | 6 | Jun | 27 | 6 | 0 | 28.67% | 7.9419 | 0%
2037-06-28 | 2037 | 6 | Jun | 28 | 7 | 0 | 28.67% | 7.9419 | 0%
2037-06-29 | 2037 | 6 | Jun | 29 | 1 | 1 | 28.67% | 7.9419 | 0%
2037-06-30 | 2037 | 6 | Jun | 30 | 2 | 1 | 28.67% | 7.9419 | 0%
2037-07-01 | 2037 | 7 | Jul | 1 | 3 | 1 | 24.73% | 8.3739 | 0%
2037-07-02 | 2037 | 7 | Jul | 2 | 4 | 1 | 24.73% | 8.3739 | 0%
2037-07-03 | 2037 | 7 | Jul | 3 | 5 | 1 | 24.73% | 8.3739 | 0%
2037-07-04 | 2037 | 7 | Jul | 4 | 6 | 0 | 24.73% | 8.3739 | 0%
2037-07-05 | 2037 | 7 | Jul | 5 | 7 | 0 | 24.73% | 8.3739 | 0%
2037-07-06 | 2037 | 7 | Jul | 6 | 1 | 1 | 24.73% | 8.3739 | 0%
2037-07-07 | 2037 | 7 | Jul | 7 | 2 | 1 | 24.73% | 8.3739 | 0%
2037-07-08 | 2037 | 7 | Jul | 8 | 3 | 1 | 24.73% | 8.3739 | 0%
2037-07-09 | 2037 | 7 | Jul | 9 | 4 | 1 | 24.73% | 8.3739 | 0%
2037-07-10 | 2037 | 7 | Jul | 10 | 5 | 1 | 24.73% | 8.3739 | 0%
2037-07-11 | 2037 | 7 | Jul | 11 | 6 | 0 | 24.73% | 8.3739 | 0%
2037-07-12 | 2037 | 7 | Jul | 12 | 7 | 0 | 24.73% | 8.3739 | 0%
2037-07-13 | 2037 | 7 | Jul | 13 | 1 | 1 | 24.73% | 8.3739 | 0%
2037-07-14 | 2037 | 7 | Jul | 14 | 2 | 1 | 24.73% | 8.3739 | 0%
2037-07-15 | 2037 | 7 | Jul | 15 | 3 | 1 | 24.73% | 8.3739 | 0%
2037-07-16 | 2037 | 7 | Jul | 16 | 4 | 1 | 24.73% | 8.3739 | 0%
2037-07-17 | 2037 | 7 | Jul | 17 | 5 | 1 | 24.73% | 8.3739 | 0%
2037-07-18 | 2037 | 7 | Jul | 18 | 6 | 0 | 24.73% | 8.3739 | 0%
2037-07-19 | 2037 | 7 | Jul | 19 | 7 | 0 | 24.73% | 8.3739 | 0%
2037-07-20 | 2037 | 7 | Jul | 20 | 1 | 1 | 24.73% | 8.3739 | 0%
2037-07-21 | 2037 | 7 | Jul | 21 | 2 | 1 | 24.73% | 8.3739 | 0%
2037-07-22 | 2037 | 7 | Jul | 22 | 3 | 1 | 24.73% | 8.3739 | 0%
2037-07-23 | 2037 | 7 | Jul | 23 | 4 | 1 | 24.73% | 8.3739 | 0%
2037-07-24 | 2037 | 7 | Jul | 24 | 5 | 1 | 24.73% | 8.3739 | 0%
2037-07-25 | 2037 | 7 | Jul | 25 | 6 | 0 | 24.73% | 8.3739 | 0%
2037-07-26 | 2037 | 7 | Jul | 26 | 7 | 0 | 24.73% | 8.3739 | 0%
2037-07-27 | 2037 | 7 | Jul | 27 | 1 | 1 | 24.73% | 8.3739 | 0%
2037-07-28 | 2037 | 7 | Jul | 28 | 2 | 1 | 24.73% | 8.3739 | 0%
2037-07-29 | 2037 | 7 | Jul | 29 | 3 | 1 | 24.73% | 8.3739 | 0%
2037-07-30 | 2037 | 7 | Jul | 30 | 4 | 1 | 24.73% | 8.3739 | 0%
2037-07-31 | 2037 | 7 | Jul | 31 | 5 | 1 | 24.73% | 8.3739 | 0%
2037-08-01 | 2037 | 8 | Aug | 1 | 6 | 0 | 23.55% | 7.9589 | 0%
2037-08-02 | 2037 | 8 | Aug | 2 | 7 | 0 | 23.55% | 7.9589 | 0%
2037-08-03 | 2037 | 8 | Aug | 3 | 1 | 1 | 23.55% | 7.9589 | 0%
2037-08-04 | 2037 | 8 | Aug | 4 | 2 | 1 | 23.55% | 7.9589 | 0%
2037-08-05 | 2037 | 8 | Aug | 5 | 3 | 1 | 23.55% | 7.9589 | 0%
2037-08-06 | 2037 | 8 | Aug | 6 | 4 | 1 | 23.55% | 7.9589 | 0%
2037-08-07 | 2037 | 8 | Aug | 7 | 5 | 1 | 23.55% | 7.9589 | 0%
2037-08-08 | 2037 | 8 | Aug | 8 | 6 | 0 | 23.55% | 7.9589 | 0%
2037-08-09 | 2037 | 8 | Aug | 9 | 7 | 0 | 23.55% | 7.9589 | 0%
2037-08-10 | 2037 | 8 | Aug | 10 | 1 | 1 | 23.55% | 7.9589 | 0%
2037-08-11 | 2037 | 8 | Aug | 11 | 2 | 1 | 23.55% | 7.9589 | 0%
2037-08-12 | 2037 | 8 | Aug | 12 | 3 | 1 | 23.55% | 7.9589 | 0%
2037-08-13 | 2037 | 8 | Aug | 13 | 4 | 1 | 23.55% | 7.9589 | 0%
2037-08-14 | 2037 | 8 | Aug | 14 | 5 | 1 | 23.55% | 7.9589 | 0%
2037-08-15 | 2037 | 8 | Aug | 15 | 6 | 0 | 23.55% | 7.9589 | 0%
2037-08-16 | 2037 | 8 | Aug | 16 | 7 | 0 | 23.55% | 7.9589 | 0%
2037-08-17 | 2037 | 8 | Aug | 17 | 1 | 1 | 23.55% | 7.9589 | 0%
2037-08-18 | 2037 | 8 | Aug | 18 | 2 | 1 | 23.55% | 7.9589 | 0%
2037-08-19 | 2037 | 8 | Aug | 19 | 3 | 1 | 23.55% | 7.9589 | 0%
2037-08-20 | 2037 | 8 | Aug | 20 | 4 | 1 | 23.55% | 7.9589 | 0%
2037-08-21 | 2037 | 8 | Aug | 21 | 5 | 1 | 23.55% | 7.9589 | 0%
2037-08-22 | 2037 | 8 | Aug | 22 | 6 | 0 | 23.55% | 7.9589 | 0%
2037-08-23 | 2037 | 8 | Aug | 23 | 7 | 0 | 23.55% | 7.9589 | 0%
2037-08-24 | 2037 | 8 | Aug | 24 | 1 | 1 | 23.55% | 7.9589 | 0%
2037-08-25 | 2037 | 8 | Aug | 25 | 2 | 1 | 23.55% | 7.9589 | 0%
2037-08-26 | 2037 | 8 | Aug | 26 | 3 | 1 | 23.55% | 7.9589 | 0%
2037-08-27 | 2037 | 8 | Aug | 27 | 4 | 1 | 23.55% | 7.9589 | 0%
2037-08-28 | 2037 | 8 | Aug | 28 | 5 | 1 | 23.55% | 7.9589 | 0%
2037-08-29 | 2037 | 8 | Aug | 29 | 6 | 0 | 23.55% | 7.9589 | 0%
2037-08-30 | 2037 | 8 | Aug | 30 | 7 | 0 | 23.55% | 7.9589 | 0%
2037-08-31 | 2037 | 8 | Aug | 31 | 1 | 1 | 23.55% | 7.9589 | 0%
2037-09-01 | 2037 | 9 | Sep | 1 | 2 | 1 | 20.67% | 6.8065 | 0%
2037-09-02 | 2037 | 9 | Sep | 2 | 3 | 1 | 20.67% | 6.8065 | 0%
2037-09-03 | 2037 | 9 | Sep | 3 | 4 | 1 | 20.67% | 6.8065 | 0%
2037-09-04 | 2037 | 9 | Sep | 4 | 5 | 1 | 20.67% | 6.8065 | 0%
2037-09-05 | 2037 | 9 | Sep | 5 | 6 | 0 | 20.67% | 6.8065 | 0%
2037-09-06 | 2037 | 9 | Sep | 6 | 7 | 0 | 20.67% | 6.8065 | 0%
2037-09-07 | 2037 | 9 | Sep | 7 | 1 | 1 | 20.67% | 6.8065 | 0%
2037-09-08 | 2037 | 9 | Sep | 8 | 2 | 1 | 20.67% | 6.8065 | 0%
2037-09-09 | 2037 | 9 | Sep | 9 | 3 | 1 | 20.67% | 6.8065 | 0%
2037-09-10 | 2037 | 9 | Sep | 10 | 4 | 1 | 20.67% | 6.8065 | 0%
2037-09-11 | 2037 | 9 | Sep | 11 | 5 | 1 | 20.67% | 6.8065 | 0%
2037-09-12 | 2037 | 9 | Sep | 12 | 6 | 0 | 20.67% | 6.8065 | 0%
2037-09-13 | 2037 | 9 | Sep | 13 | 7 | 0 | 20.67% | 6.8065 | 0%
2037-09-14 | 2037 | 9 | Sep | 14 | 1 | 1 | 20.67% | 6.8065 | 0%
2037-09-15 | 2037 | 9 | Sep | 15 | 2 | 1 | 20.67% | 6.8065 | 0%
2037-09-16 | 2037 | 9 | Sep | 16 | 3 | 1 | 20.67% | 6.8065 | 0%
2037-09-17 | 2037 | 9 | Sep | 17 | 4 | 1 | 20.67% | 6.8065 | 0%
2037-09-18 | 2037 | 9 | Sep | 18 | 5 | 1 | 20.67% | 6.8065 | 0%
2037-09-19 | 2037 | 9 | Sep | 19 | 6 | 0 | 20.67% | 6.8065 | 0%
2037-09-20 | 2037 | 9 | Sep | 20 | 7 | 0 | 20.67% | 6.8065 | 0%
2037-09-21 | 2037 | 9 | Sep | 21 | 1 | 1 | 20.67% | 6.8065 | 0%
2037-09-22 | 2037 | 9 | Sep | 22 | 2 | 1 | 20.67% | 6.8065 | 0%
2037-09-23 | 2037 | 9 | Sep | 23 | 3 | 1 | 20.67% | 6.8065 | 0%
2037-09-24 | 2037 | 9 | Sep | 24 | 4 | 1 | 20.67% | 6.8065 | 0%
2037-09-25 | 2037 | 9 | Sep | 25 | 5 | 1 | 20.67% | 6.8065 | 0%
2037-09-26 | 2037 | 9 | Sep | 26 | 6 | 0 | 20.67% | 6.8065 | 0%
2037-09-27 | 2037 | 9 | Sep | 27 | 7 | 0 | 20.67% | 6.8065 | 0%
2037-09-28 | 2037 | 9 | Sep | 28 | 1 | 1 | 20.67% | 6.8065 | 0%
2037-09-29 | 2037 | 9 | Sep | 29 | 2 | 1 | 20.67% | 6.8065 | 0%
2037-09-30 | 2037 | 9 | Sep | 30 | 3 | 1 | 20.67% | 6.8065 | 0%
2037-10-01 | 2037 | 10 | Oct | 1 | 4 | 1 | 23.23% | 6.8194 | 0%
2037-10-02 | 2037 | 10 | Oct | 2 | 5 | 1 | 23.23% | 6.8194 | 0%
2037-10-03 | 2037 | 10 | Oct | 3 | 6 | 0 | 23.23% | 6.8194 | 0%
2037-10-04 | 2037 | 10 | Oct | 4 | 7 | 0 | 23.23% | 6.8194 | 0%
2037-10-05 | 2037 | 10 | Oct | 5 | 1 | 1 | 23.23% | 6.8194 | 0%
2037-10-06 | 2037 | 10 | Oct | 6 | 2 | 1 | 23.23% | 6.8194 | 0%
2037-10-07 | 2037 | 10 | Oct | 7 | 3 | 1 | 23.23% | 6.8194 | 0%
2037-10-08 | 2037 | 10 | Oct | 8 | 4 | 1 | 23.23% | 6.8194 | 0%
2037-10-09 | 2037 | 10 | Oct | 9 | 5 | 1 | 23.23% | 6.8194 | 0%
2037-10-10 | 2037 | 10 | Oct | 10 | 6 | 0 | 23.23% | 6.8194 | 0%
2037-10-11 | 2037 | 10 | Oct | 11 | 7 | 0 | 23.23% | 6.8194 | 0%
2037-10-12 | 2037 | 10 | Oct | 12 | 1 | 1 | 23.23% | 6.8194 | 0%
2037-10-13 | 2037 | 10 | Oct | 13 | 2 | 1 | 23.23% | 6.8194 | 0%
2037-10-14 | 2037 | 10 | Oct | 14 | 3 | 1 | 23.23% | 6.8194 | 0%
2037-10-15 | 2037 | 10 | Oct | 15 | 4 | 1 | 23.23% | 6.8194 | 0%
2037-10-16 | 2037 | 10 | Oct | 16 | 5 | 1 | 23.23% | 6.8194 | 0%
2037-10-17 | 2037 | 10 | Oct | 17 | 6 | 0 | 23.23% | 6.8194 | 0%
2037-10-18 | 2037 | 10 | Oct | 18 | 7 | 0 | 23.23% | 6.8194 | 0%
2037-10-19 | 2037 | 10 | Oct | 19 | 1 | 1 | 23.23% | 6.8194 | 0%
2037-10-20 | 2037 | 10 | Oct | 20 | 2 | 1 | 23.23% | 6.8194 | 0%
2037-10-21 | 2037 | 10 | Oct | 21 | 3 | 1 | 23.23% | 6.8194 | 0%
2037-10-22 | 2037 | 10 | Oct | 22 | 4 | 1 | 23.23% | 6.8194 | 0%
2037-10-23 | 2037 | 10 | Oct | 23 | 5 | 1 | 23.23% | 6.8194 | 0%
2037-10-24 | 2037 | 10 | Oct | 24 | 6 | 0 | 23.23% | 6.8194 | 0%
2037-10-25 | 2037 | 10 | Oct | 25 | 7 | 0 | 23.23% | 6.8194 | 0%
2037-10-26 | 2037 | 10 | Oct | 26 | 1 | 1 | 23.23% | 6.8194 | 0%
2037-10-27 | 2037 | 10 | Oct | 27 | 2 | 1 | 23.23% | 6.8194 | 0%
2037-10-28 | 2037 | 10 | Oct | 28 | 3 | 1 | 23.23% | 6.8194 | 0%
2037-10-29 | 2037 | 10 | Oct | 29 | 4 | 1 | 23.23% | 6.8194 | 0%
2037-10-30 | 2037 | 10 | Oct | 30 | 5 | 1 | 23.23% | 6.8194 | 0%
2037-10-31 | 2037 | 10 | Oct | 31 | 6 | 0 | 23.23% | 6.8194 | 0%
2037-11-01 | 2037 | 11 | Nov | 1 | 7 | 0 | 23.33% | 6.4429 | 0%
2037-11-02 | 2037 | 11 | Nov | 2 | 1 | 1 | 23.33% | 6.4429 | 0%
2037-11-03 | 2037 | 11 | Nov | 3 | 2 | 1 | 23.33% | 6.4429 | 0%
2037-11-04 | 2037 | 11 | Nov | 4 | 3 | 1 | 23.33% | 6.4429 | 0%
2037-11-05 | 2037 | 11 | Nov | 5 | 4 | 1 | 23.33% | 6.4429 | 0%
2037-11-06 | 2037 | 11 | Nov | 6 | 5 | 1 | 23.33% | 6.4429 | 0%
2037-11-07 | 2037 | 11 | Nov | 7 | 6 | 0 | 23.33% | 6.4429 | 0%
2037-11-08 | 2037 | 11 | Nov | 8 | 7 | 0 | 23.33% | 6.4429 | 0%
2037-11-09 | 2037 | 11 | Nov | 9 | 1 | 1 | 23.33% | 6.4429 | 0%
2037-11-10 | 2037 | 11 | Nov | 10 | 2 | 1 | 23.33% | 6.4429 | 0%
2037-11-11 | 2037 | 11 | Nov | 11 | 3 | 1 | 23.33% | 6.4429 | 0%
2037-11-12 | 2037 | 11 | Nov | 12 | 4 | 1 | 23.33% | 6.4429 | 0%
2037-11-13 | 2037 | 11 | Nov | 13 | 5 | 1 | 23.33% | 6.4429 | 0%
2037-11-14 | 2037 | 11 | Nov | 14 | 6 | 0 | 23.33% | 6.4429 | 0%
2037-11-15 | 2037 | 11 | Nov | 15 | 7 | 0 | 23.33% | 6.4429 | 0%
2037-11-16 | 2037 | 11 | Nov | 16 | 1 | 1 | 23.33% | 6.4429 | 0%
2037-11-17 | 2037 | 11 | Nov | 17 | 2 | 1 | 23.33% | 6.4429 | 0%
2037-11-18 | 2037 | 11 | Nov | 18 | 3 | 1 | 23.33% | 6.4429 | 0%
2037-11-19 | 2037 | 11 | Nov | 19 | 4 | 1 | 23.33% | 6.4429 | 0%
2037-11-20 | 2037 | 11 | Nov | 20 | 5 | 1 | 23.33% | 6.4429 | 0%
2037-11-21 | 2037 | 11 | Nov | 21 | 6 | 0 | 23.33% | 6.4429 | 0%
2037-11-22 | 2037 | 11 | Nov | 22 | 7 | 0 | 23.33% | 6.4429 | 0%
2037-11-23 | 2037 | 11 | Nov | 23 | 1 | 1 | 23.33% | 6.4429 | 0%
2037-11-24 | 2037 | 11 | Nov | 24 | 2 | 1 | 23.33% | 6.4429 | 0%
2037-11-25 | 2037 | 11 | Nov | 25 | 3 | 1 | 23.33% | 6.4429 | 0%
2037-11-26 | 2037 | 11 | Nov | 26 | 4 | 1 | 23.33% | 6.4429 | 0%
2037-11-27 | 2037 | 11 | Nov | 27 | 5 | 1 | 23.33% | 6.4429 | 0%
2037-11-28 | 2037 | 11 | Nov | 28 | 6 | 0 | 23.33% | 6.4429 | 0%
2037-11-29 | 2037 | 11 | Nov | 29 | 7 | 0 | 23.33% | 6.4429 | 0%
2037-11-30 | 2037 | 11 | Nov | 30 | 1 | 1 | 23.33% | 6.4429 | 0%
2037-12-01 | 2037 | 12 | Dec | 1 | 2 | 1 | 22.69% | 6.7962 | 0%
2037-12-02 | 2037 | 12 | Dec | 2 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-12-03 | 2037 | 12 | Dec | 3 | 4 | 1 | 22.69% | 6.7962 | 0%
2037-12-04 | 2037 | 12 | Dec | 4 | 5 | 1 | 22.69% | 6.7962 | 0%
2037-12-05 | 2037 | 12 | Dec | 5 | 6 | 0 | 22.69% | 6.7962 | 0%
2037-12-06 | 2037 | 12 | Dec | 6 | 7 | 0 | 22.69% | 6.7962 | 0%
2037-12-07 | 2037 | 12 | Dec | 7 | 1 | 1 | 22.69% | 6.7962 | 0%
2037-12-08 | 2037 | 12 | Dec | 8 | 2 | 1 | 22.69% | 6.7962 | 0%
2037-12-09 | 2037 | 12 | Dec | 9 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-12-10 | 2037 | 12 | Dec | 10 | 4 | 1 | 22.69% | 6.7962 | 0%
2037-12-11 | 2037 | 12 | Dec | 11 | 5 | 1 | 22.69% | 6.7962 | 0%
2037-12-12 | 2037 | 12 | Dec | 12 | 6 | 0 | 22.69% | 6.7962 | 0%
2037-12-13 | 2037 | 12 | Dec | 13 | 7 | 0 | 22.69% | 6.7962 | 0%
2037-12-14 | 2037 | 12 | Dec | 14 | 1 | 1 | 22.69% | 6.7962 | 0%
2037-12-15 | 2037 | 12 | Dec | 15 | 2 | 1 | 22.69% | 6.7962 | 0%
2037-12-16 | 2037 | 12 | Dec | 16 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-12-17 | 2037 | 12 | Dec | 17 | 4 | 1 | 22.69% | 6.7962 | 0%
2037-12-18 | 2037 | 12 | Dec | 18 | 5 | 1 | 22.69% | 6.7962 | 0%
2037-12-19 | 2037 | 12 | Dec | 19 | 6 | 0 | 22.69% | 6.7962 | 0%
2037-12-20 | 2037 | 12 | Dec | 20 | 7 | 0 | 22.69% | 6.7962 | 0%
2037-12-21 | 2037 | 12 | Dec | 21 | 1 | 1 | 22.69% | 6.7962 | 0%
2037-12-22 | 2037 | 12 | Dec | 22 | 2 | 1 | 22.69% | 6.7962 | 0%
2037-12-23 | 2037 | 12 | Dec | 23 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-12-24 | 2037 | 12 | Dec | 24 | 4 | 1 | 22.69% | 6.7962 | 0%
2037-12-25 | 2037 | 12 | Dec | 25 | 5 | 1 | 22.69% | 6.7962 | 0%
2037-12-26 | 2037 | 12 | Dec | 26 | 6 | 0 | 22.69% | 6.7962 | 0%
2037-12-27 | 2037 | 12 | Dec | 27 | 7 | 0 | 22.69% | 6.7962 | 0%
2037-12-28 | 2037 | 12 | Dec | 28 | 1 | 1 | 22.69% | 6.7962 | 0%
2037-12-29 | 2037 | 12 | Dec | 29 | 2 | 1 | 22.69% | 6.7962 | 0%
2037-12-30 | 2037 | 12 | Dec | 30 | 3 | 1 | 22.69% | 6.7962 | 0%
2037-12-31 | 2037 | 12 | Dec | 31 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-01-01 | 2038 | 1 | Jan | 1 | 5 | 1 | 19.46% | 7.0276 | 0%
2038-01-02 | 2038 | 1 | Jan | 2 | 6 | 0 | 19.46% | 7.0276 | 0%
2038-01-03 | 2038 | 1 | Jan | 3 | 7 | 0 | 19.46% | 7.0276 | 0%
2038-01-04 | 2038 | 1 | Jan | 4 | 1 | 1 | 19.46% | 7.0276 | 0%
2038-01-05 | 2038 | 1 | Jan | 5 | 2 | 1 | 19.46% | 7.0276 | 0%
2038-01-06 | 2038 | 1 | Jan | 6 | 3 | 1 | 19.46% | 7.0276 | 0%
2038-01-07 | 2038 | 1 | Jan | 7 | 4 | 1 | 19.46% | 7.0276 | 0%
2038-01-08 | 2038 | 1 | Jan | 8 | 5 | 1 | 19.46% | 7.0276 | 0%
2038-01-09 | 2038 | 1 | Jan | 9 | 6 | 0 | 19.46% | 7.0276 | 0%
2038-01-10 | 2038 | 1 | Jan | 10 | 7 | 0 | 19.46% | 7.0276 | 0%
2038-01-11 | 2038 | 1 | Jan | 11 | 1 | 1 | 19.46% | 7.0276 | 0%
2038-01-12 | 2038 | 1 | Jan | 12 | 2 | 1 | 19.46% | 7.0276 | 0%
2038-01-13 | 2038 | 1 | Jan | 13 | 3 | 1 | 19.46% | 7.0276 | 0%
2038-01-14 | 2038 | 1 | Jan | 14 | 4 | 1 | 19.46% | 7.0276 | 0%
2038-01-15 | 2038 | 1 | Jan | 15 | 5 | 1 | 19.46% | 7.0276 | 0%
2038-01-16 | 2038 | 1 | Jan | 16 | 6 | 0 | 19.46% | 7.0276 | 0%
2038-01-17 | 2038 | 1 | Jan | 17 | 7 | 0 | 19.46% | 7.0276 | 0%
2038-01-18 | 2038 | 1 | Jan | 18 | 1 | 1 | 19.46% | 7.0276 | 0%
2038-01-19 | 2038 | 1 | Jan | 19 | 2 | 1 | 19.46% | 7.0276 | 0%
2038-01-20 | 2038 | 1 | Jan | 20 | 3 | 1 | 19.46% | 7.0276 | 0%
2038-01-21 | 2038 | 1 | Jan | 21 | 4 | 1 | 19.46% | 7.0276 | 0%
2038-01-22 | 2038 | 1 | Jan | 22 | 5 | 1 | 19.46% | 7.0276 | 0%
2038-01-23 | 2038 | 1 | Jan | 23 | 6 | 0 | 19.46% | 7.0276 | 0%
2038-01-24 | 2038 | 1 | Jan | 24 | 7 | 0 | 19.46% | 7.0276 | 0%
2038-01-25 | 2038 | 1 | Jan | 25 | 1 | 1 | 19.46% | 7.0276 | 0%
2038-01-26 | 2038 | 1 | Jan | 26 | 2 | 1 | 19.46% | 7.0276 | 0%
2038-01-27 | 2038 | 1 | Jan | 27 | 3 | 1 | 19.46% | 7.0276 | 0%
2038-01-28 | 2038 | 1 | Jan | 28 | 4 | 1 | 19.46% | 7.0276 | 0%
2038-01-29 | 2038 | 1 | Jan | 29 | 5 | 1 | 19.46% | 7.0276 | 0%
2038-01-30 | 2038 | 1 | Jan | 30 | 6 | 0 | 19.46% | 7.0276 | 0%
2038-01-31 | 2038 | 1 | Jan | 31 | 7 | 0 | 19.46% | 7.0276 | 0%
2038-02-01 | 2038 | 2 | Feb | 1 | 1 | 1 | 18.87% | 7.4625 | 0%
2038-02-02 | 2038 | 2 | Feb | 2 | 2 | 1 | 18.87% | 7.4625 | 0%
2038-02-03 | 2038 | 2 | Feb | 3 | 3 | 1 | 18.87% | 7.4625 | 0%
2038-02-04 | 2038 | 2 | Feb | 4 | 4 | 1 | 18.87% | 7.4625 | 0%
2038-02-05 | 2038 | 2 | Feb | 5 | 5 | 1 | 18.87% | 7.4625 | 0%
2038-02-06 | 2038 | 2 | Feb | 6 | 6 | 0 | 18.87% | 7.4625 | 0%
2038-02-07 | 2038 | 2 | Feb | 7 | 7 | 0 | 18.87% | 7.4625 | 0%
2038-02-08 | 2038 | 2 | Feb | 8 | 1 | 1 | 18.87% | 7.4625 | 0%
2038-02-09 | 2038 | 2 | Feb | 9 | 2 | 1 | 18.87% | 7.4625 | 0%
2038-02-10 | 2038 | 2 | Feb | 10 | 3 | 1 | 18.87% | 7.4625 | 0%
2038-02-11 | 2038 | 2 | Feb | 11 | 4 | 1 | 18.87% | 7.4625 | 0%
2038-02-12 | 2038 | 2 | Feb | 12 | 5 | 1 | 18.87% | 7.4625 | 0%
2038-02-13 | 2038 | 2 | Feb | 13 | 6 | 0 | 18.87% | 7.4625 | 0%
2038-02-14 | 2038 | 2 | Feb | 14 | 7 | 0 | 18.87% | 7.4625 | 0%
2038-02-15 | 2038 | 2 | Feb | 15 | 1 | 1 | 18.87% | 7.4625 | 0%
2038-02-16 | 2038 | 2 | Feb | 16 | 2 | 1 | 18.87% | 7.4625 | 0%
2038-02-17 | 2038 | 2 | Feb | 17 | 3 | 1 | 18.87% | 7.4625 | 0%
2038-02-18 | 2038 | 2 | Feb | 18 | 4 | 1 | 18.87% | 7.4625 | 0%
2038-02-19 | 2038 | 2 | Feb | 19 | 5 | 1 | 18.87% | 7.4625 | 0%
2038-02-20 | 2038 | 2 | Feb | 20 | 6 | 0 | 18.87% | 7.4625 | 0%
2038-02-21 | 2038 | 2 | Feb | 21 | 7 | 0 | 18.87% | 7.4625 | 0%
2038-02-22 | 2038 | 2 | Feb | 22 | 1 | 1 | 18.87% | 7.4625 | 0%
2038-02-23 | 2038 | 2 | Feb | 23 | 2 | 1 | 18.87% | 7.4625 | 0%
2038-02-24 | 2038 | 2 | Feb | 24 | 3 | 1 | 18.87% | 7.4625 | 0%
2038-02-25 | 2038 | 2 | Feb | 25 | 4 | 1 | 18.87% | 7.4625 | 0%
2038-02-26 | 2038 | 2 | Feb | 26 | 5 | 1 | 18.87% | 7.4625 | 0%
2038-02-27 | 2038 | 2 | Feb | 27 | 6 | 0 | 18.87% | 7.4625 | 0%
2038-02-28 | 2038 | 2 | Feb | 28 | 7 | 0 | 18.87% | 7.4625 | 0%
2038-03-01 | 2038 | 3 | Mar | 1 | 1 | 1 | 18.49% | 7.8663 | 0%
2038-03-02 | 2038 | 3 | Mar | 2 | 2 | 1 | 18.49% | 7.8663 | 0%
2038-03-03 | 2038 | 3 | Mar | 3 | 3 | 1 | 18.49% | 7.8663 | 0%
2038-03-04 | 2038 | 3 | Mar | 4 | 4 | 1 | 18.49% | 7.8663 | 0%
2038-03-05 | 2038 | 3 | Mar | 5 | 5 | 1 | 18.49% | 7.8663 | 0%
2038-03-06 | 2038 | 3 | Mar | 6 | 6 | 0 | 18.49% | 7.8663 | 0%
2038-03-07 | 2038 | 3 | Mar | 7 | 7 | 0 | 18.49% | 7.8663 | 0%
2038-03-08 | 2038 | 3 | Mar | 8 | 1 | 1 | 18.49% | 7.8663 | 0%
2038-03-09 | 2038 | 3 | Mar | 9 | 2 | 1 | 18.49% | 7.8663 | 0%
2038-03-10 | 2038 | 3 | Mar | 10 | 3 | 1 | 18.49% | 7.8663 | 0%
2038-03-11 | 2038 | 3 | Mar | 11 | 4 | 1 | 18.49% | 7.8663 | 0%
2038-03-12 | 2038 | 3 | Mar | 12 | 5 | 1 | 18.49% | 7.8663 | 0%
2038-03-13 | 2038 | 3 | Mar | 13 | 6 | 0 | 18.49% | 7.8663 | 0%
2038-03-14 | 2038 | 3 | Mar | 14 | 7 | 0 | 18.49% | 7.8663 | 0%
2038-03-15 | 2038 | 3 | Mar | 15 | 1 | 1 | 18.49% | 7.8663 | 0%
2038-03-16 | 2038 | 3 | Mar | 16 | 2 | 1 | 18.49% | 7.8663 | 0%
2038-03-17 | 2038 | 3 | Mar | 17 | 3 | 1 | 18.49% | 7.8663 | 0%
2038-03-18 | 2038 | 3 | Mar | 18 | 4 | 1 | 18.49% | 7.8663 | 0%
2038-03-19 | 2038 | 3 | Mar | 19 | 5 | 1 | 18.49% | 7.8663 | 0%
2038-03-20 | 2038 | 3 | Mar | 20 | 6 | 0 | 18.49% | 7.8663 | 0%
2038-03-21 | 2038 | 3 | Mar | 21 | 7 | 0 | 18.49% | 7.8663 | 0%
2038-03-22 | 2038 | 3 | Mar | 22 | 1 | 1 | 18.49% | 7.8663 | 0%
2038-03-23 | 2038 | 3 | Mar | 23 | 2 | 1 | 18.49% | 7.8663 | 0%
2038-03-24 | 2038 | 3 | Mar | 24 | 3 | 1 | 18.49% | 7.8663 | 0%
2038-03-25 | 2038 | 3 | Mar | 25 | 4 | 1 | 18.49% | 7.8663 | 0%
2038-03-26 | 2038 | 3 | Mar | 26 | 5 | 1 | 18.49% | 7.8663 | 0%
2038-03-27 | 2038 | 3 | Mar | 27 | 6 | 0 | 18.49% | 7.8663 | 0%
2038-03-28 | 2038 | 3 | Mar | 28 | 7 | 0 | 18.49% | 7.8663 | 0%
2038-03-29 | 2038 | 3 | Mar | 29 | 1 | 1 | 18.49% | 7.8663 | 0%
2038-03-30 | 2038 | 3 | Mar | 30 | 2 | 1 | 18.49% | 7.8663 | 0%
2038-03-31 | 2038 | 3 | Mar | 31 | 3 | 1 | 18.49% | 7.8663 | 0%
2038-04-01 | 2038 | 4 | Apr | 1 | 4 | 1 | 25.56% | 7.5 | 0%
2038-04-02 | 2038 | 4 | Apr | 2 | 5 | 1 | 25.56% | 7.5 | 0%
2038-04-03 | 2038 | 4 | Apr | 3 | 6 | 0 | 25.56% | 7.5 | 0%
2038-04-04 | 2038 | 4 | Apr | 4 | 7 | 0 | 25.56% | 7.5 | 0%
2038-04-05 | 2038 | 4 | Apr | 5 | 1 | 1 | 25.56% | 7.5 | 0%
2038-04-06 | 2038 | 4 | Apr | 6 | 2 | 1 | 25.56% | 7.5 | 0%
2038-04-07 | 2038 | 4 | Apr | 7 | 3 | 1 | 25.56% | 7.5 | 0%
2038-04-08 | 2038 | 4 | Apr | 8 | 4 | 1 | 25.56% | 7.5 | 0%
2038-04-09 | 2038 | 4 | Apr | 9 | 5 | 1 | 25.56% | 7.5 | 0%
2038-04-10 | 2038 | 4 | Apr | 10 | 6 | 0 | 25.56% | 7.5 | 0%
2038-04-11 | 2038 | 4 | Apr | 11 | 7 | 0 | 25.56% | 7.5 | 0%
2038-04-12 | 2038 | 4 | Apr | 12 | 1 | 1 | 25.56% | 7.5 | 0%
2038-04-13 | 2038 | 4 | Apr | 13 | 2 | 1 | 25.56% | 7.5 | 0%
2038-04-14 | 2038 | 4 | Apr | 14 | 3 | 1 | 25.56% | 7.5 | 0%
2038-04-15 | 2038 | 4 | Apr | 15 | 4 | 1 | 25.56% | 7.5 | 0%
2038-04-16 | 2038 | 4 | Apr | 16 | 5 | 1 | 25.56% | 7.5 | 0%
2038-04-17 | 2038 | 4 | Apr | 17 | 6 | 0 | 25.56% | 7.5 | 0%
2038-04-18 | 2038 | 4 | Apr | 18 | 7 | 0 | 25.56% | 7.5 | 0%
2038-04-19 | 2038 | 4 | Apr | 19 | 1 | 1 | 25.56% | 7.5 | 0%
2038-04-20 | 2038 | 4 | Apr | 20 | 2 | 1 | 25.56% | 7.5 | 0%
2038-04-21 | 2038 | 4 | Apr | 21 | 3 | 1 | 25.56% | 7.5 | 0%
2038-04-22 | 2038 | 4 | Apr | 22 | 4 | 1 | 25.56% | 7.5 | 0%
2038-04-23 | 2038 | 4 | Apr | 23 | 5 | 1 | 25.56% | 7.5 | 0%
2038-04-24 | 2038 | 4 | Apr | 24 | 6 | 0 | 25.56% | 7.5 | 0%
2038-04-25 | 2038 | 4 | Apr | 25 | 7 | 0 | 25.56% | 7.5 | 0%
2038-04-26 | 2038 | 4 | Apr | 26 | 1 | 1 | 25.56% | 7.5 | 0%
2038-04-27 | 2038 | 4 | Apr | 27 | 2 | 1 | 25.56% | 7.5 | 0%
2038-04-28 | 2038 | 4 | Apr | 28 | 3 | 1 | 25.56% | 7.5 | 0%
2038-04-29 | 2038 | 4 | Apr | 29 | 4 | 1 | 25.56% | 7.5 | 0%
2038-04-30 | 2038 | 4 | Apr | 30 | 5 | 1 | 25.56% | 7.5 | 0%
2038-05-01 | 2038 | 5 | May | 1 | 6 | 0 | 23.01% | 8.1449 | 0%
2038-05-02 | 2038 | 5 | May | 2 | 7 | 0 | 23.01% | 8.1449 | 0%
2038-05-03 | 2038 | 5 | May | 3 | 1 | 1 | 23.01% | 8.1449 | 0%
2038-05-04 | 2038 | 5 | May | 4 | 2 | 1 | 23.01% | 8.1449 | 0%
2038-05-05 | 2038 | 5 | May | 5 | 3 | 1 | 23.01% | 8.1449 | 0%
2038-05-06 | 2038 | 5 | May | 6 | 4 | 1 | 23.01% | 8.1449 | 0%
2038-05-07 | 2038 | 5 | May | 7 | 5 | 1 | 23.01% | 8.1449 | 0%
2038-05-08 | 2038 | 5 | May | 8 | 6 | 0 | 23.01% | 8.1449 | 0%
2038-05-09 | 2038 | 5 | May | 9 | 7 | 0 | 23.01% | 8.1449 | 0%
2038-05-10 | 2038 | 5 | May | 10 | 1 | 1 | 23.01% | 8.1449 | 0%
2038-05-11 | 2038 | 5 | May | 11 | 2 | 1 | 23.01% | 8.1449 | 0%
2038-05-12 | 2038 | 5 | May | 12 | 3 | 1 | 23.01% | 8.1449 | 0%
2038-05-13 | 2038 | 5 | May | 13 | 4 | 1 | 23.01% | 8.1449 | 0%
2038-05-14 | 2038 | 5 | May | 14 | 5 | 1 | 23.01% | 8.1449 | 0%
2038-05-15 | 2038 | 5 | May | 15 | 6 | 0 | 23.01% | 8.1449 | 0%
2038-05-16 | 2038 | 5 | May | 16 | 7 | 0 | 23.01% | 8.1449 | 0%
2038-05-17 | 2038 | 5 | May | 17 | 1 | 1 | 23.01% | 8.1449 | 0%
2038-05-18 | 2038 | 5 | May | 18 | 2 | 1 | 23.01% | 8.1449 | 0%
2038-05-19 | 2038 | 5 | May | 19 | 3 | 1 | 23.01% | 8.1449 | 0%
2038-05-20 | 2038 | 5 | May | 20 | 4 | 1 | 23.01% | 8.1449 | 0%
2038-05-21 | 2038 | 5 | May | 21 | 5 | 1 | 23.01% | 8.1449 | 0%
2038-05-22 | 2038 | 5 | May | 22 | 6 | 0 | 23.01% | 8.1449 | 0%
2038-05-23 | 2038 | 5 | May | 23 | 7 | 0 | 23.01% | 8.1449 | 0%
2038-05-24 | 2038 | 5 | May | 24 | 1 | 1 | 23.01% | 8.1449 | 0%
2038-05-25 | 2038 | 5 | May | 25 | 2 | 1 | 23.01% | 8.1449 | 0%
2038-05-26 | 2038 | 5 | May | 26 | 3 | 1 | 23.01% | 8.1449 | 0%
2038-05-27 | 2038 | 5 | May | 27 | 4 | 1 | 23.01% | 8.1449 | 0%
2038-05-28 | 2038 | 5 | May | 28 | 5 | 1 | 23.01% | 8.1449 | 0%
2038-05-29 | 2038 | 5 | May | 29 | 6 | 0 | 23.01% | 8.1449 | 0%
2038-05-30 | 2038 | 5 | May | 30 | 7 | 0 | 23.01% | 8.1449 | 0%
2038-05-31 | 2038 | 5 | May | 31 | 1 | 1 | 23.01% | 8.1449 | 0%
2038-06-01 | 2038 | 6 | Jun | 1 | 2 | 1 | 28.67% | 7.9419 | 0%
2038-06-02 | 2038 | 6 | Jun | 2 | 3 | 1 | 28.67% | 7.9419 | 0%
2038-06-03 | 2038 | 6 | Jun | 3 | 4 | 1 | 28.67% | 7.9419 | 0%
2038-06-04 | 2038 | 6 | Jun | 4 | 5 | 1 | 28.67% | 7.9419 | 0%
2038-06-05 | 2038 | 6 | Jun | 5 | 6 | 0 | 28.67% | 7.9419 | 0%
2038-06-06 | 2038 | 6 | Jun | 6 | 7 | 0 | 28.67% | 7.9419 | 0%
2038-06-07 | 2038 | 6 | Jun | 7 | 1 | 1 | 28.67% | 7.9419 | 0%
2038-06-08 | 2038 | 6 | Jun | 8 | 2 | 1 | 28.67% | 7.9419 | 0%
2038-06-09 | 2038 | 6 | Jun | 9 | 3 | 1 | 28.67% | 7.9419 | 0%
2038-06-10 | 2038 | 6 | Jun | 10 | 4 | 1 | 28.67% | 7.9419 | 0%
2038-06-11 | 2038 | 6 | Jun | 11 | 5 | 1 | 28.67% | 7.9419 | 0%
2038-06-12 | 2038 | 6 | Jun | 12 | 6 | 0 | 28.67% | 7.9419 | 0%
2038-06-13 | 2038 | 6 | Jun | 13 | 7 | 0 | 28.67% | 7.9419 | 0%
2038-06-14 | 2038 | 6 | Jun | 14 | 1 | 1 | 28.67% | 7.9419 | 0%
2038-06-15 | 2038 | 6 | Jun | 15 | 2 | 1 | 28.67% | 7.9419 | 0%
2038-06-16 | 2038 | 6 | Jun | 16 | 3 | 1 | 28.67% | 7.9419 | 0%
2038-06-17 | 2038 | 6 | Jun | 17 | 4 | 1 | 28.67% | 7.9419 | 0%
2038-06-18 | 2038 | 6 | Jun | 18 | 5 | 1 | 28.67% | 7.9419 | 0%
2038-06-19 | 2038 | 6 | Jun | 19 | 6 | 0 | 28.67% | 7.9419 | 0%
2038-06-20 | 2038 | 6 | Jun | 20 | 7 | 0 | 28.67% | 7.9419 | 0%
2038-06-21 | 2038 | 6 | Jun | 21 | 1 | 1 | 28.67% | 7.9419 | 0%
2038-06-22 | 2038 | 6 | Jun | 22 | 2 | 1 | 28.67% | 7.9419 | 0%
2038-06-23 | 2038 | 6 | Jun | 23 | 3 | 1 | 28.67% | 7.9419 | 0%
2038-06-24 | 2038 | 6 | Jun | 24 | 4 | 1 | 28.67% | 7.9419 | 0%
2038-06-25 | 2038 | 6 | Jun | 25 | 5 | 1 | 28.67% | 7.9419 | 0%
2038-06-26 | 2038 | 6 | Jun | 26 | 6 | 0 | 28.67% | 7.9419 | 0%
2038-06-27 | 2038 | 6 | Jun | 27 | 7 | 0 | 28.67% | 7.9419 | 0%
2038-06-28 | 2038 | 6 | Jun | 28 | 1 | 1 | 28.67% | 7.9419 | 0%
2038-06-29 | 2038 | 6 | Jun | 29 | 2 | 1 | 28.67% | 7.9419 | 0%
2038-06-30 | 2038 | 6 | Jun | 30 | 3 | 1 | 28.67% | 7.9419 | 0%
2038-07-01 | 2038 | 7 | Jul | 1 | 4 | 1 | 24.73% | 8.3739 | 0%
2038-07-02 | 2038 | 7 | Jul | 2 | 5 | 1 | 24.73% | 8.3739 | 0%
2038-07-03 | 2038 | 7 | Jul | 3 | 6 | 0 | 24.73% | 8.3739 | 0%
2038-07-04 | 2038 | 7 | Jul | 4 | 7 | 0 | 24.73% | 8.3739 | 0%
2038-07-05 | 2038 | 7 | Jul | 5 | 1 | 1 | 24.73% | 8.3739 | 0%
2038-07-06 | 2038 | 7 | Jul | 6 | 2 | 1 | 24.73% | 8.3739 | 0%
2038-07-07 | 2038 | 7 | Jul | 7 | 3 | 1 | 24.73% | 8.3739 | 0%
2038-07-08 | 2038 | 7 | Jul | 8 | 4 | 1 | 24.73% | 8.3739 | 0%
2038-07-09 | 2038 | 7 | Jul | 9 | 5 | 1 | 24.73% | 8.3739 | 0%
2038-07-10 | 2038 | 7 | Jul | 10 | 6 | 0 | 24.73% | 8.3739 | 0%
2038-07-11 | 2038 | 7 | Jul | 11 | 7 | 0 | 24.73% | 8.3739 | 0%
2038-07-12 | 2038 | 7 | Jul | 12 | 1 | 1 | 24.73% | 8.3739 | 0%
2038-07-13 | 2038 | 7 | Jul | 13 | 2 | 1 | 24.73% | 8.3739 | 0%
2038-07-14 | 2038 | 7 | Jul | 14 | 3 | 1 | 24.73% | 8.3739 | 0%
2038-07-15 | 2038 | 7 | Jul | 15 | 4 | 1 | 24.73% | 8.3739 | 0%
2038-07-16 | 2038 | 7 | Jul | 16 | 5 | 1 | 24.73% | 8.3739 | 0%
2038-07-17 | 2038 | 7 | Jul | 17 | 6 | 0 | 24.73% | 8.3739 | 0%
2038-07-18 | 2038 | 7 | Jul | 18 | 7 | 0 | 24.73% | 8.3739 | 0%
2038-07-19 | 2038 | 7 | Jul | 19 | 1 | 1 | 24.73% | 8.3739 | 0%
2038-07-20 | 2038 | 7 | Jul | 20 | 2 | 1 | 24.73% | 8.3739 | 0%
2038-07-21 | 2038 | 7 | Jul | 21 | 3 | 1 | 24.73% | 8.3739 | 0%
2038-07-22 | 2038 | 7 | Jul | 22 | 4 | 1 | 24.73% | 8.3739 | 0%
2038-07-23 | 2038 | 7 | Jul | 23 | 5 | 1 | 24.73% | 8.3739 | 0%
2038-07-24 | 2038 | 7 | Jul | 24 | 6 | 0 | 24.73% | 8.3739 | 0%
2038-07-25 | 2038 | 7 | Jul | 25 | 7 | 0 | 24.73% | 8.3739 | 0%
2038-07-26 | 2038 | 7 | Jul | 26 | 1 | 1 | 24.73% | 8.3739 | 0%
2038-07-27 | 2038 | 7 | Jul | 27 | 2 | 1 | 24.73% | 8.3739 | 0%
2038-07-28 | 2038 | 7 | Jul | 28 | 3 | 1 | 24.73% | 8.3739 | 0%
2038-07-29 | 2038 | 7 | Jul | 29 | 4 | 1 | 24.73% | 8.3739 | 0%
2038-07-30 | 2038 | 7 | Jul | 30 | 5 | 1 | 24.73% | 8.3739 | 0%
2038-07-31 | 2038 | 7 | Jul | 31 | 6 | 0 | 24.73% | 8.3739 | 0%
2038-08-01 | 2038 | 8 | Aug | 1 | 7 | 0 | 23.55% | 7.9589 | 0%
2038-08-02 | 2038 | 8 | Aug | 2 | 1 | 1 | 23.55% | 7.9589 | 0%
2038-08-03 | 2038 | 8 | Aug | 3 | 2 | 1 | 23.55% | 7.9589 | 0%
2038-08-04 | 2038 | 8 | Aug | 4 | 3 | 1 | 23.55% | 7.9589 | 0%
2038-08-05 | 2038 | 8 | Aug | 5 | 4 | 1 | 23.55% | 7.9589 | 0%
2038-08-06 | 2038 | 8 | Aug | 6 | 5 | 1 | 23.55% | 7.9589 | 0%
2038-08-07 | 2038 | 8 | Aug | 7 | 6 | 0 | 23.55% | 7.9589 | 0%
2038-08-08 | 2038 | 8 | Aug | 8 | 7 | 0 | 23.55% | 7.9589 | 0%
2038-08-09 | 2038 | 8 | Aug | 9 | 1 | 1 | 23.55% | 7.9589 | 0%
2038-08-10 | 2038 | 8 | Aug | 10 | 2 | 1 | 23.55% | 7.9589 | 0%
2038-08-11 | 2038 | 8 | Aug | 11 | 3 | 1 | 23.55% | 7.9589 | 0%
2038-08-12 | 2038 | 8 | Aug | 12 | 4 | 1 | 23.55% | 7.9589 | 0%
2038-08-13 | 2038 | 8 | Aug | 13 | 5 | 1 | 23.55% | 7.9589 | 0%
2038-08-14 | 2038 | 8 | Aug | 14 | 6 | 0 | 23.55% | 7.9589 | 0%
2038-08-15 | 2038 | 8 | Aug | 15 | 7 | 0 | 23.55% | 7.9589 | 0%
2038-08-16 | 2038 | 8 | Aug | 16 | 1 | 1 | 23.55% | 7.9589 | 0%
2038-08-17 | 2038 | 8 | Aug | 17 | 2 | 1 | 23.55% | 7.9589 | 0%
2038-08-18 | 2038 | 8 | Aug | 18 | 3 | 1 | 23.55% | 7.9589 | 0%
2038-08-19 | 2038 | 8 | Aug | 19 | 4 | 1 | 23.55% | 7.9589 | 0%
2038-08-20 | 2038 | 8 | Aug | 20 | 5 | 1 | 23.55% | 7.9589 | 0%
2038-08-21 | 2038 | 8 | Aug | 21 | 6 | 0 | 23.55% | 7.9589 | 0%
2038-08-22 | 2038 | 8 | Aug | 22 | 7 | 0 | 23.55% | 7.9589 | 0%
2038-08-23 | 2038 | 8 | Aug | 23 | 1 | 1 | 23.55% | 7.9589 | 0%
2038-08-24 | 2038 | 8 | Aug | 24 | 2 | 1 | 23.55% | 7.9589 | 0%
2038-08-25 | 2038 | 8 | Aug | 25 | 3 | 1 | 23.55% | 7.9589 | 0%
2038-08-26 | 2038 | 8 | Aug | 26 | 4 | 1 | 23.55% | 7.9589 | 0%
2038-08-27 | 2038 | 8 | Aug | 27 | 5 | 1 | 23.55% | 7.9589 | 0%
2038-08-28 | 2038 | 8 | Aug | 28 | 6 | 0 | 23.55% | 7.9589 | 0%
2038-08-29 | 2038 | 8 | Aug | 29 | 7 | 0 | 23.55% | 7.9589 | 0%
2038-08-30 | 2038 | 8 | Aug | 30 | 1 | 1 | 23.55% | 7.9589 | 0%
2038-08-31 | 2038 | 8 | Aug | 31 | 2 | 1 | 23.55% | 7.9589 | 0%
2038-09-01 | 2038 | 9 | Sep | 1 | 3 | 1 | 20.67% | 6.8065 | 0%
2038-09-02 | 2038 | 9 | Sep | 2 | 4 | 1 | 20.67% | 6.8065 | 0%
2038-09-03 | 2038 | 9 | Sep | 3 | 5 | 1 | 20.67% | 6.8065 | 0%
2038-09-04 | 2038 | 9 | Sep | 4 | 6 | 0 | 20.67% | 6.8065 | 0%
2038-09-05 | 2038 | 9 | Sep | 5 | 7 | 0 | 20.67% | 6.8065 | 0%
2038-09-06 | 2038 | 9 | Sep | 6 | 1 | 1 | 20.67% | 6.8065 | 0%
2038-09-07 | 2038 | 9 | Sep | 7 | 2 | 1 | 20.67% | 6.8065 | 0%
2038-09-08 | 2038 | 9 | Sep | 8 | 3 | 1 | 20.67% | 6.8065 | 0%
2038-09-09 | 2038 | 9 | Sep | 9 | 4 | 1 | 20.67% | 6.8065 | 0%
2038-09-10 | 2038 | 9 | Sep | 10 | 5 | 1 | 20.67% | 6.8065 | 0%
2038-09-11 | 2038 | 9 | Sep | 11 | 6 | 0 | 20.67% | 6.8065 | 0%
2038-09-12 | 2038 | 9 | Sep | 12 | 7 | 0 | 20.67% | 6.8065 | 0%
2038-09-13 | 2038 | 9 | Sep | 13 | 1 | 1 | 20.67% | 6.8065 | 0%
2038-09-14 | 2038 | 9 | Sep | 14 | 2 | 1 | 20.67% | 6.8065 | 0%
2038-09-15 | 2038 | 9 | Sep | 15 | 3 | 1 | 20.67% | 6.8065 | 0%
2038-09-16 | 2038 | 9 | Sep | 16 | 4 | 1 | 20.67% | 6.8065 | 0%
2038-09-17 | 2038 | 9 | Sep | 17 | 5 | 1 | 20.67% | 6.8065 | 0%
2038-09-18 | 2038 | 9 | Sep | 18 | 6 | 0 | 20.67% | 6.8065 | 0%
2038-09-19 | 2038 | 9 | Sep | 19 | 7 | 0 | 20.67% | 6.8065 | 0%
2038-09-20 | 2038 | 9 | Sep | 20 | 1 | 1 | 20.67% | 6.8065 | 0%
2038-09-21 | 2038 | 9 | Sep | 21 | 2 | 1 | 20.67% | 6.8065 | 0%
2038-09-22 | 2038 | 9 | Sep | 22 | 3 | 1 | 20.67% | 6.8065 | 0%
2038-09-23 | 2038 | 9 | Sep | 23 | 4 | 1 | 20.67% | 6.8065 | 0%
2038-09-24 | 2038 | 9 | Sep | 24 | 5 | 1 | 20.67% | 6.8065 | 0%
2038-09-25 | 2038 | 9 | Sep | 25 | 6 | 0 | 20.67% | 6.8065 | 0%
2038-09-26 | 2038 | 9 | Sep | 26 | 7 | 0 | 20.67% | 6.8065 | 0%
2038-09-27 | 2038 | 9 | Sep | 27 | 1 | 1 | 20.67% | 6.8065 | 0%
2038-09-28 | 2038 | 9 | Sep | 28 | 2 | 1 | 20.67% | 6.8065 | 0%
2038-09-29 | 2038 | 9 | Sep | 29 | 3 | 1 | 20.67% | 6.8065 | 0%
2038-09-30 | 2038 | 9 | Sep | 30 | 4 | 1 | 20.67% | 6.8065 | 0%
2038-10-01 | 2038 | 10 | Oct | 1 | 5 | 1 | 23.23% | 6.8194 | 0%
2038-10-02 | 2038 | 10 | Oct | 2 | 6 | 0 | 23.23% | 6.8194 | 0%
2038-10-03 | 2038 | 10 | Oct | 3 | 7 | 0 | 23.23% | 6.8194 | 0%
2038-10-04 | 2038 | 10 | Oct | 4 | 1 | 1 | 23.23% | 6.8194 | 0%
2038-10-05 | 2038 | 10 | Oct | 5 | 2 | 1 | 23.23% | 6.8194 | 0%
2038-10-06 | 2038 | 10 | Oct | 6 | 3 | 1 | 23.23% | 6.8194 | 0%
2038-10-07 | 2038 | 10 | Oct | 7 | 4 | 1 | 23.23% | 6.8194 | 0%
2038-10-08 | 2038 | 10 | Oct | 8 | 5 | 1 | 23.23% | 6.8194 | 0%
2038-10-09 | 2038 | 10 | Oct | 9 | 6 | 0 | 23.23% | 6.8194 | 0%
2038-10-10 | 2038 | 10 | Oct | 10 | 7 | 0 | 23.23% | 6.8194 | 0%
2038-10-11 | 2038 | 10 | Oct | 11 | 1 | 1 | 23.23% | 6.8194 | 0%
2038-10-12 | 2038 | 10 | Oct | 12 | 2 | 1 | 23.23% | 6.8194 | 0%
2038-10-13 | 2038 | 10 | Oct | 13 | 3 | 1 | 23.23% | 6.8194 | 0%
2038-10-14 | 2038 | 10 | Oct | 14 | 4 | 1 | 23.23% | 6.8194 | 0%
2038-10-15 | 2038 | 10 | Oct | 15 | 5 | 1 | 23.23% | 6.8194 | 0%
2038-10-16 | 2038 | 10 | Oct | 16 | 6 | 0 | 23.23% | 6.8194 | 0%
2038-10-17 | 2038 | 10 | Oct | 17 | 7 | 0 | 23.23% | 6.8194 | 0%
2038-10-18 | 2038 | 10 | Oct | 18 | 1 | 1 | 23.23% | 6.8194 | 0%
2038-10-19 | 2038 | 10 | Oct | 19 | 2 | 1 | 23.23% | 6.8194 | 0%
2038-10-20 | 2038 | 10 | Oct | 20 | 3 | 1 | 23.23% | 6.8194 | 0%
2038-10-21 | 2038 | 10 | Oct | 21 | 4 | 1 | 23.23% | 6.8194 | 0%
2038-10-22 | 2038 | 10 | Oct | 22 | 5 | 1 | 23.23% | 6.8194 | 0%
2038-10-23 | 2038 | 10 | Oct | 23 | 6 | 0 | 23.23% | 6.8194 | 0%
2038-10-24 | 2038 | 10 | Oct | 24 | 7 | 0 | 23.23% | 6.8194 | 0%
2038-10-25 | 2038 | 10 | Oct | 25 | 1 | 1 | 23.23% | 6.8194 | 0%
2038-10-26 | 2038 | 10 | Oct | 26 | 2 | 1 | 23.23% | 6.8194 | 0%
2038-10-27 | 2038 | 10 | Oct | 27 | 3 | 1 | 23.23% | 6.8194 | 0%
2038-10-28 | 2038 | 10 | Oct | 28 | 4 | 1 | 23.23% | 6.8194 | 0%
2038-10-29 | 2038 | 10 | Oct | 29 | 5 | 1 | 23.23% | 6.8194 | 0%
2038-10-30 | 2038 | 10 | Oct | 30 | 6 | 0 | 23.23% | 6.8194 | 0%
2038-10-31 | 2038 | 10 | Oct | 31 | 7 | 0 | 23.23% | 6.8194 | 0%
2038-11-01 | 2038 | 11 | Nov | 1 | 1 | 1 | 23.33% | 6.4429 | 0%
2038-11-02 | 2038 | 11 | Nov | 2 | 2 | 1 | 23.33% | 6.4429 | 0%
2038-11-03 | 2038 | 11 | Nov | 3 | 3 | 1 | 23.33% | 6.4429 | 0%
2038-11-04 | 2038 | 11 | Nov | 4 | 4 | 1 | 23.33% | 6.4429 | 0%
2038-11-05 | 2038 | 11 | Nov | 5 | 5 | 1 | 23.33% | 6.4429 | 0%
2038-11-06 | 2038 | 11 | Nov | 6 | 6 | 0 | 23.33% | 6.4429 | 0%
2038-11-07 | 2038 | 11 | Nov | 7 | 7 | 0 | 23.33% | 6.4429 | 0%
2038-11-08 | 2038 | 11 | Nov | 8 | 1 | 1 | 23.33% | 6.4429 | 0%
2038-11-09 | 2038 | 11 | Nov | 9 | 2 | 1 | 23.33% | 6.4429 | 0%
2038-11-10 | 2038 | 11 | Nov | 10 | 3 | 1 | 23.33% | 6.4429 | 0%
2038-11-11 | 2038 | 11 | Nov | 11 | 4 | 1 | 23.33% | 6.4429 | 0%
2038-11-12 | 2038 | 11 | Nov | 12 | 5 | 1 | 23.33% | 6.4429 | 0%
2038-11-13 | 2038 | 11 | Nov | 13 | 6 | 0 | 23.33% | 6.4429 | 0%
2038-11-14 | 2038 | 11 | Nov | 14 | 7 | 0 | 23.33% | 6.4429 | 0%
2038-11-15 | 2038 | 11 | Nov | 15 | 1 | 1 | 23.33% | 6.4429 | 0%
2038-11-16 | 2038 | 11 | Nov | 16 | 2 | 1 | 23.33% | 6.4429 | 0%
2038-11-17 | 2038 | 11 | Nov | 17 | 3 | 1 | 23.33% | 6.4429 | 0%
2038-11-18 | 2038 | 11 | Nov | 18 | 4 | 1 | 23.33% | 6.4429 | 0%
2038-11-19 | 2038 | 11 | Nov | 19 | 5 | 1 | 23.33% | 6.4429 | 0%
2038-11-20 | 2038 | 11 | Nov | 20 | 6 | 0 | 23.33% | 6.4429 | 0%
2038-11-21 | 2038 | 11 | Nov | 21 | 7 | 0 | 23.33% | 6.4429 | 0%
2038-11-22 | 2038 | 11 | Nov | 22 | 1 | 1 | 23.33% | 6.4429 | 0%
2038-11-23 | 2038 | 11 | Nov | 23 | 2 | 1 | 23.33% | 6.4429 | 0%
2038-11-24 | 2038 | 11 | Nov | 24 | 3 | 1 | 23.33% | 6.4429 | 0%
2038-11-25 | 2038 | 11 | Nov | 25 | 4 | 1 | 23.33% | 6.4429 | 0%
2038-11-26 | 2038 | 11 | Nov | 26 | 5 | 1 | 23.33% | 6.4429 | 0%
2038-11-27 | 2038 | 11 | Nov | 27 | 6 | 0 | 23.33% | 6.4429 | 0%
2038-11-28 | 2038 | 11 | Nov | 28 | 7 | 0 | 23.33% | 6.4429 | 0%
2038-11-29 | 2038 | 11 | Nov | 29 | 1 | 1 | 23.33% | 6.4429 | 0%
2038-11-30 | 2038 | 11 | Nov | 30 | 2 | 1 | 23.33% | 6.4429 | 0%
2038-12-01 | 2038 | 12 | Dec | 1 | 3 | 1 | 22.69% | 6.7962 | 0%
2038-12-02 | 2038 | 12 | Dec | 2 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-12-03 | 2038 | 12 | Dec | 3 | 5 | 1 | 22.69% | 6.7962 | 0%
2038-12-04 | 2038 | 12 | Dec | 4 | 6 | 0 | 22.69% | 6.7962 | 0%
2038-12-05 | 2038 | 12 | Dec | 5 | 7 | 0 | 22.69% | 6.7962 | 0%
2038-12-06 | 2038 | 12 | Dec | 6 | 1 | 1 | 22.69% | 6.7962 | 0%
2038-12-07 | 2038 | 12 | Dec | 7 | 2 | 1 | 22.69% | 6.7962 | 0%
2038-12-08 | 2038 | 12 | Dec | 8 | 3 | 1 | 22.69% | 6.7962 | 0%
2038-12-09 | 2038 | 12 | Dec | 9 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-12-10 | 2038 | 12 | Dec | 10 | 5 | 1 | 22.69% | 6.7962 | 0%
2038-12-11 | 2038 | 12 | Dec | 11 | 6 | 0 | 22.69% | 6.7962 | 0%
2038-12-12 | 2038 | 12 | Dec | 12 | 7 | 0 | 22.69% | 6.7962 | 0%
2038-12-13 | 2038 | 12 | Dec | 13 | 1 | 1 | 22.69% | 6.7962 | 0%
2038-12-14 | 2038 | 12 | Dec | 14 | 2 | 1 | 22.69% | 6.7962 | 0%
2038-12-15 | 2038 | 12 | Dec | 15 | 3 | 1 | 22.69% | 6.7962 | 0%
2038-12-16 | 2038 | 12 | Dec | 16 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-12-17 | 2038 | 12 | Dec | 17 | 5 | 1 | 22.69% | 6.7962 | 0%
2038-12-18 | 2038 | 12 | Dec | 18 | 6 | 0 | 22.69% | 6.7962 | 0%
2038-12-19 | 2038 | 12 | Dec | 19 | 7 | 0 | 22.69% | 6.7962 | 0%
2038-12-20 | 2038 | 12 | Dec | 20 | 1 | 1 | 22.69% | 6.7962 | 0%
2038-12-21 | 2038 | 12 | Dec | 21 | 2 | 1 | 22.69% | 6.7962 | 0%
2038-12-22 | 2038 | 12 | Dec | 22 | 3 | 1 | 22.69% | 6.7962 | 0%
2038-12-23 | 2038 | 12 | Dec | 23 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-12-24 | 2038 | 12 | Dec | 24 | 5 | 1 | 22.69% | 6.7962 | 0%
2038-12-25 | 2038 | 12 | Dec | 25 | 6 | 0 | 22.69% | 6.7962 | 0%
2038-12-26 | 2038 | 12 | Dec | 26 | 7 | 0 | 22.69% | 6.7962 | 0%
2038-12-27 | 2038 | 12 | Dec | 27 | 1 | 1 | 22.69% | 6.7962 | 0%
2038-12-28 | 2038 | 12 | Dec | 28 | 2 | 1 | 22.69% | 6.7962 | 0%
2038-12-29 | 2038 | 12 | Dec | 29 | 3 | 1 | 22.69% | 6.7962 | 0%
2038-12-30 | 2038 | 12 | Dec | 30 | 4 | 1 | 22.69% | 6.7962 | 0%
2038-12-31 | 2038 | 12 | Dec | 31 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-01-01 | 2039 | 1 | Jan | 1 | 6 | 0 | 19.46% | 7.0276 | 0%
2039-01-02 | 2039 | 1 | Jan | 2 | 7 | 0 | 19.46% | 7.0276 | 0%
2039-01-03 | 2039 | 1 | Jan | 3 | 1 | 1 | 19.46% | 7.0276 | 0%
2039-01-04 | 2039 | 1 | Jan | 4 | 2 | 1 | 19.46% | 7.0276 | 0%
2039-01-05 | 2039 | 1 | Jan | 5 | 3 | 1 | 19.46% | 7.0276 | 0%
2039-01-06 | 2039 | 1 | Jan | 6 | 4 | 1 | 19.46% | 7.0276 | 0%
2039-01-07 | 2039 | 1 | Jan | 7 | 5 | 1 | 19.46% | 7.0276 | 0%
2039-01-08 | 2039 | 1 | Jan | 8 | 6 | 0 | 19.46% | 7.0276 | 0%
2039-01-09 | 2039 | 1 | Jan | 9 | 7 | 0 | 19.46% | 7.0276 | 0%
2039-01-10 | 2039 | 1 | Jan | 10 | 1 | 1 | 19.46% | 7.0276 | 0%
2039-01-11 | 2039 | 1 | Jan | 11 | 2 | 1 | 19.46% | 7.0276 | 0%
2039-01-12 | 2039 | 1 | Jan | 12 | 3 | 1 | 19.46% | 7.0276 | 0%
2039-01-13 | 2039 | 1 | Jan | 13 | 4 | 1 | 19.46% | 7.0276 | 0%
2039-01-14 | 2039 | 1 | Jan | 14 | 5 | 1 | 19.46% | 7.0276 | 0%
2039-01-15 | 2039 | 1 | Jan | 15 | 6 | 0 | 19.46% | 7.0276 | 0%
2039-01-16 | 2039 | 1 | Jan | 16 | 7 | 0 | 19.46% | 7.0276 | 0%
2039-01-17 | 2039 | 1 | Jan | 17 | 1 | 1 | 19.46% | 7.0276 | 0%
2039-01-18 | 2039 | 1 | Jan | 18 | 2 | 1 | 19.46% | 7.0276 | 0%
2039-01-19 | 2039 | 1 | Jan | 19 | 3 | 1 | 19.46% | 7.0276 | 0%
2039-01-20 | 2039 | 1 | Jan | 20 | 4 | 1 | 19.46% | 7.0276 | 0%
2039-01-21 | 2039 | 1 | Jan | 21 | 5 | 1 | 19.46% | 7.0276 | 0%
2039-01-22 | 2039 | 1 | Jan | 22 | 6 | 0 | 19.46% | 7.0276 | 0%
2039-01-23 | 2039 | 1 | Jan | 23 | 7 | 0 | 19.46% | 7.0276 | 0%
2039-01-24 | 2039 | 1 | Jan | 24 | 1 | 1 | 19.46% | 7.0276 | 0%
2039-01-25 | 2039 | 1 | Jan | 25 | 2 | 1 | 19.46% | 7.0276 | 0%
2039-01-26 | 2039 | 1 | Jan | 26 | 3 | 1 | 19.46% | 7.0276 | 0%
2039-01-27 | 2039 | 1 | Jan | 27 | 4 | 1 | 19.46% | 7.0276 | 0%
2039-01-28 | 2039 | 1 | Jan | 28 | 5 | 1 | 19.46% | 7.0276 | 0%
2039-01-29 | 2039 | 1 | Jan | 29 | 6 | 0 | 19.46% | 7.0276 | 0%
2039-01-30 | 2039 | 1 | Jan | 30 | 7 | 0 | 19.46% | 7.0276 | 0%
2039-01-31 | 2039 | 1 | Jan | 31 | 1 | 1 | 19.46% | 7.0276 | 0%
2039-02-01 | 2039 | 2 | Feb | 1 | 2 | 1 | 18.87% | 7.4625 | 0%
2039-02-02 | 2039 | 2 | Feb | 2 | 3 | 1 | 18.87% | 7.4625 | 0%
2039-02-03 | 2039 | 2 | Feb | 3 | 4 | 1 | 18.87% | 7.4625 | 0%
2039-02-04 | 2039 | 2 | Feb | 4 | 5 | 1 | 18.87% | 7.4625 | 0%
2039-02-05 | 2039 | 2 | Feb | 5 | 6 | 0 | 18.87% | 7.4625 | 0%
2039-02-06 | 2039 | 2 | Feb | 6 | 7 | 0 | 18.87% | 7.4625 | 0%
2039-02-07 | 2039 | 2 | Feb | 7 | 1 | 1 | 18.87% | 7.4625 | 0%
2039-02-08 | 2039 | 2 | Feb | 8 | 2 | 1 | 18.87% | 7.4625 | 0%
2039-02-09 | 2039 | 2 | Feb | 9 | 3 | 1 | 18.87% | 7.4625 | 0%
2039-02-10 | 2039 | 2 | Feb | 10 | 4 | 1 | 18.87% | 7.4625 | 0%
2039-02-11 | 2039 | 2 | Feb | 11 | 5 | 1 | 18.87% | 7.4625 | 0%
2039-02-12 | 2039 | 2 | Feb | 12 | 6 | 0 | 18.87% | 7.4625 | 0%
2039-02-13 | 2039 | 2 | Feb | 13 | 7 | 0 | 18.87% | 7.4625 | 0%
2039-02-14 | 2039 | 2 | Feb | 14 | 1 | 1 | 18.87% | 7.4625 | 0%
2039-02-15 | 2039 | 2 | Feb | 15 | 2 | 1 | 18.87% | 7.4625 | 0%
2039-02-16 | 2039 | 2 | Feb | 16 | 3 | 1 | 18.87% | 7.4625 | 0%
2039-02-17 | 2039 | 2 | Feb | 17 | 4 | 1 | 18.87% | 7.4625 | 0%
2039-02-18 | 2039 | 2 | Feb | 18 | 5 | 1 | 18.87% | 7.4625 | 0%
2039-02-19 | 2039 | 2 | Feb | 19 | 6 | 0 | 18.87% | 7.4625 | 0%
2039-02-20 | 2039 | 2 | Feb | 20 | 7 | 0 | 18.87% | 7.4625 | 0%
2039-02-21 | 2039 | 2 | Feb | 21 | 1 | 1 | 18.87% | 7.4625 | 0%
2039-02-22 | 2039 | 2 | Feb | 22 | 2 | 1 | 18.87% | 7.4625 | 0%
2039-02-23 | 2039 | 2 | Feb | 23 | 3 | 1 | 18.87% | 7.4625 | 0%
2039-02-24 | 2039 | 2 | Feb | 24 | 4 | 1 | 18.87% | 7.4625 | 0%
2039-02-25 | 2039 | 2 | Feb | 25 | 5 | 1 | 18.87% | 7.4625 | 0%
2039-02-26 | 2039 | 2 | Feb | 26 | 6 | 0 | 18.87% | 7.4625 | 0%
2039-02-27 | 2039 | 2 | Feb | 27 | 7 | 0 | 18.87% | 7.4625 | 0%
2039-02-28 | 2039 | 2 | Feb | 28 | 1 | 1 | 18.87% | 7.4625 | 0%
2039-03-01 | 2039 | 3 | Mar | 1 | 2 | 1 | 18.49% | 7.8663 | 0%
2039-03-02 | 2039 | 3 | Mar | 2 | 3 | 1 | 18.49% | 7.8663 | 0%
2039-03-03 | 2039 | 3 | Mar | 3 | 4 | 1 | 18.49% | 7.8663 | 0%
2039-03-04 | 2039 | 3 | Mar | 4 | 5 | 1 | 18.49% | 7.8663 | 0%
2039-03-05 | 2039 | 3 | Mar | 5 | 6 | 0 | 18.49% | 7.8663 | 0%
2039-03-06 | 2039 | 3 | Mar | 6 | 7 | 0 | 18.49% | 7.8663 | 0%
2039-03-07 | 2039 | 3 | Mar | 7 | 1 | 1 | 18.49% | 7.8663 | 0%
2039-03-08 | 2039 | 3 | Mar | 8 | 2 | 1 | 18.49% | 7.8663 | 0%
2039-03-09 | 2039 | 3 | Mar | 9 | 3 | 1 | 18.49% | 7.8663 | 0%
2039-03-10 | 2039 | 3 | Mar | 10 | 4 | 1 | 18.49% | 7.8663 | 0%
2039-03-11 | 2039 | 3 | Mar | 11 | 5 | 1 | 18.49% | 7.8663 | 0%
2039-03-12 | 2039 | 3 | Mar | 12 | 6 | 0 | 18.49% | 7.8663 | 0%
2039-03-13 | 2039 | 3 | Mar | 13 | 7 | 0 | 18.49% | 7.8663 | 0%
2039-03-14 | 2039 | 3 | Mar | 14 | 1 | 1 | 18.49% | 7.8663 | 0%
2039-03-15 | 2039 | 3 | Mar | 15 | 2 | 1 | 18.49% | 7.8663 | 0%
2039-03-16 | 2039 | 3 | Mar | 16 | 3 | 1 | 18.49% | 7.8663 | 0%
2039-03-17 | 2039 | 3 | Mar | 17 | 4 | 1 | 18.49% | 7.8663 | 0%
2039-03-18 | 2039 | 3 | Mar | 18 | 5 | 1 | 18.49% | 7.8663 | 0%
2039-03-19 | 2039 | 3 | Mar | 19 | 6 | 0 | 18.49% | 7.8663 | 0%
2039-03-20 | 2039 | 3 | Mar | 20 | 7 | 0 | 18.49% | 7.8663 | 0%
2039-03-21 | 2039 | 3 | Mar | 21 | 1 | 1 | 18.49% | 7.8663 | 0%
2039-03-22 | 2039 | 3 | Mar | 22 | 2 | 1 | 18.49% | 7.8663 | 0%
2039-03-23 | 2039 | 3 | Mar | 23 | 3 | 1 | 18.49% | 7.8663 | 0%
2039-03-24 | 2039 | 3 | Mar | 24 | 4 | 1 | 18.49% | 7.8663 | 0%
2039-03-25 | 2039 | 3 | Mar | 25 | 5 | 1 | 18.49% | 7.8663 | 0%
2039-03-26 | 2039 | 3 | Mar | 26 | 6 | 0 | 18.49% | 7.8663 | 0%
2039-03-27 | 2039 | 3 | Mar | 27 | 7 | 0 | 18.49% | 7.8663 | 0%
2039-03-28 | 2039 | 3 | Mar | 28 | 1 | 1 | 18.49% | 7.8663 | 0%
2039-03-29 | 2039 | 3 | Mar | 29 | 2 | 1 | 18.49% | 7.8663 | 0%
2039-03-30 | 2039 | 3 | Mar | 30 | 3 | 1 | 18.49% | 7.8663 | 0%
2039-03-31 | 2039 | 3 | Mar | 31 | 4 | 1 | 18.49% | 7.8663 | 0%
2039-04-01 | 2039 | 4 | Apr | 1 | 5 | 1 | 25.56% | 7.5 | 0%
2039-04-02 | 2039 | 4 | Apr | 2 | 6 | 0 | 25.56% | 7.5 | 0%
2039-04-03 | 2039 | 4 | Apr | 3 | 7 | 0 | 25.56% | 7.5 | 0%
2039-04-04 | 2039 | 4 | Apr | 4 | 1 | 1 | 25.56% | 7.5 | 0%
2039-04-05 | 2039 | 4 | Apr | 5 | 2 | 1 | 25.56% | 7.5 | 0%
2039-04-06 | 2039 | 4 | Apr | 6 | 3 | 1 | 25.56% | 7.5 | 0%
2039-04-07 | 2039 | 4 | Apr | 7 | 4 | 1 | 25.56% | 7.5 | 0%
2039-04-08 | 2039 | 4 | Apr | 8 | 5 | 1 | 25.56% | 7.5 | 0%
2039-04-09 | 2039 | 4 | Apr | 9 | 6 | 0 | 25.56% | 7.5 | 0%
2039-04-10 | 2039 | 4 | Apr | 10 | 7 | 0 | 25.56% | 7.5 | 0%
2039-04-11 | 2039 | 4 | Apr | 11 | 1 | 1 | 25.56% | 7.5 | 0%
2039-04-12 | 2039 | 4 | Apr | 12 | 2 | 1 | 25.56% | 7.5 | 0%
2039-04-13 | 2039 | 4 | Apr | 13 | 3 | 1 | 25.56% | 7.5 | 0%
2039-04-14 | 2039 | 4 | Apr | 14 | 4 | 1 | 25.56% | 7.5 | 0%
2039-04-15 | 2039 | 4 | Apr | 15 | 5 | 1 | 25.56% | 7.5 | 0%
2039-04-16 | 2039 | 4 | Apr | 16 | 6 | 0 | 25.56% | 7.5 | 0%
2039-04-17 | 2039 | 4 | Apr | 17 | 7 | 0 | 25.56% | 7.5 | 0%
2039-04-18 | 2039 | 4 | Apr | 18 | 1 | 1 | 25.56% | 7.5 | 0%
2039-04-19 | 2039 | 4 | Apr | 19 | 2 | 1 | 25.56% | 7.5 | 0%
2039-04-20 | 2039 | 4 | Apr | 20 | 3 | 1 | 25.56% | 7.5 | 0%
2039-04-21 | 2039 | 4 | Apr | 21 | 4 | 1 | 25.56% | 7.5 | 0%
2039-04-22 | 2039 | 4 | Apr | 22 | 5 | 1 | 25.56% | 7.5 | 0%
2039-04-23 | 2039 | 4 | Apr | 23 | 6 | 0 | 25.56% | 7.5 | 0%
2039-04-24 | 2039 | 4 | Apr | 24 | 7 | 0 | 25.56% | 7.5 | 0%
2039-04-25 | 2039 | 4 | Apr | 25 | 1 | 1 | 25.56% | 7.5 | 0%
2039-04-26 | 2039 | 4 | Apr | 26 | 2 | 1 | 25.56% | 7.5 | 0%
2039-04-27 | 2039 | 4 | Apr | 27 | 3 | 1 | 25.56% | 7.5 | 0%
2039-04-28 | 2039 | 4 | Apr | 28 | 4 | 1 | 25.56% | 7.5 | 0%
2039-04-29 | 2039 | 4 | Apr | 29 | 5 | 1 | 25.56% | 7.5 | 0%
2039-04-30 | 2039 | 4 | Apr | 30 | 6 | 0 | 25.56% | 7.5 | 0%
2039-05-01 | 2039 | 5 | May | 1 | 7 | 0 | 23.01% | 8.1449 | 0%
2039-05-02 | 2039 | 5 | May | 2 | 1 | 1 | 23.01% | 8.1449 | 0%
2039-05-03 | 2039 | 5 | May | 3 | 2 | 1 | 23.01% | 8.1449 | 0%
2039-05-04 | 2039 | 5 | May | 4 | 3 | 1 | 23.01% | 8.1449 | 0%
2039-05-05 | 2039 | 5 | May | 5 | 4 | 1 | 23.01% | 8.1449 | 0%
2039-05-06 | 2039 | 5 | May | 6 | 5 | 1 | 23.01% | 8.1449 | 0%
2039-05-07 | 2039 | 5 | May | 7 | 6 | 0 | 23.01% | 8.1449 | 0%
2039-05-08 | 2039 | 5 | May | 8 | 7 | 0 | 23.01% | 8.1449 | 0%
2039-05-09 | 2039 | 5 | May | 9 | 1 | 1 | 23.01% | 8.1449 | 0%
2039-05-10 | 2039 | 5 | May | 10 | 2 | 1 | 23.01% | 8.1449 | 0%
2039-05-11 | 2039 | 5 | May | 11 | 3 | 1 | 23.01% | 8.1449 | 0%
2039-05-12 | 2039 | 5 | May | 12 | 4 | 1 | 23.01% | 8.1449 | 0%
2039-05-13 | 2039 | 5 | May | 13 | 5 | 1 | 23.01% | 8.1449 | 0%
2039-05-14 | 2039 | 5 | May | 14 | 6 | 0 | 23.01% | 8.1449 | 0%
2039-05-15 | 2039 | 5 | May | 15 | 7 | 0 | 23.01% | 8.1449 | 0%
2039-05-16 | 2039 | 5 | May | 16 | 1 | 1 | 23.01% | 8.1449 | 0%
2039-05-17 | 2039 | 5 | May | 17 | 2 | 1 | 23.01% | 8.1449 | 0%
2039-05-18 | 2039 | 5 | May | 18 | 3 | 1 | 23.01% | 8.1449 | 0%
2039-05-19 | 2039 | 5 | May | 19 | 4 | 1 | 23.01% | 8.1449 | 0%
2039-05-20 | 2039 | 5 | May | 20 | 5 | 1 | 23.01% | 8.1449 | 0%
2039-05-21 | 2039 | 5 | May | 21 | 6 | 0 | 23.01% | 8.1449 | 0%
2039-05-22 | 2039 | 5 | May | 22 | 7 | 0 | 23.01% | 8.1449 | 0%
2039-05-23 | 2039 | 5 | May | 23 | 1 | 1 | 23.01% | 8.1449 | 0%
2039-05-24 | 2039 | 5 | May | 24 | 2 | 1 | 23.01% | 8.1449 | 0%
2039-05-25 | 2039 | 5 | May | 25 | 3 | 1 | 23.01% | 8.1449 | 0%
2039-05-26 | 2039 | 5 | May | 26 | 4 | 1 | 23.01% | 8.1449 | 0%
2039-05-27 | 2039 | 5 | May | 27 | 5 | 1 | 23.01% | 8.1449 | 0%
2039-05-28 | 2039 | 5 | May | 28 | 6 | 0 | 23.01% | 8.1449 | 0%
2039-05-29 | 2039 | 5 | May | 29 | 7 | 0 | 23.01% | 8.1449 | 0%
2039-05-30 | 2039 | 5 | May | 30 | 1 | 1 | 23.01% | 8.1449 | 0%
2039-05-31 | 2039 | 5 | May | 31 | 2 | 1 | 23.01% | 8.1449 | 0%
2039-06-01 | 2039 | 6 | Jun | 1 | 3 | 1 | 28.67% | 7.9419 | 0%
2039-06-02 | 2039 | 6 | Jun | 2 | 4 | 1 | 28.67% | 7.9419 | 0%
2039-06-03 | 2039 | 6 | Jun | 3 | 5 | 1 | 28.67% | 7.9419 | 0%
2039-06-04 | 2039 | 6 | Jun | 4 | 6 | 0 | 28.67% | 7.9419 | 0%
2039-06-05 | 2039 | 6 | Jun | 5 | 7 | 0 | 28.67% | 7.9419 | 0%
2039-06-06 | 2039 | 6 | Jun | 6 | 1 | 1 | 28.67% | 7.9419 | 0%
2039-06-07 | 2039 | 6 | Jun | 7 | 2 | 1 | 28.67% | 7.9419 | 0%
2039-06-08 | 2039 | 6 | Jun | 8 | 3 | 1 | 28.67% | 7.9419 | 0%
2039-06-09 | 2039 | 6 | Jun | 9 | 4 | 1 | 28.67% | 7.9419 | 0%
2039-06-10 | 2039 | 6 | Jun | 10 | 5 | 1 | 28.67% | 7.9419 | 0%
2039-06-11 | 2039 | 6 | Jun | 11 | 6 | 0 | 28.67% | 7.9419 | 0%
2039-06-12 | 2039 | 6 | Jun | 12 | 7 | 0 | 28.67% | 7.9419 | 0%
2039-06-13 | 2039 | 6 | Jun | 13 | 1 | 1 | 28.67% | 7.9419 | 0%
2039-06-14 | 2039 | 6 | Jun | 14 | 2 | 1 | 28.67% | 7.9419 | 0%
2039-06-15 | 2039 | 6 | Jun | 15 | 3 | 1 | 28.67% | 7.9419 | 0%
2039-06-16 | 2039 | 6 | Jun | 16 | 4 | 1 | 28.67% | 7.9419 | 0%
2039-06-17 | 2039 | 6 | Jun | 17 | 5 | 1 | 28.67% | 7.9419 | 0%
2039-06-18 | 2039 | 6 | Jun | 18 | 6 | 0 | 28.67% | 7.9419 | 0%
2039-06-19 | 2039 | 6 | Jun | 19 | 7 | 0 | 28.67% | 7.9419 | 0%
2039-06-20 | 2039 | 6 | Jun | 20 | 1 | 1 | 28.67% | 7.9419 | 0%
2039-06-21 | 2039 | 6 | Jun | 21 | 2 | 1 | 28.67% | 7.9419 | 0%
2039-06-22 | 2039 | 6 | Jun | 22 | 3 | 1 | 28.67% | 7.9419 | 0%
2039-06-23 | 2039 | 6 | Jun | 23 | 4 | 1 | 28.67% | 7.9419 | 0%
2039-06-24 | 2039 | 6 | Jun | 24 | 5 | 1 | 28.67% | 7.9419 | 0%
2039-06-25 | 2039 | 6 | Jun | 25 | 6 | 0 | 28.67% | 7.9419 | 0%
2039-06-26 | 2039 | 6 | Jun | 26 | 7 | 0 | 28.67% | 7.9419 | 0%
2039-06-27 | 2039 | 6 | Jun | 27 | 1 | 1 | 28.67% | 7.9419 | 0%
2039-06-28 | 2039 | 6 | Jun | 28 | 2 | 1 | 28.67% | 7.9419 | 0%
2039-06-29 | 2039 | 6 | Jun | 29 | 3 | 1 | 28.67% | 7.9419 | 0%
2039-06-30 | 2039 | 6 | Jun | 30 | 4 | 1 | 28.67% | 7.9419 | 0%
2039-07-01 | 2039 | 7 | Jul | 1 | 5 | 1 | 24.73% | 8.3739 | 0%
2039-07-02 | 2039 | 7 | Jul | 2 | 6 | 0 | 24.73% | 8.3739 | 0%
2039-07-03 | 2039 | 7 | Jul | 3 | 7 | 0 | 24.73% | 8.3739 | 0%
2039-07-04 | 2039 | 7 | Jul | 4 | 1 | 1 | 24.73% | 8.3739 | 0%
2039-07-05 | 2039 | 7 | Jul | 5 | 2 | 1 | 24.73% | 8.3739 | 0%
2039-07-06 | 2039 | 7 | Jul | 6 | 3 | 1 | 24.73% | 8.3739 | 0%
2039-07-07 | 2039 | 7 | Jul | 7 | 4 | 1 | 24.73% | 8.3739 | 0%
2039-07-08 | 2039 | 7 | Jul | 8 | 5 | 1 | 24.73% | 8.3739 | 0%
2039-07-09 | 2039 | 7 | Jul | 9 | 6 | 0 | 24.73% | 8.3739 | 0%
2039-07-10 | 2039 | 7 | Jul | 10 | 7 | 0 | 24.73% | 8.3739 | 0%
2039-07-11 | 2039 | 7 | Jul | 11 | 1 | 1 | 24.73% | 8.3739 | 0%
2039-07-12 | 2039 | 7 | Jul | 12 | 2 | 1 | 24.73% | 8.3739 | 0%
2039-07-13 | 2039 | 7 | Jul | 13 | 3 | 1 | 24.73% | 8.3739 | 0%
2039-07-14 | 2039 | 7 | Jul | 14 | 4 | 1 | 24.73% | 8.3739 | 0%
2039-07-15 | 2039 | 7 | Jul | 15 | 5 | 1 | 24.73% | 8.3739 | 0%
2039-07-16 | 2039 | 7 | Jul | 16 | 6 | 0 | 24.73% | 8.3739 | 0%
2039-07-17 | 2039 | 7 | Jul | 17 | 7 | 0 | 24.73% | 8.3739 | 0%
2039-07-18 | 2039 | 7 | Jul | 18 | 1 | 1 | 24.73% | 8.3739 | 0%
2039-07-19 | 2039 | 7 | Jul | 19 | 2 | 1 | 24.73% | 8.3739 | 0%
2039-07-20 | 2039 | 7 | Jul | 20 | 3 | 1 | 24.73% | 8.3739 | 0%
2039-07-21 | 2039 | 7 | Jul | 21 | 4 | 1 | 24.73% | 8.3739 | 0%
2039-07-22 | 2039 | 7 | Jul | 22 | 5 | 1 | 24.73% | 8.3739 | 0%
2039-07-23 | 2039 | 7 | Jul | 23 | 6 | 0 | 24.73% | 8.3739 | 0%
2039-07-24 | 2039 | 7 | Jul | 24 | 7 | 0 | 24.73% | 8.3739 | 0%
2039-07-25 | 2039 | 7 | Jul | 25 | 1 | 1 | 24.73% | 8.3739 | 0%
2039-07-26 | 2039 | 7 | Jul | 26 | 2 | 1 | 24.73% | 8.3739 | 0%
2039-07-27 | 2039 | 7 | Jul | 27 | 3 | 1 | 24.73% | 8.3739 | 0%
2039-07-28 | 2039 | 7 | Jul | 28 | 4 | 1 | 24.73% | 8.3739 | 0%
2039-07-29 | 2039 | 7 | Jul | 29 | 5 | 1 | 24.73% | 8.3739 | 0%
2039-07-30 | 2039 | 7 | Jul | 30 | 6 | 0 | 24.73% | 8.3739 | 0%
2039-07-31 | 2039 | 7 | Jul | 31 | 7 | 0 | 24.73% | 8.3739 | 0%
2039-08-01 | 2039 | 8 | Aug | 1 | 1 | 1 | 23.55% | 7.9589 | 0%
2039-08-02 | 2039 | 8 | Aug | 2 | 2 | 1 | 23.55% | 7.9589 | 0%
2039-08-03 | 2039 | 8 | Aug | 3 | 3 | 1 | 23.55% | 7.9589 | 0%
2039-08-04 | 2039 | 8 | Aug | 4 | 4 | 1 | 23.55% | 7.9589 | 0%
2039-08-05 | 2039 | 8 | Aug | 5 | 5 | 1 | 23.55% | 7.9589 | 0%
2039-08-06 | 2039 | 8 | Aug | 6 | 6 | 0 | 23.55% | 7.9589 | 0%
2039-08-07 | 2039 | 8 | Aug | 7 | 7 | 0 | 23.55% | 7.9589 | 0%
2039-08-08 | 2039 | 8 | Aug | 8 | 1 | 1 | 23.55% | 7.9589 | 0%
2039-08-09 | 2039 | 8 | Aug | 9 | 2 | 1 | 23.55% | 7.9589 | 0%
2039-08-10 | 2039 | 8 | Aug | 10 | 3 | 1 | 23.55% | 7.9589 | 0%
2039-08-11 | 2039 | 8 | Aug | 11 | 4 | 1 | 23.55% | 7.9589 | 0%
2039-08-12 | 2039 | 8 | Aug | 12 | 5 | 1 | 23.55% | 7.9589 | 0%
2039-08-13 | 2039 | 8 | Aug | 13 | 6 | 0 | 23.55% | 7.9589 | 0%
2039-08-14 | 2039 | 8 | Aug | 14 | 7 | 0 | 23.55% | 7.9589 | 0%
2039-08-15 | 2039 | 8 | Aug | 15 | 1 | 1 | 23.55% | 7.9589 | 0%
2039-08-16 | 2039 | 8 | Aug | 16 | 2 | 1 | 23.55% | 7.9589 | 0%
2039-08-17 | 2039 | 8 | Aug | 17 | 3 | 1 | 23.55% | 7.9589 | 0%
2039-08-18 | 2039 | 8 | Aug | 18 | 4 | 1 | 23.55% | 7.9589 | 0%
2039-08-19 | 2039 | 8 | Aug | 19 | 5 | 1 | 23.55% | 7.9589 | 0%
2039-08-20 | 2039 | 8 | Aug | 20 | 6 | 0 | 23.55% | 7.9589 | 0%
2039-08-21 | 2039 | 8 | Aug | 21 | 7 | 0 | 23.55% | 7.9589 | 0%
2039-08-22 | 2039 | 8 | Aug | 22 | 1 | 1 | 23.55% | 7.9589 | 0%
2039-08-23 | 2039 | 8 | Aug | 23 | 2 | 1 | 23.55% | 7.9589 | 0%
2039-08-24 | 2039 | 8 | Aug | 24 | 3 | 1 | 23.55% | 7.9589 | 0%
2039-08-25 | 2039 | 8 | Aug | 25 | 4 | 1 | 23.55% | 7.9589 | 0%
2039-08-26 | 2039 | 8 | Aug | 26 | 5 | 1 | 23.55% | 7.9589 | 0%
2039-08-27 | 2039 | 8 | Aug | 27 | 6 | 0 | 23.55% | 7.9589 | 0%
2039-08-28 | 2039 | 8 | Aug | 28 | 7 | 0 | 23.55% | 7.9589 | 0%
2039-08-29 | 2039 | 8 | Aug | 29 | 1 | 1 | 23.55% | 7.9589 | 0%
2039-08-30 | 2039 | 8 | Aug | 30 | 2 | 1 | 23.55% | 7.9589 | 0%
2039-08-31 | 2039 | 8 | Aug | 31 | 3 | 1 | 23.55% | 7.9589 | 0%
2039-09-01 | 2039 | 9 | Sep | 1 | 4 | 1 | 20.67% | 6.8065 | 0%
2039-09-02 | 2039 | 9 | Sep | 2 | 5 | 1 | 20.67% | 6.8065 | 0%
2039-09-03 | 2039 | 9 | Sep | 3 | 6 | 0 | 20.67% | 6.8065 | 0%
2039-09-04 | 2039 | 9 | Sep | 4 | 7 | 0 | 20.67% | 6.8065 | 0%
2039-09-05 | 2039 | 9 | Sep | 5 | 1 | 1 | 20.67% | 6.8065 | 0%
2039-09-06 | 2039 | 9 | Sep | 6 | 2 | 1 | 20.67% | 6.8065 | 0%
2039-09-07 | 2039 | 9 | Sep | 7 | 3 | 1 | 20.67% | 6.8065 | 0%
2039-09-08 | 2039 | 9 | Sep | 8 | 4 | 1 | 20.67% | 6.8065 | 0%
2039-09-09 | 2039 | 9 | Sep | 9 | 5 | 1 | 20.67% | 6.8065 | 0%
2039-09-10 | 2039 | 9 | Sep | 10 | 6 | 0 | 20.67% | 6.8065 | 0%
2039-09-11 | 2039 | 9 | Sep | 11 | 7 | 0 | 20.67% | 6.8065 | 0%
2039-09-12 | 2039 | 9 | Sep | 12 | 1 | 1 | 20.67% | 6.8065 | 0%
2039-09-13 | 2039 | 9 | Sep | 13 | 2 | 1 | 20.67% | 6.8065 | 0%
2039-09-14 | 2039 | 9 | Sep | 14 | 3 | 1 | 20.67% | 6.8065 | 0%
2039-09-15 | 2039 | 9 | Sep | 15 | 4 | 1 | 20.67% | 6.8065 | 0%
2039-09-16 | 2039 | 9 | Sep | 16 | 5 | 1 | 20.67% | 6.8065 | 0%
2039-09-17 | 2039 | 9 | Sep | 17 | 6 | 0 | 20.67% | 6.8065 | 0%
2039-09-18 | 2039 | 9 | Sep | 18 | 7 | 0 | 20.67% | 6.8065 | 0%
2039-09-19 | 2039 | 9 | Sep | 19 | 1 | 1 | 20.67% | 6.8065 | 0%
2039-09-20 | 2039 | 9 | Sep | 20 | 2 | 1 | 20.67% | 6.8065 | 0%
2039-09-21 | 2039 | 9 | Sep | 21 | 3 | 1 | 20.67% | 6.8065 | 0%
2039-09-22 | 2039 | 9 | Sep | 22 | 4 | 1 | 20.67% | 6.8065 | 0%
2039-09-23 | 2039 | 9 | Sep | 23 | 5 | 1 | 20.67% | 6.8065 | 0%
2039-09-24 | 2039 | 9 | Sep | 24 | 6 | 0 | 20.67% | 6.8065 | 0%
2039-09-25 | 2039 | 9 | Sep | 25 | 7 | 0 | 20.67% | 6.8065 | 0%
2039-09-26 | 2039 | 9 | Sep | 26 | 1 | 1 | 20.67% | 6.8065 | 0%
2039-09-27 | 2039 | 9 | Sep | 27 | 2 | 1 | 20.67% | 6.8065 | 0%
2039-09-28 | 2039 | 9 | Sep | 28 | 3 | 1 | 20.67% | 6.8065 | 0%
2039-09-29 | 2039 | 9 | Sep | 29 | 4 | 1 | 20.67% | 6.8065 | 0%
2039-09-30 | 2039 | 9 | Sep | 30 | 5 | 1 | 20.67% | 6.8065 | 0%
2039-10-01 | 2039 | 10 | Oct | 1 | 6 | 0 | 23.23% | 6.8194 | 0%
2039-10-02 | 2039 | 10 | Oct | 2 | 7 | 0 | 23.23% | 6.8194 | 0%
2039-10-03 | 2039 | 10 | Oct | 3 | 1 | 1 | 23.23% | 6.8194 | 0%
2039-10-04 | 2039 | 10 | Oct | 4 | 2 | 1 | 23.23% | 6.8194 | 0%
2039-10-05 | 2039 | 10 | Oct | 5 | 3 | 1 | 23.23% | 6.8194 | 0%
2039-10-06 | 2039 | 10 | Oct | 6 | 4 | 1 | 23.23% | 6.8194 | 0%
2039-10-07 | 2039 | 10 | Oct | 7 | 5 | 1 | 23.23% | 6.8194 | 0%
2039-10-08 | 2039 | 10 | Oct | 8 | 6 | 0 | 23.23% | 6.8194 | 0%
2039-10-09 | 2039 | 10 | Oct | 9 | 7 | 0 | 23.23% | 6.8194 | 0%
2039-10-10 | 2039 | 10 | Oct | 10 | 1 | 1 | 23.23% | 6.8194 | 0%
2039-10-11 | 2039 | 10 | Oct | 11 | 2 | 1 | 23.23% | 6.8194 | 0%
2039-10-12 | 2039 | 10 | Oct | 12 | 3 | 1 | 23.23% | 6.8194 | 0%
2039-10-13 | 2039 | 10 | Oct | 13 | 4 | 1 | 23.23% | 6.8194 | 0%
2039-10-14 | 2039 | 10 | Oct | 14 | 5 | 1 | 23.23% | 6.8194 | 0%
2039-10-15 | 2039 | 10 | Oct | 15 | 6 | 0 | 23.23% | 6.8194 | 0%
2039-10-16 | 2039 | 10 | Oct | 16 | 7 | 0 | 23.23% | 6.8194 | 0%
2039-10-17 | 2039 | 10 | Oct | 17 | 1 | 1 | 23.23% | 6.8194 | 0%
2039-10-18 | 2039 | 10 | Oct | 18 | 2 | 1 | 23.23% | 6.8194 | 0%
2039-10-19 | 2039 | 10 | Oct | 19 | 3 | 1 | 23.23% | 6.8194 | 0%
2039-10-20 | 2039 | 10 | Oct | 20 | 4 | 1 | 23.23% | 6.8194 | 0%
2039-10-21 | 2039 | 10 | Oct | 21 | 5 | 1 | 23.23% | 6.8194 | 0%
2039-10-22 | 2039 | 10 | Oct | 22 | 6 | 0 | 23.23% | 6.8194 | 0%
2039-10-23 | 2039 | 10 | Oct | 23 | 7 | 0 | 23.23% | 6.8194 | 0%
2039-10-24 | 2039 | 10 | Oct | 24 | 1 | 1 | 23.23% | 6.8194 | 0%
2039-10-25 | 2039 | 10 | Oct | 25 | 2 | 1 | 23.23% | 6.8194 | 0%
2039-10-26 | 2039 | 10 | Oct | 26 | 3 | 1 | 23.23% | 6.8194 | 0%
2039-10-27 | 2039 | 10 | Oct | 27 | 4 | 1 | 23.23% | 6.8194 | 0%
2039-10-28 | 2039 | 10 | Oct | 28 | 5 | 1 | 23.23% | 6.8194 | 0%
2039-10-29 | 2039 | 10 | Oct | 29 | 6 | 0 | 23.23% | 6.8194 | 0%
2039-10-30 | 2039 | 10 | Oct | 30 | 7 | 0 | 23.23% | 6.8194 | 0%
2039-10-31 | 2039 | 10 | Oct | 31 | 1 | 1 | 23.23% | 6.8194 | 0%
2039-11-01 | 2039 | 11 | Nov | 1 | 2 | 1 | 23.33% | 6.4429 | 0%
2039-11-02 | 2039 | 11 | Nov | 2 | 3 | 1 | 23.33% | 6.4429 | 0%
2039-11-03 | 2039 | 11 | Nov | 3 | 4 | 1 | 23.33% | 6.4429 | 0%
2039-11-04 | 2039 | 11 | Nov | 4 | 5 | 1 | 23.33% | 6.4429 | 0%
2039-11-05 | 2039 | 11 | Nov | 5 | 6 | 0 | 23.33% | 6.4429 | 0%
2039-11-06 | 2039 | 11 | Nov | 6 | 7 | 0 | 23.33% | 6.4429 | 0%
2039-11-07 | 2039 | 11 | Nov | 7 | 1 | 1 | 23.33% | 6.4429 | 0%
2039-11-08 | 2039 | 11 | Nov | 8 | 2 | 1 | 23.33% | 6.4429 | 0%
2039-11-09 | 2039 | 11 | Nov | 9 | 3 | 1 | 23.33% | 6.4429 | 0%
2039-11-10 | 2039 | 11 | Nov | 10 | 4 | 1 | 23.33% | 6.4429 | 0%
2039-11-11 | 2039 | 11 | Nov | 11 | 5 | 1 | 23.33% | 6.4429 | 0%
2039-11-12 | 2039 | 11 | Nov | 12 | 6 | 0 | 23.33% | 6.4429 | 0%
2039-11-13 | 2039 | 11 | Nov | 13 | 7 | 0 | 23.33% | 6.4429 | 0%
2039-11-14 | 2039 | 11 | Nov | 14 | 1 | 1 | 23.33% | 6.4429 | 0%
2039-11-15 | 2039 | 11 | Nov | 15 | 2 | 1 | 23.33% | 6.4429 | 0%
2039-11-16 | 2039 | 11 | Nov | 16 | 3 | 1 | 23.33% | 6.4429 | 0%
2039-11-17 | 2039 | 11 | Nov | 17 | 4 | 1 | 23.33% | 6.4429 | 0%
2039-11-18 | 2039 | 11 | Nov | 18 | 5 | 1 | 23.33% | 6.4429 | 0%
2039-11-19 | 2039 | 11 | Nov | 19 | 6 | 0 | 23.33% | 6.4429 | 0%
2039-11-20 | 2039 | 11 | Nov | 20 | 7 | 0 | 23.33% | 6.4429 | 0%
2039-11-21 | 2039 | 11 | Nov | 21 | 1 | 1 | 23.33% | 6.4429 | 0%
2039-11-22 | 2039 | 11 | Nov | 22 | 2 | 1 | 23.33% | 6.4429 | 0%
2039-11-23 | 2039 | 11 | Nov | 23 | 3 | 1 | 23.33% | 6.4429 | 0%
2039-11-24 | 2039 | 11 | Nov | 24 | 4 | 1 | 23.33% | 6.4429 | 0%
2039-11-25 | 2039 | 11 | Nov | 25 | 5 | 1 | 23.33% | 6.4429 | 0%
2039-11-26 | 2039 | 11 | Nov | 26 | 6 | 0 | 23.33% | 6.4429 | 0%
2039-11-27 | 2039 | 11 | Nov | 27 | 7 | 0 | 23.33% | 6.4429 | 0%
2039-11-28 | 2039 | 11 | Nov | 28 | 1 | 1 | 23.33% | 6.4429 | 0%
2039-11-29 | 2039 | 11 | Nov | 29 | 2 | 1 | 23.33% | 6.4429 | 0%
2039-11-30 | 2039 | 11 | Nov | 30 | 3 | 1 | 23.33% | 6.4429 | 0%
2039-12-01 | 2039 | 12 | Dec | 1 | 4 | 1 | 22.69% | 6.7962 | 0%
2039-12-02 | 2039 | 12 | Dec | 2 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-12-03 | 2039 | 12 | Dec | 3 | 6 | 0 | 22.69% | 6.7962 | 0%
2039-12-04 | 2039 | 12 | Dec | 4 | 7 | 0 | 22.69% | 6.7962 | 0%
2039-12-05 | 2039 | 12 | Dec | 5 | 1 | 1 | 22.69% | 6.7962 | 0%
2039-12-06 | 2039 | 12 | Dec | 6 | 2 | 1 | 22.69% | 6.7962 | 0%
2039-12-07 | 2039 | 12 | Dec | 7 | 3 | 1 | 22.69% | 6.7962 | 0%
2039-12-08 | 2039 | 12 | Dec | 8 | 4 | 1 | 22.69% | 6.7962 | 0%
2039-12-09 | 2039 | 12 | Dec | 9 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-12-10 | 2039 | 12 | Dec | 10 | 6 | 0 | 22.69% | 6.7962 | 0%
2039-12-11 | 2039 | 12 | Dec | 11 | 7 | 0 | 22.69% | 6.7962 | 0%
2039-12-12 | 2039 | 12 | Dec | 12 | 1 | 1 | 22.69% | 6.7962 | 0%
2039-12-13 | 2039 | 12 | Dec | 13 | 2 | 1 | 22.69% | 6.7962 | 0%
2039-12-14 | 2039 | 12 | Dec | 14 | 3 | 1 | 22.69% | 6.7962 | 0%
2039-12-15 | 2039 | 12 | Dec | 15 | 4 | 1 | 22.69% | 6.7962 | 0%
2039-12-16 | 2039 | 12 | Dec | 16 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-12-17 | 2039 | 12 | Dec | 17 | 6 | 0 | 22.69% | 6.7962 | 0%
2039-12-18 | 2039 | 12 | Dec | 18 | 7 | 0 | 22.69% | 6.7962 | 0%
2039-12-19 | 2039 | 12 | Dec | 19 | 1 | 1 | 22.69% | 6.7962 | 0%
2039-12-20 | 2039 | 12 | Dec | 20 | 2 | 1 | 22.69% | 6.7962 | 0%
2039-12-21 | 2039 | 12 | Dec | 21 | 3 | 1 | 22.69% | 6.7962 | 0%
2039-12-22 | 2039 | 12 | Dec | 22 | 4 | 1 | 22.69% | 6.7962 | 0%
2039-12-23 | 2039 | 12 | Dec | 23 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-12-24 | 2039 | 12 | Dec | 24 | 6 | 0 | 22.69% | 6.7962 | 0%
2039-12-25 | 2039 | 12 | Dec | 25 | 7 | 0 | 22.69% | 6.7962 | 0%
2039-12-26 | 2039 | 12 | Dec | 26 | 1 | 1 | 22.69% | 6.7962 | 0%
2039-12-27 | 2039 | 12 | Dec | 27 | 2 | 1 | 22.69% | 6.7962 | 0%
2039-12-28 | 2039 | 12 | Dec | 28 | 3 | 1 | 22.69% | 6.7962 | 0%
2039-12-29 | 2039 | 12 | Dec | 29 | 4 | 1 | 22.69% | 6.7962 | 0%
2039-12-30 | 2039 | 12 | Dec | 30 | 5 | 1 | 22.69% | 6.7962 | 0%
2039-12-31 | 2039 | 12 | Dec | 31 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-01-01 | 2040 | 1 | Jan | 1 | 7 | 0 | 19.46% | 7.0276 | 0%
2040-01-02 | 2040 | 1 | Jan | 2 | 1 | 1 | 19.46% | 7.0276 | 0%
2040-01-03 | 2040 | 1 | Jan | 3 | 2 | 1 | 19.46% | 7.0276 | 0%
2040-01-04 | 2040 | 1 | Jan | 4 | 3 | 1 | 19.46% | 7.0276 | 0%
2040-01-05 | 2040 | 1 | Jan | 5 | 4 | 1 | 19.46% | 7.0276 | 0%
2040-01-06 | 2040 | 1 | Jan | 6 | 5 | 1 | 19.46% | 7.0276 | 0%
2040-01-07 | 2040 | 1 | Jan | 7 | 6 | 0 | 19.46% | 7.0276 | 0%
2040-01-08 | 2040 | 1 | Jan | 8 | 7 | 0 | 19.46% | 7.0276 | 0%
2040-01-09 | 2040 | 1 | Jan | 9 | 1 | 1 | 19.46% | 7.0276 | 0%
2040-01-10 | 2040 | 1 | Jan | 10 | 2 | 1 | 19.46% | 7.0276 | 0%
2040-01-11 | 2040 | 1 | Jan | 11 | 3 | 1 | 19.46% | 7.0276 | 0%
2040-01-12 | 2040 | 1 | Jan | 12 | 4 | 1 | 19.46% | 7.0276 | 0%
2040-01-13 | 2040 | 1 | Jan | 13 | 5 | 1 | 19.46% | 7.0276 | 0%
2040-01-14 | 2040 | 1 | Jan | 14 | 6 | 0 | 19.46% | 7.0276 | 0%
2040-01-15 | 2040 | 1 | Jan | 15 | 7 | 0 | 19.46% | 7.0276 | 0%
2040-01-16 | 2040 | 1 | Jan | 16 | 1 | 1 | 19.46% | 7.0276 | 0%
2040-01-17 | 2040 | 1 | Jan | 17 | 2 | 1 | 19.46% | 7.0276 | 0%
2040-01-18 | 2040 | 1 | Jan | 18 | 3 | 1 | 19.46% | 7.0276 | 0%
2040-01-19 | 2040 | 1 | Jan | 19 | 4 | 1 | 19.46% | 7.0276 | 0%
2040-01-20 | 2040 | 1 | Jan | 20 | 5 | 1 | 19.46% | 7.0276 | 0%
2040-01-21 | 2040 | 1 | Jan | 21 | 6 | 0 | 19.46% | 7.0276 | 0%
2040-01-22 | 2040 | 1 | Jan | 22 | 7 | 0 | 19.46% | 7.0276 | 0%
2040-01-23 | 2040 | 1 | Jan | 23 | 1 | 1 | 19.46% | 7.0276 | 0%
2040-01-24 | 2040 | 1 | Jan | 24 | 2 | 1 | 19.46% | 7.0276 | 0%
2040-01-25 | 2040 | 1 | Jan | 25 | 3 | 1 | 19.46% | 7.0276 | 0%
2040-01-26 | 2040 | 1 | Jan | 26 | 4 | 1 | 19.46% | 7.0276 | 0%
2040-01-27 | 2040 | 1 | Jan | 27 | 5 | 1 | 19.46% | 7.0276 | 0%
2040-01-28 | 2040 | 1 | Jan | 28 | 6 | 0 | 19.46% | 7.0276 | 0%
2040-01-29 | 2040 | 1 | Jan | 29 | 7 | 0 | 19.46% | 7.0276 | 0%
2040-01-30 | 2040 | 1 | Jan | 30 | 1 | 1 | 19.46% | 7.0276 | 0%
2040-01-31 | 2040 | 1 | Jan | 31 | 2 | 1 | 19.46% | 7.0276 | 0%
2040-02-01 | 2040 | 2 | Feb | 1 | 3 | 1 | 18.87% | 7.4625 | 0%
2040-02-02 | 2040 | 2 | Feb | 2 | 4 | 1 | 18.87% | 7.4625 | 0%
2040-02-03 | 2040 | 2 | Feb | 3 | 5 | 1 | 18.87% | 7.4625 | 0%
2040-02-04 | 2040 | 2 | Feb | 4 | 6 | 0 | 18.87% | 7.4625 | 0%
2040-02-05 | 2040 | 2 | Feb | 5 | 7 | 0 | 18.87% | 7.4625 | 0%
2040-02-06 | 2040 | 2 | Feb | 6 | 1 | 1 | 18.87% | 7.4625 | 0%
2040-02-07 | 2040 | 2 | Feb | 7 | 2 | 1 | 18.87% | 7.4625 | 0%
2040-02-08 | 2040 | 2 | Feb | 8 | 3 | 1 | 18.87% | 7.4625 | 0%
2040-02-09 | 2040 | 2 | Feb | 9 | 4 | 1 | 18.87% | 7.4625 | 0%
2040-02-10 | 2040 | 2 | Feb | 10 | 5 | 1 | 18.87% | 7.4625 | 0%
2040-02-11 | 2040 | 2 | Feb | 11 | 6 | 0 | 18.87% | 7.4625 | 0%
2040-02-12 | 2040 | 2 | Feb | 12 | 7 | 0 | 18.87% | 7.4625 | 0%
2040-02-13 | 2040 | 2 | Feb | 13 | 1 | 1 | 18.87% | 7.4625 | 0%
2040-02-14 | 2040 | 2 | Feb | 14 | 2 | 1 | 18.87% | 7.4625 | 0%
2040-02-15 | 2040 | 2 | Feb | 15 | 3 | 1 | 18.87% | 7.4625 | 0%
2040-02-16 | 2040 | 2 | Feb | 16 | 4 | 1 | 18.87% | 7.4625 | 0%
2040-02-17 | 2040 | 2 | Feb | 17 | 5 | 1 | 18.87% | 7.4625 | 0%
2040-02-18 | 2040 | 2 | Feb | 18 | 6 | 0 | 18.87% | 7.4625 | 0%
2040-02-19 | 2040 | 2 | Feb | 19 | 7 | 0 | 18.87% | 7.4625 | 0%
2040-02-20 | 2040 | 2 | Feb | 20 | 1 | 1 | 18.87% | 7.4625 | 0%
2040-02-21 | 2040 | 2 | Feb | 21 | 2 | 1 | 18.87% | 7.4625 | 0%
2040-02-22 | 2040 | 2 | Feb | 22 | 3 | 1 | 18.87% | 7.4625 | 0%
2040-02-23 | 2040 | 2 | Feb | 23 | 4 | 1 | 18.87% | 7.4625 | 0%
2040-02-24 | 2040 | 2 | Feb | 24 | 5 | 1 | 18.87% | 7.4625 | 0%
2040-02-25 | 2040 | 2 | Feb | 25 | 6 | 0 | 18.87% | 7.4625 | 0%
2040-02-26 | 2040 | 2 | Feb | 26 | 7 | 0 | 18.87% | 7.4625 | 0%
2040-02-27 | 2040 | 2 | Feb | 27 | 1 | 1 | 18.87% | 7.4625 | 0%
2040-02-28 | 2040 | 2 | Feb | 28 | 2 | 1 | 18.87% | 7.4625 | 0%
2040-02-29 | 2040 | 2 | Feb | 29 | 3 | 1 | 18.87% | 7.4625 | 0%
2040-03-01 | 2040 | 3 | Mar | 1 | 4 | 1 | 18.49% | 7.8663 | 0%
2040-03-02 | 2040 | 3 | Mar | 2 | 5 | 1 | 18.49% | 7.8663 | 0%
2040-03-03 | 2040 | 3 | Mar | 3 | 6 | 0 | 18.49% | 7.8663 | 0%
2040-03-04 | 2040 | 3 | Mar | 4 | 7 | 0 | 18.49% | 7.8663 | 0%
2040-03-05 | 2040 | 3 | Mar | 5 | 1 | 1 | 18.49% | 7.8663 | 0%
2040-03-06 | 2040 | 3 | Mar | 6 | 2 | 1 | 18.49% | 7.8663 | 0%
2040-03-07 | 2040 | 3 | Mar | 7 | 3 | 1 | 18.49% | 7.8663 | 0%
2040-03-08 | 2040 | 3 | Mar | 8 | 4 | 1 | 18.49% | 7.8663 | 0%
2040-03-09 | 2040 | 3 | Mar | 9 | 5 | 1 | 18.49% | 7.8663 | 0%
2040-03-10 | 2040 | 3 | Mar | 10 | 6 | 0 | 18.49% | 7.8663 | 0%
2040-03-11 | 2040 | 3 | Mar | 11 | 7 | 0 | 18.49% | 7.8663 | 0%
2040-03-12 | 2040 | 3 | Mar | 12 | 1 | 1 | 18.49% | 7.8663 | 0%
2040-03-13 | 2040 | 3 | Mar | 13 | 2 | 1 | 18.49% | 7.8663 | 0%
2040-03-14 | 2040 | 3 | Mar | 14 | 3 | 1 | 18.49% | 7.8663 | 0%
2040-03-15 | 2040 | 3 | Mar | 15 | 4 | 1 | 18.49% | 7.8663 | 0%
2040-03-16 | 2040 | 3 | Mar | 16 | 5 | 1 | 18.49% | 7.8663 | 0%
2040-03-17 | 2040 | 3 | Mar | 17 | 6 | 0 | 18.49% | 7.8663 | 0%
2040-03-18 | 2040 | 3 | Mar | 18 | 7 | 0 | 18.49% | 7.8663 | 0%
2040-03-19 | 2040 | 3 | Mar | 19 | 1 | 1 | 18.49% | 7.8663 | 0%
2040-03-20 | 2040 | 3 | Mar | 20 | 2 | 1 | 18.49% | 7.8663 | 0%
2040-03-21 | 2040 | 3 | Mar | 21 | 3 | 1 | 18.49% | 7.8663 | 0%
2040-03-22 | 2040 | 3 | Mar | 22 | 4 | 1 | 18.49% | 7.8663 | 0%
2040-03-23 | 2040 | 3 | Mar | 23 | 5 | 1 | 18.49% | 7.8663 | 0%
2040-03-24 | 2040 | 3 | Mar | 24 | 6 | 0 | 18.49% | 7.8663 | 0%
2040-03-25 | 2040 | 3 | Mar | 25 | 7 | 0 | 18.49% | 7.8663 | 0%
2040-03-26 | 2040 | 3 | Mar | 26 | 1 | 1 | 18.49% | 7.8663 | 0%
2040-03-27 | 2040 | 3 | Mar | 27 | 2 | 1 | 18.49% | 7.8663 | 0%
2040-03-28 | 2040 | 3 | Mar | 28 | 3 | 1 | 18.49% | 7.8663 | 0%
2040-03-29 | 2040 | 3 | Mar | 29 | 4 | 1 | 18.49% | 7.8663 | 0%
2040-03-30 | 2040 | 3 | Mar | 30 | 5 | 1 | 18.49% | 7.8663 | 0%
2040-03-31 | 2040 | 3 | Mar | 31 | 6 | 0 | 18.49% | 7.8663 | 0%
2040-04-01 | 2040 | 4 | Apr | 1 | 7 | 0 | 25.56% | 7.5 | 0%
2040-04-02 | 2040 | 4 | Apr | 2 | 1 | 1 | 25.56% | 7.5 | 0%
2040-04-03 | 2040 | 4 | Apr | 3 | 2 | 1 | 25.56% | 7.5 | 0%
2040-04-04 | 2040 | 4 | Apr | 4 | 3 | 1 | 25.56% | 7.5 | 0%
2040-04-05 | 2040 | 4 | Apr | 5 | 4 | 1 | 25.56% | 7.5 | 0%
2040-04-06 | 2040 | 4 | Apr | 6 | 5 | 1 | 25.56% | 7.5 | 0%
2040-04-07 | 2040 | 4 | Apr | 7 | 6 | 0 | 25.56% | 7.5 | 0%
2040-04-08 | 2040 | 4 | Apr | 8 | 7 | 0 | 25.56% | 7.5 | 0%
2040-04-09 | 2040 | 4 | Apr | 9 | 1 | 1 | 25.56% | 7.5 | 0%
2040-04-10 | 2040 | 4 | Apr | 10 | 2 | 1 | 25.56% | 7.5 | 0%
2040-04-11 | 2040 | 4 | Apr | 11 | 3 | 1 | 25.56% | 7.5 | 0%
2040-04-12 | 2040 | 4 | Apr | 12 | 4 | 1 | 25.56% | 7.5 | 0%
2040-04-13 | 2040 | 4 | Apr | 13 | 5 | 1 | 25.56% | 7.5 | 0%
2040-04-14 | 2040 | 4 | Apr | 14 | 6 | 0 | 25.56% | 7.5 | 0%
2040-04-15 | 2040 | 4 | Apr | 15 | 7 | 0 | 25.56% | 7.5 | 0%
2040-04-16 | 2040 | 4 | Apr | 16 | 1 | 1 | 25.56% | 7.5 | 0%
2040-04-17 | 2040 | 4 | Apr | 17 | 2 | 1 | 25.56% | 7.5 | 0%
2040-04-18 | 2040 | 4 | Apr | 18 | 3 | 1 | 25.56% | 7.5 | 0%
2040-04-19 | 2040 | 4 | Apr | 19 | 4 | 1 | 25.56% | 7.5 | 0%
2040-04-20 | 2040 | 4 | Apr | 20 | 5 | 1 | 25.56% | 7.5 | 0%
2040-04-21 | 2040 | 4 | Apr | 21 | 6 | 0 | 25.56% | 7.5 | 0%
2040-04-22 | 2040 | 4 | Apr | 22 | 7 | 0 | 25.56% | 7.5 | 0%
2040-04-23 | 2040 | 4 | Apr | 23 | 1 | 1 | 25.56% | 7.5 | 0%
2040-04-24 | 2040 | 4 | Apr | 24 | 2 | 1 | 25.56% | 7.5 | 0%
2040-04-25 | 2040 | 4 | Apr | 25 | 3 | 1 | 25.56% | 7.5 | 0%
2040-04-26 | 2040 | 4 | Apr | 26 | 4 | 1 | 25.56% | 7.5 | 0%
2040-04-27 | 2040 | 4 | Apr | 27 | 5 | 1 | 25.56% | 7.5 | 0%
2040-04-28 | 2040 | 4 | Apr | 28 | 6 | 0 | 25.56% | 7.5 | 0%
2040-04-29 | 2040 | 4 | Apr | 29 | 7 | 0 | 25.56% | 7.5 | 0%
2040-04-30 | 2040 | 4 | Apr | 30 | 1 | 1 | 25.56% | 7.5 | 0%
2040-05-01 | 2040 | 5 | May | 1 | 2 | 1 | 23.01% | 8.1449 | 0%
2040-05-02 | 2040 | 5 | May | 2 | 3 | 1 | 23.01% | 8.1449 | 0%
2040-05-03 | 2040 | 5 | May | 3 | 4 | 1 | 23.01% | 8.1449 | 0%
2040-05-04 | 2040 | 5 | May | 4 | 5 | 1 | 23.01% | 8.1449 | 0%
2040-05-05 | 2040 | 5 | May | 5 | 6 | 0 | 23.01% | 8.1449 | 0%
2040-05-06 | 2040 | 5 | May | 6 | 7 | 0 | 23.01% | 8.1449 | 0%
2040-05-07 | 2040 | 5 | May | 7 | 1 | 1 | 23.01% | 8.1449 | 0%
2040-05-08 | 2040 | 5 | May | 8 | 2 | 1 | 23.01% | 8.1449 | 0%
2040-05-09 | 2040 | 5 | May | 9 | 3 | 1 | 23.01% | 8.1449 | 0%
2040-05-10 | 2040 | 5 | May | 10 | 4 | 1 | 23.01% | 8.1449 | 0%
2040-05-11 | 2040 | 5 | May | 11 | 5 | 1 | 23.01% | 8.1449 | 0%
2040-05-12 | 2040 | 5 | May | 12 | 6 | 0 | 23.01% | 8.1449 | 0%
2040-05-13 | 2040 | 5 | May | 13 | 7 | 0 | 23.01% | 8.1449 | 0%
2040-05-14 | 2040 | 5 | May | 14 | 1 | 1 | 23.01% | 8.1449 | 0%
2040-05-15 | 2040 | 5 | May | 15 | 2 | 1 | 23.01% | 8.1449 | 0%
2040-05-16 | 2040 | 5 | May | 16 | 3 | 1 | 23.01% | 8.1449 | 0%
2040-05-17 | 2040 | 5 | May | 17 | 4 | 1 | 23.01% | 8.1449 | 0%
2040-05-18 | 2040 | 5 | May | 18 | 5 | 1 | 23.01% | 8.1449 | 0%
2040-05-19 | 2040 | 5 | May | 19 | 6 | 0 | 23.01% | 8.1449 | 0%
2040-05-20 | 2040 | 5 | May | 20 | 7 | 0 | 23.01% | 8.1449 | 0%
2040-05-21 | 2040 | 5 | May | 21 | 1 | 1 | 23.01% | 8.1449 | 0%
2040-05-22 | 2040 | 5 | May | 22 | 2 | 1 | 23.01% | 8.1449 | 0%
2040-05-23 | 2040 | 5 | May | 23 | 3 | 1 | 23.01% | 8.1449 | 0%
2040-05-24 | 2040 | 5 | May | 24 | 4 | 1 | 23.01% | 8.1449 | 0%
2040-05-25 | 2040 | 5 | May | 25 | 5 | 1 | 23.01% | 8.1449 | 0%
2040-05-26 | 2040 | 5 | May | 26 | 6 | 0 | 23.01% | 8.1449 | 0%
2040-05-27 | 2040 | 5 | May | 27 | 7 | 0 | 23.01% | 8.1449 | 0%
2040-05-28 | 2040 | 5 | May | 28 | 1 | 1 | 23.01% | 8.1449 | 0%
2040-05-29 | 2040 | 5 | May | 29 | 2 | 1 | 23.01% | 8.1449 | 0%
2040-05-30 | 2040 | 5 | May | 30 | 3 | 1 | 23.01% | 8.1449 | 0%
2040-05-31 | 2040 | 5 | May | 31 | 4 | 1 | 23.01% | 8.1449 | 0%
2040-06-01 | 2040 | 6 | Jun | 1 | 5 | 1 | 28.67% | 7.9419 | 0%
2040-06-02 | 2040 | 6 | Jun | 2 | 6 | 0 | 28.67% | 7.9419 | 0%
2040-06-03 | 2040 | 6 | Jun | 3 | 7 | 0 | 28.67% | 7.9419 | 0%
2040-06-04 | 2040 | 6 | Jun | 4 | 1 | 1 | 28.67% | 7.9419 | 0%
2040-06-05 | 2040 | 6 | Jun | 5 | 2 | 1 | 28.67% | 7.9419 | 0%
2040-06-06 | 2040 | 6 | Jun | 6 | 3 | 1 | 28.67% | 7.9419 | 0%
2040-06-07 | 2040 | 6 | Jun | 7 | 4 | 1 | 28.67% | 7.9419 | 0%
2040-06-08 | 2040 | 6 | Jun | 8 | 5 | 1 | 28.67% | 7.9419 | 0%
2040-06-09 | 2040 | 6 | Jun | 9 | 6 | 0 | 28.67% | 7.9419 | 0%
2040-06-10 | 2040 | 6 | Jun | 10 | 7 | 0 | 28.67% | 7.9419 | 0%
2040-06-11 | 2040 | 6 | Jun | 11 | 1 | 1 | 28.67% | 7.9419 | 0%
2040-06-12 | 2040 | 6 | Jun | 12 | 2 | 1 | 28.67% | 7.9419 | 0%
2040-06-13 | 2040 | 6 | Jun | 13 | 3 | 1 | 28.67% | 7.9419 | 0%
2040-06-14 | 2040 | 6 | Jun | 14 | 4 | 1 | 28.67% | 7.9419 | 0%
2040-06-15 | 2040 | 6 | Jun | 15 | 5 | 1 | 28.67% | 7.9419 | 0%
2040-06-16 | 2040 | 6 | Jun | 16 | 6 | 0 | 28.67% | 7.9419 | 0%
2040-06-17 | 2040 | 6 | Jun | 17 | 7 | 0 | 28.67% | 7.9419 | 0%
2040-06-18 | 2040 | 6 | Jun | 18 | 1 | 1 | 28.67% | 7.9419 | 0%
2040-06-19 | 2040 | 6 | Jun | 19 | 2 | 1 | 28.67% | 7.9419 | 0%
2040-06-20 | 2040 | 6 | Jun | 20 | 3 | 1 | 28.67% | 7.9419 | 0%
2040-06-21 | 2040 | 6 | Jun | 21 | 4 | 1 | 28.67% | 7.9419 | 0%
2040-06-22 | 2040 | 6 | Jun | 22 | 5 | 1 | 28.67% | 7.9419 | 0%
2040-06-23 | 2040 | 6 | Jun | 23 | 6 | 0 | 28.67% | 7.9419 | 0%
2040-06-24 | 2040 | 6 | Jun | 24 | 7 | 0 | 28.67% | 7.9419 | 0%
2040-06-25 | 2040 | 6 | Jun | 25 | 1 | 1 | 28.67% | 7.9419 | 0%
2040-06-26 | 2040 | 6 | Jun | 26 | 2 | 1 | 28.67% | 7.9419 | 0%
2040-06-27 | 2040 | 6 | Jun | 27 | 3 | 1 | 28.67% | 7.9419 | 0%
2040-06-28 | 2040 | 6 | Jun | 28 | 4 | 1 | 28.67% | 7.9419 | 0%
2040-06-29 | 2040 | 6 | Jun | 29 | 5 | 1 | 28.67% | 7.9419 | 0%
2040-06-30 | 2040 | 6 | Jun | 30 | 6 | 0 | 28.67% | 7.9419 | 0%
2040-07-01 | 2040 | 7 | Jul | 1 | 7 | 0 | 24.73% | 8.3739 | 0%
2040-07-02 | 2040 | 7 | Jul | 2 | 1 | 1 | 24.73% | 8.3739 | 0%
2040-07-03 | 2040 | 7 | Jul | 3 | 2 | 1 | 24.73% | 8.3739 | 0%
2040-07-04 | 2040 | 7 | Jul | 4 | 3 | 1 | 24.73% | 8.3739 | 0%
2040-07-05 | 2040 | 7 | Jul | 5 | 4 | 1 | 24.73% | 8.3739 | 0%
2040-07-06 | 2040 | 7 | Jul | 6 | 5 | 1 | 24.73% | 8.3739 | 0%
2040-07-07 | 2040 | 7 | Jul | 7 | 6 | 0 | 24.73% | 8.3739 | 0%
2040-07-08 | 2040 | 7 | Jul | 8 | 7 | 0 | 24.73% | 8.3739 | 0%
2040-07-09 | 2040 | 7 | Jul | 9 | 1 | 1 | 24.73% | 8.3739 | 0%
2040-07-10 | 2040 | 7 | Jul | 10 | 2 | 1 | 24.73% | 8.3739 | 0%
2040-07-11 | 2040 | 7 | Jul | 11 | 3 | 1 | 24.73% | 8.3739 | 0%
2040-07-12 | 2040 | 7 | Jul | 12 | 4 | 1 | 24.73% | 8.3739 | 0%
2040-07-13 | 2040 | 7 | Jul | 13 | 5 | 1 | 24.73% | 8.3739 | 0%
2040-07-14 | 2040 | 7 | Jul | 14 | 6 | 0 | 24.73% | 8.3739 | 0%
2040-07-15 | 2040 | 7 | Jul | 15 | 7 | 0 | 24.73% | 8.3739 | 0%
2040-07-16 | 2040 | 7 | Jul | 16 | 1 | 1 | 24.73% | 8.3739 | 0%
2040-07-17 | 2040 | 7 | Jul | 17 | 2 | 1 | 24.73% | 8.3739 | 0%
2040-07-18 | 2040 | 7 | Jul | 18 | 3 | 1 | 24.73% | 8.3739 | 0%
2040-07-19 | 2040 | 7 | Jul | 19 | 4 | 1 | 24.73% | 8.3739 | 0%
2040-07-20 | 2040 | 7 | Jul | 20 | 5 | 1 | 24.73% | 8.3739 | 0%
2040-07-21 | 2040 | 7 | Jul | 21 | 6 | 0 | 24.73% | 8.3739 | 0%
2040-07-22 | 2040 | 7 | Jul | 22 | 7 | 0 | 24.73% | 8.3739 | 0%
2040-07-23 | 2040 | 7 | Jul | 23 | 1 | 1 | 24.73% | 8.3739 | 0%
2040-07-24 | 2040 | 7 | Jul | 24 | 2 | 1 | 24.73% | 8.3739 | 0%
2040-07-25 | 2040 | 7 | Jul | 25 | 3 | 1 | 24.73% | 8.3739 | 0%
2040-07-26 | 2040 | 7 | Jul | 26 | 4 | 1 | 24.73% | 8.3739 | 0%
2040-07-27 | 2040 | 7 | Jul | 27 | 5 | 1 | 24.73% | 8.3739 | 0%
2040-07-28 | 2040 | 7 | Jul | 28 | 6 | 0 | 24.73% | 8.3739 | 0%
2040-07-29 | 2040 | 7 | Jul | 29 | 7 | 0 | 24.73% | 8.3739 | 0%
2040-07-30 | 2040 | 7 | Jul | 30 | 1 | 1 | 24.73% | 8.3739 | 0%
2040-07-31 | 2040 | 7 | Jul | 31 | 2 | 1 | 24.73% | 8.3739 | 0%
2040-08-01 | 2040 | 8 | Aug | 1 | 3 | 1 | 23.55% | 7.9589 | 0%
2040-08-02 | 2040 | 8 | Aug | 2 | 4 | 1 | 23.55% | 7.9589 | 0%
2040-08-03 | 2040 | 8 | Aug | 3 | 5 | 1 | 23.55% | 7.9589 | 0%
2040-08-04 | 2040 | 8 | Aug | 4 | 6 | 0 | 23.55% | 7.9589 | 0%
2040-08-05 | 2040 | 8 | Aug | 5 | 7 | 0 | 23.55% | 7.9589 | 0%
2040-08-06 | 2040 | 8 | Aug | 6 | 1 | 1 | 23.55% | 7.9589 | 0%
2040-08-07 | 2040 | 8 | Aug | 7 | 2 | 1 | 23.55% | 7.9589 | 0%
2040-08-08 | 2040 | 8 | Aug | 8 | 3 | 1 | 23.55% | 7.9589 | 0%
2040-08-09 | 2040 | 8 | Aug | 9 | 4 | 1 | 23.55% | 7.9589 | 0%
2040-08-10 | 2040 | 8 | Aug | 10 | 5 | 1 | 23.55% | 7.9589 | 0%
2040-08-11 | 2040 | 8 | Aug | 11 | 6 | 0 | 23.55% | 7.9589 | 0%
2040-08-12 | 2040 | 8 | Aug | 12 | 7 | 0 | 23.55% | 7.9589 | 0%
2040-08-13 | 2040 | 8 | Aug | 13 | 1 | 1 | 23.55% | 7.9589 | 0%
2040-08-14 | 2040 | 8 | Aug | 14 | 2 | 1 | 23.55% | 7.9589 | 0%
2040-08-15 | 2040 | 8 | Aug | 15 | 3 | 1 | 23.55% | 7.9589 | 0%
2040-08-16 | 2040 | 8 | Aug | 16 | 4 | 1 | 23.55% | 7.9589 | 0%
2040-08-17 | 2040 | 8 | Aug | 17 | 5 | 1 | 23.55% | 7.9589 | 0%
2040-08-18 | 2040 | 8 | Aug | 18 | 6 | 0 | 23.55% | 7.9589 | 0%
2040-08-19 | 2040 | 8 | Aug | 19 | 7 | 0 | 23.55% | 7.9589 | 0%
2040-08-20 | 2040 | 8 | Aug | 20 | 1 | 1 | 23.55% | 7.9589 | 0%
2040-08-21 | 2040 | 8 | Aug | 21 | 2 | 1 | 23.55% | 7.9589 | 0%
2040-08-22 | 2040 | 8 | Aug | 22 | 3 | 1 | 23.55% | 7.9589 | 0%
2040-08-23 | 2040 | 8 | Aug | 23 | 4 | 1 | 23.55% | 7.9589 | 0%
2040-08-24 | 2040 | 8 | Aug | 24 | 5 | 1 | 23.55% | 7.9589 | 0%
2040-08-25 | 2040 | 8 | Aug | 25 | 6 | 0 | 23.55% | 7.9589 | 0%
2040-08-26 | 2040 | 8 | Aug | 26 | 7 | 0 | 23.55% | 7.9589 | 0%
2040-08-27 | 2040 | 8 | Aug | 27 | 1 | 1 | 23.55% | 7.9589 | 0%
2040-08-28 | 2040 | 8 | Aug | 28 | 2 | 1 | 23.55% | 7.9589 | 0%
2040-08-29 | 2040 | 8 | Aug | 29 | 3 | 1 | 23.55% | 7.9589 | 0%
2040-08-30 | 2040 | 8 | Aug | 30 | 4 | 1 | 23.55% | 7.9589 | 0%
2040-08-31 | 2040 | 8 | Aug | 31 | 5 | 1 | 23.55% | 7.9589 | 0%
2040-09-01 | 2040 | 9 | Sep | 1 | 6 | 0 | 20.67% | 6.8065 | 0%
2040-09-02 | 2040 | 9 | Sep | 2 | 7 | 0 | 20.67% | 6.8065 | 0%
2040-09-03 | 2040 | 9 | Sep | 3 | 1 | 1 | 20.67% | 6.8065 | 0%
2040-09-04 | 2040 | 9 | Sep | 4 | 2 | 1 | 20.67% | 6.8065 | 0%
2040-09-05 | 2040 | 9 | Sep | 5 | 3 | 1 | 20.67% | 6.8065 | 0%
2040-09-06 | 2040 | 9 | Sep | 6 | 4 | 1 | 20.67% | 6.8065 | 0%
2040-09-07 | 2040 | 9 | Sep | 7 | 5 | 1 | 20.67% | 6.8065 | 0%
2040-09-08 | 2040 | 9 | Sep | 8 | 6 | 0 | 20.67% | 6.8065 | 0%
2040-09-09 | 2040 | 9 | Sep | 9 | 7 | 0 | 20.67% | 6.8065 | 0%
2040-09-10 | 2040 | 9 | Sep | 10 | 1 | 1 | 20.67% | 6.8065 | 0%
2040-09-11 | 2040 | 9 | Sep | 11 | 2 | 1 | 20.67% | 6.8065 | 0%
2040-09-12 | 2040 | 9 | Sep | 12 | 3 | 1 | 20.67% | 6.8065 | 0%
2040-09-13 | 2040 | 9 | Sep | 13 | 4 | 1 | 20.67% | 6.8065 | 0%
2040-09-14 | 2040 | 9 | Sep | 14 | 5 | 1 | 20.67% | 6.8065 | 0%
2040-09-15 | 2040 | 9 | Sep | 15 | 6 | 0 | 20.67% | 6.8065 | 0%
2040-09-16 | 2040 | 9 | Sep | 16 | 7 | 0 | 20.67% | 6.8065 | 0%
2040-09-17 | 2040 | 9 | Sep | 17 | 1 | 1 | 20.67% | 6.8065 | 0%
2040-09-18 | 2040 | 9 | Sep | 18 | 2 | 1 | 20.67% | 6.8065 | 0%
2040-09-19 | 2040 | 9 | Sep | 19 | 3 | 1 | 20.67% | 6.8065 | 0%
2040-09-20 | 2040 | 9 | Sep | 20 | 4 | 1 | 20.67% | 6.8065 | 0%
2040-09-21 | 2040 | 9 | Sep | 21 | 5 | 1 | 20.67% | 6.8065 | 0%
2040-09-22 | 2040 | 9 | Sep | 22 | 6 | 0 | 20.67% | 6.8065 | 0%
2040-09-23 | 2040 | 9 | Sep | 23 | 7 | 0 | 20.67% | 6.8065 | 0%
2040-09-24 | 2040 | 9 | Sep | 24 | 1 | 1 | 20.67% | 6.8065 | 0%
2040-09-25 | 2040 | 9 | Sep | 25 | 2 | 1 | 20.67% | 6.8065 | 0%
2040-09-26 | 2040 | 9 | Sep | 26 | 3 | 1 | 20.67% | 6.8065 | 0%
2040-09-27 | 2040 | 9 | Sep | 27 | 4 | 1 | 20.67% | 6.8065 | 0%
2040-09-28 | 2040 | 9 | Sep | 28 | 5 | 1 | 20.67% | 6.8065 | 0%
2040-09-29 | 2040 | 9 | Sep | 29 | 6 | 0 | 20.67% | 6.8065 | 0%
2040-09-30 | 2040 | 9 | Sep | 30 | 7 | 0 | 20.67% | 6.8065 | 0%
2040-10-01 | 2040 | 10 | Oct | 1 | 1 | 1 | 23.23% | 6.8194 | 0%
2040-10-02 | 2040 | 10 | Oct | 2 | 2 | 1 | 23.23% | 6.8194 | 0%
2040-10-03 | 2040 | 10 | Oct | 3 | 3 | 1 | 23.23% | 6.8194 | 0%
2040-10-04 | 2040 | 10 | Oct | 4 | 4 | 1 | 23.23% | 6.8194 | 0%
2040-10-05 | 2040 | 10 | Oct | 5 | 5 | 1 | 23.23% | 6.8194 | 0%
2040-10-06 | 2040 | 10 | Oct | 6 | 6 | 0 | 23.23% | 6.8194 | 0%
2040-10-07 | 2040 | 10 | Oct | 7 | 7 | 0 | 23.23% | 6.8194 | 0%
2040-10-08 | 2040 | 10 | Oct | 8 | 1 | 1 | 23.23% | 6.8194 | 0%
2040-10-09 | 2040 | 10 | Oct | 9 | 2 | 1 | 23.23% | 6.8194 | 0%
2040-10-10 | 2040 | 10 | Oct | 10 | 3 | 1 | 23.23% | 6.8194 | 0%
2040-10-11 | 2040 | 10 | Oct | 11 | 4 | 1 | 23.23% | 6.8194 | 0%
2040-10-12 | 2040 | 10 | Oct | 12 | 5 | 1 | 23.23% | 6.8194 | 0%
2040-10-13 | 2040 | 10 | Oct | 13 | 6 | 0 | 23.23% | 6.8194 | 0%
2040-10-14 | 2040 | 10 | Oct | 14 | 7 | 0 | 23.23% | 6.8194 | 0%
2040-10-15 | 2040 | 10 | Oct | 15 | 1 | 1 | 23.23% | 6.8194 | 0%
2040-10-16 | 2040 | 10 | Oct | 16 | 2 | 1 | 23.23% | 6.8194 | 0%
2040-10-17 | 2040 | 10 | Oct | 17 | 3 | 1 | 23.23% | 6.8194 | 0%
2040-10-18 | 2040 | 10 | Oct | 18 | 4 | 1 | 23.23% | 6.8194 | 0%
2040-10-19 | 2040 | 10 | Oct | 19 | 5 | 1 | 23.23% | 6.8194 | 0%
2040-10-20 | 2040 | 10 | Oct | 20 | 6 | 0 | 23.23% | 6.8194 | 0%
2040-10-21 | 2040 | 10 | Oct | 21 | 7 | 0 | 23.23% | 6.8194 | 0%
2040-10-22 | 2040 | 10 | Oct | 22 | 1 | 1 | 23.23% | 6.8194 | 0%
2040-10-23 | 2040 | 10 | Oct | 23 | 2 | 1 | 23.23% | 6.8194 | 0%
2040-10-24 | 2040 | 10 | Oct | 24 | 3 | 1 | 23.23% | 6.8194 | 0%
2040-10-25 | 2040 | 10 | Oct | 25 | 4 | 1 | 23.23% | 6.8194 | 0%
2040-10-26 | 2040 | 10 | Oct | 26 | 5 | 1 | 23.23% | 6.8194 | 0%
2040-10-27 | 2040 | 10 | Oct | 27 | 6 | 0 | 23.23% | 6.8194 | 0%
2040-10-28 | 2040 | 10 | Oct | 28 | 7 | 0 | 23.23% | 6.8194 | 0%
2040-10-29 | 2040 | 10 | Oct | 29 | 1 | 1 | 23.23% | 6.8194 | 0%
2040-10-30 | 2040 | 10 | Oct | 30 | 2 | 1 | 23.23% | 6.8194 | 0%
2040-10-31 | 2040 | 10 | Oct | 31 | 3 | 1 | 23.23% | 6.8194 | 0%
2040-11-01 | 2040 | 11 | Nov | 1 | 4 | 1 | 23.33% | 6.4429 | 0%
2040-11-02 | 2040 | 11 | Nov | 2 | 5 | 1 | 23.33% | 6.4429 | 0%
2040-11-03 | 2040 | 11 | Nov | 3 | 6 | 0 | 23.33% | 6.4429 | 0%
2040-11-04 | 2040 | 11 | Nov | 4 | 7 | 0 | 23.33% | 6.4429 | 0%
2040-11-05 | 2040 | 11 | Nov | 5 | 1 | 1 | 23.33% | 6.4429 | 0%
2040-11-06 | 2040 | 11 | Nov | 6 | 2 | 1 | 23.33% | 6.4429 | 0%
2040-11-07 | 2040 | 11 | Nov | 7 | 3 | 1 | 23.33% | 6.4429 | 0%
2040-11-08 | 2040 | 11 | Nov | 8 | 4 | 1 | 23.33% | 6.4429 | 0%
2040-11-09 | 2040 | 11 | Nov | 9 | 5 | 1 | 23.33% | 6.4429 | 0%
2040-11-10 | 2040 | 11 | Nov | 10 | 6 | 0 | 23.33% | 6.4429 | 0%
2040-11-11 | 2040 | 11 | Nov | 11 | 7 | 0 | 23.33% | 6.4429 | 0%
2040-11-12 | 2040 | 11 | Nov | 12 | 1 | 1 | 23.33% | 6.4429 | 0%
2040-11-13 | 2040 | 11 | Nov | 13 | 2 | 1 | 23.33% | 6.4429 | 0%
2040-11-14 | 2040 | 11 | Nov | 14 | 3 | 1 | 23.33% | 6.4429 | 0%
2040-11-15 | 2040 | 11 | Nov | 15 | 4 | 1 | 23.33% | 6.4429 | 0%
2040-11-16 | 2040 | 11 | Nov | 16 | 5 | 1 | 23.33% | 6.4429 | 0%
2040-11-17 | 2040 | 11 | Nov | 17 | 6 | 0 | 23.33% | 6.4429 | 0%
2040-11-18 | 2040 | 11 | Nov | 18 | 7 | 0 | 23.33% | 6.4429 | 0%
2040-11-19 | 2040 | 11 | Nov | 19 | 1 | 1 | 23.33% | 6.4429 | 0%
2040-11-20 | 2040 | 11 | Nov | 20 | 2 | 1 | 23.33% | 6.4429 | 0%
2040-11-21 | 2040 | 11 | Nov | 21 | 3 | 1 | 23.33% | 6.4429 | 0%
2040-11-22 | 2040 | 11 | Nov | 22 | 4 | 1 | 23.33% | 6.4429 | 0%
2040-11-23 | 2040 | 11 | Nov | 23 | 5 | 1 | 23.33% | 6.4429 | 0%
2040-11-24 | 2040 | 11 | Nov | 24 | 6 | 0 | 23.33% | 6.4429 | 0%
2040-11-25 | 2040 | 11 | Nov | 25 | 7 | 0 | 23.33% | 6.4429 | 0%
2040-11-26 | 2040 | 11 | Nov | 26 | 1 | 1 | 23.33% | 6.4429 | 0%
2040-11-27 | 2040 | 11 | Nov | 27 | 2 | 1 | 23.33% | 6.4429 | 0%
2040-11-28 | 2040 | 11 | Nov | 28 | 3 | 1 | 23.33% | 6.4429 | 0%
2040-11-29 | 2040 | 11 | Nov | 29 | 4 | 1 | 23.33% | 6.4429 | 0%
2040-11-30 | 2040 | 11 | Nov | 30 | 5 | 1 | 23.33% | 6.4429 | 0%
2040-12-01 | 2040 | 12 | Dec | 1 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-12-02 | 2040 | 12 | Dec | 2 | 7 | 0 | 22.69% | 6.7962 | 0%
2040-12-03 | 2040 | 12 | Dec | 3 | 1 | 1 | 22.69% | 6.7962 | 0%
2040-12-04 | 2040 | 12 | Dec | 4 | 2 | 1 | 22.69% | 6.7962 | 0%
2040-12-05 | 2040 | 12 | Dec | 5 | 3 | 1 | 22.69% | 6.7962 | 0%
2040-12-06 | 2040 | 12 | Dec | 6 | 4 | 1 | 22.69% | 6.7962 | 0%
2040-12-07 | 2040 | 12 | Dec | 7 | 5 | 1 | 22.69% | 6.7962 | 0%
2040-12-08 | 2040 | 12 | Dec | 8 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-12-09 | 2040 | 12 | Dec | 9 | 7 | 0 | 22.69% | 6.7962 | 0%
2040-12-10 | 2040 | 12 | Dec | 10 | 1 | 1 | 22.69% | 6.7962 | 0%
2040-12-11 | 2040 | 12 | Dec | 11 | 2 | 1 | 22.69% | 6.7962 | 0%
2040-12-12 | 2040 | 12 | Dec | 12 | 3 | 1 | 22.69% | 6.7962 | 0%
2040-12-13 | 2040 | 12 | Dec | 13 | 4 | 1 | 22.69% | 6.7962 | 0%
2040-12-14 | 2040 | 12 | Dec | 14 | 5 | 1 | 22.69% | 6.7962 | 0%
2040-12-15 | 2040 | 12 | Dec | 15 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-12-16 | 2040 | 12 | Dec | 16 | 7 | 0 | 22.69% | 6.7962 | 0%
2040-12-17 | 2040 | 12 | Dec | 17 | 1 | 1 | 22.69% | 6.7962 | 0%
2040-12-18 | 2040 | 12 | Dec | 18 | 2 | 1 | 22.69% | 6.7962 | 0%
2040-12-19 | 2040 | 12 | Dec | 19 | 3 | 1 | 22.69% | 6.7962 | 0%
2040-12-20 | 2040 | 12 | Dec | 20 | 4 | 1 | 22.69% | 6.7962 | 0%
2040-12-21 | 2040 | 12 | Dec | 21 | 5 | 1 | 22.69% | 6.7962 | 0%
2040-12-22 | 2040 | 12 | Dec | 22 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-12-23 | 2040 | 12 | Dec | 23 | 7 | 0 | 22.69% | 6.7962 | 0%
2040-12-24 | 2040 | 12 | Dec | 24 | 1 | 1 | 22.69% | 6.7962 | 0%
2040-12-25 | 2040 | 12 | Dec | 25 | 2 | 1 | 22.69% | 6.7962 | 0%
2040-12-26 | 2040 | 12 | Dec | 26 | 3 | 1 | 22.69% | 6.7962 | 0%
2040-12-27 | 2040 | 12 | Dec | 27 | 4 | 1 | 22.69% | 6.7962 | 0%
2040-12-28 | 2040 | 12 | Dec | 28 | 5 | 1 | 22.69% | 6.7962 | 0%
2040-12-29 | 2040 | 12 | Dec | 29 | 6 | 0 | 22.69% | 6.7962 | 0%
2040-12-30 | 2040 | 12 | Dec | 30 | 7 | 0 | 22.69% | 6.7962 | 0%
2040-12-31 | 2040 | 12 | Dec | 31 | 1 | 1 | 22.69% | 6.7962 | 0%