ESTIMATING SYSTEM - CLIENT ISSUE STANDARD

# Estimate Basis & Tender Report

Master specification, template and release standard

DEVELOPMENT CANDIDATE - TEST BEFORE PERMANENT PROMOTION

REVISION  Rev2

DATE  15 August 2026

PURPOSE  Define the mandatory client-facing narrative that accompanies the estimate and programme

STATUS  Development candidate pending live-job testing

# 1. Purpose and required issue pack

For Tender and equivalent detailed estimates, the normal client issue pack should contain three aligned deliverables:

Estimate / Pricing Schedule - the commercial number and priced work breakdown.

Programme of Works - the intended sequence, working duration, calendar basis and key dependencies.

Estimate Basis & Tender Report - the narrative record explaining what the number and programme actually mean.

Core principle
The Master Estimate Workbook remains the calculation source of truth. The report explains the meaning, assumptions, scope, programme and risk basis of those calculations. It must never create a second price, upgrade a release status or contradict the controlling workbook.

# 2. Source-of-truth hierarchy

| Priority | Source | Report use |
| --- | --- | --- |
| 1 | Current approved Master Estimate Workbook | Controlling totals, quantities, commercial selections, Risk Truth, Weather Risk, release status and reconciliations. |
| 2 | Current programme / Programme Export | Working-day basis, sequence, dependencies, critical-path assumptions and calendar dates. |
| 3 | Issued drawings, specifications and addenda | Scope, quantities, methods, exclusions and source register. |
| 4 | Current project quotes / consultant evidence | PC sums, quoted packages, supplier obligations and validity. |
| 5 | Approved backend tools and libraries | Weather, rates, productivity, risk and other specialist evidence. |

No silent correction
If the workbook, programme or source documents conflict, the report must state the conflict and hold or qualify issue. It must not quietly choose the version that produces the cleanest narrative.

# 3. Mandatory release rules

The report total must reconcile exactly to the controlling Tender Build-Up / Summary.

The report revision must identify the exact estimate/workbook revision and programme revision used.

The report cannot present a RED/HOLD estimate as approved or firm.

Material AMBER items must be disclosed in plain English with the required firm-up action.

Internal overhead/profit detail, raw resource costs and commercially sensitive rate build-ups are not disclosed unless the procurement model requires open-book pricing.

Risk Truth is summarised for the client as tender treatment and baseline; the internal risk engine is not dumped wholesale into the report.

Weather is explained as an evidence-based modelled allowance, not as a promise that a fixed number of rainy days is absorbed.

Contract entitlement remains separate from estimating allowance. The report states the priced baseline; the contract governs events outside it.

Any material change to price, programme, weather inputs, risk baseline, PC/provisional items or document revision requires the report to be regenerated or formally revised.

The report may not invent missing client, contract, scope or technical information. Missing information becomes an RFI, qualification, provisional item or exclusion.

# 4. Client-facing information vs internal information

| Client report normally includes | Client report normally does not include |
| --- | --- |
| Tender total and tax basis | Internal labour cost / payroll assumptions |
| Major scope breakdown | Plant ownership economics and internal charge-out logic |
| PC sums / provisional quantities / allowances | Raw subcontractor comparison sheets unless required |
| Weather basis and included effect | Internal profit or overhead percentages unless open-book |
| Material risk treatment and tender baseline | Raw Risk Truth scoring, internal management notes or strategy |
| Assumptions, exclusions, interfaces and RFIs | Sensitive supplier negotiation positions |
| Programme basis and key dates | Unapproved internal alternative prices |

# 5. Mandatory report structure

| Section | Required content |
| --- | --- |
| 1. Executive Summary | Project, work package, estimate revision/status, tender total, programme headline, validity and key caveat. |
| 2. Project Understanding | What is being built, why, work-package boundary and dominant cost/programme drivers. |
| 3. Basis Documents | Drawing/specification/addenda register used for the estimate, with revision/date and outstanding documents. |
| 4. Scope Included | Practical work-package scope by construction heading. |
| 5. Exclusions and By Others | Explicit defensive exclusions and interfaces. |
| 6. Estimate Assumptions | Access, haul, ground, hours, testing, methodology, programme, commercial and other estimate assumptions. |
| 7. Pricing Basis and Summary | Client-level price breakdown, classification of allowance/PC/provisional items and tax basis. |
| 8. Programme Basis | Start assumption, working calendar, productive/working/elapsed duration, sequence, work fronts, hold points and long leads. |
| 9. Weather Basis | Station/tool/version, task exposure, normal-weather treatment, cost buckets, programme effect, status and rerun trigger. |
| 10. Risk Basis | Material foreseeable risks, tender baseline, included treatment, provisional/excluded treatment and outside-baseline principle. |
| 11. PC Sums, Provisional Quantities and Allowances | Separate register identifying amount/quantity, basis, uncertainty and closeout action. |
| 12. RFIs and Outstanding Information | Material issues that can change quantity, method, programme or cost. |
| 13. Verification / Confidence Position | Client-readable summary of verified versus allowance/outstanding status and release state. |
| 14. Tender Qualifications and Validity | Validity, escalation basis, approvals, possession/access dependencies, GST and revision-control statements. |
| 15. Attachments and Reconciliation | Exact estimate and programme revisions that form the issue pack. |

# 6. Executive Summary standard

The first page must allow a director, client or project manager to understand the commercial position without reading the entire report. Include:

Project and location

Nominated work package

Estimate type/status and revision

Tender total excl. GST and GST treatment

Programme start assumption and baseline duration

Headline weather/risk treatment

Three to five major qualifications or outstanding items

Tender validity

Explicit release status: Approved / Tender with disclosed limitations / HOLD - not for issue

# 7. Pricing presentation rules

Client-level, not open-book by accident
Use WBS/section totals and clearly identified PC/provisional/allowance items. Do not expose internal profit, overhead recovery, wage build-ups, supplier negotiation positions or sensitive resource data unless contractually required.

| Classification | Client wording |
| --- | --- |
| Measured / priced | Included in tender based on the listed drawing/specification basis. |
| Quoted | Based on current project-specific quotation; state quote date/validity where material. |
| PC Sum | Budget allowance pending final supplier/design confirmation. |
| Provisional Quantity | Quantity basis stated; final value subject to actual measured/confirmed extent. |
| Allowance | Explicit estimate where evidence is incomplete; state basis and closeout action. |
| Excluded / By Others | Not included unless later added by instruction. |

# 8. Weather narrative standard

Weather must be explained in practical terms. State the climate source/tool, programme period, weather-sensitive exposure, included cost categories and programme effect. The report should make clear that modelled normal weather is included in the tender basis while contractual entitlement for materially different events is governed by the contract.

Prohibited wording
Do not state or imply that every rainy day equals one lost day, that a fixed daily weather rate automatically applies, or that the estimate itself determines EOT/variation entitlement.

# 9. Risk narrative standard

Translate Risk Truth into a client-readable basis. For each material risk, explain what was known, how it was treated in the tender and what remains outside or provisional. Do not add a second risk allowance in the report.

| Risk / uncertainty | Tender baseline | Treatment | Outside-baseline / closeout |
| --- | --- | --- | --- |
| [example] Normal weather | Programme dated to stated start using approved climate tool | Modelled and included | Materially different event assessed under contract |
| [example] Unsuitable ground | [x] m3 provisional based on geotech | Provisional quantity in QS | Remeasure / geotech direction |
| [example] Unknown services | Known services as documented | Locate/protect allowance | Undocumented conflicts excluded / RFI |

# 10. Programme narrative standard

State productive crew days, working days and elapsed calendar span separately where they differ.

State work week/hours/day and start-date basis.

Identify concurrent work fronts rather than adding every task duration together.

Identify critical dependencies, approvals and long leads.

Separate statutory holidays/shutdowns from weather delay.

If programme is not reconciled to time-related costs, the report is HOLD.

# 11. Report status and confidence language

| Internal state | Client-facing report wording |
| --- | --- |
| GREEN / Approved | Estimate issued on the stated basis; listed qualifications remain part of the tender. |
| AMBER / Tender with limitations | Estimate may be issued only with the identified allowances, provisional items and firm-up actions disclosed. |
| RED / HOLD | Draft / budget information only; not for tender or contract award until listed blockers are resolved, excluded or formally accepted. |

# 12. Workbook-to-report mapping

| Report section | Primary workbook source |
| --- | --- |
| Executive summary / total | Summary + Tender Build-Up |
| Documents | Cover & Instructions / document register |
| Scope / assumptions / exclusions / RFIs | Cover & Instructions |
| Price summary | Tender Build-Up + QS Takeoff |
| PC/provisional/allowance register | QS Takeoff + Resource Build-Up + Commercial Inputs |
| Programme | Programme Export / live programme |
| Weather | Weather Risk |
| Risk | Risk Truth |
| Verification/release | Summary + Rate Verification + Risk Truth |
| Attachments/revision | Document Control / revision register |

# 13. Mandatory pre-issue reconciliation checklist

Report tender total equals live workbook tender total.

GST basis matches tender submission.

Report WBS totals reconcile to the issued pricing schedule where applicable.

Programme revision and start/calendar match the estimate basis.

Weather report values equal current Weather Risk output and rerun gate is current.

Risk summary reflects current Risk Truth baseline and release gate.

PC sums/provisional quantities/allowances match the live estimate exactly.

All material RFIs and exclusions are carried through.

Document revisions match the files actually priced.

No internal-only commercial information is disclosed accidentally.

Report issue status is no better than the workbook release status.

Estimate, report and programme share a common revision/issue record.

# 14. Standard client report template

Populate the following headings for every detailed tender estimate. Sections may be shortened for smaller jobs but must not be omitted where material.

## Executive Summary

[Populate from controlling estimate evidence. Do not invent missing information.]

## Project Understanding

[Populate from controlling estimate evidence. Do not invent missing information.]

## Basis Documents

[Populate from controlling estimate evidence. Do not invent missing information.]

## Scope Included

[Populate from controlling estimate evidence. Do not invent missing information.]

## Exclusions and By Others

[Populate from controlling estimate evidence. Do not invent missing information.]

## Estimate Assumptions

[Populate from controlling estimate evidence. Do not invent missing information.]

## Pricing Basis and Summary

[Populate from controlling estimate evidence. Do not invent missing information.]

## Programme Basis

[Populate from controlling estimate evidence. Do not invent missing information.]

## Weather Basis

[Populate from controlling estimate evidence. Do not invent missing information.]

## Risk Basis

[Populate from controlling estimate evidence. Do not invent missing information.]

## PC Sums / Provisional Quantities / Allowances

[Populate from controlling estimate evidence. Do not invent missing information.]

## RFIs and Outstanding Information

[Populate from controlling estimate evidence. Do not invent missing information.]

## Verification / Confidence Position

[Populate from controlling estimate evidence. Do not invent missing information.]

## Tender Qualifications and Validity

[Populate from controlling estimate evidence. Do not invent missing information.]

## Attachments and Reconciliation

[Populate from controlling estimate evidence. Do not invent missing information.]

# 15. Development / promotion decision

Current status
This Rev2 master is a development candidate. Test it against at least one real estimate, review the client-readability and Word/PDF rendering, then red-team the content for usefulness, duplication, commercial sensitivity and release controls before adding it permanently to the Master Prompt / Project Files.